## Sheet1
Steel Structure Greenfield (material +sandwitch Panel) | Start date | End date
Delivery of Civil Bulk Material | 2026-03-04 | 2026-03-18
Delivery of Structural Steel GF | 2026-03-19 | 2026-04-09
Steel Structure Brownfield
Delivery of (Steel Structure - PostTA) | 2026-02-23 | 2026-03-02
Piping 1st Lot for GF
Delivery of Piping Material in Warehouse (1st Lot, GF) | 2025-12-30 | 2026-01-12
Piping 2 nd Lot for GF
Delivery of Piping Material in Warehouse (2nd Lot) | 2026-02-16 | 2026-03-02
Piping 3 nd Lot for GF
Piping 3rd Lot GF (CS Material) | 2026-04-16 | 2026-04-30

## Sheet3
Activity ID | Activity Name | Early Finish | Late Finish | Start | Finish | Remaining Duration
Borouge EU3 H2 Extraction EPC Project |  | 2027-07-20 | 2027-07-20 | 07-Nov-24 A | 2027-07-20 | 462
COMPANY / PKG 1&2 Interfaces |  | 2027-01-20 | 2027-04-27 | 20-Nov-24 A | 2027-01-20 | 333
Engineering |  | 2026-02-13 | 2026-07-23 | 20-Nov-24 A | 2026-02-13 | 105
Required Inputs from COMPANY / Pkg 1&2 |  |  |  | 20-Nov-24 A | 31-Aug-25 A | 0
A5200 | TA Construction Dossier (IFC) - Pkg 1&2 |  |  |  | 04-Apr-25 A | 0
A60650 | Receipt of SP3D database |  |  |  | 25-Apr-25 A | 0
A60660 | Receipt of SPI database login |  |  |  | 11-Feb-25 A | 0
A60670 | Receipt of Updated P&ID's - Pkg 1&2 |  |  |  | 19-Jun-25 A | 0
A60680 | Receipt of Updated P&ID's Updated Line List (Tie-in list, PDS …etc) - Pkg 1&2 |  |  |  | 31-Aug-25 A | 0
A60690 | Receipt of Unit Plot Plan Native File - Pkg 1&2 |  |  |  | 25-Mar-25 A | 0
A60700 | Receipt of Drawings for all UG systems |  |  |  | 20-Nov-24 A | 0
A60710 | Receipt of Native files of 3D model building & structural design (FEED stage) - Pkg 1&2 |  |  |  | 20-May-25 A | 0
A60720 | Receipt of Native files of 3D model, STAAD model, calculations for brown field - Pkg 1&2 |  |  |  | 15-Jan-25 A | 0
A60730 | Receipt of PSCAD native files for electrical studies - Pkg 1&2 |  |  |  | 15-Jan-25 A | 0
A60740 | Receipt of System architecture & cable block diagram for MCMS, compressor control |  |  |  | 13-Feb-25 A | 0
A60750 | Receipt of FEED datasheets for all telecom systems - Pkg 1&2 |  |  |  | 15-Jan-25 A | 0
A60760 | Receipt of Piping TA MTO |  |  |  | 20-Feb-25 A | 0
A60770 | Receipt of Approved Vendor data - GAD for PSA-2 unit |  |  |  | 17-Mar-25 A | 0
A60780 | Receipt of Approved vendor data for FG & OG compressor |  |  |  | 24-Apr-25 A | 0
A60790 | Receipt of Design parameters within received line list - Pkg 1&2 |  |  |  | 15-Jun-25 A | 0
Required Inputs from Pkg 3 to Pkg 1&2 |  | 2026-02-13 | 2026-07-23 | 04-Mar-25 A | 2026-02-13 | 105
A60810 | All EPC Contractor G status input (detail refer Main Activities for P&ID) |  |  |  | 13-Mar-25 A | 0
A60820 | All EPC Contractor H status input (detail refer Main Activities for P&ID) | 2025-09-24 | 2026-07-03 |  | 2025-09-24 | 0
A60830 | Piping isos for main process piping and 3D model | 2025-11-05 | 2026-03-05 |  | 2025-11-05 | 0
A60840 | Mechanical data sheet (vendor data sheet) of vessels and exchangers |  |  |  | 20-Jun-25 A | 0
A60850 | Data sheet of control valve, shut down, PSV, check valve and flow element (vendor data sheet) | 2025-09-19 | 2026-03-05 |  | 2025-09-19 | 0
A60860 | Cause and effect update |  |  |  | 13-Mar-25 A | 0
A60870 | Instrument data sheet for level, pressure and temperature | 2025-12-29 | 2026-03-05 |  | 2025-12-29 | 0
A60880 | Review & Confirmation on compressor GAD, Foundation plan & Anchor bolt locations |  |  |  | 20-Mar-25 A | 0
A60890 | Review and Confirmation by Pkg -3 contractor as per issue 02 for EICT Cables | 2025-09-19 | 2026-03-05 |  | 2025-09-19 | 0
A60900 | List of inputs required in compressor process loop |  |  |  | 23-Apr-25 A | 0
A60910 | By-pass line sizing and routing and hot gas bypass valve details |  |  |  | 23-Apr-25 A | 0
A60920 | GF Balance of Plant maturity w.r.t. Compressor & PSA2 model integration |  |  |  | 27-Mar-25 A | 0
A60930 | H2-SIS layout required + power cable details. |  |  |  | 16-Apr-25 A | 0
A60940 | Homerun cable length with its datasheet required for UCP signal IS calculation |  |  |  | 04-Apr-25 A | 0
A60950 | Vendor manuals package to be provided by EPC Contractor for Linde's review | 2026-02-13 | 2026-07-03 |  | 2026-02-13 | 0
A60960 | Follow up HAZOP/LOPA Recommendations report - 13-KC-701 - PSA2 Feed Gas Compressor - Pkg 3 related |  |  |  | 23-Apr-25 A | 0
A60970 | HSE Action Tracking Register - Pkg 3 Actions | 2025-09-19 | 2026-07-23 |  | 2025-09-19 | 0
A60980 | Safty Follow up HAZOP/LOPA Recommendations Package 1c - Pkg 3 related |  |  |  | 23-Apr-25 A | 0
A60990 | Selection for Option of MV motor (650% or 500% of rated current) or Starting VFD for Off Comp. |  |  |  | 04-Mar-25 A | 0
A61000 | Compressor Motor VDDR Motor datasheet - Electrical Cable list |  |  |  | 20-Mar-25 A | 0
Procurement |  | 2026-10-07 | 2027-01-20 | 15-Apr-25 A | 2026-10-07 | 384
76.D | FG Compressor - Delivery | 2026-03-03 | 2026-03-03 |  | 2026-03-03 | 0
78.D | OG Compressor - Delivery | 2026-02-06 | 2026-06-04 |  | 2026-02-06 | 0
A5170 | Key Vendor Data (LLI, Package Details and Design Data) | 2025-09-19 | 2026-03-03 |  | 2025-09-19 | 0
A5190 | Free Issue TA Material latest delivery |  |  |  | 15-Apr-25 A | 0
A5210 | BFW Preheater - Delivery |  |  |  | 15-Apr-25 A | 0
A61070 | Approved Key Vendor Data (LLI, Package Details and Design Data) | 2025-09-19 | 2026-03-03 |  | 2025-09-19 | 0
A9950 | PSA Unit Delivery - Delivery | 2025-09-29 | 2026-03-16 |  | 2025-09-29 | 0
Feed Gas Compressor - Delivery |  | 2026-05-25 | 2027-01-20 | 2026-01-02 | 2026-05-25 | 143
A62300 | Feed Gas Compressor (incl. Baseplate, Gear, Gas seal module & Booster) | 2026-03-03 | 2026-03-03 |  | 2026-03-03 | 0
A62310 | LO Console | 2026-03-16 | 2026-08-23 |  | 2026-03-16 | 0
A62320 | Anti-surge valve | 2026-05-25 | 2026-09-27 |  | 2026-05-25 | 0
A62330 | Capital Spares | 2026-03-09 | 2027-01-20 |  | 2026-03-09 | 0
A62340 | Main Driver (Motor) for FGC | 2026-03-09 | 2026-06-24 |  | 2026-03-09 | 0
A62350 | UCP | 2026-01-02 | 2026-01-02 |  | 2026-01-02 | 0
A62360 | VSD | 2026-01-21 | 2026-01-21 |  | 2026-01-21 | 0
A62370 | Transformer | 2026-04-27 | 2026-08-23 |  | 2026-04-27 | 0
Off Gas Compressor: Vendor - Delivery |  | 2026-02-12 | 2026-08-31 | 2026-01-27 | 2026-02-12 | 15
A62380 | Off Gas Compressor | 2026-02-06 | 2026-06-04 |  | 2026-02-06 | 0
A62390 | Capital Spares | 2026-01-30 | 2026-05-28 |  | 2026-01-30 | 0
A62400 | Main Driver (Motor) for OGC | 2026-02-09 | 2026-07-04 |  | 2026-02-09 | 0
A62410 | UCP | 2026-01-27 | 2026-05-25 |  | 2026-01-27 | 0
A62420 | Lube Oil Unit | 2026-02-06 | 2026-07-01 |  | 2026-02-06 | 0
A62430 | Seal Gas Unit | 2026-02-12 | 2026-08-31 |  | 2026-02-12 | 0
PSA Unit: Vendor - Delivery |  | 2026-10-07 | 2026-12-21 | 03-Sep-25 A | 2026-10-07 | 352
A62440 | PSA Pressure vessels |  |  |  | 03-Sep-25 A | 0
A62450 | PSA Valve Skid | 2025-10-20 | 2026-05-31 |  | 2025-10-20 | 0
A62460 | PLC Cabinet |  |  |  | 03-Sep-25 A | 0
A62470 | Adsorbent Material (PO pending) | 2026-08-21 | 2026-09-29 |  | 2026-08-21 | 0
A62480 | Analyzer (PO pending) | 2026-10-07 | 2026-12-21 |  | 2026-10-07 | 0
Construction & Commissioning |  | 2027-01-20 | 2027-04-27 | 2027-01-20 | 2027-01-20 | 0
A40220 | Potable Water and Service water (Needs) | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
A40230 | SANITARY Water system (Needs) | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
A40240 | Chilled Water for Safety Shower | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
A40250 | Instrument Air (Needs) for Boiler RFSU | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
A40260 | Fire Water (Needs) | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
A40270 | ETP (Effluent Treatment Package) System (Needs) | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
A40280 | Demin water (Needs) | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
A40290 | Nitrogen (Needs) | 2027-01-20 | 2027-04-27 |  | 2027-01-20 | 0
Project Management |  | 2027-07-20 | 2027-07-20 | 07-Nov-24 A | 2027-07-20 | 462
Project Management |  | 2027-05-07 | 2027-07-20 | 07-Nov-24 A | 2027-05-07 | 410
Project Management Deliverables |  | 2026-01-01 | 2027-07-20 | 22-Mar-25 A | 2026-01-01 | 71
A1-PM-PMD-0001 | PM-001-Job Bulletins |  |  | 25-May-25 A | 15-Aug-25 A | 0
A1-PM-PMD-0002 | PM-002-Project Coordination Procedure |  |  |  | 18-Apr-25 A | 0
A1-PM-PMD-0003 | PM-003-Code of accounts |  |  | 25-May-25 A | 15-Aug-25 A | 0
A1-PM-PMD-0004 | PM-004-PDS / Smart3D 3D Modeling Guideline for End User |  |  | 25-May-25 A | 25-Aug-25 A | 0
A1-PM-PMD-0005 | PM-005-SPI (Smart Plant Instrumentation) INtoos Guideline for End User |  |  | 25-May-25 A | 26-Aug-25 A | 0
A1-PM-PMD-0006 | PM-006-SP PID (Smart Plant P&ID ) Guideline for End User |  |  | 25-May-25 A | 30-Aug-25 A | 0
A1-PM-PMD-0007 | PM-007-SPEL (Smart Plant Electrical) Guideline for End Users |  |  | 25-May-25 A | 02-Sep-25 A | 0
A1-PM-PMD-0008 | PM-008-PDS / Smart3D CADD Area/Model Index/ Plan |  |  | 25-May-25 A | 08-Sep-25 A | 0
A1-PM-PMD-0009 | PM-009-CADD Project Hierarchy & Setup Guideline (PDS /Intools/ SP PID/ SPEL) |  |  | 25-May-25 A | 12-Sep-25 A | 0
A1-PM-PMD-0010 | PM-010-PDS / Smart3D Physical Support Modeling Guideline for End Users |  |  | 25-May-25 A | 16-Sep-25 A | 0
A1-PM-PMD-0011 | PM-011-Project Engineering CADD Applications & Deliverables Guideline |  |  | 25-May-25 A | 21-Aug-25 A | 0
A1-PM-PMD-0012 | PM-012-PDS / Smart3D Raceways Guideline |  |  | 25-May-25 A | 23-Aug-25 A | 0
A1-PM-PMD-0013 | PM-013-PDS / Smart3D Generated List of Drawings / Documents |  |  | 25-May-25 A | 27-Aug-25 A | 0
A1-PM-PMD-0014 | PM-014-Documentation and CADD Systems / Database Handover Schedule |  |  | 25-May-25 A | 01-Sep-25 A | 0
A1-PM-PMD-0015 | PM-015-CADD Systems As-built Database and System integrated Deliverables (PDS/IN Tools/SP PID/SPEL/ETAP/ Caesar-II / STA |  |  | 25-May-25 A | 05-Sep-25 A | 0
A1-PM-PMD-0016 | PM-016-Site Mobilization Plan |  |  | 25-May-25 A | 07-Sep-25 A | 0
A1-PM-PMD-0017 | PM-017-HSE Training plan & procedure |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PMD-0018 | PM-028-Project Organization Charts |  |  | 25-May-25 A | 27-Aug-25 A | 0
A1-PM-PMD-0019 | PM-029-Recovery Plan |  |  | 25-May-25 A | 12-Jul-25 A | 0
A1-PM-PMD-0020 | PM-030-Worksite HSE Plan |  |  | 25-May-25 A | 28-May-25 A | 0
A1-PM-PMD-0021 | PM-031-Temporary Site Establishment plan |  |  | 25-May-25 A | 25-Aug-25 A | 0
A1-PM-PMD-0022 | PM-032-Tie-in & Interface Matrix |  |  | 25-May-25 A | 26-Aug-25 A | 0
A1-PM-PMD-0023 | PM-037-Document/Drawing Index |  |  | 25-May-25 A | 30-Aug-25 A | 0
A1-PM-PMD-0024 | PM-038-Documentation List |  |  | 25-May-25 A | 04-Sep-25 A | 0
A1-PM-PMD-0025 | PM-039-List of Claims for Damage |  |  | 25-May-25 A | 12-Jul-25 A | 0
A1-PM-PMD-0026 | PM-040-List of Commissioning Spares | 2025-09-25 | 2027-07-06 | 30-Jul-25 A | 2025-09-25 | 5
A1-PM-PMD-0027 | PM-041-List of startup spares | 2025-10-02 | 2027-07-13 | 2025-09-26 | 2025-10-02 | 5
A1-PM-PMD-0028 | PM-045-Project Close out Report | 2025-10-09 | 2027-07-20 | 2025-10-03 | 2025-10-09 | 5
A1-PM-PMD-0029 | PM-046-Procurement Status Report |  |  | 25-May-25 A | 25-Jul-25 A | 0
A1-PM-PMD-0030 | PM-047-Project Execution Plan | 2025-09-30 | 2026-10-29 |  | 2025-09-30 | 0
A1-PM-PMD-0031 | PM-048-HSE Audit Procedure |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PMD-0032 | PM-049-Risk Analysis |  |  | 25-May-25 A | 17-Sep-25 A | 0
A1-PM-PMD-0033 | PM-050-Acceptance Certificate | 2025-09-22 | 2027-07-20 | 2025-09-19 | 2025-09-22 | 4
A1-PM-PMD-0034 | PM-052-Contract Trending procedure |  |  | 25-May-25 A | 26-Aug-25 A | 0
A1-PM-PMD-0035 | PM-053-Contract Trend notice / Log |  |  | 22-Mar-25 A | 27-Aug-25 A | 0
A1-PM-PMD-0036 | PM-054-Master Document schedule and Status Report |  |  | 25-May-25 A | 25-Jul-25 A | 0
A1-PM-PMD-0037 | PM-057-Project Specification |  |  | 25-May-25 A | 25-Aug-25 A | 0
A1-PM-PMD-0038 | PM-061-Insurance Policies |  |  | 25-May-25 A | 01-Sep-25 A | 0
A1-PM-PMD-0039 | PM-062-Insurance Claims |  |  | 25-Aug-25 A | 05-Sep-25 A | 0
A1-PM-PMD-0040 | PM-063-Insurance claim status report |  |  | 23-Aug-25 A | 26-Aug-25 A | 0
A1-PM-PMD-0041 | PM-064-Claims |  |  | 27-Aug-25 A | 30-Aug-25 A | 0
A1-PM-PMD-0042 | PM-065-Requests for Variation |  |  | 01-Sep-25 A | 04-Sep-25 A | 0
A1-PM-PMD-0043 | PM-073-Feed Documents |  |  | 25-May-25 A | 08-Sep-25 A | 0
A1-PM-PMD-0044 | PM-074-Asset Integrated Management System (AIMS) / Project Integrity Management Plan | 2025-09-25 | 2025-12-08 | 2025-09-19 | 2025-09-25 | 5
A1-PM-PMD-0045 | PM-075-Constructability Action Closeout Report | 2025-10-02 | 2025-12-15 | 2025-09-26 | 2025-10-02 | 5
A1-PM-PMD-0046 | PM-076-Project Training Requirements and Training Plan | 2025-10-09 | 2025-12-22 | 2025-10-03 | 2025-10-09 | 5
A1-PM-PMD-0047 | PM-077-Operating Procedure/Guidelines | 2025-10-16 | 2025-12-29 | 2025-10-10 | 2025-10-16 | 5
A1-PM-PMD-0048 | PM-078-Guidelines for Acceptance of Work | 2025-10-23 | 2026-01-05 | 2025-10-17 | 2025-10-23 | 5
A1-PM-PMD-0049 | PM-079-Synergies Study Report | 2025-10-30 | 2026-01-12 | 2025-10-24 | 2025-10-30 | 5
A1-PM-PMD-0050 | PM-080-Project IT/EDMS Requirements |  |  | 25-May-25 A | 16-Sep-25 A | 0
A1-PM-PMD-0051 | PM-081-Interface Management Plan - EPC |  |  | 25-May-25 A | 10-Sep-25 A | 0
A1-PM-PMD-0052 | PM-082-Interface Responsibility Philosophy |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PMD-0053 | PM-083-EPC Responsibility Matrix for Control Systems | 2025-09-25 | 2026-01-12 | 25-Jul-25 A | 2025-09-25 | 5
A1-PM-PMD-0054 | PM-084-EPC Responsibility Matrix for ICT & IT/OT | 2025-11-06 | 2026-01-19 | 2025-10-31 | 2025-11-06 | 5
A1-PM-PMD-0055 | PM-085-Interface Point Registers | 2025-11-13 | 2026-01-26 | 2025-11-07 | 2025-11-13 | 5
A1-PM-PMD-0056 | PM-086-Interface Dependency Table | 2025-09-19 | 2026-01-26 | 14-Jul-25 A | 2025-09-19 | 0
A1-PM-PMD-0057 | PM-087-Master Boundary Interface Layout Drawing | 2025-11-20 | 2026-02-02 | 2025-11-14 | 2025-11-20 | 5
A1-PM-PMD-0058 | PM-088-Process and Utilities Overall Block Flow Diagram Borouge-4 Facilities | 2025-09-25 | 2026-02-02 | 21-Jul-25 A | 2025-09-25 | 5
A1-PM-PMD-0059 | PM-089-Process and Utilities Block Flow Diagram Interconnecting | 2025-11-27 | 2026-02-09 | 2025-11-21 | 2025-11-27 | 5
A1-PM-PMD-0060 | PM-090-Piping External/Internal Connections Layout drawings | 2025-12-04 | 2026-02-16 | 2025-11-28 | 2025-12-04 | 5
A1-PM-PMD-0061 | PM-091-MRB Index | 2025-12-11 | 2026-02-23 | 2025-12-05 | 2025-12-11 | 5
A1-PM-PMD-0062 | PM-092-Material Record Book (MRB) | 2025-12-18 | 2026-03-02 | 2025-12-12 | 2025-12-18 | 5
A1-PM-PMD-0063 | PM-093-QA/QC Dossiers | 2025-12-25 | 2026-03-09 | 2025-12-19 | 2025-12-25 | 5
A1-PM-PMD-0064 | PM-094-Package 1 Deliverables IFC | 2026-01-01 | 2026-03-16 | 2025-12-26 | 2026-01-01 | 5
Project Control Deliverables |  | 2025-10-10 | 2026-11-06 | 15-Feb-25 A | 2025-10-10 | 16
A1-PM-PCD-0001 | PC-001-Procedures |  |  | 15-Feb-25 A | 14-May-25 A | 0
A1-PM-PCD-0002 | PC-002-Distribution Matrix |  |  | 04-Mar-25 A | 12-Mar-25 A | 0
A1-PM-PCD-0003 | PC-003-Time Schedule / Program |  |  | 15-Feb-25 A | 17-Jun-25 A | 0
A1-PM-PCD-0004 | PC-004-Overall Project Schedule |  |  | 15-Feb-25 A | 17-Jun-25 A | 0
A1-PM-PCD-0005 | PC-005-Detailed Procurement schedule |  |  | 15-Feb-25 A | 17-Jun-25 A | 0
A1-PM-PCD-0006 | PC-006-Detailed Engineering Schedule |  |  | 15-Feb-25 A | 17-Jun-25 A | 0
A1-PM-PCD-0007 | PC-007-Detailed Construction Schedule |  |  | 15-Feb-25 A | 17-Jun-25 A | 0
A1-PM-PCD-0008 | PC-008-Detailed Control Log / Schedule |  |  | 15-Feb-25 A | 17-Jun-25 A | 0
A1-PM-PCD-0009 | PC-009-Detailed Commissioning and Pre Commissioning Schedule |  |  | 15-Feb-25 A | 17-Jun-25 A | 0
A1-PM-PCD-0010 | PC-010-Variations |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PCD-0011 | PC-011-Document/Drawing Index |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PCD-0012 | PC-012-Specialty Item List |  |  | 21-Jun-25 A | 21-Aug-25 A | 0
A1-PM-PCD-0013 | PC-013-Spares Lists |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PCD-0014 | PC-014-Suppliers Lists |  |  | 19-Aug-25 A | 20-Aug-25 A | 0
A1-PM-PCD-0015 | PC-015-Annual Reports |  |  | 15-May-25 A | 23-May-25 A | 0
A1-PM-PCD-0016 | PC-016-Monthly Reports |  |  | 26-May-25 A | 20-Jul-25 A | 0
A1-PM-PCD-0017 | PC-017-Weekly Reports |  |  | 25-May-25 A | 19-Aug-25 A | 0
A1-PM-PCD-0018 | PC-018-Forecasts for Completion |  |  | 25-May-25 A | 21-Aug-25 A | 0
A1-PM-PCD-0019 | PC-019-Project Execution Plan | 2025-09-30 | 2026-10-27 |  | 2025-09-30 | 0
A1-PM-PCD-0020 | PC-020-FAT Procedures | 2025-10-02 | 2026-10-29 | 2025-09-30 | 2025-10-02 | 2
A1-PM-PCD-0021 | PC-021-FAT Reports | 2025-10-06 | 2026-11-02 | 2025-10-02 | 2025-10-06 | 2
A1-PM-PCD-0022 | PC-022-SAT Procedures | 2025-10-08 | 2026-11-04 | 2025-10-06 | 2025-10-08 | 2
A1-PM-PCD-0023 | PC-023-SAT Reports | 2025-10-10 | 2026-11-06 | 2025-10-08 | 2025-10-10 | 2
A1-PM-PCD-0024 | PC-024-P&ID change notes |  |  | 06-Sep-25 A | 07-Sep-25 A | 0
A1-PM-PCD-0025 | PC-025-Engineering Document Change Note |  |  | 25-May-25 A | 02-Sep-25 A | 0
A1-PM-PCD-0026 | PC-026-Query Form |  |  | 25-May-25 A | 09-Sep-25 A | 0
A1-PM-PCD-0027 | PC-027-Change Orders |  |  | 25-Aug-25 A | 29-Aug-25 A | 0
A1-PM-PCD-0028 | PC-028-Field Queries |  |  | 01-Sep-25 A | 08-Sep-25 A | 0
A1-PM-PCD-0029 | PC-029-Site Queries |  |  | 27-Aug-25 A | 29-Aug-25 A | 0
A1-PM-PCD-0030 | . |  |  | 25-May-25 A | 27-Aug-25 A | 0
A1-PM-PCD-0031 | PC-031-Invoices |  |  | 25-May-25 A | 02-Sep-25 A | 0
A1-PM-PCD-0032 | PC-032-Invoices Status Report |  |  | 25-May-25 A | 03-Sep-25 A | 0
A1-PM-PCD-0033 | PC-033-Bank Bonds and Guarantees |  |  | 25-May-25 A | 26-Aug-25 A | 0
A1-PM-PCD-0034 | PC-034-Cash Flow Forecast |  |  | 25-May-25 A | 25-Aug-25 A | 0
A1-PM-PCD-0035 | PC-035-Back charges Status Report |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PCD-0036 | PC-036-Progress Review and Certification Procedure |  |  | 15-Feb-25 A | 10-Sep-25 A | 0
A1-PM-PCD-0037 | PC-037-Schedule Risk Analysis Reports |  |  | 15-Feb-25 A | 28-Jun-25 A | 0
A1-PM-PCD-0038 | PC-038-Manpower Mobilization Plan |  |  | 15-Feb-25 A | 29-Aug-25 A | 0
A1-PM-PCD-0039 | PC-039-Equipment Deployment Plan |  |  | 15-Feb-25 A | 03-Sep-25 A | 0
A1-PM-PCD-0040 | PC-040-Planning Package | 2025-09-19 | 2026-02-20 | 15-Feb-25 A | 2025-09-19 | 1
Project Risk Analysis Workshops |  | 2027-04-28 | 2027-07-09 | 25-May-25 A | 2027-04-28 | 360
A1-PM-PRA-0001 | PRA01-Project Risk Analysis - Risk Identifications Workshop |  |  |  | 25-May-25 A | 0
A1-PM-PRA-0002 | PRA02-Project Risk Analysis Workshop - Update - Q01 |  |  |  | 21-Jun-25 A | 0
A1-PM-PRA-0003 | PRA03-Project Risk Analysis Workshop - Update - Q02 |  |  |  | 20-Aug-25 A | 0
A1-PM-PRA-0004 | PRA04-Project Risk Analysis Workshop - Update - Q03 | 2025-12-10 | 2026-02-20 |  | 2025-12-10 | 0
A1-PM-PRA-0005 | PRA05-Project Risk Analysis Workshop - Update - Q04 | 2026-04-15 | 2026-06-26 |  | 2026-04-15 | 0
A1-PM-PRA-0006 | PRA06-Project Risk Analysis Workshop - Update - Q05 | 2026-08-19 | 2026-10-30 |  | 2026-08-19 | 0
A1-PM-PRA-0007 | PRA07-Project Risk Analysis Workshop - Update - Q06 | 2026-12-23 | 2027-03-05 |  | 2026-12-23 | 0
A1-PM-PRA-0008 | PRA08-Project Risk Analysis Workshop - Update - Q07 | 2027-04-28 | 2027-07-09 |  | 2027-04-28 | 0
Schedule Risk Analysis Workshops |  | 2027-05-07 | 2027-07-20 | 15-May-25 A | 2027-05-07 | 338
A1-PM-SRA-0001 | SRA01-Schedule Risk Analysis Workshop - Baseline Schedule |  |  |  | 15-May-25 A | 0
A1-PM-SRA-0002 | SRA02-Schedule Risk Analysis Workshop - UpdatedSchedule - Q01 |  |  |  | 10-Jul-25 A | 0
A1-PM-SRA-0003 | SRA03-Schedule Risk Analysis Workshop - Updated Schedule - Q02 |  |  |  | 17-Sep-25 A | 0
A1-PM-SRA-0004 | SRA04-Schedule Risk Analysis Workshop - Updated Schedule - Q03 | 2026-01-20 | 2026-06-19 |  | 2026-01-20 | 0
A1-PM-SRA-0005 | SRA05-Schedule Risk Analysis Workshop - Updated Schedule - Q04 | 2026-05-26 | 2026-10-23 |  | 2026-05-26 | 0
A1-PM-SRA-0006 | SRA06-Schedule Risk Analysis Workshop - Updated Schedule - Q05 | 2026-09-29 | 2027-02-26 |  | 2026-09-29 | 0
A1-PM-SRA-0007 | SRA07-Schedule Risk Analysis Workshop - Updated Schedule - Q06 | 2027-02-02 | 2027-07-02 |  | 2027-02-02 | 0
A1-PM-SRA-0008 | SRA08-Schedule Risk Analysis Workshop - Updated Schedule - Q07 | 2027-05-07 | 2027-07-20 |  | 2027-05-07 | 0
Project Lesson Learn Workshops |  | 2027-05-03 | 2027-07-20 | 25-May-25 A | 2027-05-03 | 360
A1-PM-LLW-0001 | PRA01-Project Lesson Learn Workshop - Lesson Learn Identifications |  |  |  | 25-May-25 A | 0
A1-PM-LLW-0002 | PRA02-Project Lesson Learn Workshop - Update - Q01 |  |  |  | 21-Jun-25 A | 0
A1-PM-LLW-0003 | PRA03-Project Lesson Learn Workshop - Update - Q02 |  |  |  | 15-Sep-25 A | 0
A1-PM-LLW-0004 | PRA04-Project Lesson Learn Workshop - Update - Q03 | 2025-12-15 | 2026-03-05 |  | 2025-12-15 | 0
A1-PM-LLW-0005 | PRA05-Project Lesson Learn Workshop - Update - Q04 | 2026-04-20 | 2026-07-07 |  | 2026-04-20 | 0
A1-PM-LLW-0006 | PRA06-Project Lesson Learn Workshop - Update - Q05 | 2026-08-24 | 2026-11-10 |  | 2026-08-24 | 0
A1-PM-LLW-0007 | PRA07-Project Lesson Learn Workshop - Update - Q06 | 2026-12-28 | 2027-03-16 |  | 2026-12-28 | 0
A1-PM-LLW-0008 | PRA08-Project Lesson Learn Workshop - Update - Q07 | 2027-05-03 | 2027-07-20 |  | 2027-05-03 | 0
Project Management Interim Milestones |  | 2025-09-30 | 2026-12-09 | 07-Nov-24 A | 2025-09-30 | 3
A1-PM-PMM-0001 | Letter of Award (LOA) Recieved - Project Commencement Date |  |  |  | 07-Nov-24 A | 0
A1-PM-PMM-0002 | 10.A-Kick-off Meeting Completed |  |  |  | 06-Dec-24 A | 0
A1-PM-PMM-0003 | 1.A*-Issue Overall Project Execution Plan | 2025-09-30 | 2026-10-29 |  | 2025-09-30 | 0
A1-PM-PMM-0004 | 1.A*-Issue Coordination Procedure |  |  |  | 30-Apr-25 A | 0
QAQC Interim Milestones |  | 2025-09-25 | 2026-12-09 | 2025-09-25 | 2025-09-25 | 0
General Project Management |  | 2025-09-25 | 2026-12-09 | 2025-09-25 | 2025-09-25 | 0
A1-PM-QCM-0001 | 1.A*-Issue Project Quality Procedures (Final Issue). | 2025-09-25 | 2026-12-09 |  | 2025-09-25 | 0
HSE Interim Milestones |  |  |  | 30-Apr-25 A | 30-Apr-25 A | 0
General Project Management |  |  |  | 30-Apr-25 A | 30-Apr-25 A | 0
A1-PM-HSM-0001 | 1.A*-Issue Project HSE Procedure. |  |  |  | 30-Apr-25 A | 0
Project Control Interim Milestones |  |  |  | 24-Mar-25 A | 24-Mar-25 A | 0
A1-PM-PCM-0001 | 2.A-Issue Project Control Propcedures |  |  |  | 24-Mar-25 A | 0
A1-PM-PCM-0002 | 2.A-Issue Progress Measurement & Reporting System |  |  |  | 24-Mar-25 A | 0
A1-PM-PCM-0003 | 2.A-Issue Cost Control Procedure |  |  |  | 24-Mar-25 A | 0
A1-PM-PCM-0004 | 2.A-Issue Planning Docs |  |  |  | 24-Mar-25 A | 0
Moblization of Key Personnel |  | 2025-11-17 | 2026-03-05 | 15-Nov-24 A | 2025-11-17 | 42
A1-PM-KPM-0001 | Moblization of Project Director or Project Manager * |  |  |  | 18-Dec-24 A | 0
A1-PM-KPM-0002 | Moblization of Project Turnaround Manager * |  |  |  | 21-Nov-24 A | 0
A1-PM-KPM-0003 | Moblization of Engineering Manager * |  |  |  | 15-Feb-25 A | 0
A1-PM-KPM-0004 | Moblization of Quality Assurance and Quality Control Manager (Home Office/SITE) |  |  |  | 20-Feb-25 A | 0
A1-PM-KPM-0005 | Moblization of Lead Discipline and Supervisory Engineers * - RAD |  |  |  | 01-Dec-24 A | 0
A1-PM-KPM-0006 | Moblization of Process Manager (s) * |  |  |  | 01-Feb-25 A | 0
A1-PM-KPM-0007 | Moblization of Procurement Manager (s) * |  |  |  | 15-Nov-24 A | 0
A1-PM-KPM-0008 | Moblization of Project Commercial/Prime Contracts Manager |  |  |  | 01-Jan-25 A | 0
A1-PM-KPM-0009 | Moblization of Project Traffic and Logistics Manager |  |  |  | 01-Dec-24 A | 0
A1-PM-KPM-0010 | Moblization of Project Control Manager* |  |  |  | 15-Nov-24 A | 0
A1-PM-KPM-0011 | Moblization of Lead Planner |  |  |  | 21-Jun-25 A | 0
A1-PM-KPM-0012 | Moblization of Construction Planner |  |  |  | 27-Mar-25 A | 0
A1-PM-KPM-0013 | Moblization of Project Contracts/Subcontracts Manager* |  |  |  | 01-Jun-25 A | 0
A1-PM-KPM-0014 | Moblization of Project Construction Director/Manager(s)* |  |  |  | 14-Apr-25 A | 0
A1-PM-KPM-0015 | Moblization of Project Construction Chief Field Engineer |  |  |  | 01-Mar-25 A | 0
A1-PM-KPM-0016 | Moblization of Project Construction Field Superintendent |  |  |  | 15-Apr-25 A | 0
A1-PM-KPM-0017 | Moblization of Project HSE Manager(s) (Home Office/Construction) |  |  |  | 20-Dec-24 A | 0
A1-PM-KPM-0018 | Moblization of Lead Cost Engineer / Estimator |  |  |  | 01-Apr-25 A | 0
A1-PM-KPM-0019 | Moblization of Project Commissioning Manager* | 2025-09-19 | 2026-03-05 |  | 2025-09-19 | 0
A1-PM-KPM-0020 | Moblization of Project Training Manager* | 2025-11-17 | 2026-03-05 |  | 2025-11-17 | 0
A1-PM-KPM-0021 | Moblization of Project IT Manager |  |  |  | 15-May-25 A | 0
A1-PM-KPM-0022 | Moblization of Field Engineering Manager | 2025-11-17 | 2026-03-05 |  | 2025-11-17 | 0
Detailed Design and Engineering |  | 2027-01-20 | 2027-07-20 | 02-Apr-25 A | 2027-01-20 | 331
Engineering Workshops |  | 2026-01-02 | 2026-03-05 | 25-May-25 A | 2026-01-02 | 0
A1-PM-EWS-0001 | Engineering Workshops - 30% Model Review |  |  |  | 25-May-25 A | 0
A1-PM-EWS-0002 | Engineering Workshops - 60% Model Review |  |  |  | 19-Sep-25 A | 0
A1-PM-EWS-0003 | Engineering Workshops - 90% Model Review | 2026-01-02 | 2026-03-05 |  | 2026-01-02 | 0
Engineering Interim Milestones |  | 2027-01-20 | 2027-07-20 | 02-Apr-25 A | 2027-01-20 | 331
General Project Management |  | 2027-01-20 | 2027-07-20 | 30-Apr-25 A | 2027-01-20 | 0
A1-PM-EIM-0001 | 1.A*-Issue Engineering Procedure. |  |  |  | 30-Apr-25 A | 0
A1-PM-EIM-0002 | 8.A*-As Built drawings handover to COMPANY | 2027-01-20 | 2027-07-20 |  | 2027-01-20 | 0
Detail Engineering |  | 2026-02-27 | 2027-01-20 | 02-Apr-25 A | 2026-02-27 | 98
A1-PM-EIM-0003 | 9.B*-Issue Utility demands, associated line sizes and electrical load data and equipment ratings final. | 2025-11-11 | 2026-03-05 |  | 2025-11-11 | 0
A1-PM-EIM-0004 | 10.B-Issue for COMPANY approval all documents for HAZOP / SIL review |  |  |  | 21-Jun-25 A | 0
A1-PM-EIM-0005 | 11.B-Complete HAZOP/ SIL Review and submit Close Out Report with all actions closed. | 2025-11-11 | 2026-02-25 |  | 2025-11-11 | 0
A1-PM-EIM-0006 | 12.B-Process design frozen | 2025-10-20 | 2027-01-20 |  | 2025-10-20 | 0
A1-PM-EIM-0007 | 13.B*-Issue IFC PFDs, P&IDs, Data Sheets, Equipment Lists, Line Lists complete incorporating HAZOP comments | 2025-11-11 | 2026-06-24 |  | 2025-11-11 | 0
A1-PM-EIM-0008 | 14.B*-Issue IFC Plot Plans, Equipment Layouts etc. complete |  |  |  | 06-May-25 A | 0
A1-PM-EIM-0009 | 15.B-Utility Consumption Issued for U&O |  |  |  | 20-Jun-25 A | 0
A1-PM-EIM-0010 | 16.B-Effluent Summary & Flare Loads Frozen for U&O | 2025-11-11 | 2026-03-05 |  | 2025-11-11 | 0
A1-PM-EIM-0011 | 17.B-Steam Balance Frozen for U&O | 2025-11-18 | 2026-03-05 |  | 2025-11-18 | 0
A1-PM-EIM-0012 | 18.B-Issue IFC all Single Line Diagrams, Hazardous Area classification details for all facilities (complete). | 2025-11-18 | 2026-03-05 |  | 2025-11-18 | 0
A1-PM-EIM-0013 | 19.B*-Issue MRs for all Major Equipment & Packages for purchase. |  |  |  | 16-Sep-25 A | 0
A1-PM-EIM-0014 | 20.B*-Receipt of key VENDOR data (by major equipment) | 2026-02-10 | 2026-08-14 |  | 2026-02-10 | 0
A1-PM-EIM-0015 | 21.B*-Issue IFC all underground services drawings | 2025-11-11 | 2026-03-05 |  | 2025-11-11 | 0
A1-PM-EIM-0016 | 22.B*-Issue IFC all foundation & superstructure drawings for all Equipment & Packages | 2025-11-18 | 2026-04-03 |  | 2025-11-18 | 0
A1-PM-EIM-0017 | 23.B-Issue IFC 95% of Civil / Structural drawings for pipe supports, pipe trestles, sleepers etc. complete. | 2026-01-16 | 2026-06-24 |  | 2026-01-16 | 0
A1-PM-EIM-0018 | 24.B-Issue IFC 95% of Civil / Structural drawings etc. for all Buildings. | 2025-10-24 | 2026-10-07 |  | 2025-10-24 | 0
A1-PM-EIM-0019 | 25.B-Complete 30% 3D-CAD model review |  |  |  | 25-May-25 A | 0
A1-PM-EIM-0020 | 26.B*-Complete 60% 3D-CAD model review |  |  |  | 18-Sep-25 A | 0
A1-PM-EIM-0021 | 27.B-Complete 90% 3D-CAD model review | 2026-01-02 | 2026-05-06 |  | 2026-01-02 | 0
A1-PM-EIM-0022 | 28.B*-Start issue piping isometrics IFC | 2025-11-05 | 2026-03-05 |  | 2025-11-05 | 0
A1-PM-EIM-0023 | 29.B-Issue 50% Piping Isometrics IFC | 2026-01-13 | 2026-06-24 |  | 2026-01-13 | 0
A1-PM-EIM-0024 | 30.B-Complete Piping Isometrics IFC | 2026-02-27 | 2026-06-24 |  | 2026-02-27 | 0
A1-PM-EIM-0025 | 31.B*-Issue 1st MTO and MRs for piping bulk materials |  |  |  | 21-Jun-25 A | 0
A1-PM-EIM-0026 | 32.B-Issue Intermediate MTO and MR’s for piping bulk materials | 2025-10-14 | 2026-03-05 |  | 2025-10-14 | 0
A1-PM-EIM-0027 | 33.B-Issue final MTO and MRs for piping bulk materials | 2025-10-22 | 2026-03-05 |  | 2025-10-22 | 0
A1-PM-EIM-0028 | 34.B-Establish piping interface details and finalize procedures with COMPANY | 2026-01-06 | 2026-10-15 |  | 2026-01-06 | 0
A1-PM-EIM-0029 | 35.B*-Issue IFC Electrical cable schedules, cable layouts, equipment layouts earthing layouts, lighting layouts, JB deta | 2026-02-11 | 2026-06-24 |  | 2026-02-11 | 0
A1-PM-EIM-0030 | 36.B-Issue first MTO and MRs for electrical bulk materials |  |  |  | 21-Jun-25 A | 0
A1-PM-EIM-0031 | 38.B*-Issue IFC Instrument cable schedules, cable layouts, equipment layouts, JB details, trench details etc. complete | 2026-01-07 | 2026-06-08 |  | 2026-01-07 | 0
A1-PM-EIM-0032 | 39.B-Issue first MTO and MRs for instrument bulk materials |  |  |  | 21-Jun-25 A | 0
A1-PM-EIM-0033 | 41.B*-Issue IFC Electrical/Instrument layouts, interconnection diagrams etc. including all building control SYSTEMS, HVA | 2025-11-18 | 2026-03-05 |  | 2025-11-18 | 0
A1-PM-EIM-0034 | 42.B-Finalize and issue IFC all instrumentation loop diagrams. | 2025-12-11 | 2026-03-05 |  | 2025-12-11 | 0
A1-PM-EIM-0035 | 44.B-Issue Operating, Maintenance and Safety Manual. | 2025-11-18 | 2026-03-05 |  | 2025-11-18 | 0
A1-PM-EIM-0036 | 45.B-Design for Turnaround Works |  |  |  | 02-Apr-25 A | 0
Procurement |  | 2027-01-20 | 2027-07-20 | 21-Feb-25 A | 2027-01-20 | 333
Procurement Deliverables |  | 2025-09-25 | 2026-07-13 | 03-Mar-25 A | 2025-09-25 | 5
A1-PM-PRD-0001 | PM-018-Equipment Delivery and storage Plan |  |  | 25-May-25 A | 25-Aug-25 A | 0
A1-PM-PRD-0002 | PM-019-Subcontracting Procedure |  |  | 25-May-25 A | 02-Sep-25 A | 0
A1-PM-PRD-0003 | PM-020-Procurement Procedures |  |  | 01-Jun-25 A | 25-Aug-25 A | 0
A1-PM-PRD-0004 | PM-021-Procurement Plan |  |  | 25-May-25 A | 15-Jun-25 A | 0
A1-PM-PRD-0005 | PM-022-Procurement Control Log |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0006 | PM-023-Transportation Plan & Procedure |  |  | 24-May-25 A | 25-Aug-25 A | 0
A1-PM-PRD-0007 | PM-024-Shipping Forecast |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0008 | PM-025-Copy of priced and unpriced Purchase Order |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0009 | PM-026-Vendor Schedules |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0010 | PM-027-Shipping Progress Report |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0011 | PM-033-Commercial Bid Analysis |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0012 | PM-034-Subcontract Award Recommendation |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0013 | PM-035-Vendor Prequalification's |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0014 | PM-036-Vendor Technical Queries /Answers |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0015 | PM-042-Subcontract Bidders List |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0016 | PM-043-Vendors List / Bidders Lists |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0017 | PM-044-Vendor List |  |  | 12-Jun-25 A | 25-Aug-25 A | 0
A1-PM-PRD-0018 | PM-051-Copy of unpriced sub contract agreement |  |  | 19-Jun-25 A | 02-Sep-25 A | 0
A1-PM-PRD-0019 | PM-055-Subcontract Pre Qualification |  |  | 19-Jun-25 A | 25-Aug-25 A | 0
A1-PM-PRD-0020 | PM-056-Vendor Manufacturing Quality Plan |  |  | 21-Jun-25 A | 23-Jul-25 A | 0
A1-PM-PRD-0021 | PM-058-Subcontract technical & commercial bid evaluation |  |  | 03-Mar-25 A | 28-May-25 A | 0
A1-PM-PRD-0022 | PM-059-Subcontract control log |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0023 | PM-060-Award Recommendation |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0024 | PM-066-Copy of Bill of Loading |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0025 | PM-067-Delivery Certificate on Site |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0026 | PM-068-Subcontract status report |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0027 | PM-069-Sub contractor performance feed back report |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0028 | PM-070-Material Status Report |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0029 | PM-071-Purchasing Status Report |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-PRD-0030 | PM-072-Vendor Performance feed back report | 2025-09-25 | 2026-07-13 | 2025-09-19 | 2025-09-25 | 5
Procurement Interim Milestones |  | 2027-01-20 | 2027-07-20 | 21-Feb-25 A | 2027-01-20 | 333
General Project Management |  | 2026-09-26 | 2027-01-03 | 28-Mar-25 A | 2026-09-26 | 0
A1-PM-PRM-0001 | 1.A*-Issue Procurement Procedures. |  |  |  | 28-Mar-25 A | 0
A1-PM-PRM-0002 | 7.A-VENDOR training and visits planned | 2026-09-26 | 2027-01-03 |  | 2026-09-26 | 0
Procurement Equipment & Materials |  | 2026-01-16 | 2026-11-11 | 21-Feb-25 A | 2026-01-16 | 66
A1-PM-PRM-0003 | 49.C*-Issue purchase order for Compressors Centrifugal / Reciprocating |  |  |  | 30-May-25 A | 0
A1-PM-PRM-0004 | 50.C*-Issue purchase orders for Furnaces |  |  |  | 21-Jun-25 A | 0
A1-PM-PRM-0005 | 51.C*-Issue purchase orders for all remaining Mechanical / Rotating Equipment & Equipment Packages | 2025-12-12 | 2026-11-11 |  | 2025-12-12 | 0
A1-PM-PRM-0006 | 52.C*-Issue purchase orders for all major electrical Equipment | 2026-01-16 | 2026-07-13 |  | 2026-01-16 | 0
A1-PM-PRM-0007 | 54.C*-Issue purchase order for all major instrument control SYSTEMS | 2025-12-16 | 2026-10-08 |  | 2025-12-16 | 0
A1-PM-PRM-0008 | 55.C*-Issue first purchase order for piping bulk materials | 2025-10-16 | 2025-11-07 |  | 2025-10-16 | 0
A1-PM-PRM-0009 | 56.C-Issue intermediate purchase order for piping bulk materials | 2025-10-16 | 2026-04-13 |  | 2025-10-16 | 0
A1-PM-PRM-0010 | 57.C-Issue final purchase order for piping bulk materials | 2025-12-30 | 2026-04-13 |  | 2025-12-30 | 0
A1-PM-PRM-0011 | 58.C-Issue purchase orders for all field instrument tagged items | 2025-11-25 | 2026-10-08 |  | 2025-11-25 | 0
A1-PM-PRM-0012 | 59.C*-Issue first purchase orders for bulk electrical materials |  |  |  | 21-Jun-25 A | 0
A1-PM-PRM-0013 | 60.C-Issue purchase orders for all Shut Down Materials (Piping, Electrical and Instrumentation |  |  |  | 28-Mar-25 A | 0
A1-PM-PRM-0014 | 61.C*-Issue first purchase orders for bulk instrument materials |  |  |  | 21-Jun-25 A | 0
A1-PM-PRM-0015 | 62.C-Issue purchase order Piping MTO for Shut Down Works |  |  |  | 21-Feb-25 A | 0
Subcontracts |  | 2025-09-19 | 2025-11-07 | 30-May-25 A | 2025-09-19 | 0
A1-PM-PRM-0016 | 63.C-Piling subcontract award |  |  |  | 01-Jun-25 A | 0
A1-PM-PRM-0017 | 64.C*-Civil subcontract award |  |  |  | 15-Jun-25 A | 0
A1-PM-PRM-0018 | 65.C-Steel fabrication/erection subcontract award | 2025-09-19 | 2025-11-07 |  | 2025-09-19 | 0
A1-PM-PRM-0019 | 66.C*-Mechanical subcontract award |  |  |  | 15-Jun-25 A | 0
A1-PM-PRM-0020 | 67.C-Insulation subcontract award |  |  |  | 15-Jun-25 A | 0
A1-PM-PRM-0021 | 68.C-Painting subcontract award |  |  |  | 15-Jun-25 A | 0
A1-PM-PRM-0022 | 69.C*-Electrical subcontract award |  |  |  | 15-Jun-25 A | 0
A1-PM-PRM-0023 | 70.C*-Instrument subcontract award |  |  |  | 15-Jun-25 A | 0
A1-PM-PRM-0024 | 71.C*-Buildings subcontract award |  |  |  | 30-May-25 A | 0
Manufacturing & Delivery |  | 2027-01-20 | 2027-07-20 | 20-Mar-25 A | 2027-01-20 | 255
A1-PM-PRM-0025 | 76.D*-Compressors Centrifugal / Reciprocating delivered to SITE | 2026-03-03 | 2026-04-26 |  | 2026-03-03 | 0
A1-PM-PRM-0026 | 77.D*-Furnaces delivered to SITE |  |  |  | 10-Sep-25 A | 0
A1-PM-PRM-0027 | 78.D*-Remaining Mechanical / Rotating Equipment & Equipment Packages delivered to SITE | 2026-09-18 | 2026-11-11 |  | 2026-09-18 | 0
A1-PM-PRM-0028 | 79.D*-All major electrical Equipment delivered to SITE | 2026-09-25 | 2027-01-03 |  | 2026-09-25 | 0
A1-PM-PRM-0029 | 80.D*-HVAC, Fire Detection and Fire Fighting SYSTEMS for all buildings delivered to SITE | 2026-08-27 | 2026-12-28 |  | 2026-08-27 | 0
A1-PM-PRM-0030 | 81.D*-Major instrument control SYSTEMS delivered to SITE | 2026-09-24 | 2026-12-10 |  | 2026-09-24 | 0
A1-PM-PRM-0031 | 82.D-Instrument Control SYSTEMS for CCB delivered to SITE | 2026-09-24 | 2026-12-10 |  | 2026-09-24 | 0
A1-PM-PRM-0032 | 83.D-Field instrument tagged items delivered to SITE | 2026-09-09 | 2026-12-10 |  | 2026-09-09 | 0
A1-PM-PRM-0033 | 84.D*-Bulk piping materials initial MTO delivered to SITE | 2026-01-12 | 2026-05-06 |  | 2026-01-12 | 0
A1-PM-PRM-0034 | 85.D*-Bulk piping materials intermediate MTO delivered to SITE | 2026-03-02 | 2026-03-26 |  | 2026-03-02 | 0
A1-PM-PRM-0035 | 86.D*-Bulk piping materials final MTO delivered to SITE | 2026-04-30 | 2026-10-07 |  | 2026-04-30 | 0
A1-PM-PRM-0036 | 88.D-Bulk electrical materials final MTO delivered to SITE | 2026-08-06 | 2026-12-10 |  | 2026-08-06 | 0
A1-PM-PRM-0037 | 90.D-Bulk instrument materials final MTO delivered to SITE | 2026-07-29 | 2026-10-07 |  | 2026-07-29 | 0
A1-PM-PRM-0038 | 91.D-Insurance spares for all equipment & packages arrival at SITE and handover to COMPANY | 2027-01-20 | 2027-07-20 |  | 2027-01-20 | 0
A1-PM-PRM-0039 | 92.D*-Operating Spares for all item’s arrival at SITE and handover to COMPANY. | 2027-01-20 | 2027-07-20 |  | 2027-01-20 | 0
A1-PM-PRM-0040 | 93.D*-All VENDOR Documentation Handed over to COMPANY | 2027-01-20 | 2027-07-20 |  | 2027-01-20 | 0
A1-PM-PRM-0041 | 94.D-Piping MTO for Shut Down Works Delivered to SITE |  |  |  | 20-Mar-25 A | 0
Construction |  | 2027-03-10 | 2027-07-20 | 19-Mar-25 A | 2027-03-10 | 368
Construction Deliverables |  | 2027-03-10 | 2027-04-21 | 19-Mar-25 A | 2027-03-10 | 384
A1-PM-COD-0001 | CS-001-QC Dossier | 2027-01-27 | 2027-03-10 | 2027-01-21 | 2027-01-27 | 5
A1-PM-COD-0002 | CS-002-Construction Handover Dossier ( ALL Discipline wise) | 2027-03-10 | 2027-04-21 | 2027-03-04 | 2027-03-10 | 5
A1-PM-COD-0003 | CS-003-Execution Plan | 2025-09-25 | 2026-07-20 | 25-May-25 A | 2025-09-25 | 5
A1-PM-COD-0004 | CS-004-Procedures |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0005 | CS-005-Field instructions | 2025-09-25 | 2026-07-06 | 05-Sep-25 A | 2025-09-25 | 5
A1-PM-COD-0006 | CS-006-Method Statements |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0007 | CS-007-Time Schedule / Programme |  |  | 19-Mar-25 A | 19-Jun-25 A | 0
A1-PM-COD-0008 | CS-008-Lifting |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0009 | CS-009-Site plans |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0010 | CS-010-Demolition plan |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0011 | CS-011-Temporary Works |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0012 | CS-012-label |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0013 | CS-013-Locking List |  |  | 02-Jun-25 A | 20-Jun-25 A | 0
A1-PM-COD-0014 | CS-014-Technical Bid Analysis |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0015 | CS-015-Insulation / Painting / Fire Proofing | 2025-09-25 | 2026-07-13 | 2025-09-19 | 2025-09-25 | 5
A1-PM-COD-0016 | CS-016-Punch List | 2025-09-25 | 2026-07-06 | 21-Jun-25 A | 2025-09-25 | 5
A1-PM-COD-0017 | CS-017-Check List | 2025-10-02 | 2026-07-13 | 2025-09-26 | 2025-10-02 | 5
A1-PM-COD-0018 | CS-018-Quality Assurance Docs |  |  | 02-Jun-25 A | 19-Jun-25 A | 0
A1-PM-COD-0019 | CS-019-HSE | 2025-09-25 | 2026-07-13 | 21-Jun-25 A | 2025-09-25 | 5
A1-PM-COD-0020 | CS-020-Test Certificate | 2025-10-09 | 2026-07-20 | 2025-10-03 | 2025-10-09 | 5
A1-PM-COD-0021 | CS-021-Quality Control Procedure | 2025-09-25 | 2026-07-20 | 21-Jun-25 A | 2025-09-25 | 5
A1-PM-COD-0022 | CS-022-Construction Strategies | 2025-10-16 | 2026-07-27 | 2025-10-10 | 2025-10-16 | 5
A1-PM-COD-0023 | CS-023-Concession Requests | 2025-10-23 | 2026-08-03 | 2025-10-17 | 2025-10-23 | 5
A1-PM-COD-0024 | CS-024-Non-Conformance Requests | 2025-10-30 | 2026-08-10 | 2025-10-24 | 2025-10-30 | 5
A1-PM-COD-0025 | CS-025-Electrical Specifications |  |  | 21-Jun-25 A | 20-Aug-25 A | 0
A1-PM-COD-0026 | CS-026-Civil Specifications |  |  | 21-Jun-25 A | 31-Jul-25 A | 0
A1-PM-COD-0027 | CS-027-Temporary facilities plan |  |  | 21-Jun-25 A | 30-Jun-25 A | 0
A1-PM-COD-0028 | CS-028-Construction execution methodologies (work methods) |  |  | 01-Apr-25 A | 07-Apr-25 A | 0
A1-PM-COD-0029 | CS-029-Logistics plan |  |  | 21-Jun-25 A | 30-Jun-25 A | 0
A1-PM-COD-0030 | CS-030-mobilisation/demobilisation plan | 2025-09-25 | 2026-07-13 | 01-Jul-25 A | 2025-09-25 | 5
A1-PM-COD-0031 | CS-031-Construction Cleanliness Plant | 2025-10-02 | 2026-07-20 | 2025-09-26 | 2025-10-02 | 5
A1-PM-COD-0032 | CS-032-Camp and Accommodation Plan |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-COD-0033 | CS-033-Construction logistic plan | 2025-11-06 | 2026-08-17 | 2025-10-31 | 2025-11-06 | 5
A1-PM-COD-0034 | CS-034-Field Construction Execution plan | 2025-10-17 | 2027-02-08 | 08-Apr-25 A | 2025-10-17 | 21
Construction Interim Milestones |  | 2027-02-21 | 2027-07-20 | 25-Mar-25 A | 2027-02-21 | 318
General Project Management |  | 2025-11-11 | 2027-02-08 | 31-May-25 A | 2025-11-11 | 0
A1-PM-CIM-0001 | 3.A-Issue Construction Execution Plan (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proc |  |  |  | 21-Jun-25 A | 0
A1-PM-CIM-0002 | 3.A-Issue Construction Execution Procedures (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONIN |  |  |  | 21-Jun-25 A | 0
A1-PM-CIM-0003 | 3.A-Issue Construction Execution Method Statements (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMI |  |  |  | 21-Jun-25 A | 0
A1-PM-CIM-0004 | 3.A-Tie-in/Shutdown philosophy etc. (Excluding Hydrotesting, Drying, Purging, PRE-COMMISSIONING and COMMISSIONING Proced |  |  |  | 31-May-25 A | 0
A1-PM-CIM-0005 | 4.A-Issue Hydrotesting Procedures and plan (Final). | 2025-11-11 | 2027-02-08 |  | 2025-11-11 | 0
A1-PM-CIM-0006 | 4.A-Issue Drying Procedures and plan (Final). | 2025-11-11 | 2027-02-08 |  | 2025-11-11 | 0
A1-PM-CIM-0007 | 4.A-Issue Purging Procedures and plan (Final). | 2025-11-11 | 2027-02-08 |  | 2025-11-11 | 0
A1-PM-CIM-0008 | 4.A-Issue PRECOMMISSIONING Procedures and plan (Final). | 2025-11-11 | 2027-02-08 |  | 2025-11-11 | 0
A1-PM-CIM-0009 | 4.A-Issue COMMISSIONING Procedures and plan (Final). | 2025-11-11 | 2027-02-08 |  | 2025-11-11 | 0
A1-PM-CIM-0010 | 4.A-Issue Handover Procedures and plan (Final). | 2025-11-11 | 2026-12-09 |  | 2025-11-11 | 0
Construction & Commissioning |  | 2026-12-12 | 2027-01-20 | 25-Mar-25 A | 2026-12-12 | 264
A1-PM-CIM-0011 | 94.E*-Commence on SITE |  |  |  | 31-May-25 A | 0
A1-PM-CIM-0012 | 95.E-Complete Construction of Temporary Facilities at SITE. | 2025-11-16 | 2026-08-22 |  | 2025-11-16 | 0
A1-PM-CIM-0013 | 96.E-Complete SITE preparation and grading works |  |  |  | 21-Jun-25 A | 0
A1-PM-CIM-0014 | 100.E-Complete construction of foundations for all remaining mechanical, rotating & packaged equipment | 2026-05-05 | 2026-08-22 |  | 2026-05-05 | 0
A1-PM-CIM-0015 | 101.E-Complete all Piperack foundations | 2026-03-05 | 2027-01-20 |  | 2026-03-05 | 0
A1-PM-CIM-0016 | 102.E-Complete all underground piping | 2026-03-07 | 2027-01-20 |  | 2026-03-07 | 0
A1-PM-CIM-0017 | 103.E-Complete installation of all underground electrical cabling | 2026-03-30 | 2026-12-09 |  | 2026-03-30 | 0
A1-PM-CIM-0018 | 104.E-Complete installation of all underground instrument cabling | 2026-07-25 | 2026-12-09 |  | 2026-07-25 | 0
A1-PM-CIM-0019 | 105.E-Trench for data highway cables SIS to Control Building available | 2026-03-30 | 2027-01-20 |  | 2026-03-30 | 0
A1-PM-CIM-0020 | 106.E-Complete installation of steel structural works for shelters, and Package Units etc. | 2026-09-10 | 2027-01-20 |  | 2026-09-10 | 0
A1-PM-CIM-0021 | 110.E-Complete installation of Turbines/Compressors | 2026-05-10 | 2027-01-20 |  | 2026-05-10 | 0
A1-PM-CIM-0022 | 111.E-Complete installation of all remaining mechanical, rotating & packaged equipment | 2026-11-02 | 2027-01-20 |  | 2026-11-02 | 0
A1-PM-CIM-0023 | 112.E-Completion of Heavy Lifts | 2026-05-10 | 2026-07-30 |  | 2026-05-10 | 0
A1-PM-CIM-0024 | 113.E-Start Piping Prefabrication |  |  |  | 25-Mar-25 A | 0
A1-PM-CIM-0025 | 114.E-Complete prefabrication 50% piping. | 2026-07-20 | 2027-01-20 |  | 2026-07-20 | 0
A1-PM-CIM-0026 | 115.E-Complete prefabrication 98% piping | 2026-08-24 | 2027-01-20 |  | 2026-08-24 | 0
A1-PM-CIM-0027 | 116.E-Complete installation of pipe supports, sleepers, trestles etc. | 2026-10-21 | 2027-01-20 |  | 2026-10-21 | 0
A1-PM-CIM-0028 | 117.E-Start Piping erection |  |  |  | 15-Apr-25 A | 0
A1-PM-CIM-0029 | 118.E-Piping erection 50% Complete | 2026-10-21 | 2027-01-20 |  | 2026-10-21 | 0
A1-PM-CIM-0030 | 119.E-Piping Erection 100% complete | 2026-10-21 | 2027-01-20 |  | 2026-10-21 | 0
A1-PM-CIM-0031 | 120.E-Commence hydrotesting of Pipework | 2026-11-25 | 2027-01-20 |  | 2026-11-25 | 0
A1-PM-CIM-0032 | 121.E-Piping Hydrotesting 50% complete | 2026-11-25 | 2027-01-20 |  | 2026-11-25 | 0
A1-PM-CIM-0033 | 122.E-Piping Hydrotesting 100% complete | 2026-12-03 | 2027-01-20 |  | 2026-12-03 | 0
A1-PM-CIM-0034 | 123.E-Complete all piping tie-ins (Including Interface Tie-Ins) |  |  |  | 20-May-25 A | 0
A1-PM-CIM-0035 | 124.E-Complete Fire Water System including tanks, pumps and piping works up to Mechanical Completion. | 2026-12-03 | 2027-01-20 |  | 2026-12-03 | 0
A1-PM-CIM-0036 | 125.E-Complete Heat Tracing, Insulation, Fire Proofing and Painting works | 2026-12-12 | 2027-01-20 |  | 2026-12-12 | 0
A1-PM-CIM-0037 | 126.E-Complete installation of platforms, walkways, crossovers etc. | 2026-09-10 | 2027-01-20 |  | 2026-09-10 | 0
A1-PM-CIM-0038 | 127.E-Complete installation of all Substation electrical equipment | 2026-09-26 | 2027-01-20 |  | 2026-09-26 | 0
A1-PM-CIM-0039 | 128.E-Trench for Main Electrical Feeder cables Main to Unit Substations available | 2026-03-30 | 2026-08-06 |  | 2026-03-30 | 0
A1-PM-CIM-0040 | 129.E-Complete electrical cabling and termination works (field works) for all plant facilities including continuity chec | 2026-12-06 | 2027-01-20 |  | 2026-12-06 | 0
A1-PM-CIM-0041 | 130.E-Complete Street lighting | 2026-09-13 | 2027-01-20 |  | 2026-09-13 | 0
Eelectrical |  | 2027-02-21 | 2027-07-20 | 2027-01-20 | 2027-02-21 | 22
A1-PM-CIM-0042 | 131.E-Power from TRANSCO (Needs) | 2027-01-20 | 2027-07-20 |  | 2027-01-20 | 0
A1-PM-CIM-0043 | 134.E-Complete motor run | 2027-02-21 | 2027-04-21 |  | 2027-02-21 | 0
Instrumentation |  | 2026-12-06 | 2027-04-21 | 2026-11-02 | 2026-12-06 | 30
A1-PM-CIM-0044 | 135.E-Control System Cables including Fiber opticinstalled and tested | 2026-11-02 | 2027-04-21 |  | 2026-11-02 | 0
A1-PM-CIM-0045 | 136.E-Complete instrumentation system loop checks and other PRE-COMMISSIONING checks | 2026-12-06 | 2027-04-21 |  | 2026-12-06 | 0
Mechanical Completion & Ready for START UP |  | 2027-01-20 | 2027-07-20 | 2027-01-20 | 2027-01-20 | 0
A1-PM-CIM-0046 | 138.F-Mechanical Completion | 2027-01-20 | 2027-07-20 |  | 2027-01-20 | 0
Construction Workshops |  |  |  | 27-Aug-25 A | 29-Aug-25 A | 0
A1-PM-CWS-0001 | Constructabilty Workshop |  |  | 27-Aug-25 A | 27-Aug-25 A | 0
A1-PM-CWS-0002 | SIMOPS Workshop |  |  | 28-Aug-25 A | 29-Aug-25 A | 0
Commissioning |  | 2027-07-20 | 2027-07-20 | 2025-09-19 | 2027-07-20 | 462
Commissioning Deliverables |  | 2026-02-12 | 2026-12-30 | 2025-09-19 | 2026-02-12 | 105
A1-PM-CMD-0001 | CM-001-Performance Test Run Procedure | 2025-10-09 | 2026-08-26 | 2025-09-19 | 2025-10-09 | 15
A1-PM-CMD-0002 | CM-002-Performance Test Run Report | 2025-10-30 | 2026-09-16 | 2025-10-10 | 2025-10-30 | 15
A1-PM-CMD-0003 | CM-003-Commissioning Procedures | 2025-11-20 | 2026-10-07 | 2025-10-31 | 2025-11-20 | 15
A1-PM-CMD-0004 | CM-004-Pre-Commisioning & Commissioning Schedule | 2025-12-11 | 2026-10-28 | 2025-11-21 | 2025-12-11 | 15
A1-PM-CMD-0005 | CM-005-Pre-Commisioning & Commissioning systems identification drawings (P&IDs, single line diagram, etc) | 2026-01-01 | 2026-11-18 | 2025-12-12 | 2026-01-01 | 15
A1-PM-CMD-0006 | CM-006-Pre- Commissioning Procedure | 2026-01-22 | 2026-12-09 | 2026-01-02 | 2026-01-22 | 15
A1-PM-CMD-0007 | CM-007-Pre-Commisioning & Commissioning Method of Statements | 2026-02-12 | 2026-12-30 | 2026-01-23 | 2026-02-12 | 15
Commissioning Interim Milestones |  | 2027-07-20 | 2027-07-20 | 2026-10-19 | 2027-07-20 | 194
General Project Management |  | 2027-01-20 | 2027-04-21 | 2027-01-20 | 2027-01-20 | 0
A1-PM-CMM-0001 | 6.A-Training program for COMPANY staff issued to COMPANY for APPROVAL | 2027-01-20 | 2027-04-21 |  | 2027-01-20 | 0
A1-PM-CMM-0006 | 5.A-Issue SYSTEMS definition IFC & SYSTEMS completion Schedule | 2027-01-20 | 2027-04-21 |  | 2027-01-20 | 0
Mechanical Completion & Ready for START UP |  | 2027-07-20 | 2027-07-20 | 2026-10-19 | 2027-07-20 | 194
A1-PM-CMM-0002 | 145.F-Ready for Start-Up | 2027-04-21 | 2027-07-20 |  | 2027-04-21 | 0
A1-PM-CMM-0003 | 142.F-Commercial Production | 2027-04-14 | 2027-07-20 |  | 2027-04-14 | 0
A1-PM-CMM-0004 | 143.F-Issue "AS BUILT STATUS”
operating/Maintenance & Safety Manual |  | 46588 |  | 2026-10-19 | 0
A1-PM-CMM-0005 | 144.F-PROVISIONAL ACCEPTANCE CERTIFICATE | 2027-07-20 | 2027-07-20 |  | 2027-07-20 | 0
HSE Management |  | 2026-07-24 | 2027-01-20 | 17-Feb-25 A | 2026-07-24 | 209
HSE Deliverables |  | 2026-01-14 | 2026-09-03 | 17-Feb-25 A | 2026-01-14 | 83
A1-PM-HSD-0001 | S-001-Procedures & Management of Change |  |  | 17-Feb-25 A | 03-Mar-25 A | 0
A1-PM-HSD-0002 | S-002-Requisition / Supply Specifications/ Technical Specifications | 2025-09-25 | 2026-07-23 | 2025-09-19 | 2025-09-25 | 5
A1-PM-HSD-0003 | S-003-HSE Requirements | 2025-09-19 | 2026-07-16 | 03-Mar-25 A | 2025-09-19 | 0
A1-PM-HSD-0004 | S-004-Fire Fighting Diagram / Fire Protection Diagram | 2025-09-25 | 2026-07-23 | 2025-09-19 | 2025-09-25 | 5
A1-PM-HSD-0005 | S-005-Site Plans / Plot Plans / Key Plans |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-HSD-0006 | S-006-Overall Fire Water & Ringman Header Layout |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-HSD-0007 | S-007-Project Construction HSE Plan / House Keeping Plan |  |  | 10-Jun-25 A | 11-Jul-25 A | 0
A1-PM-HSD-0008 | S-008-Fire Proofing Zone layout (Plant / Area Wise) | 2025-09-25 | 2026-07-16 | 2025-09-19 | 2025-09-25 | 5
A1-PM-HSD-0009 | S-009-HSE Layouts |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-HSD-0010 | S-010-Hazardous area Layouts | 2025-09-25 | 2026-06-25 | 22-Jul-25 A | 2025-09-25 | 5
A1-PM-HSD-0011 | S-011-Fire Exposure Envelop Drawings / Heat Flux Boundary Drawings | 2025-10-02 | 2026-07-02 | 2025-09-26 | 2025-10-02 | 5
A1-PM-HSD-0012 | S-012-Fire Alarm Drawings (Plant) | 2025-10-09 | 2026-07-09 | 2025-10-03 | 2025-10-09 | 5
A1-PM-HSD-0013 | S-013-Fire Alarm Drawings (Building) | 2025-10-16 | 2026-07-16 | 2025-10-10 | 2025-10-16 | 5
A1-PM-HSD-0014 | S-014-Bill of material |  |  | 02-Jun-25 A | 09-Jun-25 A | 0
A1-PM-HSD-0015 | S-015-Safety Schedule / Sheets |  |  | 09-Jun-25 A | 20-Jun-25 A | 0
A1-PM-HSD-0016 | S-016-Technical Bid Analysis |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-HSD-0017 | S-017-Hazard and Effect Register / HSECES Register/ HSE Critical Activities | 2025-10-02 | 2026-07-30 | 2025-09-26 | 2025-10-02 | 5
A1-PM-HSD-0018 | S-018-Equipment List |  |  | 21-Jun-25 A | 21-Jul-25 A | 0
A1-PM-HSD-0019 | S-019-Fire and Safety Calculations / Explosion Over Pressure Calculations / Hydraulic Calculation | 2025-10-23 | 2026-07-23 | 2025-10-17 | 2025-10-23 | 5
A1-PM-HSD-0020 | S-020-Hydraulic Calculations Report | 2025-10-30 | 2026-07-30 | 2025-10-24 | 2025-10-30 | 5
A1-PM-HSD-0021 | S-021-HAZOP / SIL (LOPA) Reports |  |  |  | 18-Jul-25 A | 0
A1-PM-HSD-0022 | S-022-Hazard Study / Fire Protection Design Study / Noise Vibration Study/ SIMOPS Study |  |  | 11-Aug-25 A | 29-Aug-25 A | 0
A1-PM-HSD-0023 | S-023-Quality Assurance Docs | 2025-09-25 | 2026-07-23 | 2025-09-19 | 2025-09-25 | 5
A1-PM-HSD-0024 | S-024-Manufacturing Data Report | 2025-10-02 | 2026-07-30 | 2025-09-26 | 2025-10-02 | 5
A1-PM-HSD-0025 | S-025-Installation, Operation and Maintenance | 2025-11-06 | 2026-08-06 | 2025-10-31 | 2025-11-06 | 5
A1-PM-HSD-0026 | S-026-Environmental / Effluent Disposal System/ Gas Dispersion /Environmental Pollution Reports / Fugitive Emissions Rep | 2025-11-13 | 2026-08-13 | 2025-11-07 | 2025-11-13 | 5
A1-PM-HSD-0027 | S-027-HSE Report / Close out Report/Atmospheric Relief System Report/ HSE- Safety Reviews | 2025-11-20 | 2026-08-20 | 2025-11-14 | 2025-11-20 | 5
A1-PM-HSD-0028 | S-028-QRA Reports | 2025-11-27 | 2026-08-27 | 2025-11-21 | 2025-11-27 | 5
A1-PM-HSD-0029 | S-029-COSHH Assessments | 2026-01-14 | 2026-09-03 | 2026-01-07 | 2026-01-14 | 5
A1-PM-HSD-0030 | S-030-Risk Assessment |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-HSD-0031 | S-031-Process Philosophies & HSE Plan |  |  | 14-Jul-25 A | 13-Aug-25 A | 0
A1-PM-HSD-0032 | S-032-Philosophies |  |  | 14-Aug-25 A | 19-Aug-25 A | 0
A1-PM-HSD-0033 | S-033-Data sheets (ALL Type of Safety Data sheets) |  |  | 20-Aug-25 A | 26-Aug-25 A | 0
A1-PM-HSD-0034 | S-034-Specifications |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1-PM-HSD-0035 | S-035-Ergonomic Study/ Human Factor Engineering / Assessment | 2025-10-02 | 2026-07-30 | 2025-09-26 | 2025-10-02 | 5
A1-PM-HSD-0036 | S-036-Safety Equipment and safety Routes Layout | 2025-10-09 | 2026-08-06 | 2025-10-03 | 2025-10-09 | 5
A1-PM-HSD-0037 | S-037-PHSER and Close Out Report | 2025-10-16 | 2026-08-13 | 2025-10-10 | 2025-10-16 | 5
A1-PM-HSD-0038 | S-038-List of Applicable Regulatory Requirements | 2025-10-23 | 2026-08-20 | 2025-10-17 | 2025-10-23 | 5
A1-PM-HSD-0039 | S-039-Waste Management Plan | 2025-09-25 | 2026-02-17 | 25-May-25 A | 2025-09-25 | 5
A1-PM-HSD-0040 | S-040-HSEIA Screening/ HSEIA Report/ HSEIA Dossier | 2025-12-31 | 2026-08-20 | 2025-12-24 | 2025-12-31 | 5
A1-PM-HSD-0041 | S-041-HSE deliverables as per HSE-RM-ST02 EPC deliverable requirements; not limited to : Building Fire and Safety revie | 2026-01-07 | 2026-08-27 | 2025-12-31 | 2026-01-07 | 5
HSE Studies |  | 2026-07-24 | 2027-01-20 | 01-May-25 A | 2026-07-24 | 209
HAZID/ENVID/OHID |  | 2025-12-23 | 2026-02-17 | 01-May-25 A | 2025-12-23 | 68
A58780 | HAZID / ENVID / OHID Workshop |  |  | 01-May-25 A | 10-May-25 A | 0
A58790 | HAZID / ENVID / OHID /_RCC | 2025-10-13 | 2025-12-09 | 26-May-25 A | 2025-10-13 | 17
A58800 | HAZID / ENVID / OHID /_IFA | 2025-11-05 | 2025-12-31 | 2025-10-13 | 2025-11-05 | 17
A58810 | HAZID / ENVID / OHID /_RCA | 2025-11-28 | 2026-01-23 | 2025-11-05 | 2025-11-28 | 17
A58820 | HAZID / ENVID / OHID /_IFD/IFC | 2025-12-23 | 2026-02-17 | 2025-11-28 | 2025-12-23 | 17
A60330 | HAZID / ENVID / OHID /_IFR |  |  | 11-May-25 A | 20-May-25 A | 0
Inherent Safer Design Review |  | 2025-12-23 | 2027-01-20 | 23-Jul-25 A | 2025-12-23 | 68
A59430 | Inherent Safer Design Review Preparation |  |  | 23-Jul-25 A | 31-Jul-25 A | 0
A59440 | Inherent Safer Design Review_RCC | 2025-10-13 | 2026-11-11 | 2025-09-19 | 2025-10-13 | 17
A59450 | Inherent Safer Design Review_IFA | 2025-11-05 | 2026-12-04 | 2025-10-13 | 2025-11-05 | 17
A59460 | Inherent Safer Design Review_RCA | 2025-11-28 | 2026-12-29 | 2025-11-05 | 2025-11-28 | 17
A59470 | Inherent Safer Design Review_IFD/IFC | 2025-12-23 | 2027-01-20 | 2025-11-28 | 2025-12-23 | 17
A60460 | Inherent Safer Design Review_IFR | 2025-09-19 | 2026-10-19 | 01-Aug-25 A | 2025-09-19 | 0
Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards |  | 2025-12-23 | 2026-02-17 | 25-Jul-25 A | 2025-12-23 | 68
A59280 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_Workshop |  |  | 25-Jul-25 A | 31-Jul-25 A | 0
A59290 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCC | 2025-10-13 | 2025-12-09 | 2025-09-19 | 2025-10-13 | 17
A59300 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFA | 2025-11-05 | 2025-12-31 | 2025-10-13 | 2025-11-05 | 17
A59310 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_RCA | 2025-11-28 | 2026-01-23 | 2025-11-05 | 2025-11-28 | 17
A59320 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 2025-12-23 | 2026-02-17 | 2025-11-28 | 2025-12-23 | 17
A60430 | Bow-tie Development & HSE Critical Equipment & Systems and Performance Standards_IFR |  |  | 01-Aug-25 A | 12-Aug-25 A | 0
HSECES and Performance Standards |  | 2026-01-07 | 2027-01-20 | 23-Jul-25 A | 2026-01-07 | 79
A61970 | HSE Critical Equipment & Systems and Performance Standards_Preparation |  |  | 23-Jul-25 A | 31-Jul-25 A | 0
A61980 | HSE Critical Equipment & Systems and Performance Standards_IFR | 2025-10-06 | 2026-10-19 | 2025-09-19 | 2025-10-06 | 11
A61990 | HSE Critical Equipment & Systems and Performance Standards_RCC | 2025-10-29 | 2026-11-11 | 2025-10-06 | 2025-10-29 | 17
A62000 | HSE Critical Equipment & Systems and Performance Standards_IFA | 2025-11-20 | 2026-12-04 | 2025-10-29 | 2025-11-20 | 17
A62010 | HSE Critical Equipment & Systems and Performance Standards_RCA | 2025-12-15 | 2026-12-29 | 2025-11-21 | 2025-12-15 | 17
A62020 | HSE Critical Equipment & Systems and Performance Standards_IFD/IFC | 2026-01-07 | 2027-01-20 | 2025-12-15 | 2026-01-07 | 17
HAZOP |  | 2026-01-07 | 2026-02-17 | 01-Jul-25 A | 2026-01-07 | 79
A62030 | HAZOP_Workshop |  |  | 01-Jul-25 A | 11-Jul-25 A | 0
A62040 | HAZOP_IFR | 2025-10-06 | 2025-11-14 | 12-Jul-25 A | 2025-10-06 | 11
A62050 | HAZOP_RCC | 2025-10-29 | 2025-12-09 | 2025-10-06 | 2025-10-29 | 17
A62060 | HAZOP_IFA | 2025-11-20 | 2025-12-31 | 2025-10-29 | 2025-11-20 | 17
A62070 | HAZOP_RCA | 2025-12-15 | 2026-01-23 | 2025-11-21 | 2025-12-15 | 17
A62080 | HAZOP_IFD/IFC | 2026-01-07 | 2026-02-17 | 2025-12-15 | 2026-01-07 | 17
SIL |  | 2025-10-30 | 2026-02-17 | 15-Aug-25 A | 2025-10-30 | 30
A23200 | SIL Review Workshop |  |  | 15-Aug-25 A | 17-Aug-25 A | 0
A23210 | Issue for Company Approval | 2025-10-23 | 2026-02-10 | 2025-10-09 | 2025-10-23 | 11
A23220 | Issue for Construction | 2025-10-30 | 2026-02-17 | 2025-10-24 | 2025-10-30 | 5
A60510 | Issue for Company Review | 2025-10-08 | 2026-01-26 | 2025-09-19 | 2025-10-08 | 14
Fire and Explosion Risk Assessment (FERA) |  | 2025-12-19 | 2026-02-17 | 01-Aug-25 A | 2025-12-19 | 65
A59480 | Fire and Explosion Risk Assessment (FERA)_Preparation |  |  | 01-Aug-25 A | 20-Aug-25 A | 0
A59490 | Fire and Explosion Risk Assessment (FERA)_RCC | 2025-11-19 | 2026-01-19 | 2025-10-29 | 2025-11-19 | 16
A59500 | Fire and Explosion Risk Assessment (FERA)_IFA | 2025-11-25 | 2026-01-22 | 2025-11-19 | 2025-11-25 | 3
A59510 | Fire and Explosion Risk Assessment (FERA)_RCA | 2025-12-16 | 2026-02-13 | 2025-11-25 | 2025-12-16 | 16
A59520 | Fire and Explosion Risk Assessment (FERA)_IFD/IFC | 2025-12-19 | 2026-02-17 | 2025-12-17 | 2025-12-19 | 2
A60470 | Fire and Explosion Risk Assessment (FERA)_IFR | 2025-10-29 | 2025-12-26 | 22-Aug-25 A | 2025-10-29 | 28
QRA |  | 2025-12-19 | 2026-02-17 | 07-Jul-25 A | 2025-12-19 | 65
A60590 | Workshop - QRA |  |  | 07-Jul-25 A | 15-Jul-25 A | 0
A60600 | QRA Report_IFR | 2025-10-29 | 2025-12-26 | 2025-09-19 | 2025-10-29 | 28
A60610 | QRA Report_RCC | 2025-11-19 | 2026-01-19 | 2025-10-29 | 2025-11-19 | 16
A60620 | QRA Report_IFA | 2025-11-25 | 2026-01-22 | 2025-11-19 | 2025-11-25 | 3
A60630 | QRA Report_RCA | 2025-12-16 | 2026-02-13 | 2025-11-25 | 2025-12-16 | 16
A60640 | QRA Report_IFD/IFC | 2025-12-19 | 2026-02-17 | 2025-12-17 | 2025-12-19 | 2
BRA |  | 2025-12-19 | 2026-11-20 | 07-Jul-25 A | 2025-12-19 | 65
A23290 | Workshop - BRA |  |  | 07-Jul-25 A | 15-Jul-25 A | 0
A60540 | BRA Report_IFR | 2025-10-29 | 2026-09-29 | 2025-09-19 | 2025-10-29 | 28
A60550 | BRA Report_RCC | 2025-11-19 | 2026-10-21 | 2025-10-29 | 2025-11-19 | 16
A60560 | BRA Report_IFA | 2025-11-25 | 2026-10-27 | 2025-11-19 | 2025-11-25 | 3
A60570 | BRA Report_RCA | 2025-12-16 | 2026-11-17 | 2025-11-25 | 2025-12-16 | 16
A60580 | BRA Report_IFD/IFC | 2025-12-19 | 2026-11-20 | 2025-12-17 | 2025-12-19 | 2
Escape Evacuation and Rescue Assessment (EERA) |  | 2025-12-19 | 2026-02-17 | 01-Aug-25 A | 2025-12-19 | 65
A59530 | Escape Evacuation and Rescue Assessment (EERA)_Preparation |  |  | 01-Aug-25 A | 15-Aug-25 A | 0
A59540 | Escape Evacuation and Rescue Assessment (EERA)_RCC | 2025-11-19 | 2026-01-19 | 2025-10-29 | 2025-11-19 | 16
A59550 | Escape Evacuation and Rescue Assessment (EERA)_IFA | 2025-11-25 | 2026-01-22 | 2025-11-19 | 2025-11-25 | 3
A59560 | Escape Evacuation and Rescue Assessment (EERA)_RCA | 2025-12-16 | 2026-02-13 | 2025-11-25 | 2025-12-16 | 16
A59570 | Escape Evacuation and Rescue Assessment (EERA)_IFD/IFC | 2025-12-19 | 2026-02-17 | 2025-12-17 | 2025-12-19 | 2
A60480 | Escape Evacuation and Rescue Assessment (EERA)_IFR | 2025-10-29 | 2025-12-26 | 16-Aug-25 A | 2025-10-29 | 28
Emergency Systems Survivability Analysis (ESSA) |  | 2025-12-19 | 2026-02-17 | 01-Aug-25 A | 2025-12-19 | 65
A58830 | Emergency Systems Survivability Analysis (ESSA)_IFR | 2025-10-29 | 2025-12-26 | 2025-09-19 | 2025-10-29 | 28
A58840 | Emergency Systems Survivability Analysis (ESSA)_RCC | 2025-11-19 | 2026-01-19 | 2025-10-29 | 2025-11-19 | 16
A58850 | Emergency Systems Survivability Analysis (ESSA)_IFA | 2025-11-25 | 2026-01-22 | 2025-11-19 | 2025-11-25 | 3
A58860 | Emergency Systems Survivability Analysis (ESSA)_RCA | 2025-12-16 | 2026-02-13 | 2025-11-25 | 2025-12-16 | 16
A58870 | Emergency Systems Survivability Analysis (ESSA)_IFD/IFC | 2025-12-19 | 2026-02-17 | 2025-12-17 | 2025-12-19 | 2
A60340 | Emergency Systems Survivability Analysis (ESSA)_Preparation |  |  | 01-Aug-25 A | 15-Aug-25 A | 0
Risk Reduction ALARP Workshop |  | 2026-02-19 | 2027-01-20 | 2025-12-19 | 2026-02-19 | 44
A59130 | Risk Reduction ALARP Workshop | 2025-12-26 | 2026-11-27 | 2025-12-19 | 2025-12-26 | 6
A59140 | Risk Reduction ALARP Workshop_Report RCC | 2026-01-20 | 2026-12-22 | 2026-01-05 | 2026-01-20 | 11
A59150 | Risk Reduction ALARP Workshop Report_IFA | 2026-01-26 | 2026-12-25 | 2026-01-20 | 2026-01-26 | 3
A59160 | Risk Reduction ALARP Workshop Report_RCA | 2026-02-16 | 2027-01-18 | 2026-01-26 | 2026-02-16 | 16
A59170 | Risk Reduction ALARP Workshop Report_IFD/IFC | 2026-02-19 | 2027-01-20 | 2026-02-16 | 2026-02-19 | 2
A60400 | Risk Reduction ALARP Workshop Report_IFR | 2026-01-05 | 2026-12-07 | 2025-12-26 | 2026-01-05 | 6
Air Emission Dispersion Assessment |  | 2025-12-11 | 2026-02-17 | 01-Aug-25 A | 2025-12-11 | 60
A59080 | Air Emission Dispersion Assessment_IFR | 2025-10-21 | 2025-12-26 | 16-Aug-25 A | 2025-10-21 | 23
A59090 | Air Emission Dispersion Assessment_RCC | 2025-11-12 | 2026-01-19 | 2025-10-21 | 2025-11-12 | 16
A59100 | Air Emission Dispersion Assessment_IFA | 2025-11-17 | 2026-01-22 | 2025-11-12 | 2025-11-17 | 3
A59110 | Air Emission Dispersion Assessment_RCA | 2025-12-09 | 2026-02-13 | 2025-11-17 | 2025-12-09 | 16
A59120 | Air Emission Dispersion Assessment_IFD/IFC | 2025-12-11 | 2026-02-17 | 2025-12-09 | 2025-12-11 | 2
A60390 | Air Emission Dispersion Assessment_Preparation |  |  | 01-Aug-25 A | 15-Aug-25 A | 0
Noise Study & Contours Report |  | 2025-11-13 | 2026-02-17 | 01-Aug-25 A | 2025-11-13 | 40
A62090 | Noise study & control report_Preparation |  |  | 01-Aug-25 A | 15-Aug-25 A | 0
A62100 | Noise study & control report_IFR | 2025-09-26 | 2025-11-21 | 16-Aug-25 A | 2025-09-26 | 6
A62110 | Noise study & control report_RCC | 2025-10-16 | 2025-12-11 | 2025-09-29 | 2025-10-16 | 14
A62120 | Noise study & control report_IFA | 2025-10-22 | 2025-12-16 | 2025-10-17 | 2025-10-22 | 3
A62130 | Noise study & control report_RCA | 2025-11-11 | 2026-02-13 | 2025-10-22 | 2025-11-11 | 14
A62140 | Noise study & control report_IFD/IFC | 2025-11-13 | 2026-02-17 | 2025-11-11 | 2025-11-13 | 2
Best Available Techniques Study (BAT) |  | 2025-11-28 | 2026-02-17 | 2025-09-23 | 2025-11-28 | 48
A58930 | Best Available Techniques Study_IFR | 2025-10-08 | 2025-12-18 | 2025-09-30 | 2025-10-08 | 6
A58940 | Best Available Techniques Study_RCC | 2025-10-29 | 2026-01-09 | 2025-10-08 | 2025-10-29 | 16
A58950 | Best Available Techniques Study_IFA | 2025-11-04 | 2026-01-22 | 2025-10-30 | 2025-11-04 | 3
A58960 | Best Available Techniques Study_RCA | 2025-11-26 | 2026-02-13 | 2025-11-04 | 2025-11-26 | 16
A58970 | Best Available Techniques Study_IFD/IFC | 2025-11-28 | 2026-02-17 | 2025-11-26 | 2025-11-28 | 2
A60360 | Best Available Techniques Study_Workshop | 2025-09-30 | 2025-12-11 | 2025-09-23 | 2025-09-30 | 6
Energy Review Workshop & Report |  | 2025-12-15 | 2027-01-20 | 2025-10-08 | 2025-12-15 | 48
A59380 | Energy Review Workshop | 2025-10-15 | 2025-12-26 | 2025-10-08 | 2025-10-15 | 6
A59390 | Energy Review Workshop & Report_RCC | 2025-11-14 | 2026-12-22 | 2025-10-23 | 2025-11-14 | 16
A59400 | Energy Review Workshop & Report_IFA | 2025-11-19 | 2026-12-25 | 2025-11-14 | 2025-11-19 | 3
A59410 | Energy Review Workshop & Report_RCA | 2025-12-11 | 2027-01-18 | 2025-11-19 | 2025-12-11 | 16
A59420 | Energy Review Workshop & Report_IFD/IFC | 2025-12-15 | 2027-01-20 | 2025-12-11 | 2025-12-15 | 2
A60450 | Energy Review Workshop & Report_IFR | 2025-10-23 | 2026-11-30 | 2025-10-15 | 2025-10-23 | 6
Vent & Flare Dispersion and Radiation Study |  | 2025-12-25 | 2026-02-17 | 2025-10-20 | 2025-12-25 | 48
A59630 | Vent & Flare Dispersion and Radiation Study Preparation ---- | 2025-10-27 | 2025-12-18 | 2025-10-20 | 2025-10-27 | 6
A59640 | Vent & Flare Dispersion and Radiation Study_RCC | 2025-11-25 | 2026-01-19 | 2025-11-04 | 2025-11-25 | 16
A59650 | Vent & Flare Dispersion and Radiation Study_IFA | 2025-12-01 | 2026-01-22 | 2025-11-26 | 2025-12-01 | 3
A59660 | Vent & Flare Dispersion and Radiation Study_RCA | 2025-12-23 | 2026-02-13 | 2025-12-01 | 2025-12-23 | 16
A59670 | Vent & Flare Dispersion and Radiation Study_IFD/IFC | 2025-12-25 | 2026-02-17 | 2025-12-23 | 2025-12-25 | 2
A60500 | Vent & Flare Dispersion and Radiation Study_IFR | 2025-11-04 | 2025-12-26 | 2025-10-27 | 2025-11-04 | 6
Environment Impact Assessment |  | 2025-12-24 | 2026-02-17 | 2025-10-22 | 2025-12-24 | 45
A59030 | Environment Impact Assessment_IFR | 2025-11-06 | 2026-01-01 | 2025-10-30 | 2025-11-06 | 6
A59040 | Environment Impact Assessment_RCC | 2025-11-26 | 2026-01-21 | 2025-11-06 | 2025-11-26 | 14
A59050 | Environment Impact Assessment_IFA | 2025-12-01 | 2026-01-26 | 2025-11-26 | 2025-12-01 | 3
A59060 | Environment Impact Assessment_RCA | 2025-12-19 | 2026-02-13 | 2025-12-02 | 2025-12-19 | 14
A59070 | Environment Impact Assessment_IFD/IFC | 2025-12-24 | 2026-02-17 | 2025-12-22 | 2025-12-24 | 2
A60380 | Environment Impact Assessment_Workshop ---- | 2025-10-29 | 2025-12-24 | 2025-10-22 | 2025-10-29 | 6
Ergonomics and Human Factor Engineering Study |  | 2026-04-13 | 2027-01-20 | 2025-11-26 | 2026-04-13 | 98
A58730 | Ergonomics and Human Factor Engineering Study_IFR | 2025-12-10 | 2026-09-21 | 2025-12-03 | 2025-12-10 | 6
A58740 | Ergonomics and Human Factor Engineering Study_RCC | 2026-01-13 | 2026-10-22 | 2025-12-10 | 2026-01-13 | 24
A58750 | Ergonomics and Human Factor Engineering Study_IFA | 2026-02-13 | 2026-11-25 | 2026-01-13 | 2026-02-13 | 24
A58760 | Ergonomics and Human Factor Engineering Study_RCA | 2026-03-19 | 2026-12-29 | 2026-02-16 | 2026-03-19 | 24
A58770 | Ergonomics and Human Factor Engineering Study_IFD/IFC | 2026-04-13 | 2027-01-20 | 2026-03-19 | 2026-04-13 | 17
A60320 | Ergonomics and Human Factor Engineering Study Workshop | 2025-12-03 | 2026-09-11 | 2025-11-26 | 2025-12-03 | 5
Dropped Objects Study (DOS) |  | 2026-02-23 | 2027-01-20 | 2025-11-26 | 2026-02-23 | 63
A58880 | Dropped Objects Study (DOS)_IFR | 2025-12-31 | 2026-11-30 | 2025-12-03 | 2025-12-31 | 20
A58890 | Dropped Objects Study (DOS)_RCC | 2026-01-22 | 2026-12-22 | 2026-01-01 | 2026-01-22 | 16
A58900 | Dropped Objects Study (DOS)_IFA | 2026-01-28 | 2026-12-25 | 2026-01-22 | 2026-01-28 | 3
A58910 | Dropped Objects Study (DOS)_RCA | 2026-02-18 | 2027-01-18 | 2026-01-28 | 2026-02-18 | 16
A58920 | Dropped Objects Study (DOS)_IFD/IFC | 2026-02-23 | 2027-01-20 | 2026-02-18 | 2026-02-23 | 2
A60350 | Dropped Objects Study (DOS)_Workshop | 2025-12-03 | 2026-11-02 | 2025-11-26 | 2025-12-03 | 6
3D F&G mapping study |  | 2026-02-02 | 2027-01-20 | 2025-11-26 | 2026-02-02 | 48
A58980 | 3D F&G mapping study_IFR | 2025-12-11 | 2026-11-30 | 2025-12-03 | 2025-12-11 | 6
A58990 | 3D F&G mapping study_RCC | 2026-01-02 | 2026-12-22 | 2025-12-11 | 2026-01-02 | 16
A59000 | 3D F&G mapping study_IFA | 2026-01-07 | 2026-12-25 | 2026-01-02 | 2026-01-07 | 3
A59010 | 3D F&G mapping study_RCA | 2026-01-29 | 2027-01-18 | 2026-01-07 | 2026-01-29 | 16
A59020 | 3D F&G mapping study_IFD/IFC | 2026-02-02 | 2027-01-20 | 2026-01-29 | 2026-02-02 | 2
A60370 | 3D F&G mapping study_Preparation | 2025-12-03 | 2026-11-23 | 2025-11-26 | 2025-12-03 | 6
E-HAZOP |  | 2025-12-03 | 2027-01-20 | 2025-09-30 | 2025-12-03 | 46
A62150 | E-HAZOP_Workshop | 2025-10-03 | 2026-02-23 | 2025-09-30 | 2025-10-03 | 3
A62160 | E-HAZOP_IFR | 2025-10-13 | 2026-11-30 | 2025-10-06 | 2025-10-13 | 6
A62170 | E-HAZOP_RCC | 2025-11-04 | 2026-12-22 | 2025-10-13 | 2025-11-04 | 16
A62180 | E-HAZOP_IFA | 2025-11-07 | 2026-12-25 | 2025-11-04 | 2025-11-07 | 3
A62190 | E-HAZOP_RCA | 2025-12-01 | 2027-01-18 | 2025-11-07 | 2025-12-01 | 16
A62200 | E-HAZOP_IFD/IFC | 2025-12-03 | 2027-01-20 | 2025-12-01 | 2025-12-03 | 2
Constructability Review |  | 2025-11-18 | 2026-03-05 | 27-Aug-25 A | 2025-11-18 | 43
A59180 | Constructability Review Workshop |  |  | 27-Aug-25 A | 27-Aug-25 A | 0
A59190 | Constructability Review_RCC | 2025-10-20 | 2026-02-03 | 2025-09-26 | 2025-10-20 | 16
A59200 | Constructability Review_IFA | 2025-10-23 | 2026-02-09 | 2025-10-20 | 2025-10-23 | 3
A59210 | Constructability Review_RCA | 2025-11-14 | 2026-03-02 | 2025-10-23 | 2025-11-14 | 16
A59220 | Constructability Review_IFD/IFC | 2025-11-18 | 2026-03-05 | 2025-11-14 | 2025-11-18 | 2
A60410 | Constructability Review_IFR | 2025-09-26 | 2026-01-13 | 2025-09-19 | 2025-09-26 | 6
SIMPOS |  | 2025-11-18 | 2026-03-05 | 28-Aug-25 A | 2025-11-18 | 43
A59680 | SIMOPS Workshop |  |  | 28-Aug-25 A | 28-Aug-25 A | 0
A59690 | SIMOPS Report_RCC | 2025-10-20 | 2026-02-03 | 2025-09-26 | 2025-10-20 | 16
A59700 | SIMOPS Report_IFA | 2025-10-23 | 2026-02-09 | 2025-10-20 | 2025-10-23 | 3
A59710 | SIMOPS Report_RCA | 2025-11-14 | 2026-03-02 | 2025-10-23 | 2025-11-14 | 16
A59720 | SIMOPS Report_IFD/IFC | 2025-11-18 | 2026-03-05 | 2025-11-14 | 2025-11-18 | 2
A60520 | SIMOPS Report_IFR | 2025-09-26 | 2026-01-13 | 2025-09-19 | 2025-09-26 | 6
HSEIA |  | 2026-03-26 | 2027-01-20 | 2026-01-07 | 2026-03-26 | 56
A61370 | HSEIA Report Preparation | 2026-01-15 | 2026-02-25 | 2026-01-07 | 2026-01-15 | 6
A61380 | HSEIA Report_IFR | 2026-01-22 | 2026-03-04 | 2026-01-15 | 2026-01-22 | 6
A61390 | HSEIA Report_RCC | 2026-02-13 | 2026-12-22 | 2026-01-23 | 2026-02-13 | 16
A61400 | HSEIA Report_IFA | 2026-02-19 | 2026-12-25 | 2026-02-13 | 2026-02-19 | 3
A61410 | HSEIA Report_RCA | 2026-03-12 | 2027-01-18 | 2026-02-19 | 2026-03-12 | 16
A61420 | HSEIA Report_IFD/IFC | 2026-03-17 | 2027-01-20 | 2026-03-12 | 2026-03-17 | 2
A61840 | HSEIA Report ADNOC Approval | 2026-03-26 | 2026-05-06 | 2026-01-23 | 2026-03-26 | 45
HSEIA Report | [5 empty] | 0
PHSER III |  | 2026-03-11 | 2026-09-08 | 2026-01-02 | 2026-03-11 | 48
A59330 | PHSER III_Workshop | 2026-01-09 | 2026-07-09 | 2026-01-02 | 2026-01-09 | 6
A59340 | PHSER III_RCC | 2026-02-10 | 2026-08-07 | 2026-01-19 | 2026-02-10 | 16
A59350 | PHSER III_IFA | 2026-02-13 | 2026-08-13 | 2026-02-10 | 2026-02-13 | 3
A59360 | PHSER III_RCA | 2026-03-09 | 2026-09-03 | 2026-02-13 | 2026-03-09 | 16
A59370 | PHSER III_IFD/IFC | 2026-03-11 | 2026-09-08 | 2026-03-09 | 2026-03-11 | 2
A60440 | PHSER III_IFR | 2026-01-19 | 2026-07-17 | 2026-01-12 | 2026-01-19 | 6
PHSER IV |  | 2026-05-19 | 2026-11-13 | 2026-03-11 | 2026-05-19 | 48
A61850 | PHSER IV_Workshop | 2026-03-19 | 2026-09-15 | 2026-03-11 | 2026-03-19 | 6
A61860 | PHSER IV_RCC | 2026-04-17 | 2026-10-15 | 2026-03-27 | 2026-04-17 | 16
A61870 | PHSER IV_IFA | 2026-04-23 | 2026-10-20 | 2026-04-17 | 2026-04-23 | 3
A61880 | PHSER IV_RCA | 2026-05-14 | 2026-11-11 | 2026-04-23 | 2026-05-14 | 16
A61890 | PHSER IV_IFD/IFC | 2026-05-19 | 2026-11-13 | 2026-05-14 | 2026-05-19 | 2
A61900 | PHSER IV_IFR | 2026-03-26 | 2026-09-23 | 2026-03-19 | 2026-03-26 | 6
PHSER V |  | 2026-07-24 | 2027-01-20 | 2026-05-19 | 2026-07-24 | 48
A61910 | PHSER V_Workshop | 2026-05-26 | 2026-11-23 | 2026-05-19 | 2026-05-26 | 6
A61920 | PHSER V_RCC | 2026-06-25 | 2026-12-22 | 2026-06-03 | 2026-06-25 | 16
A61930 | PHSER V_FA | 2026-06-30 | 2026-12-25 | 2026-06-25 | 2026-06-30 | 3
A61940 | PHSER V_RCA | 2026-07-22 | 2027-01-18 | 2026-06-30 | 2026-07-22 | 16
A61950 | PHSER V_IFD/IFC | 2026-07-24 | 2027-01-20 | 2026-07-22 | 2026-07-24 | 2
A61960 | PHSER V_IFR | 2026-06-03 | 2026-11-30 | 2026-05-26 | 2026-06-03 | 6
QA/QC Management |  | 2027-03-04 | 2027-07-20 | 25-May-25 A | 2027-03-04 | 380
QAQC Deliverables |  | 2025-12-11 | 2026-10-29 | 25-May-25 A | 2025-12-11 | 60
A1-PM-QCD-0001 | PCQ-001-Inspection Record | 2025-09-25 | 2025-12-18 | 2025-09-19 | 2025-09-25 | 5
A1-PM-QCD-0002 | PCQ-002-Inspection Check List | 2025-10-02 | 2025-12-25 | 2025-09-26 | 2025-10-02 | 5
A1-PM-QCD-0003 | PCQ-003-Test Certificate | 2025-10-09 | 2026-01-01 | 2025-10-03 | 2025-10-09 | 5
A1-PM-QCD-0004 | PCQ-004-Inspection and Test Plan Vendor | 2025-10-16 | 2026-01-08 | 2025-10-10 | 2025-10-16 | 5
A1-PM-QCD-0005 | PCQ-005-Inspection and Test Plan Site | 2025-10-23 | 2026-01-15 | 2025-10-17 | 2025-10-23 | 5
A1-PM-QCD-0006 | PCQ-006-Inspection and Test Plan | 2025-10-30 | 2026-01-22 | 2025-10-24 | 2025-10-30 | 5
A1-PM-QCD-0007 | PCQ-007-Quality Assurance Docs | 2025-11-06 | 2026-01-29 | 2025-10-31 | 2025-11-06 | 5
A1-PM-QCD-0008 | PCQ-008-Inspection Guidelines (Source and Field) | 2025-11-13 | 2026-02-05 | 2025-11-07 | 2025-11-13 | 5
A1-PM-QCD-0009 | PCQ-009-Inspection / Expediting / Reports | 2025-11-20 | 2026-02-12 | 2025-11-14 | 2025-11-20 | 5
A1-PM-QCD-0010 | PCQ-010-Vendor Shop Inspection & Quality Control Plans | 2025-11-27 | 2026-02-19 | 2025-11-21 | 2025-11-27 | 5
A1-PM-QCD-0011 | PCQ-011-Site Contractors Quality Plans |  |  | 25-May-25 A | 03-Sep-25 A | 0
A1-PM-QCD-0012 | PCQ-012-Worksite Quality Plan | 2025-09-25 | 2026-10-29 | 03-Sep-25 A | 2025-09-25 | 5
A1-PM-QCD-0013 | PCQ-013-Inspection Plan and Schedule | 2025-12-04 | 2026-02-26 | 2025-11-28 | 2025-12-04 | 5
A1-PM-QCD-0014 | PCQ-014-Inspection Release Report | 2025-12-11 | 2026-03-05 | 2025-12-05 | 2025-12-11 | 5
QAQC Audit Plan |  | 2027-03-04 | 2027-07-20 | 25-May-25 A | 2027-03-04 | 380
A1-PM-QAP-0001 | QAQC Audit Plan | 2027-03-04 | 2027-07-20 | 25-May-25 A | 2027-03-04 | 380
Contractor's Temporary Facilities |  |  |  | 20-Jan-25 A | 20-Jan-25 A | 0
Home Office |  |  |  | 20-Jan-25 A | 20-Jan-25 A | 0
A1-PM-CTF-0001 | Home Office Ready for IPMT Moblization |  |  |  | 20-Jan-25 A | 0
Others |  | 2027-07-20 | 2027-07-20 | 20-Dec-24 A | 2027-07-20 | 462
Project Key Milestones |  | 2027-07-20 | 2027-07-20 | 12-Apr-25 A | 2027-07-20 | 181
A1-PM-PKM-0001 | Turnaround Scope Completion (TA) |  |  | 12-Apr-25 A | 17-May-25 A | 0
A1-PM-PKM-0002 | Mechanical Completion (MC) | 2027-01-20 | 2027-01-20 |  | 2027-01-20 | 0
A1-PM-PKM-0003 | Ready for Start-up (RFSU) | 2027-04-21 | 2027-04-21 |  | 2027-04-21 | 0
A1-PM-PKM-0004 | Provisional Acceptance Certificate (PAC) | 2027-07-20 | 2027-07-20 |  | 2027-07-20 | 0
Weekly Progress Report |  | 2026-11-18 | 2027-07-20 | 03-Jan-25 A | 2026-11-18 | 283
A1-PM-WPR-0001 | Weekly Progress Report Issuance - WPR0001 |  |  |  | 03-Jan-25 A | 0
A1-PM-WPR-0002 | Weekly Progress Report Issuance - WPR0002 |  |  |  | 10-Jan-25 A | 0
A1-PM-WPR-0003 | Weekly Progress Report Issuance - WPR0003 |  |  |  | 17-Jan-25 A | 0
A1-PM-WPR-0004 | Weekly Progress Report Issuance - WPR0004 |  |  |  | 24-Jan-25 A | 0
A1-PM-WPR-0005 | Weekly Progress Report Issuance - WPR0005 |  |  |  | 31-Jan-25 A | 0
A1-PM-WPR-0006 | Weekly Progress Report Issuance - WPR0006 |  |  |  | 07-Feb-25 A | 0
A1-PM-WPR-0007 | Weekly Progress Report Issuance - WPR0007 |  |  |  | 14-Feb-25 A | 0
A1-PM-WPR-0008 | Weekly Progress Report Issuance - WPR0008 |  |  |  | 21-Feb-25 A | 0
A1-PM-WPR-0009 | Weekly Progress Report Issuance - WPR0009 |  |  |  | 28-Feb-25 A | 0
A1-PM-WPR-0010 | Weekly Progress Report Issuance - WPR0010 |  |  |  | 06-May-25 A | 0
A1-PM-WPR-0011 | Weekly Progress Report Issuance - WPR0011 |  |  |  | 06-May-25 A | 0
A1-PM-WPR-0012 | Weekly Progress Report Issuance - WPR0012 |  |  |  | 06-May-25 A | 0
A1-PM-WPR-0013 | Weekly Progress Report Issuance - WPR0013 |  |  |  | 06-May-25 A | 0
A1-PM-WPR-0014 | Weekly Progress Report Issuance - WPR0014 |  |  |  | 06-May-25 A | 0
A1-PM-WPR-0015 | Weekly Progress Report Issuance - WPR0015 |  |  |  | 06-May-25 A | 0
A1-PM-WPR-0016 | Weekly Progress Report Issuance - WPR0016 |  |  |  | 18-Apr-25 A | 0
A1-PM-WPR-0017 | Weekly Progress Report Issuance - WPR0017 |  |  |  | 09-May-25 A | 0
A1-PM-WPR-0018 | Weekly Progress Report Issuance - WPR0018 |  |  |  | 09-May-25 A | 0
A1-PM-WPR-0019 | Weekly Progress Report Issuance - WPR0019 |  |  |  | 13-May-25 A | 0
A1-PM-WPR-0020 | Weekly Progress Report Issuance - WPR0020 |  |  |  | 21-May-25 A | 0
A1-PM-WPR-0021 | Weekly Progress Report Issuance - WPR0021 |  |  |  | 28-May-25 A | 0
A1-PM-WPR-0022 | Weekly Progress Report Issuance - WPR0022 |  |  |  | 08-Jun-25 A | 0
A1-PM-WPR-0023 | Weekly Progress Report Issuance - WPR0023 |  |  |  | 06-Jun-25 A | 0
A1-PM-WPR-0024 | Weekly Progress Report Issuance - WPR0024 |  |  |  | 13-Jun-25 A | 0
A1-PM-WPR-0025 | Weekly Progress Report Issuance - WPR0025 |  |  |  | 21-Jun-25 A | 0
A1-PM-WPR-0026 | Weekly Progress Report Issuance - WPR0026 |  |  |  | 30-Jun-25 A | 0
A1-PM-WPR-0027 | Weekly Progress Report Issuance - WPR0027 |  |  |  | 10-Jul-25 A | 0
A1-PM-WPR-0028 | Weekly Progress Report Issuance - WPR0028 |  |  |  | 18-Jul-25 A | 0
A1-PM-WPR-0029 | Weekly Progress Report Issuance - WPR0029 |  |  |  | 22-Aug-25 A | 0
A1-PM-WPR-0030 | Weekly Progress Report Issuance - WPR0030 |  |  |  | 27-Aug-25 A | 0
A1-PM-WPR-0031 | Weekly Progress Report Issuance - WPR0031 |  |  |  | 02-Sep-25 A | 0
A1-PM-WPR-0032 | Weekly Progress Report Issuance - WPR0032 |  |  |  | 07-Sep-25 A | 0
A1-PM-WPR-0033 | Weekly Progress Report Issuance - WPR0033 |  |  |  | 13-Sep-25 A | 0
A1-PM-WPR-0034 | Weekly Progress Report Issuance - WPR0034 |  |  |  | 27-Aug-25 A | 0
A1-PM-WPR-0035 | Weekly Progress Report Issuance - WPR0035 |  |  |  | 15-Sep-25 A | 0
A1-PM-WPR-0036 | Weekly Progress Report Issuance - WPR0036 |  |  |  | 15-Sep-25 A | 0
A1-PM-WPR-0037 | Weekly Progress Report Issuance - WPR0037 |  |  |  | 12-Sep-25 A | 0
A1-PM-WPR-0038 | Weekly Progress Report Issuance - WPR0038 |  |  |  | 19-Sep-25 A | 0
A1-PM-WPR-0039 | Weekly Progress Report Issuance - WPR0039 | 2025-09-29 | 2026-06-01 |  | 2025-09-29 | 0
A1-PM-WPR-0040 | Weekly Progress Report Issuance - WPR0040 | 2025-10-05 | 2026-06-07 |  | 2025-10-05 | 0
A1-PM-WPR-0041 | Weekly Progress Report Issuance - WPR0041 | 2025-10-11 | 2026-06-12 |  | 2025-10-11 | 0
A1-PM-WPR-0042 | Weekly Progress Report Issuance - WPR0042 | 2025-10-16 | 2026-06-18 |  | 2025-10-16 | 0
A1-PM-WPR-0043 | Weekly Progress Report Issuance - WPR0043 | 2025-10-22 | 2026-06-23 |  | 2025-10-22 | 0
A1-PM-WPR-0044 | Weekly Progress Report Issuance - WPR0044 | 2025-10-27 | 2026-06-29 |  | 2025-10-27 | 0
A1-PM-WPR-0045 | Weekly Progress Report Issuance - WPR0045 | 2025-11-02 | 2026-07-05 |  | 2025-11-02 | 0
A1-PM-WPR-0046 | Weekly Progress Report Issuance - WPR0046 | 2025-11-08 | 2026-07-10 |  | 2025-11-08 | 0
A1-PM-WPR-0047 | Weekly Progress Report Issuance - WPR0047 | 2025-11-13 | 2026-07-16 |  | 2025-11-13 | 0
A1-PM-WPR-0048 | Weekly Progress Report Issuance - WPR0048 | 2025-11-19 | 2026-07-21 |  | 2025-11-19 | 0
A1-PM-WPR-0049 | Weekly Progress Report Issuance - WPR0049 | 2025-11-24 | 2026-07-27 |  | 2025-11-24 | 0
A1-PM-WPR-0050 | Weekly Progress Report Issuance - WPR0050 | 2025-11-30 | 2026-08-02 |  | 2025-11-30 | 0
A1-PM-WPR-0051 | Weekly Progress Report Issuance - WPR0051 | 2025-12-06 | 2026-08-07 |  | 2025-12-06 | 0
A1-PM-WPR-0052 | Weekly Progress Report Issuance - WPR0052 | 2025-12-11 | 2026-08-13 |  | 2025-12-11 | 0
A1-PM-WPR-0053 | Weekly Progress Report Issuance - WPR0053 | 2025-12-17 | 2026-08-18 |  | 2025-12-17 | 0
A1-PM-WPR-0054 | Weekly Progress Report Issuance - WPR0054 | 2025-12-22 | 2026-08-24 |  | 2025-12-22 | 0
A1-PM-WPR-0055 | Weekly Progress Report Issuance - WPR0055 | 2025-12-28 | 2026-08-30 |  | 2025-12-28 | 0
A1-PM-WPR-0056 | Weekly Progress Report Issuance - WPR0056 | 2026-01-03 | 2026-09-04 |  | 2026-01-03 | 0
A1-PM-WPR-0057 | Weekly Progress Report Issuance - WPR0057 | 2026-01-08 | 2026-09-10 |  | 2026-01-08 | 0
A1-PM-WPR-0058 | Weekly Progress Report Issuance - WPR0058 | 2026-01-14 | 2026-09-15 |  | 2026-01-14 | 0
A1-PM-WPR-0059 | Weekly Progress Report Issuance - WPR0059 | 2026-01-19 | 2026-09-21 |  | 2026-01-19 | 0
A1-PM-WPR-0060 | Weekly Progress Report Issuance - WPR0060 | 2026-01-25 | 2026-09-27 |  | 2026-01-25 | 0
A1-PM-WPR-0061 | Weekly Progress Report Issuance - WPR0061 | 2026-01-31 | 2026-10-02 |  | 2026-01-31 | 0
A1-PM-WPR-0062 | Weekly Progress Report Issuance - WPR0062 | 2026-02-05 | 2026-10-08 |  | 2026-02-05 | 0
A1-PM-WPR-0063 | Weekly Progress Report Issuance - WPR0063 | 2026-02-11 | 2026-10-13 |  | 2026-02-11 | 0
A1-PM-WPR-0064 | Weekly Progress Report Issuance - WPR0064 | 2026-02-16 | 2026-10-19 |  | 2026-02-16 | 0
A1-PM-WPR-0065 | Weekly Progress Report Issuance - WPR0065 | 2026-02-22 | 2026-10-25 |  | 2026-02-22 | 0
A1-PM-WPR-0066 | Weekly Progress Report Issuance - WPR0066 | 2026-02-28 | 2026-10-30 |  | 2026-02-28 | 0
A1-PM-WPR-0067 | Weekly Progress Report Issuance - WPR0067 | 2026-03-05 | 2026-11-05 |  | 2026-03-05 | 0
A1-PM-WPR-0068 | Weekly Progress Report Issuance - WPR0068 | 2026-03-11 | 2026-11-10 |  | 2026-03-11 | 0
A1-PM-WPR-0069 | Weekly Progress Report Issuance - WPR0069 | 2026-03-16 | 2026-11-16 |  | 2026-03-16 | 0
A1-PM-WPR-0070 | Weekly Progress Report Issuance - WPR0070 | 2026-03-22 | 2026-11-22 |  | 2026-03-22 | 0
A1-PM-WPR-0071 | Weekly Progress Report Issuance - WPR0071 | 2026-03-28 | 2026-11-27 |  | 2026-03-28 | 0
A1-PM-WPR-0072 | Weekly Progress Report Issuance - WPR0072 | 2026-04-02 | 2026-12-03 |  | 2026-04-02 | 0
A1-PM-WPR-0073 | Weekly Progress Report Issuance - WPR0073 | 2026-04-08 | 2026-12-08 |  | 2026-04-08 | 0
A1-PM-WPR-0074 | Weekly Progress Report Issuance - WPR0074 | 2026-04-13 | 2026-12-14 |  | 2026-04-13 | 0
A1-PM-WPR-0075 | Weekly Progress Report Issuance - WPR0075 | 2026-04-19 | 2026-12-20 |  | 2026-04-19 | 0
A1-PM-WPR-0076 | Weekly Progress Report Issuance - WPR0076 | 2026-04-25 | 2026-12-25 |  | 2026-04-25 | 0
A1-PM-WPR-0077 | Weekly Progress Report Issuance - WPR0077 | 2026-04-30 | 2026-12-31 |  | 2026-04-30 | 0
A1-PM-WPR-0078 | Weekly Progress Report Issuance - WPR0078 | 2026-05-06 | 2027-01-05 |  | 2026-05-06 | 0
A1-PM-WPR-0079 | Weekly Progress Report Issuance - WPR0079 | 2026-05-11 | 2027-01-11 |  | 2026-05-11 | 0
A1-PM-WPR-0080 | Weekly Progress Report Issuance - WPR0080 | 2026-05-17 | 2027-01-17 |  | 2026-05-17 | 0
A1-PM-WPR-0081 | Weekly Progress Report Issuance - WPR0081 | 2026-05-23 | 2027-01-22 |  | 2026-05-23 | 0
A1-PM-WPR-0082 | Weekly Progress Report Issuance - WPR0082 | 2026-05-28 | 2027-01-28 |  | 2026-05-28 | 0
A1-PM-WPR-0083 | Weekly Progress Report Issuance - WPR0083 | 2026-06-03 | 2027-02-02 |  | 2026-06-03 | 0
A1-PM-WPR-0084 | Weekly Progress Report Issuance - WPR0084 | 2026-06-08 | 2027-02-08 |  | 2026-06-08 | 0
A1-PM-WPR-0085 | Weekly Progress Report Issuance - WPR0085 | 2026-06-14 | 2027-02-14 |  | 2026-06-14 | 0
A1-PM-WPR-0086 | Weekly Progress Report Issuance - WPR0086 | 2026-06-20 | 2027-02-19 |  | 2026-06-20 | 0
A1-PM-WPR-0087 | Weekly Progress Report Issuance - WPR0087 | 2026-06-25 | 2027-02-25 |  | 2026-06-25 | 0
A1-PM-WPR-0088 | Weekly Progress Report Issuance - WPR0088 | 2026-07-01 | 2027-03-02 |  | 2026-07-01 | 0
A1-PM-WPR-0089 | Weekly Progress Report Issuance - WPR0089 | 2026-07-06 | 2027-03-08 |  | 2026-07-06 | 0
A1-PM-WPR-0090 | Weekly Progress Report Issuance - WPR0090 | 2026-07-12 | 2027-03-14 |  | 2026-07-12 | 0
A1-PM-WPR-0091 | Weekly Progress Report Issuance - WPR0091 | 2026-07-18 | 2027-03-19 |  | 2026-07-18 | 0
A1-PM-WPR-0092 | Weekly Progress Report Issuance - WPR0092 | 2026-07-23 | 2027-03-25 |  | 2026-07-23 | 0
A1-PM-WPR-0093 | Weekly Progress Report Issuance - WPR0093 | 2026-07-29 | 2027-03-30 |  | 2026-07-29 | 0
A1-PM-WPR-0094 | Weekly Progress Report Issuance - WPR0094 | 2026-08-03 | 2027-04-05 |  | 2026-08-03 | 0
A1-PM-WPR-0095 | Weekly Progress Report Issuance - WPR0095 | 2026-08-09 | 2027-04-11 |  | 2026-08-09 | 0
A1-PM-WPR-0096 | Weekly Progress Report Issuance - WPR0096 | 2026-08-15 | 2027-04-16 |  | 2026-08-15 | 0
A1-PM-WPR-0097 | Weekly Progress Report Issuance - WPR0097 | 2026-08-20 | 2027-04-22 |  | 2026-08-20 | 0
A1-PM-WPR-0098 | Weekly Progress Report Issuance - WPR0098 | 2026-08-26 | 2027-04-27 |  | 2026-08-26 | 0
A1-PM-WPR-0099 | Weekly Progress Report Issuance - WPR0099 | 2026-08-31 | 2027-05-03 |  | 2026-08-31 | 0
A1-PM-WPR-0100 | Weekly Progress Report Issuance - WPR0100 | 2026-09-06 | 2027-05-09 |  | 2026-09-06 | 0
A1-PM-WPR-0101 | Weekly Progress Report Issuance - WPR0101 | 2026-09-12 | 2027-05-14 |  | 2026-09-12 | 0
A1-PM-WPR-0102 | Weekly Progress Report Issuance - WPR0102 | 2026-09-17 | 2027-05-20 |  | 2026-09-17 | 0
A1-PM-WPR-0103 | Weekly Progress Report Issuance - WPR0103 | 2026-09-23 | 2027-05-25 |  | 2026-09-23 | 0
A1-PM-WPR-0104 | Weekly Progress Report Issuance - WPR0104 | 2026-09-28 | 2027-05-31 |  | 2026-09-28 | 0
A1-PM-WPR-0105 | Weekly Progress Report Issuance - WPR0105 | 2026-10-04 | 2027-06-06 |  | 2026-10-04 | 0
A1-PM-WPR-0106 | Weekly Progress Report Issuance - WPR0106 | 2026-10-10 | 2027-06-11 |  | 2026-10-10 | 0
A1-PM-WPR-0107 | Weekly Progress Report Issuance - WPR0107 | 2026-10-15 | 2027-06-17 |  | 2026-10-15 | 0
A1-PM-WPR-0108 | Weekly Progress Report Issuance - WPR0108 | 2026-10-21 | 2027-06-22 |  | 2026-10-21 | 0
A1-PM-WPR-0109 | Weekly Progress Report Issuance - WPR0109 | 2026-10-26 | 2027-06-28 |  | 2026-10-26 | 0
A1-PM-WPR-0110 | Weekly Progress Report Issuance - WPR0110 | 2026-11-01 | 2027-07-04 |  | 2026-11-01 | 0
A1-PM-WPR-0111 | Weekly Progress Report Issuance - WPR0111 | 2026-11-07 | 2027-07-09 |  | 2026-11-07 | 0
A1-PM-WPR-0112 | Weekly Progress Report Issuance - WPR0112 | 2026-11-12 | 2027-07-15 |  | 2026-11-12 | 0
A1-PM-WPR-0113 | Weekly Progress Report Issuance - WPR0113 | 2026-11-18 | 2027-07-20 |  | 2026-11-18 | 0
Monthly Progress Report |  | 2026-11-20 | 2027-07-20 | 20-Dec-24 A | 2026-11-20 | 414
A1-PM-MPR-0001 | Monthly Progress Report Issuance - MPR001 |  |  |  | 20-Dec-24 A | 0
A1-PM-MPR-0002 | Monthly Progress Report Issuance - MPR002 |  |  |  | 24-Jan-25 A | 0
A1-PM-MPR-0003 | Monthly Progress Report Issuance - MPR003 |  |  |  | 17-Jun-25 A | 0
A1-PM-MPR-0004 | Monthly Progress Report Issuance - MPR004 |  |  |  | 14-Apr-25 A | 0
A1-PM-MPR-0005 | Monthly Progress Report Issuance - MPR005 |  |  |  | 13-May-25 A | 0
A1-PM-MPR-0006 | Monthly Progress Report Issuance - MPR006 |  |  |  | 17-Jun-25 A | 0
A1-PM-MPR-0007 | Monthly Progress Report Issuance - MPR007 |  |  |  | 01-Jul-25 A | 0
A1-PM-MPR-0008 | Monthly Progress Report Issuance - MPR008 |  |  |  | 22-Aug-25 A | 0
A1-PM-MPR-0009 | Monthly Progress Report Issuance - MPR009 |  |  |  | 10-Sep-25 A | 0
A1-PM-MPR-0010 | Monthly Progress Report Issuance - MPR010 | 2025-10-02 | 2026-06-01 |  | 2025-10-02 | 0
A1-PM-MPR-0011 | Monthly Progress Report Issuance - MPR011 | 2025-10-30 | 2026-06-29 |  | 2025-10-30 | 0
A1-PM-MPR-0012 | Monthly Progress Report Issuance - MPR012 | 2025-11-21 | 2026-07-21 |  | 2025-11-21 | 0
A1-PM-MPR-0013 | Monthly Progress Report Issuance - MPR013 | 2025-12-14 | 2026-08-13 |  | 2025-12-14 | 0
A1-PM-MPR-0014 | Monthly Progress Report Issuance - MPR014 | 2026-01-11 | 2026-09-10 |  | 2026-01-11 | 0
A1-PM-MPR-0015 | Monthly Progress Report Issuance - MPR015 | 2026-02-02 | 2026-10-02 |  | 2026-02-02 | 0
A1-PM-MPR-0016 | Monthly Progress Report Issuance - MPR016 | 2026-02-24 | 2026-10-25 |  | 2026-02-24 | 0
A1-PM-MPR-0017 | Monthly Progress Report Issuance - MPR017 | 2026-03-19 | 2026-11-16 |  | 2026-03-19 | 0
A1-PM-MPR-0018 | Monthly Progress Report Issuance - MPR018 | 2026-04-16 | 2026-12-14 |  | 2026-04-16 | 0
A1-PM-MPR-0019 | Monthly Progress Report Issuance - MPR019 | 2026-05-08 | 2027-01-05 |  | 2026-05-08 | 0
A1-PM-MPR-0020 | Monthly Progress Report Issuance - MPR020 | 2026-06-05 | 2027-02-02 |  | 2026-06-05 | 0
A1-PM-MPR-0021 | Monthly Progress Report Issuance - MPR021 | 2026-06-28 | 2027-02-25 |  | 2026-06-28 | 0
A1-PM-MPR-0022 | Monthly Progress Report Issuance - MPR022 | 2026-07-20 | 2027-03-19 |  | 2026-07-20 | 0
A1-PM-MPR-0023 | Monthly Progress Report Issuance - MPR023 | 2026-08-17 | 2027-04-16 |  | 2026-08-17 | 0
A1-PM-MPR-0024 | Monthly Progress Report Issuance - MPR024 | 2026-09-08 | 2027-05-09 |  | 2026-09-08 | 0
A1-PM-MPR-0025 | Monthly Progress Report Issuance - MPR025 | 2026-10-01 | 2027-05-31 |  | 2026-10-01 | 0
A1-PM-MPR-0026 | Monthly Progress Report Issuance - MPR026 | 2026-10-29 | 2027-06-28 |  | 2026-10-29 | 0
A1-PM-MPR-0027 | Monthly Progress Report Issuance - MPR027 | 2026-11-20 | 2027-07-20 |  | 2026-11-20 | 0
Team Building Workshops |  | 2026-08-30 | 2027-07-20 | 06-Mar-25 A | 2026-08-30 | 288
A1-PM-TBW-0001 | TBW01-Team Building Event-001 |  |  |  | 06-Mar-25 A | 0
A1-PM-TBW-0002 | TBW01-Team Building Event-002 |  |  |  | 21-Jun-25 A | 0
A1-PM-TBW-0003 | TBW01-Team Building Event-003 |  |  |  | 12-Aug-25 A | 0
A1-PM-TBW-0004 | TBW01-Team Building Event-004 | 2025-11-15 | 2026-10-05 |  | 2025-11-15 | 0
A1-PM-TBW-0005 | TBW01-Team Building Event-005 | 2026-02-19 | 2027-01-09 |  | 2026-02-19 | 0
A1-PM-TBW-0006 | TBW01-Team Building Event-006 | 2026-05-26 | 2027-04-15 |  | 2026-05-26 | 0
A1-PM-TBW-0007 | TBW01-Team Building Event-007 | 2026-08-30 | 2027-07-20 |  | 2026-08-30 | 0
Invoicing Plan |  | 2026-12-23 | 2027-07-20 | 07-Feb-25 A | 2026-12-23 | 460
A1-PM-MIP-0001 | Monthly Invoicing Plan - MIP001 (Advanced Payment) |  |  |  | 07-Feb-25 A | 0
A1-PM-MIP-0002 | Monthly Invoicing Plan - MIP002 |  |  |  | 07-Mar-25 A | 0
A1-PM-MIP-0003 | Monthly Invoicing Plan - MIP003 |  |  |  | 10-Apr-25 A | 0
A1-PM-MIP-0004 | Monthly Invoicing Plan - MIP004 |  |  |  | 10-May-25 A | 0
A1-PM-MIP-0005 | Monthly Invoicing Plan - MIP005 |  |  |  | 21-Jun-25 A | 0
A1-PM-MIP-0006 | Monthly Invoicing Plan - MIP006 |  |  |  | 21-Jun-25 A | 0
A1-PM-MIP-0007 | Monthly Invoicing Plan - MIP007 |  |  |  | 21-Jun-25 A | 0
A1-PM-MIP-0008 | Monthly Invoicing Plan - MIP008 |  |  |  | 29-Aug-25 A | 0
A1-PM-MIP-0009 | Monthly Invoicing Plan - MIP009 | 2025-09-19 | 2026-04-16 |  | 2025-09-19 | 0
A1-PM-MIP-0010 | Monthly Invoicing Plan - MIP010 | 2025-10-05 | 2026-05-03 |  | 2025-10-05 | 0
A1-PM-MIP-0011 | Monthly Invoicing Plan - MIP011 | 2025-10-22 | 2026-05-20 |  | 2025-10-22 | 0
A1-PM-MIP-0012 | Monthly Invoicing Plan - MIP012 | 2025-11-08 | 2026-06-06 |  | 2025-11-08 | 0
A1-PM-MIP-0013 | Monthly Invoicing Plan - MIP013 | 2025-11-25 | 2026-06-22 |  | 2025-11-25 | 0
A1-PM-MIP-0014 | Monthly Invoicing Plan - MIP014 | 2025-12-23 | 2026-07-20 |  | 2025-12-23 | 0
A1-PM-MIP-0015 | Monthly Invoicing Plan - MIP015 | 2026-01-23 | 2026-08-20 |  | 2026-01-23 | 0
A1-PM-MIP-0016 | Monthly Invoicing Plan - MIP016 | 2026-02-22 | 2026-09-19 |  | 2026-02-22 | 0
A1-PM-MIP-0017 | Monthly Invoicing Plan - MIP017 | 2026-03-25 | 2026-10-20 |  | 2026-03-25 | 0
A1-PM-MIP-0018 | Monthly Invoicing Plan - MIP018 | 2026-04-24 | 2026-11-19 |  | 2026-04-24 | 0
A1-PM-MIP-0019 | Monthly Invoicing Plan - MIP019 | 2026-04-24 | 2026-11-19 |  | 2026-04-24 | 0
A1-PM-MIP-0020 | Monthly Invoicing Plan - MIP020 | 2026-05-25 | 2026-12-20 |  | 2026-05-25 | 0
A1-PM-MIP-0021 | Monthly Invoicing Plan - MIP021 | 2026-06-25 | 2027-01-20 |  | 2026-06-25 | 0
A1-PM-MIP-0022 | Monthly Invoicing Plan - MIP022 | 2026-07-25 | 2027-02-19 |  | 2026-07-25 | 0
A1-PM-MIP-0023 | Monthly Invoicing Plan - MIP023 | 2026-08-25 | 2027-03-22 |  | 2026-08-25 | 0
A1-PM-MIP-0024 | Monthly Invoicing Plan - MIP024 | 2026-09-24 | 2027-04-21 |  | 2026-09-24 | 0
A1-PM-MIP-0025 | Monthly Invoicing Plan - MIP025 | 2026-10-25 | 2027-05-22 |  | 2026-10-25 | 0
A1-PM-MIP-0026 | Monthly Invoicing Plan - MIP026 | 2026-11-25 | 2027-06-22 |  | 2026-11-25 | 0
A1-PM-MIP-0027 | Monthly Invoicing Plan - MIP027 | 2026-12-23 | 2027-07-20 |  | 2026-12-23 | 0
Home Office Services |  | 2027-07-14 | 2027-07-20 | 14-Nov-24 A | 2027-07-14 | 458
Detailed Design - EDDR |  | 2026-07-24 | 2027-01-20 | 27-Nov-24 A | 2026-07-24 | 209
Package 1&2 |  |  |  | 01-Aug-25 A | 22-Aug-25 A | 0
Deliverables to be Recieved from Pkg 1&2 |  |  |  | 01-Aug-25 A | 22-Aug-25 A | 0
1B-DE-P12-0001 | Civil / Architecture / Structure - 63 Deleverables |  |  |  | 01-Aug-25 A | 0
1B-DE-P12-0011 | Construction - 30 Deleverables |  |  |  | 04-Aug-25 A | 0
1B-DE-P12-0021 | Electrical Engineering - 73 Deleverables |  |  |  | 05-Aug-25 A | 0
1B-DE-P12-0031 | HVAC - 26 Deleverables |  |  |  | 06-Aug-25 A | 0
1B-DE-P12-0041 | Instrument and Control System - 90 Deleverables |  |  |  | 07-Aug-25 A | 0
1B-DE-P12-0051 | IT/TELECOM - 69 Deleverables |  |  |  | 08-Aug-25 A | 0
1B-DE-P12-0061 | Material and Corrosion - 24 Deleverables |  |  |  | 11-Aug-25 A | 0
1B-DE-P12-0071 | Mechanical Rotating - 19 Deleverables |  |  |  | 12-Aug-25 A | 0
1B-DE-P12-0081 | Mechanical Rotating/Package - 9 Deleverables |  |  |  | 13-Aug-25 A | 0
1B-DE-P12-0091 | MS-Mechanical Static - 9 Deleverables |  |  |  | 14-Aug-25 A | 0
1B-DE-P12-0101 | Piping Engineering - 43 Deleverables |  |  |  | 15-Aug-25 A | 0
1B-DE-P12-0111 | Process and Safety Engineering - 38 Deleverables |  |  |  | 18-Aug-25 A | 0
1B-DE-P12-0121 | Project Control - 29 Deleverables |  |  |  | 19-Aug-25 A | 0
1B-DE-P12-0131 | Project Control Quality - 14 Deleverables |  |  |  | 20-Aug-25 A | 0
1B-DE-P12-0141 | Project Management - 86 Deleverables |  |  |  | 21-Aug-25 A | 0
1B-DE-P12-0151 | Safety - 11 Deleverables |  |  |  | 22-Aug-25 A | 0
Deliverables to be Reviewed and approved by Pkg 1&2 | [5 empty] | 0
Package 3 |  | 2026-07-24 | 2027-01-20 | 27-Nov-24 A | 2026-07-24 | 209
Milestone |  | 2026-07-24 | 2027-01-20 | 11-Dec-24 A | 2026-07-24 | 0
General |  | 2026-07-24 | 2027-01-20 | 11-Dec-24 A | 2026-07-24 | 0
Turnaround |  |  |  | 11-Dec-24 A | 11-Dec-24 A | 0
A40690 | Commencement of TA Engginering Works |  |  | 11-Dec-24 A |  | 0
Balance of Plant |  | 2026-07-24 | 2027-01-20 | 11-Dec-24 A | 2026-07-24 | 0
A120 | Commencement of BOP Engineering Works |  |  | 11-Dec-24 A |  | 0
A40320 | Completion of Engineering |  |  | 2026-07-24 |  | 0
General / Common |  |  |  | 27-Nov-24 A | 21-Jan-25 A | 0
MSE1300 | Site Survey & Data Collection / FEED Verification |  |  | 27-Nov-24 A | 21-Jan-25 A | 0
Project Management |  | 2026-01-29 | 2027-01-11 | 04-Dec-24 A | 2026-01-29 | 94
Preliminaries |  |  |  | 04-Dec-24 A | 23-May-25 A | 0
A40350 | Site Visit for TA Activities (CSA, Piping) |  |  | 09-Jan-25 A | 16-Jan-25 A | 0
A40360 | Site Visit Report Before TA |  |  | 09-Jan-25 A | 16-Jan-25 A | 0
A53280 | Engineering Subcontractor KOM |  |  | 04-Dec-24 A | 04-Dec-24 A | 0
A53290 | LOA Request |  |  | 05-Dec-24 A | 13-Dec-24 A | 0
A53320 | Receipt of Source Data |  |  | 05-Dec-24 A | 23-May-25 A | 0
A53330 | Medicals and CICPA Passes |  |  | 05-Dec-24 A | 24-Dec-24 A | 0
A53340 | Site Visit for BOP |  |  | 25-Dec-24 A | 31-Dec-24 A | 0
TA related Inputs |  | 2026-01-29 | 2027-01-11 | 12-Dec-24 A | 2026-01-29 | 94
TA Phase |  |  |  | 12-Dec-24 A | 22-Apr-25 A | 0
A28140 | Receipt of Approved Topo, UG & geotechnical investigation report |  |  | 08-Apr-25 A | 22-Apr-25 A | 0
A40330 | Receipt of Approved ICT Site Adequacy Report |  |  | 12-Feb-25 A | 13-Feb-25 A | 0
A40340 | Receipt of Approved Electrical Site Adequacy Report |  |  | 12-Feb-25 A | 13-Feb-25 A | 0
A55740 | Receipt of HSE third party offers by RAD (Descon) |  |  | 12-Dec-24 A | 12-Dec-24 A | 0
Vendor Offer Receipt (to enable Eng Subcon to perform TBE) |  |  |  | 09-Jan-25 A | 15-Jul-25 A | 0
Piping |  |  |  | 03-Feb-25 A | 24-Feb-25 A | 0
A53550 | Piping Bulk_All Technical Vendor Offers Receipt |  |  |  | 03-Feb-25 A | 0
A53560 | Manual Valves_All Technical Vendor Offers Receipt |  |  |  | 11-Feb-25 A | 0
A53570 | Piping Speciality Items_All Technical Vendor Offers Receipt |  |  |  | 24-Feb-25 A | 0
A53580 | Spring Hangers_All Technical Vendor Offers Receipt |  |  |  | 21-Feb-25 A | 0
A53590 | Rigid Struts_All Technical Vendor Offers Receipt |  |  |  | 17-Feb-25 A | 0
Mechanical |  |  |  | 07-Feb-25 A | 07-May-25 A | 0
A53400 | Heat Exchangers_All Technical Vendor Offers Receipt |  |  |  | 14-Mar-25 A | 0
A53410 | Centrifugal Pump_All Technical Vendor Offers Receipt |  |  |  | 21-Mar-25 A | 0
A53420 | EOT Crane_All Technical Vendor Offers Receipt |  |  |  | 07-May-25 A | 0
A53430 | Coalscer_All Technical Vendor Offers Receipt |  |  |  | 21-Mar-25 A | 0
A53440 | Pressure Vessels & Internals_All Technical Vendor Offers Receipt |  |  |  | 07-Feb-25 A | 0
Electrical |  |  |  | 09-Jan-25 A | 13-May-25 A | 0
A53600 | Transformer (Power And Distribution)_All Technical Vendor Offers Receipt |  |  |  | 09-Jan-25 A | 0
A53610 | 11KV Switchgear_All Technical Vendor Offers Receipt |  |  |  | 06-Mar-25 A | 0
A53620 | LV Switchgear_All Technical Vendor Offers Receipt |  |  |  | 28-Feb-25 A | 0
A53630 | AC UPS_All Technical Vendor Offers Receipt |  |  |  | 22-Jan-25 A | 0
A53640 | DC UPS_All Technical Vendor Offers Receipt |  |  |  | 21-Feb-25 A | 0
A53650 | Capacitor Bank_All Technical Vendor Offers Receipt |  |  |  | 21-Apr-25 A | 0
A53660 | Power, Control And Earthing Cables_All Technical Vendor Offers Receipt |  |  |  | 13-May-25 A | 0
A53670 | Neutral Grounding Resistor_All Technical Vendor Offers Receipt |  |  |  | 17-Jan-25 A | 0
A53680 | Emergency Diesel Generator Set_All Technical Vendor Offers Receipt |  |  |  | 22-Jan-25 A | 0
A53690 | LV Variable Frequency Drive_All Technical Vendor Offers Receipt |  |  |  | 21-Feb-25 A | 0
Instrumentation & Controls |  |  |  | 23-Apr-25 A | 15-Jul-25 A | 0
A25910 | Flow Element (Venturi Tube)_All Technical Vendor Offers Receipt |  |  |  | 30-Apr-25 A | 0
A25920 | Temperature Element / Thermowell_All Technical Vendor Offers Receipt |  |  |  | 07-May-25 A | 0
A25930 | Temperature Gauges / Pressure Gauges_All Technical Vendor Offers Receipt |  |  |  | 30-Apr-25 A | 0
A25940 | Analyzers_All Technical Vendor Offers Receipt |  |  |  | 15-Jul-25 A | 0
A25950 | Level Gauges (Magnetic Type)_All Technical Vendor Offers Receipt |  |  |  | 23-Apr-25 A | 0
A25960 | Control Valves_All Technical Vendor Offers Receipt |  |  |  | 27-Apr-25 A | 0
A25970 | Fire & Gas Detectors_All Technical Vendor Offers Receipt |  |  |  | 05-Jul-25 A | 0
A25980 | Level Transmitters (GWR type)_All Technical Vendor Offers Receipt |  |  |  | 28-Apr-25 A | 0
A25990 | Motor Operated Valves_All Technical Vendor Offers Receipt |  |  |  | 27-Apr-25 A | 0
A26000 | ESD Valves_All Technical Vendor Offers Receipt |  |  |  | 30-Apr-25 A | 0
A26010 | Rotameter_All Technical Vendor Offers Receipt |  |  |  | 01-May-25 A | 0
A53700 | Electronic Transmitters_All Technical Vendor Offers Receipt |  |  |  | 28-Apr-25 A | 0
A53710 | Flow Element (Orifice Plate)_All Technical Vendor Offers Receipt |  |  |  | 29-Apr-25 A | 0
A53720 | Instrument Cables_All Technical Vendor Offers Receipt |  |  |  | 05-Jul-25 A | 0
A53730 | Junction Boxes_All Technical Vendor Offers Receipt |  |  |  | 05-Jul-25 A | 0
A53740 | ICSS System_All Technical Vendor Offers Receipt |  |  |  | 24-Apr-25 A | 0
A53750 | Fire Detection System & LFCP_All Technical Vendor Offers Receipt |  |  |  | 12-Jun-25 A | 0
Telecom |  |  |  | 26-Apr-25 A | 22-May-25 A | 0
A53760 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_All Technical Vendor Offers Receipt |  |  |  | 26-Apr-25 A | 0
A53770 | Telecom Cables_All Technical Vendor Offers Receipt |  |  |  | 22-May-25 A | 0
HVAC |  |  |  | 03-Jun-25 A | 03-Jun-25 A | 0
A53780 | HVAC Equipments_All Technical Vendor Offers Receipt |  |  |  | 03-Jun-25 A | 0
Ist Issuance of Vendor Data Receipt-1 |  | 2026-01-06 | 2026-06-04 | 03-Feb-25 A | 2026-01-06 | 77
Piping |  | 2026-01-06 | 2026-06-04 | 05-Aug-25 A | 2026-01-06 | 40
A53790 | Piping Bulk_1st issuance of Vendor Data Receipt | 2025-11-11 | 2026-02-02 |  | 2025-11-11 | 0
A53800 | Manual Valves_1st issuance of Vendor Data Receipt | 2025-11-13 | 2026-02-05 |  | 2025-11-13 | 0
A53810 | Piping Speciality Items_1st issuance of Vendor Data Receipt |  |  |  | 05-Aug-25 A | 0
A53820 | Spring Hangers_1st issuance of Vendor Data Receipt | 2026-01-06 | 2026-06-04 |  | 2026-01-06 | 0
A53830 | Rigid Struts_1st issuance of Vendor Data Receipt | 2025-11-25 | 2026-02-02 |  | 2025-11-25 | 0
Mechanical |  | 2025-11-04 | 2026-02-02 | 27-Aug-25 A | 2025-11-04 | 33
A28770 | Compressors (FG & OG)_1st issuance of Vendor Data Receipt |  |  |  | 27-Aug-25 A | 0
A28780 | PSA Unit_1st issuance of Vendor Data Receipt |  |  |  | 09-Sep-25 A | 0
A53500 | Heat Exchangers_1st issuance of Vendor Data Receipt |  |  |  | 02-Sep-25 A | 0
A53510 | Centrifugal Pump_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
A53520 | EOT Crane_1st issuance of Vendor Data Receipt | 2025-10-01 | 2026-02-02 |  | 2025-10-01 | 0
A53530 | Coalscer_1st issuance of Vendor Data Receipt | 2025-11-04 | 2026-02-02 |  | 2025-11-04 | 0
A53540 | Pressure Vessels & Internals_1st issuance of Vendor Data Receipt |  |  |  | 02-Sep-25 A | 0
Electrical |  | 2025-11-25 | 2026-02-02 | 2025-09-19 | 2025-11-25 | 47
A53840 | Transformer (Power And Distribution)_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
A53850 | 11KV Switchgear_1st issuance of Vendor Data Receipt | 2025-11-17 | 2026-02-02 |  | 2025-11-17 | 0
A53860 | LV Switchgear_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
A53870 | AC UPS_1st issuance of Vendor Data Receipt | 2025-11-20 | 2026-02-02 |  | 2025-11-20 | 0
A53880 | DC UPS_1st issuance of Vendor Data Receipt | 2025-11-25 | 2026-02-02 |  | 2025-11-25 | 0
A53890 | Capacitor Bank_1st issuance of Vendor Data Receipt | 2025-11-04 | 2026-02-02 |  | 2025-11-04 | 0
A53900 | Power, Control And Earthing Cables_1st issuance of Vendor Data Receipt | 2025-11-04 | 2026-02-02 |  | 2025-11-04 | 0
A53910 | Neutral Grounding Resistor_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
A53920 | Emergency Diesel Generator Set_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
A53930 | LV Variable Frequency Drive_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
Instrumentation & Controls |  | 2025-11-28 | 2026-02-02 | 03-Feb-25 A | 2025-11-28 | 51
A53940 | Electronic Transmitters_1st issuance of Vendor Data Receipt | 2025-11-04 | 2026-02-02 |  | 2025-11-04 | 0
A53950 | Flow Element (Orifice Plate)_1st issuance of Vendor Data Receipt | 2025-11-17 | 2026-02-02 |  | 2025-11-17 | 0
A53960 | Flow Element (Venturi Tube)_1st issuance of Vendor Data Receipt | 2025-11-24 | 2026-02-02 |  | 2025-11-24 | 0
A53970 | Temperature Element / Thermowell_1st issuance of Vendor Data Receipt | 2025-11-25 | 2026-02-02 |  | 2025-11-25 | 0
A53980 | Temperature Gauges / Pressure Gauges_1st issuance of Vendor Data Receipt | 2025-11-17 | 2026-02-02 |  | 2025-11-17 | 0
A53990 | Analyzers_1st issuance of Vendor Data Receipt |  |  |  | 03-Feb-25 A | 0
A54000 | Level Gauges (Magnetic Type)_1st issuance of Vendor Data Receipt | 2025-11-03 | 2026-02-02 |  | 2025-11-03 | 0
A54010 | Control Valves_1st issuance of Vendor Data Receipt | 2025-11-28 | 2026-02-02 |  | 2025-11-28 | 0
A54020 | Fire & Gas Detectors_1st issuance of Vendor Data Receipt | 2025-11-27 | 2026-02-02 |  | 2025-11-27 | 0
A54030 | Level Transmitters (GWR type)_1st issuance of Vendor Data Receipt | 2025-11-17 | 2026-02-02 |  | 2025-11-17 | 0
A54040 | Motor Operated Valves_1st issuance of Vendor Data Receipt | 2025-09-30 | 2026-02-02 |  | 2025-09-30 | 0
A54050 | ESD Valves_1st issuance of Vendor Data Receipt | 2025-11-25 | 2026-02-02 |  | 2025-11-25 | 0
A54060 | Rotameter_1st issuance of Vendor Data Receipt | 2025-11-25 | 2026-02-02 |  | 2025-11-25 | 0
A54070 | Instrument Cables_1st issuance of Vendor Data Receipt | 2025-11-18 | 2026-02-02 |  | 2025-11-18 | 0
A54080 | Junction Boxes_1st issuance of Vendor Data Receipt | 2025-11-18 | 2026-02-02 |  | 2025-11-18 | 0
A54090 | ICSS System_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
A54100 | Fire Detection System & LFCP_1st issuance of Vendor Data Receipt | 2025-11-18 | 2026-02-02 |  | 2025-11-18 | 0
Telecom |  | 2025-11-25 | 2026-02-02 | 2025-11-06 | 2025-11-25 | 13
A54110 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_1st issuance of Vendor Data Receipt | 2025-11-06 | 2026-02-02 |  | 2025-11-06 | 0
A54120 | Telecom Cables_1st issuance of Vendor Data Receipt | 2025-11-25 | 2026-02-02 |  | 2025-11-25 | 0
HVAC |  | 2025-09-19 | 2026-02-02 | 2025-09-19 | 2025-09-19 | 0
A54130 | HVAC Equipments_1st issuance of Vendor Data Receipt | 2025-09-19 | 2026-02-02 |  | 2025-09-19 | 0
Approved Vender Data Receipt |  | 2026-01-29 | 2027-01-11 | 04-Mar-25 A | 2026-01-29 | 94
Piping |  | 2026-01-29 | 2026-06-26 | 26-Aug-25 A | 2026-01-29 | 40
A54140 | Piping Bulk_Approved Vendor Data Receipt | 2025-12-03 | 2026-02-25 |  | 2025-12-03 | 0
A54150 | Manual Valves_Approved Vendor Data Receipt | 2025-12-08 | 2026-02-27 |  | 2025-12-08 | 0
A54160 | Piping Speciality Items_Approved Vendor Data Receipt |  |  |  | 26-Aug-25 A | 0
A54170 | Spring Hangers_Approved Vendor Data Receipt | 2026-01-29 | 2026-06-26 |  | 2026-01-29 | 0
A54180 | Rigid Struts_Approved Vendor Data Receipt | 2025-12-18 | 2026-02-25 |  | 2025-12-18 | 0
Mechanical |  | 2025-11-27 | 2026-02-25 | 10-Jun-25 A | 2025-11-27 | 33
A28150 | Compressors (FG & OG)_Approved Vendor Data Receipt |  |  |  | 19-Sep-25 A | 0
A53450 | Heat Exchangers_Approved Vendor Data Receipt |  |  |  | 02-Sep-25 A | 0
A53460 | Centrifugal Pump_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
A53470 | EOT Crane_Approved Vendor Data Receipt | 2025-10-24 | 2026-02-25 |  | 2025-10-24 | 0
A53480 | Coalscer_Approved Vendor Data Receipt | 2025-11-27 | 2026-02-25 |  | 2025-11-27 | 0
A53490 | Pressure Vessels & Internals_Approved Vendor Data Receipt |  |  |  | 02-Sep-25 A | 0
A55640 | PSA Unit_Approved Vendor Data Receipt |  |  |  | 10-Jun-25 A | 0
Electrical |  | 2025-12-18 | 2027-01-11 | 2025-09-19 | 2025-12-18 | 64
A54190 | Transformer (Power And Distribution)_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
A54200 | 11KV Switchgear_Approved Vendor Data Receipt | 2025-12-10 | 2026-02-25 |  | 2025-12-10 | 0
A54210 | LV Switchgear_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
A54220 | AC UPS_Approved Vendor Data Receipt | 2025-12-15 | 2026-02-25 |  | 2025-12-15 | 0
A54230 | DC UPS_Approved Vendor Data Receipt | 2025-12-18 | 2026-02-25 |  | 2025-12-18 | 0
A54240 | Capacitor Bank_Approved Vendor Data Receipt | 2025-11-27 | 2026-02-25 |  | 2025-11-27 | 0
A54250 | Power, Control And Earthing Cables_Approved Vendor Data Receipt | 2025-11-27 | 2026-02-25 |  | 2025-11-27 | 0
A54260 | Neutral Grounding Resistor_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
A54270 | Emergency Diesel Generator Set_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
A54280 | LV Variable Frequency Drive_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
A55650 | Notice to proceed - All Electrical equipment footprint & load data to freeze Electrical building Equipment layout | 2025-09-19 | 2027-01-11 |  | 2025-09-19 | 0
Instrumentation & Controls |  | 2025-12-23 | 2026-02-25 | 04-Mar-25 A | 2025-12-23 | 51
A54290 | Electronic Transmitters_Approved Vendor Data Receipt | 2025-11-27 | 2026-02-25 |  | 2025-11-27 | 0
A54300 | Flow Element (Orifice Plate)_Approved Vendor Data Receipt | 2025-12-10 | 2026-02-25 |  | 2025-12-10 | 0
A54310 | Flow Element (Venturi Tube)_Approved Vendor Data Receipt | 2025-12-16 | 2026-02-25 |  | 2025-12-16 | 0
A54320 | Temperature Element / Thermowell_Approved Vendor Data Receipt | 2025-12-18 | 2026-02-25 |  | 2025-12-18 | 0
A54330 | Temperature Gauges / Pressure Gauges_Approved Vendor Data Receipt | 2025-12-10 | 2026-02-25 |  | 2025-12-10 | 0
A54340 | Analyzers_Approved Vendor Data Receipt |  |  |  | 04-Mar-25 A | 0
A54350 | Level Gauges (Magnetic Type)_Approved Vendor Data Receipt | 2025-11-26 | 2026-02-25 |  | 2025-11-26 | 0
A54360 | Control Valves_Approved Vendor Data Receipt | 2025-12-23 | 2026-02-25 |  | 2025-12-23 | 0
A54370 | Fire & Gas Detectors_Approved Vendor Data Receipt | 2025-12-22 | 2026-02-25 |  | 2025-12-22 | 0
A54380 | Level Transmitters (GWR type)_Approved Vendor Data Receipt | 2025-12-10 | 2026-02-25 |  | 2025-12-10 | 0
A54390 | Motor Operated Valves_Approved Vendor Data Receipt | 2025-10-23 | 2026-02-25 |  | 2025-10-23 | 0
A54400 | ESD Valves_Approved Vendor Data Receipt | 2025-12-18 | 2026-02-25 |  | 2025-12-18 | 0
A54410 | Rotameter_Approved Vendor Data Receipt | 2025-12-18 | 2026-02-25 |  | 2025-12-18 | 0
A54420 | Instrument Cables_Approved Vendor Data Receipt | 2025-12-11 | 2026-02-25 |  | 2025-12-11 | 0
A54430 | Junction Boxes_Approved Vendor Data Receipt | 2025-12-11 | 2026-02-25 |  | 2025-12-11 | 0
A54440 | ICSS System_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
A54450 | Fire Detection System & LFCP_Approved Vendor Data Receipt | 2025-12-11 | 2026-02-25 |  | 2025-12-11 | 0
A55660 | Notice to proceed - All ICT equipment footprint & load data to freeze SIS Equipment layout |  |  |  | 23-Jun-25 A | 0
Telecom |  | 2025-12-18 | 2026-02-25 | 2025-12-01 | 2025-12-18 | 13
A54460 | Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_Approved Vendor Data Receipt | 2025-12-01 | 2026-02-25 |  | 2025-12-01 | 0
A54470 | Telecom Cables_Approved Vendor Data Receipt | 2025-12-18 | 2026-02-25 |  | 2025-12-18 | 0
HVAC |  | 2025-10-13 | 2026-02-25 | 2025-10-13 | 2025-10-13 | 0
A54480 | HVAC Equipments_Approved Vendor Data Receipt | 2025-10-13 | 2026-02-25 |  | 2025-10-13 | 0
Workshops / Studies / Model Reviews |  | 2026-01-13 | 2026-11-13 | 05-May-25 A | 2026-01-13 | 78
A25330 | PHA (HAZID/ENVID/OHID) |  |  | 03-Jul-25 A | 03-Jul-25 A | 0
A25340 | ISD Workshop |  |  | 04-Jul-25 A | 04-Jul-25 A | 0
A25350 | HAZOP |  |  | 08-Jul-25 A | 20-Jul-25 A | 0
A53250 | PHSER-3 | 2026-01-13 | 2026-11-13 | 2026-01-12 | 2026-01-13 | 1
A53260 | SIL/LOPA |  |  | 17-Aug-25 A | 20-Aug-25 A | 0
A53270 | Energy Review | 2025-10-27 | 2026-02-25 | 2025-10-24 | 2025-10-27 | 1
A53350 | Design Review |  |  | 05-May-25 A | 09-May-25 A | 0
A53360 | Plot Plan Review |  |  | 13-May-25 A | 21-May-25 A | 0
A53370 | 30% Model Review |  |  | 13-May-25 A | 16-May-25 A | 0
A53380 | 60% Model Review |  |  | 08-Sep-25 A | 18-Sep-25 A | 0
A53390 | 90% Model Review | 2026-01-02 | 2026-03-05 | 2025-12-25 | 2026-01-02 | 6
A55680 | HSEIA Screening | 2025-09-29 | 2026-02-17 | 2025-09-26 | 2025-09-29 | 1
A55690 | Bow-Tie |  |  | 12-Aug-25 A | 12-Aug-25 A | 0
A55700 | E-HAZOP | 2025-10-07 | 2026-02-24 | 2025-10-06 | 2025-10-07 | 1
A55710 | ALARP Demonstration | 2025-09-26 | 2026-03-05 | 2025-09-25 | 2025-09-26 | 1
A55720 | SIMOPS |  |  | 28-Aug-25 A | 28-Aug-25 A | 0
A55730 | Constructability Review |  |  | 27-Aug-25 A | 27-Aug-25 A | 0
Turnaround (TA) |  |  |  | 27-Nov-24 A | 21-Jun-25 A | 0
TA - Engineering Workpack |  |  |  | 27-Nov-24 A | 12-Apr-25 A | 0
B1-DE-TA-TAD-0001 | Verify TA Dossier & Provid List of Missing Materials to EPC Contractor |  |  | 07-Jan-25 A | 27-Mar-25 A | 0
B1-DE-TA-TAD-0002 | Engineering Support During Pre-TA & TA Phase |  |  | 17-Jan-25 A | 12-Apr-25 A | 0
Piping Driven - Workpack |  |  |  | 27-Nov-24 A | 10-Feb-25 A | 0
Preliminary Workpack |  |  |  | 27-Nov-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0001 | Workpack Piping Nos. 0001 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0002 | Workpack Piping Nos. 0002 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0003 | Workpack Piping Nos. 0003 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0004 | Workpack Piping Nos. 0004 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0005 | Workpack Piping Nos. 0005 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0006 | Workpack Piping Nos. 0006 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0007 | Workpack Piping Nos. 0007 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0008 | Workpack Piping Nos. 0008 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0009 | Workpack Piping Nos. 0009 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0010 | Workpack Piping Nos. 0010 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0011 | Workpack Piping Nos. 0011 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0012 | Workpack Piping Nos. 0012 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0013 | Workpack Piping Nos. 0013 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0014 | Workpack Piping Nos. 0014 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0015 | Workpack Piping Nos. 0015 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0016 | Workpack Piping Nos. 0016 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0017 | Workpack Piping Nos. 0017 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0018 | Workpack Piping Nos. 0018 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0019 | Workpack Piping Nos. 0019 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0020 | Workpack Piping Nos. 0020 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0021 | Workpack Piping Nos. 0021 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0022 | Workpack Piping Nos. 0022 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0023 | Workpack Piping Nos. 0023 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0024 | Workpack Piping Nos. 0024 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0025 | Workpack Piping Nos. 0025 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0026 | Workpack Piping Nos. 0026 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0027 | Workpack Piping Nos. 0025 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0028 | Workpack Piping Nos. 0026 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0029 | Workpack Piping Nos. 0027 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0030 | Workpack Piping Nos. 0028 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0031 | Workpack Piping Nos. 0029 Preliminary Issuance |  |  | 27-Nov-24 A | 18-Dec-24 A | 0
B1-DE-TA-PIP-0032 | Workpack Piping Nos. 0030 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0033 | Workpack Piping Nos. 0031 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0034 | Workpack Piping Nos. 0032 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0035 | Workpack Piping Nos. 0033 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0036 | Workpack Piping Nos. 0034 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0037 | Workpack Piping Nos. 0035 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0038 | Workpack Piping Nos. 0036 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0039 | Workpack Piping Nos. 0037 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0040 | Workpack Piping Nos. 0038 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0041 | Workpack Piping Nos. 0039 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0042 | Workpack Piping Nos. 0040 Preliminary Issuance |  |  | 17-Dec-24 A | 07-Jan-25 A | 0
B1-DE-TA-PIP-0043 | Workpack Piping Nos. 0041 Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0044 | Workpack Piping Nos. 0042 Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0045 | Workpack Piping Nos. 0003 Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0046 | Workpack Nos. 41 to 52 - Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0047 | Workpack Nos. 41 to 52 - Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0048 | Workpack Nos. 41 to 52 - Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0049 | Workpack Nos. 41 to 52 - Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0050 | Workpack Nos. 41 to 52 - Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0051 | Workpack Nos. 41 to 52 - Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
B1-DE-TA-PIP-0052 | Workpack Nos. 41 to 52 - Preliminary Issuance |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
Final Workpack |  |  |  | 19-Dec-24 A | 10-Feb-25 A | 0
A40430 | Workpack Nos. 1 to 10 - Final Issuance |  |  | 19-Dec-24 A | 15-Jan-25 A | 0
A40440 | Workpack Nos. 11 to 20 - Final Issuance |  |  | 19-Dec-24 A | 15-Jan-25 A | 0
A40450 | Workpack Nos. 21 to 30 - Final Issuance |  |  | 08-Jan-25 A | 06-Feb-25 A | 0
A40460 | Workpack Nos. 31 to 40 - Final Issuance |  |  | 08-Jan-25 A | 06-Feb-25 A | 0
A40470 | Workpack Nos. 41 to 52 - Final Issuance |  |  | 24-Dec-24 A | 10-Feb-25 A | 0
ICT Driven - Workpack |  |  |  | 02-Jan-25 A | 20-Jan-25 A | 0
Preliminary Workpack |  |  |  | 02-Jan-25 A | 16-Jan-25 A | 0
A40480 | Workpack Nos. 53 to 56 - Preliminary Issuance |  |  | 02-Jan-25 A | 07-Jan-25 A | 0
A40490 | Workpack Nos. 57 to 59 - Preliminary Issuance |  |  | 02-Jan-25 A | 07-Jan-25 A | 0
A40500 | Workpack Nos. 60 to 63 - Preliminary Issuance |  |  | 02-Jan-25 A | 07-Jan-25 A | 0
A40510 | Workpack Nos. 64 to 67 - Preliminary Issuance |  |  | 06-Jan-25 A | 16-Jan-25 A | 0
A40520 | Workpack Nos. 68 to 70 - Preliminary Issuance |  |  | 06-Jan-25 A | 16-Jan-25 A | 0
Final Workpack |  |  |  | 08-Jan-25 A | 20-Jan-25 A | 0
A40530 | Workpack Nos. 53 to 56 - Final Issuance |  |  | 08-Jan-25 A | 16-Jan-25 A | 0
A40540 | Workpack Nos. 57 to 59 - Final Issuance |  |  | 08-Jan-25 A | 16-Jan-25 A | 0
A40550 | Workpack Nos. 60 to 63 - Final Issuance |  |  | 08-Jan-25 A | 16-Jan-25 A | 0
A40560 | Workpack Nos. 64 to 67 - Final Issuance |  |  | 17-Jan-25 A | 20-Jan-25 A | 0
A40570 | Workpack Nos. 68 to 70 - Final Issuance |  |  | 17-Jan-25 A | 20-Jan-25 A | 0
Civil/Structural/Architectural Driven - Workpack |  |  |  | 31-Dec-24 A | 29-Jan-25 A | 0
Preliminary Workpack |  |  |  | 31-Dec-24 A | 06-Jan-25 A | 0
A40580 | Workpack No. 71 - Preliminary Issuance |  |  | 31-Dec-24 A | 03-Jan-25 A | 0
A40590 | Workpack Nos. 72 - Preliminary Issuance |  |  | 01-Jan-25 A | 06-Jan-25 A | 0
Final Workpack |  |  |  | 04-Jan-25 A | 29-Jan-25 A | 0
A40600 | Workpack No. 71 - Final Issuance |  |  | 04-Jan-25 A | 16-Jan-25 A | 0
A40610 | Workpack No. 72 - Final Issuance |  |  | 29-Jan-25 A | 29-Jan-25 A | 0
Electrical Driven - Workpack |  |  |  | 27-Dec-24 A | 17-Jan-25 A | 0
Preliminary Workpack |  |  |  | 27-Dec-24 A | 02-Jan-25 A | 0
A40650 | Workpack Nos. 73 - Preliminary Issuance |  |  | 27-Dec-24 A | 02-Jan-25 A | 0
A40660 | Workpack Nos. 74 - Preliminary Issuance |  |  | 27-Dec-24 A | 02-Jan-25 A | 0
A40670 | Workpack Nos. 75 - Preliminary Issuance |  |  | 27-Dec-24 A | 02-Jan-25 A | 0
Final Workpack |  |  |  | 03-Jan-25 A | 17-Jan-25 A | 0
A40620 | Workpack No. 73 - Final Issuance |  |  | 03-Jan-25 A | 17-Jan-25 A | 0
A40630 | Workpack No. 74 - Final Issuance |  |  | 03-Jan-25 A | 17-Jan-25 A | 0
A40640 | Workpack No. 75 - Final Issuance |  |  | 03-Jan-25 A | 17-Jan-25 A | 0
Subcontracting Support |  |  |  | 01-Jan-25 A | 21-Jun-25 A | 0
SOW & Requisition for ICT System Modification |  |  |  | 15-Jan-25 A | 28-Feb-25 A | 0
A56050 | SOW & Requisition for ICT System Modification_IFR |  |  | 15-Jan-25 A | 30-Jan-25 A | 0
A56060 | SOW & Requisition for ICT System Modification_RCC |  |  | 31-Jan-25 A | 12-Feb-25 A | 0
A56070 | SOW & Requisition for ICT System Modification_IFD/IFC |  |  | 13-Feb-25 A | 28-Feb-25 A | 0
SOW & Requisition for Electrical System Modification |  |  |  | 07-Jan-25 A | 14-Feb-25 A | 0
A56080 | SOW & Requisition for Electrical System Modification_IFR |  |  | 07-Jan-25 A | 22-Jan-25 A | 0
A56090 | SOW & Requisition for Electrical System Modification_RCC |  |  | 23-Jan-25 A | 31-Jan-25 A | 0
A56100 | SOW & Requisition for Electrical System Modification_IFD/IFC |  |  | 03-Feb-25 A | 14-Feb-25 A | 0
SOW & Requisition for Topo & UG survey |  |  |  | 01-Jan-25 A | 05-Feb-25 A | 0
A28870 | SOW & Requisition for Topo & UG survey_IFD/IFC |  |  | 27-Jan-25 A | 05-Feb-25 A | 0
A56110 | SOW & Requisition for Topo & UG survey_IFR |  |  | 01-Jan-25 A | 09-Jan-25 A | 0
A56120 | SOW & Requisition for Topo & UG survey_RCC |  |  | 13-Jan-25 A | 24-Jan-25 A | 0
SOW & Requisition for Geotechnical investigation |  |  |  | 01-Jan-25 A | 05-Feb-25 A | 0
A56130 | SOW & Requisition for Geotechnical investigation_IFR |  |  | 01-Jan-25 A | 09-Jan-25 A | 0
A56140 | SOW & Requisition for Geotechnical investigation_RCC |  |  | 13-Jan-25 A | 24-Jan-25 A | 0
A56150 | SOW & Requisition for Geotechnical investigation_IFD/IFC |  |  | 27-Jan-25 A | 05-Feb-25 A | 0
SOW & Requisition for Third party HSE studies |  |  |  | 30-Jan-25 A | 01-Jun-25 A | 0
A56160 | SOW & Requisition for HSE third party studies_IFR |  |  | 30-Jan-25 A | 20-Feb-25 A | 0
A56170 | SOW & Requisition for HSE third party studies_RCC |  |  | 21-Feb-25 A | 27-Feb-25 A | 0
A56180 | SOW & Requisition for HSE third party studies_IFD/IFC |  |  | 28-Feb-25 A | 01-Jun-25 A | 0
Technical Bid Evaluation for Third Party HSE Studies |  |  |  | 25-Feb-25 A | 21-Jun-25 A | 0
A55950 | Technical Bid Evaluation for Third Party HSE Studies_IFR |  |  | 25-Feb-25 A | 18-Mar-25 A | 0
A55960 | Technical Bid Evaluation for Third Party HSE Studies_RCA |  |  | 19-Mar-25 A | 04-Jun-25 A | 0
A55970 | Technical Bid Evaluation for Third Party HSE Studies_IFD/IFC |  |  | 05-Jun-25 A | 21-Jun-25 A | 0
TBE for Topo,UG & Getechnical Survey | [5 empty] | 0
TBE for ICT System Modification | [5 empty] | 0
TBE for Electrical System Modification | [5 empty] | 0
MTO Support |  |  |  | 01-Feb-25 A | 07-Mar-25 A | 0
A40710 | Issue Preliminary MTO for Piping Bulks |  |  | 18-Feb-25 A | 28-Feb-25 A | 0
A40720 | Issue Preliminary MTO for Structural Steel Bulks |  |  | 17-Feb-25 A | 28-Feb-25 A | 0
A40730 | Issue Preliminary MTO for ICT Bulks |  |  | 01-Feb-25 A | 07-Feb-25 A | 0
A40740 | Issue Preliminary MTO for Electrical Bulks |  |  | 13-Feb-25 A | 26-Feb-25 A | 0
A40750 | Issue Final MTO for Piping Bulks |  |  | 10-Feb-25 A | 19-Feb-25 A | 0
A40760 | Issue Final MTO for Structural Steel Bulks |  |  | 24-Feb-25 A | 28-Feb-25 A | 0
A40770 | Issue Final MTO for ICT Bulks |  |  | 14-Feb-25 A | 07-Mar-25 A | 0
A40780 | Issue Final MTO for Electrical Bulks |  |  | 17-Feb-25 A | 27-Feb-25 A | 0
Balance of Plant |  | 2026-03-20 | 2027-01-20 | 28-Nov-24 A | 2026-03-20 | 124
General |  | 2026-03-12 | 2027-01-20 | 28-Nov-24 A | 2026-03-12 | 125
Master Deliverable Register (MDR) |  |  |  | 28-Nov-24 A | 16-Jan-25 A | 0
A40790 | Master Deliverable Register (MDR)_IFR |  |  | 28-Nov-24 A | 19-Dec-24 A | 0
A40800 | Master Deliverable Register (MDR)_RCC |  |  | 19-Dec-24 A | 26-Dec-24 A | 0
A40810 | Master Deliverable Register (MDR)_IFA |  |  | 27-Dec-24 A | 02-Jan-25 A | 0
A40820 | Master Deliverable Register (MDR)_RCA |  |  | 03-Jan-25 A | 09-Jan-25 A | 0
A40830 | Master Deliverable Register (MDR)_IFD/IFC |  |  | 10-Jan-25 A | 16-Jan-25 A | 0
Planning Package / EDDR |  |  |  | 01-Jan-25 A | 13-Apr-25 A | 0
A40840 | Planning Package / EDDR_IFR |  |  | 01-Jan-25 A | 22-Jan-25 A | 0
A40850 | Planning Package / EDDR_RCC |  |  | 23-Jan-25 A | 21-Mar-25 A | 0
A40860 | Planning Package / EDDR_IFA |  |  | 22-Mar-25 A | 29-Mar-25 A | 0
A40870 | Planning Package / EDDR_RCA |  |  | 30-Mar-25 A | 04-Apr-25 A | 0
A40880 | Planning Package / EDDR_IFD/IFC |  |  | 07-Apr-25 A | 13-Apr-25 A | 0
Project Execution Plan |  | 2025-09-30 | 2026-10-27 | 03-Mar-25 A | 2025-09-30 | 8
A40890 | Project Execution Plan_IFR |  |  | 03-Mar-25 A | 22-Mar-25 A | 0
A40900 | Project Execution Plan_RCC |  |  | 23-Mar-25 A | 29-Mar-25 A | 0
A40910 | Project Execution Plan_IFA |  |  | 30-Mar-25 A | 05-Apr-25 A | 0
A40920 | Project Execution Plan_RCA | 2025-09-26 | 2026-10-23 | 2025-09-19 | 2025-09-26 | 6
A40930 | Project Execution Plan_IFD/IFC | 2025-09-30 | 2026-10-27 | 2025-09-26 | 2025-09-30 | 2
FEED Verification Report |  |  |  | 27-Mar-25 A | 15-May-25 A | 0
A40940 | FEED Verification Report_IFR |  |  | 27-Mar-25 A | 04-Apr-25 A | 0
A40950 | FEED Verification Report_RCC |  |  | 07-Apr-25 A | 18-Apr-25 A | 0
A40960 | FEED Verification Report_IFA |  |  | 21-Apr-25 A | 30-Apr-25 A | 0
A40970 | FEED Verification Report_RCA |  |  | 01-May-25 A | 08-May-25 A | 0
A40980 | FEED Verification Report_IFD/IFC |  |  | 02-May-25 A | 15-May-25 A | 0
Site Visit Report for BOP |  |  |  | 15-Mar-25 A | 20-Jun-25 A | 0
A40990 | Site Visit Report for BOP_IFR |  |  | 15-Mar-25 A | 22-Mar-25 A | 0
A41000 | Site Visit Report for BOP_RCC |  |  | 23-Mar-25 A | 29-Mar-25 A | 0
A41010 | Site Visit Report for BOP_IFA |  |  | 30-Mar-25 A | 05-Apr-25 A | 0
A41020 | Site Visit Report for BOP_RCA |  |  | 06-Apr-25 A | 13-Jun-25 A | 0
A41030 | Site Visit Report for BOP_IFD/IFC |  |  | 14-Jun-25 A | 20-Jun-25 A | 0
Project Risk Register |  | 2025-12-31 | 2027-01-20 | 21-Feb-25 A | 2025-12-31 | 73
A41040 | Project Risk Register_IFR |  |  | 21-Feb-25 A | 10-Jun-25 A | 0
A41050 | Project Risk Register_RCC | 2025-10-22 | 2026-11-12 | 2025-09-19 | 2025-10-22 | 24
A41060 | Project Risk Register_IFA | 2025-11-14 | 2026-12-07 | 2025-10-22 | 2025-11-14 | 17
A41070 | Project Risk Register_RCA | 2025-12-08 | 2026-12-29 | 2025-11-14 | 2025-12-08 | 16
A41080 | Project Risk Register_IFD/IFC | 2025-12-31 | 2027-01-20 | 2025-12-08 | 2025-12-31 | 17
Project Lesson Learnt Register |  | 2025-11-11 | 2027-01-20 | 09-Jan-25 A | 2025-11-11 | 37
A1890 | Project Lesson Learnt Register_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A1900 | Project Lesson Learnt Register_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A1910 | Project Lesson Learnt Register_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A1920 | Project Lesson Learnt Register_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
A41090 | Project Lesson Learnt Register_IFR |  |  | 09-Jan-25 A | 10-Jun-25 A | 0
Criticality Rating Report |  | 2025-11-11 | 2027-01-20 | 21-Jun-25 A | 2025-11-11 | 37
A1930 | Criticality Rating Report_IFR |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A1940 | Criticality Rating Report_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A1950 | Criticality Rating Report_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A1960 | Criticality Rating Report_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A1970 | Criticality Rating Report_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Project Close Out Report |  | 2026-03-12 | 2027-01-20 | 2026-01-19 | 2026-03-12 | 38
A41100 | Project Close Out Report_IFR | 2026-01-21 | 2026-12-01 | 2026-01-19 | 2026-01-21 | 2
A41110 | Project Close Out Report_RCC | 2026-02-12 | 2026-12-23 | 2026-01-21 | 2026-02-12 | 16
A41120 | Project Close Out Report_IFA | 2026-02-17 | 2026-12-29 | 2026-02-12 | 2026-02-17 | 3
A41130 | Project Close Out Report_RCA | 2026-03-11 | 2027-01-19 | 2026-02-18 | 2026-03-11 | 16
A41140 | Project Close Out Report_IFD/IFC | 2026-03-12 | 2027-01-20 | 2026-03-11 | 2026-03-12 | 1
Energy Review Closeout Report |  | 2026-01-02 | 2027-01-20 | 2025-10-28 | 2026-01-02 | 48
A41150 | Energy Review Closeout Report_IFR | 2025-11-12 | 2026-11-30 | 2025-10-28 | 2025-11-12 | 11
A41160 | Energy Review Closeout Report_RCC | 2025-12-03 | 2026-12-22 | 2025-11-12 | 2025-12-03 | 16
A41170 | Energy Review Closeout Report_IFA | 2025-12-09 | 2026-12-25 | 2025-12-04 | 2025-12-09 | 3
A41180 | Energy Review Closeout Report_RCA | 2025-12-31 | 2027-01-18 | 2025-12-09 | 2025-12-31 | 16
A41190 | Energy Review Closeout Report_IFD/IFC | 2026-01-02 | 2027-01-20 | 2025-12-31 | 2026-01-02 | 2
Process |  | 2025-12-10 | 2027-01-20 | 27-Dec-24 A | 2025-12-10 | 59
Utility Design Basis |  | 2025-10-20 | 2027-01-20 | 27-Dec-24 A | 2025-10-20 | 21
A41200 | Utility Design Basis_IFR |  |  | 27-Dec-24 A | 17-Jan-25 A | 0
A41210 | Utility Design Basis_RCC |  |  | 18-Jan-25 A | 31-Jan-25 A | 0
A41220 | Utility Design Basis_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A41230 | Utility Design Basis_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A41240 | Utility Design Basis_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Criticality Rating of System |  | 2025-11-11 | 2027-01-20 | 10-Jan-25 A | 2025-11-11 | 37
A41250 | Criticality Rating of System_IFR |  |  | 10-Jan-25 A | 06-Jun-25 A | 0
A41260 | Criticality Rating of System_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A41270 | Criticality Rating of System_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A41280 | Criticality Rating of System_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A41290 | Criticality Rating of System_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
List Of Process Simulation Cases |  | 2025-11-11 | 2027-01-20 | 27-Dec-24 A | 2025-11-11 | 37
A41300 | List Of Process Simulation Cases_IFR |  |  | 27-Dec-24 A | 17-Jan-25 A | 0
A41310 | List Of Process Simulation Cases_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A41320 | List Of Process Simulation Cases_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A41330 | List Of Process Simulation Cases_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A41340 | List Of Process Simulation Cases_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Isolation Philosophy |  | 2025-09-23 | 2027-01-20 | 03-Jan-25 A | 2025-09-23 | 2
A3180 | Isolation Philosophy_IFR |  |  | 03-Jan-25 A | 24-Jan-25 A | 0
A3190 | Isolation Philosophy_RCC |  |  | 18-Apr-25 A | 19-Apr-25 A | 0
A41790 | Isolation Philosophy_IFA |  |  | 20-Apr-25 A | 13-Jun-25 A | 0
A41800 | Isolation Philosophy_RCA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A41810 | Isolation Philosophy_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Relief and Blowdown Philosophy |  | 2025-10-20 | 2027-01-20 | 09-Jan-25 A | 2025-10-20 | 21
A41820 | Relief and Blowdown Philosophy_IFR |  |  | 09-Jan-25 A | 30-Jan-25 A | 0
A41830 | Relief and Blowdown Philosophy_RCC |  |  | 31-Jan-25 A | 20-Apr-25 A | 0
A41840 | Relief and Blowdown Philosophy_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A41850 | Relief and Blowdown Philosophy_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A41860 | Relief and Blowdown Philosophy_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Vent and Drain Philosophy |  | 2025-11-20 | 2027-01-20 | 03-Jan-25 A | 2025-11-20 | 45
A41870 | Vent and Drain Philosophy_IFR |  |  | 03-Jan-25 A | 24-Jan-25 A | 0
A41880 | Vent and Drain Philosophy_RCC |  |  | 25-Jan-25 A | 20-Apr-25 A | 0
A41890 | Vent and Drain Philosophy_IFA |  |  | 21-Apr-25 A | 17-Jun-25 A | 0
A41900 | Vent and Drain Philosophy_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A41910 | Vent and Drain Philosophy_IFD/IFC | 2025-11-20 | 2027-01-20 | 2025-11-18 | 2025-11-20 | 2
Operating manual including operating procedure/guidelines including startup and shutdown procedure |  | 2025-11-18 | 2026-03-05 | 2025-09-19 | 2025-11-18 | 43
A55980 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFR | 2025-09-26 | 2026-01-13 | 2025-09-19 | 2025-09-26 | 6
A55990 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCC | 2025-10-20 | 2026-02-03 | 2025-09-26 | 2025-10-20 | 16
A56000 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFA | 2025-10-23 | 2026-02-09 | 2025-10-20 | 2025-10-23 | 3
A56010 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_RCA | 2025-11-14 | 2026-03-02 | 2025-10-23 | 2025-11-14 | 16
A56020 | Operating manual including operating procedure/guidelines including startup and shutdown procedure_IFD/IFC | 2025-11-18 | 2026-03-05 | 2025-11-14 | 2025-11-18 | 2
Process Safeguarding Diagram: List |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A41920 | Process Safeguarding Diagram: List_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A41930 | Process Safeguarding Diagram: List_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A41940 | Process Safeguarding Diagram: List_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A41950 | Process Safeguarding Diagram: List_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A41960 | Process Safeguarding Diagram: List_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Feed Pretreatment |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A41970 | Process Safeguarding Diagram: Feed Pretreatment_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A41980 | Process Safeguarding Diagram: Feed Pretreatment_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A41990 | Process Safeguarding Diagram: Feed Pretreatment_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42000 | Process Safeguarding Diagram: Feed Pretreatment_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42010 | Process Safeguarding Diagram: Feed Pretreatment_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Wash Water System |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42020 | Process Safeguarding Diagram: Wash Water System_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42030 | Process Safeguarding Diagram: Wash Water System_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42040 | Process Safeguarding Diagram: Wash Water System_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42050 | Process Safeguarding Diagram: Wash Water System_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42060 | Process Safeguarding Diagram: Wash Water System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Cracked Gas Compression |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42070 | Process Safeguarding Diagram: Cracked Gas Compression_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42080 | Process Safeguarding Diagram: Cracked Gas Compression_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42090 | Process Safeguarding Diagram: Cracked Gas Compression_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42100 | Process Safeguarding Diagram: Cracked Gas Compression_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42110 | Process Safeguarding Diagram: Cracked Gas Compression_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: C1/C2 Separation |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42120 | Process Safeguarding Diagram: C1/C2 Separation_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42130 | Process Safeguarding Diagram: C1/C2 Separation_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42140 | Process Safeguarding Diagram: C1/C2 Separation_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42150 | Process Safeguarding Diagram: C1/C2 Separation_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42160 | Process Safeguarding Diagram: C1/C2 Separation_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: H2 Extraction Unit |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42170 | Process Safeguarding Diagram: H2 Extraction Unit_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42180 | Process Safeguarding Diagram: H2 Extraction Unit_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42190 | Process Safeguarding Diagram: H2 Extraction Unit_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42200 | Process Safeguarding Diagram: H2 Extraction Unit_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42210 | Process Safeguarding Diagram: H2 Extraction Unit_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: H2 Extraction Unit II |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42220 | Process Safeguarding Diagram: H2 Extraction Unit II_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42230 | Process Safeguarding Diagram: H2 Extraction Unit II_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42240 | Process Safeguarding Diagram: H2 Extraction Unit II_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42250 | Process Safeguarding Diagram: H2 Extraction Unit II_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42260 | Process Safeguarding Diagram: H2 Extraction Unit II_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: C4 Selective Hydrogenation IV |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42270 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42280 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42290 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42300 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42310 | Process Safeguarding Diagram: C4 Selective Hydrogenation IV_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Fuel Gas System |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42320 | Process Safeguarding Diagram: Fuel Gas System_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42330 | Process Safeguarding Diagram: Fuel Gas System_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42340 | Process Safeguarding Diagram: Fuel Gas System_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42350 | Process Safeguarding Diagram: Fuel Gas System_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42360 | Process Safeguarding Diagram: Fuel Gas System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Regeneration System |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42370 | Process Safeguarding Diagram: Regeneration System_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42380 | Process Safeguarding Diagram: Regeneration System_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42390 | Process Safeguarding Diagram: Regeneration System_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42400 | Process Safeguarding Diagram: Regeneration System_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42410 | Process Safeguarding Diagram: Regeneration System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Boiler Feed Water System |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42420 | Process Safeguarding Diagram: Boiler Feed Water System_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42430 | Process Safeguarding Diagram: Boiler Feed Water System_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42440 | Process Safeguarding Diagram: Boiler Feed Water System_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42450 | Process Safeguarding Diagram: Boiler Feed Water System_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42460 | Process Safeguarding Diagram: Boiler Feed Water System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Condensate Collection System |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42470 | Process Safeguarding Diagram: Condensate Collection System_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42480 | Process Safeguarding Diagram: Condensate Collection System_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42490 | Process Safeguarding Diagram: Condensate Collection System_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42500 | Process Safeguarding Diagram: Condensate Collection System_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42510 | Process Safeguarding Diagram: Condensate Collection System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Cooling Water System |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42520 | Process Safeguarding Diagram: Cooling Water System_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42530 | Process Safeguarding Diagram: Cooling Water System_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42540 | Process Safeguarding Diagram: Cooling Water System_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42550 | Process Safeguarding Diagram: Cooling Water System_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42560 | Process Safeguarding Diagram: Cooling Water System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Utility System For H2 Extraction Unit |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42570 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42580 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42590 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42600 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42610 | Process Safeguarding Diagram: Utility System For H2 Extraction Unit_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42620 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42630 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42640 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42650 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42660 | Process Safeguarding Diagram: Blowdown Vessels And Acid Gas Flare_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Slop,Sewer And Drainage System |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A42670 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A42680 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A42690 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A42700 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A42710 | Process Safeguarding Diagram: Slop,Sewer And Drainage System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Process Safeguarding Diagram: Slop,Sewer And Drainage System II |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
A4130 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A4140 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCC |  |  | 26-Jan-25 A | 20-Feb-25 A | 0
A4150 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFH |  |  | 21-Feb-25 A | 27-May-25 A | 0
A4160 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_RCA |  |  | 28-May-25 A | 21-Jun-25 A | 0
A4170 | Process Safeguarding Diagram: Slop,Sewer And Drainage System II_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Utility Consumption |  | 2025-11-11 | 2026-03-05 | 21-Jun-25 A | 2025-11-11 | 37
A42760 | Utility Consumption_IFR |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A42770 | Utility Consumption_RCC | 2025-10-10 | 2026-02-03 | 2025-09-19 | 2025-10-10 | 16
A42780 | Utility Consumption_IFA | 2025-10-16 | 2026-02-09 | 2025-10-10 | 2025-10-16 | 3
A42790 | Utility Consumption_RCA | 2025-11-06 | 2026-03-02 | 2025-10-16 | 2025-11-06 | 16
A42800 | Utility Consumption_IFD/IFC | 2025-11-11 | 2026-03-05 | 2025-11-06 | 2025-11-11 | 2
Safeguarding Memorendum |  | 2025-12-10 | 2027-01-20 | 2025-10-10 | 2025-12-10 | 43
A4180 | Safeguarding Memorandum_IFR | 2025-10-20 | 2026-11-30 | 2025-10-10 | 2025-10-20 | 6
A42720 | Safeguarding Memorandum_RCC | 2025-11-11 | 2026-12-22 | 2025-10-20 | 2025-11-11 | 16
A42730 | Safeguarding Memorandum_IFA | 2025-11-14 | 2026-12-25 | 2025-11-11 | 2025-11-14 | 3
A42740 | Safeguarding Memorandum_RCA | 2025-12-08 | 2027-01-18 | 2025-11-14 | 2025-12-08 | 16
A42750 | Safeguarding Memorandum_IFD/IFC | 2025-12-10 | 2027-01-20 | 2025-12-08 | 2025-12-10 | 2
Process Utility Adequacy Check Report |  | 2025-11-18 | 2026-03-05 | 2025-09-19 | 2025-11-18 | 43
A43210 | Process Utility Adequacy Check Report_IFR | 2025-09-26 | 2026-01-13 | 2025-09-19 | 2025-09-26 | 6
A43220 | Process Utility Adequacy Check Report_RCC | 2025-10-20 | 2026-02-03 | 2025-09-26 | 2025-10-20 | 16
A43230 | Process Utility Adequacy Check Report_IFA | 2025-10-23 | 2026-02-09 | 2025-10-20 | 2025-10-23 | 3
A43240 | Process Utility Adequacy Check Report_RCA | 2025-11-14 | 2026-03-02 | 2025-10-23 | 2025-11-14 | 16
A43250 | Process Utility Adequacy Check Report_IFD/IFC | 2025-11-18 | 2026-03-05 | 2025-11-14 | 2025-11-18 | 2
Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum |  |  |  | 31-Dec-24 A | 21-May-25 A | 0
A41350 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFR |  |  | 31-Dec-24 A | 24-Jan-25 A | 0
A41360 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCC |  |  | 25-Jan-25 A | 18-Mar-25 A | 0
A41370 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFA |  |  | 19-Mar-25 A | 19-Apr-25 A | 0
A41380 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_RCA |  |  | 20-Apr-25 A | 14-May-25 A | 0
A41390 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Suction Drum_IFD/IFC |  |  | 15-May-25 A | 21-May-25 A | 0
Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler |  |  |  | 01-Jan-25 A | 21-Jun-25 A | 0
A41400 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFR |  |  | 01-Jan-25 A | 26-Jan-25 A | 0
A41410 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCC |  |  | 27-Jan-25 A | 19-Mar-25 A | 0
A41420 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFA |  |  | 20-Mar-25 A | 20-May-25 A | 0
A41430 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_RCA |  |  | 21-May-25 A | 02-Jun-25 A | 0
A41440 | Process Datasheet for PSA2 Feed Gas Compressor 1st Stage Cooler_IFD/IFC |  |  | 03-Jun-25 A | 21-Jun-25 A | 0
Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum |  |  |  | 31-Dec-24 A | 21-May-25 A | 0
A41450 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFR |  |  | 31-Dec-24 A | 24-Jan-25 A | 0
A41460 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCC |  |  | 25-Jan-25 A | 18-Mar-25 A | 0
A41470 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFA |  |  | 19-Mar-25 A | 19-Apr-25 A | 0
A41480 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_RCA |  |  | 20-Apr-25 A | 14-May-25 A | 0
A41490 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Suction Drum_IFD/IFC |  |  | 15-May-25 A | 21-May-25 A | 0
Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler |  |  |  | 01-Jan-25 A | 21-Jun-25 A | 0
A41500 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFR |  |  | 01-Jan-25 A | 26-Jan-25 A | 0
A41510 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCC |  |  | 27-Jan-25 A | 19-Mar-25 A | 0
A41520 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFA |  |  | 20-Mar-25 A | 20-May-25 A | 0
A41530 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_RCA |  |  | 21-May-25 A | 02-Jun-25 A | 0
A41540 | Process Datasheet for PSA2 Feed Gas Compressor 2nd Stage Cooler_IFD/IFC |  |  | 03-Jun-25 A | 21-Jun-25 A | 0
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum |  |  |  | 31-Dec-24 A | 20-May-25 A | 0
A41550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFR |  |  | 31-Dec-24 A | 24-Jan-25 A | 0
A41560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCC |  |  | 25-Jan-25 A | 18-Mar-25 A | 0
A41570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFA |  |  | 19-Mar-25 A | 19-Apr-25 A | 0
A41580 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_RCA |  |  | 20-Apr-25 A | 13-May-25 A | 0
A41590 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Suction Drum_IFD/IFC |  |  | 14-May-25 A | 20-May-25 A | 0
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler |  | 2025-10-14 | 2027-01-20 | 01-Jan-25 A | 2025-10-14 | 18
A41600 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFR |  |  | 01-Jan-25 A | 26-Jan-25 A | 0
A41610 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCC |  |  | 27-Jan-25 A | 19-Mar-25 A | 0
A41620 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFA |  |  | 20-Mar-25 A | 21-Jun-25 A | 0
A41630 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A41640 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Cooler_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum |  |  |  | 31-Dec-24 A | 20-May-25 A | 0
A2550 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFA |  |  | 19-Mar-25 A | 19-Apr-25 A | 0
A2560 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCA |  |  | 20-Apr-25 A | 13-May-25 A | 0
A2570 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFD/IFC |  |  | 14-May-25 A | 20-May-25 A | 0
A41650 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_IFR |  |  | 31-Dec-24 A | 24-Jan-25 A | 0
A41660 | Process Datasheet for PSA2 Feed Gas Compressor 3rd Stage Discharge Drum_RCC |  |  | 25-Jan-25 A | 18-Mar-25 A | 0
Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712 |  |  |  | 31-Dec-24 A | 12-Jun-25 A | 0
A2580 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFR |  |  | 31-Dec-24 A | 24-Jan-25 A | 0
A2590 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCC |  |  | 25-Jan-25 A | 14-May-25 A | 0
A2600 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFA |  |  | 15-May-25 A | 21-May-25 A | 0
A2610 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_RCA |  |  | 22-May-25 A | 02-Jun-25 A | 0
A2620 | Process Datasheet for PSA2 Off Gas Buffer Drum - 13-VV-712_IFD/IFC |  |  | 03-Jun-25 A | 12-Jun-25 A | 0
Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708 |  |  |  | 01-Jan-25 A | 21-Jun-25 A | 0
A2630 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFR |  |  | 01-Jan-25 A | 26-Jan-25 A | 0
A2640 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCC |  |  | 27-Jan-25 A | 19-Mar-25 A | 0
A2650 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFA |  |  | 20-Mar-25 A | 20-May-25 A | 0
A2660 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_RCA |  |  | 21-May-25 A | 11-Jun-25 A | 0
A2670 | Process Datasheet for PSA2 Off Gas Compressor Interstage Cooler - 13-HE-708_IFD/IFC |  |  | 12-Jun-25 A | 21-Jun-25 A | 0
Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713 |  |  |  | 31-Dec-24 A | 13-Jun-25 A | 0
A2680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFR |  |  | 31-Dec-24 A | 24-Jan-25 A | 0
A2720 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFD/IFC |  |  | 03-Jun-25 A | 13-Jun-25 A | 0
A41670 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCC |  |  | 25-Jan-25 A | 14-May-25 A | 0
A41680 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_IFA |  |  | 15-May-25 A | 21-May-25 A | 0
A41690 | Process Datasheet for PSA2 Off Gas Compressor 2Nd Stage Suction Drum 13-VV-713_RCA |  |  | 22-May-25 A | 02-Jun-25 A | 0
Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709 |  | 2025-09-23 | 2027-01-20 | 01-Jan-25 A | 2025-09-23 | 2
A2730 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFR |  |  | 01-Jan-25 A | 26-Jan-25 A | 0
A2740 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCC |  |  | 27-Jan-25 A | 19-Mar-25 A | 0
A2750 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFA |  |  | 20-Mar-25 A | 20-May-25 A | 0
A2760 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_RCA |  |  | 21-May-25 A | 11-Jun-25 A | 0
A2770 | Process Datasheet for PSA2 Off Gas Compressor Aftercooler - 13-HE-709_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004* |  | 2025-09-26 | 2026-06-24 | 01-Jan-25 A | 2025-09-26 | 6
A2780 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFR |  |  | 01-Jan-25 A | 24-Jan-25 A | 0
A2790 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCC |  |  | 25-Jan-25 A | 05-May-25 A | 0
A2800 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFA |  |  | 06-May-25 A | 11-Jun-25 A | 0
A2810 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_RCA |  |  | 12-Jun-25 A | 21-Jun-25 A | 0
A55750 | Process Datasheet for PSA2 Off Gas Compressor Discharge Dripleg - 13-SP-7004_IFD/IFC | 2025-09-26 | 2026-06-24 | 2025-09-19 | 2025-09-26 | 6
Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg |  | 2025-11-07 | 2027-01-20 | 01-Jan-25 A | 2025-11-07 | 36
A2830 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFR |  |  | 01-Jan-25 A | 06-Jun-25 A | 0
A2840 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCC | 2025-10-10 | 2026-12-23 | 2025-09-19 | 2025-10-10 | 16
A2850 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFA | 2025-10-14 | 2026-12-25 | 2025-10-10 | 2025-10-14 | 2
A41700 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_RCA | 2025-11-05 | 2027-01-18 | 2025-10-15 | 2025-11-05 | 16
A41710 | Process Datasheet for 52-SP-14067 Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 2025-11-07 | 2027-01-20 | 2025-11-05 | 2025-11-07 | 2
Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler |  | 2025-09-23 | 2027-01-20 | 01-Jan-25 A | 2025-09-23 | 2
A2890 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCC |  |  | 28-Apr-25 A | 04-May-25 A | 0
A2900 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFA |  |  | 05-May-25 A | 30-May-25 A | 0
A2910 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_RCA |  |  | 01-Jun-25 A | 21-Jun-25 A | 0
A2920 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
A41720 | Process Datasheet for 50-HE-1410 C4 Guard Adsorber Regeneration Gas Cooler_IFR |  |  | 01-Jan-25 A | 27-Apr-25 A | 0
Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer |  | 2025-10-17 | 2027-01-20 | 01-Jan-25 A | 2025-10-17 | 20
A2980 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFR |  |  | 01-Jan-25 A | 30-Jan-25 A | 0
A2990 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCC |  |  | 31-Jan-25 A | 20-Apr-25 A | 0
A3000 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFA | 2025-09-23 | 2026-12-25 | 2025-09-19 | 2025-09-23 | 2
A3010 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_RCA | 2025-10-14 | 2027-01-18 | 2025-09-23 | 2025-10-14 | 16
A3020 | Process Datasheet for 50-VV-1403 C4 Guard Adsorber Regeneration Gas Coalescer_IFD/IFC | 2025-10-17 | 2027-01-20 | 2025-10-15 | 2025-10-17 | 2
Process Datasheet for 70-PC-1407 Water Collection Sump Pump II |  | 2025-10-14 | 2027-01-20 | 01-Jan-25 A | 2025-10-14 | 18
A41730 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFR |  |  | 01-Jan-25 A | 24-Jan-25 A | 0
A41740 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCC |  |  | 25-Jan-25 A | 02-May-25 A | 0
A41750 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFA |  |  | 03-May-25 A | 19-Sep-25 A | 0
A41760 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A41770 | Process Datasheet for 70-PC-1407 Water Collection Sump Pump II_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump |  | 2025-10-17 | 2027-01-20 | 01-Jan-25 A | 2025-10-17 | 20
A3080 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFR |  |  | 01-Jan-25 A | 24-Jan-25 A | 0
A3090 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCC |  |  | 25-Jan-25 A | 02-May-25 A | 0
A3100 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFA | 2025-09-23 | 2026-12-25 | 2025-09-19 | 2025-09-23 | 2
A3110 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_RCA | 2025-10-14 | 2027-01-18 | 2025-09-23 | 2025-10-14 | 16
A3120 | Process Datasheet for 70-PC-1409 A/B Sanitary Waste Water Sump Pump_IFD/IFC | 2025-10-17 | 2027-01-20 | 2025-10-15 | 2025-10-17 | 2
Process Datasheet for 70-VV-1415 PSA2 Slop Drum |  | 2025-09-23 | 2027-01-20 | 01-Jan-25 A | 2025-09-23 | 2
A3130 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFR |  |  | 01-Jan-25 A | 24-Jan-25 A | 0
A3140 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCC |  |  | 25-Jan-25 A | 05-May-25 A | 0
A3150 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFA |  |  | 06-May-25 A | 11-Jun-25 A | 0
A3160 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_RCA |  |  | 12-Jun-25 A | 21-Jun-25 A | 0
A41780 | Process Datasheet for 70-VV-1415 PSA2 Slop Drum_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Process Datasheet of Off-Gas Compressor Coalescer |  | 2025-11-12 | 2027-01-20 | 03-Jul-25 A | 2025-11-12 | 38
A28230 | Process Datasheet of Off-Gas Compressor Coalescer_IFR | 2025-09-23 | 2026-12-01 | 03-Jul-25 A | 2025-09-23 | 2
A28240 | Process Datasheet of Off-Gas Compressor Coalescer_RCC | 2025-10-14 | 2026-12-23 | 2025-09-23 | 2025-10-14 | 16
A55760 | Process Datasheet of Off-Gas Compressor Coalescer_IFA | 2025-10-17 | 2026-12-25 | 2025-10-15 | 2025-10-17 | 2
A55770 | Process Datasheet of Off-Gas Compressor Coalescer_RCA | 2025-11-07 | 2027-01-18 | 2025-10-17 | 2025-11-07 | 16
A55780 | Process Datasheet of Off-Gas Compressor Coalescer_IFD/IFC | 2025-11-12 | 2027-01-20 | 2025-11-10 | 2025-11-12 | 2
Sample Point /Connection Lists |  | 2025-11-11 | 2027-01-20 | 21-Jun-25 A | 2025-11-11 | 37
A43060 | Sample Point /Connection Lists_IFR |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A43070 | Sample Point /Connection Lists_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A43080 | Sample Point /Connection Lists_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A43090 | Sample Point /Connection Lists_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A43100 | Sample Point /Connection Lists_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Process Calculation Report |  | 2025-11-18 | 2027-01-20 | 20-Feb-25 A | 2025-11-18 | 43
A42960 | Process Calculation Report_IFR | 2025-09-26 | 2026-11-30 | 20-Feb-25 A | 2025-09-26 | 6
A42970 | Process Calculation Report_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A42980 | Process Calculation Report_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A42990 | Process Calculation Report_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A43000 | Process Calculation Report_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Process Datasheet for Control Valve |  |  |  | 20-Feb-25 A | 12-Jul-25 A | 0
A42810 | Process Datasheet for Control Valve_IFR |  |  | 20-Feb-25 A | 27-Apr-25 A | 0
A42820 | Process Datasheet for Control Valve_RCC |  |  | 28-Apr-25 A | 21-Jun-25 A | 0
A42830 | Process Datasheet for Control Valve_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A42840 | Process Datasheet for Control Valve_RCA |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
A42850 | Process Datasheet for Control Valve_IFD/IFC |  |  | 06-Jul-25 A | 12-Jul-25 A | 0
Process Datasheet for Relief Valve |  | 2025-10-20 | 2027-01-20 | 25-Jan-25 A | 2025-10-20 | 21
A42860 | Process Datasheet for Relief Valve_IFR |  |  | 25-Jan-25 A | 20-Apr-25 A | 0
A42870 | Process Datasheet for Relief Valve_RCC |  |  | 21-Apr-25 A | 30-Apr-25 A | 0
A42880 | Process Datasheet for Relief Valve_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A42890 | Process Datasheet for Relief Valve_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A42900 | Process Datasheet for Relief Valve_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Process Datasheet for Flow Instrument |  | 2025-10-20 | 2027-01-20 | 20-Feb-25 A | 2025-10-20 | 21
A42910 | Process Datasheet for Flow Instrument_IFR |  |  | 20-Feb-25 A | 25-Apr-25 A | 0
A42920 | Process Datasheet for Flow Instrument_RCC |  |  | 26-Apr-25 A | 26-May-25 A | 0
A42930 | Process Datasheet for Flow Instrument_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A42940 | Process Datasheet for Flow Instrument_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A42950 | Process Datasheet for Flow Instrument_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Flare Relief Load Summary |  | 2025-11-11 | 2026-03-05 | 31-Jan-25 A | 2025-11-11 | 37
A43160 | Flare Relief Load Summary_IFR |  |  | 31-Jan-25 A | 11-Mar-25 A | 0
A43170 | Flare Relief Load Summary_RCC | 2025-10-10 | 2026-02-03 | 12-Mar-25 A | 2025-10-10 | 16
A43180 | Flare Relief Load Summary_IFA | 2025-10-16 | 2026-02-09 | 2025-10-10 | 2025-10-16 | 3
A43190 | Flare Relief Load Summary_RCA | 2025-11-06 | 2026-03-02 | 2025-10-16 | 2025-11-06 | 16
A43200 | Flare Relief Load Summary_IFD/IFC | 2025-11-11 | 2026-03-05 | 2025-11-06 | 2025-11-11 | 2
Flare Relief & Blowdown Report |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A43110 | Flare Relief & Blowdown Report_IFR | 2025-09-26 | 2026-11-23 | 2025-09-19 | 2025-09-26 | 6
A43120 | Flare Relief & Blowdown Report_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A43130 | Flare Relief & Blowdown Report_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A43140 | Flare Relief & Blowdown Report_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A43150 | Flare Relief & Blowdown Report_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Dynamic Flare Simulation Study |  | 2025-11-26 | 2027-01-20 | 2025-09-26 | 2025-11-26 | 43
A43010 | Dynamic Flare Simulation Study_IFR | 2025-10-06 | 2026-11-30 | 2025-09-26 | 2025-10-06 | 6
A43020 | Dynamic Flare Simulation Study_RCC | 2025-10-27 | 2026-12-22 | 2025-10-06 | 2025-10-27 | 16
A43030 | Dynamic Flare Simulation Study_IFA | 2025-10-31 | 2026-12-25 | 2025-10-28 | 2025-10-31 | 3
A43040 | Dynamic Flare Simulation Study_RCA | 2025-11-24 | 2027-01-18 | 2025-10-31 | 2025-11-24 | 16
A43050 | Dynamic Flare Simulation Study_IFD/IFC | 2025-11-26 | 2027-01-20 | 2025-11-24 | 2025-11-26 | 2
Piping |  | 2026-03-11 | 2027-01-20 | 16-Jan-25 A | 2026-03-11 | 120
3D Modelling Procedure |  | 2025-10-14 | 2027-01-20 | 01-Mar-25 A | 2025-10-14 | 18
A43260 | 3D Modelling Procedure_IFR |  |  | 01-Mar-25 A | 20-Apr-25 A | 0
A43270 | 3D Modelling Procedure_RCC |  |  | 21-Apr-25 A | 28-Apr-25 A | 0
A43280 | 3D Modelling Procedure_IFA |  |  | 29-Apr-25 A | 21-Jun-25 A | 0
A43290 | 3D Modelling Procedure_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A43300 | 3D Modelling Procedure_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
3D Model Execution Philosophy |  | 2025-10-14 | 2027-01-20 | 25-Mar-25 A | 2025-10-14 | 18
A55400 | 3D Model Execution Philosophy_IFR |  |  | 25-Mar-25 A | 15-Apr-25 A | 0
A55410 | 3D Model Execution Philosophy_RCC |  |  | 16-Apr-25 A | 28-Apr-25 A | 0
A55420 | 3D Model Execution Philosophy_IFA |  |  | 29-Apr-25 A | 21-Jun-25 A | 0
A55430 | 3D Model Execution Philosophy_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A55440 | 3D Model Execution Philosophy_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
3D Model Review Procedure |  | 2025-09-23 | 2027-01-20 | 25-Mar-25 A | 2025-09-23 | 2
A43310 | 3D Model Review Procedure_IFR |  |  | 25-Mar-25 A | 15-Apr-25 A | 0
A43320 | 3D Model Review Procedure_RCC |  |  | 16-Apr-25 A | 28-Apr-25 A | 0
A43330 | 3D Model Review Procedure_IFA |  |  | 29-Apr-25 A | 21-Jun-25 A | 0
A43340 | 3D Model Review Procedure_RCA |  |  | 22-Jun-25 A | 05-Sep-25 A | 0
A43350 | 3D Model Review Procedure_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Clash Check Procedure |  |  |  | 22-Mar-25 A | 11-May-25 A | 0
A27870 | Clash Check Procedure_RCC |  |  | 13-Apr-25 A | 20-Apr-25 A | 0
A27880 | Clash Check Procedure_IFA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A55450 | Clash Check Procedure_IFR |  |  | 22-Mar-25 A | 12-Apr-25 A | 0
A55460 | Clash Check Procedure_RCA |  |  | 28-Apr-25 A | 04-May-25 A | 0
A55470 | Clash Check Procedure_IFD/IFC |  |  | 05-May-25 A | 11-May-25 A | 0
Deliverables Extraction Procedure |  |  |  | 23-Jan-25 A | 12-Mar-25 A | 0
A55480 | Deliverables Extraction Procedure_IFR |  |  | 23-Jan-25 A | 12-Feb-25 A | 0
A55490 | Deliverables Extraction Procedure_RCC |  |  | 13-Feb-25 A | 19-Feb-25 A | 0
A55500 | Deliverables Extraction Procedure_IFA |  |  | 20-Feb-25 A | 26-Feb-25 A | 0
A55510 | Deliverables Extraction Procedure_RCA |  |  | 27-Feb-25 A | 05-Mar-25 A | 0
A55520 | Deliverables Extraction Procedure_IFD/IFC |  |  | 06-Mar-25 A | 12-Mar-25 A | 0
Data Handover Procedure |  | 2025-11-11 | 2026-12-09 | 21-Jun-25 A | 2025-11-11 | 37
A27960 | Data Handover Procedure_IFR |  |  | 21-Jun-25 A | 12-Jul-25 A | 0
A27970 | Data Handover Procedure_RCC | 2025-10-10 | 2026-11-10 | 2025-09-19 | 2025-10-10 | 16
A55530 | Data Handover Procedure_IFA | 2025-10-16 | 2026-11-13 | 2025-10-10 | 2025-10-16 | 3
A55540 | Data Handover Procedure_RCA | 2025-11-06 | 2026-12-07 | 2025-10-16 | 2025-11-06 | 16
A55550 | Data Handover Procedure_IFD/IFC | 2025-11-11 | 2026-12-09 | 2025-11-06 | 2025-11-11 | 2
Stress Critical Line List |  | 2025-10-20 | 2027-01-20 | 15-Apr-25 A | 2025-10-20 | 21
A43460 | Stress Critical Line List_IFR |  |  | 15-Apr-25 A | 06-May-25 A | 0
A43470 | Stress Critical Line List_RCC |  |  | 07-May-25 A | 13-May-25 A | 0
A43480 | Stress Critical Line List_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A43490 | Stress Critical Line List_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A43500 | Stress Critical Line List_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Datasheets for Ball Valves |  | 2025-11-11 | 2025-12-16 | 16-Jan-25 A | 2025-11-11 | 37
A43660 | Datasheets for Ball Valves_IFR |  |  | 16-Jan-25 A | 14-May-25 A | 0
A43670 | Datasheets for Ball Valves_RCC | 2025-10-10 | 2025-11-17 | 2025-09-19 | 2025-10-10 | 16
A43680 | Datasheets for Ball Valves_IFA | 2025-10-16 | 2025-11-20 | 2025-10-10 | 2025-10-16 | 3
A43690 | Datasheets for Ball Valves_RCA | 2025-11-06 | 2025-12-12 | 2025-10-16 | 2025-11-06 | 16
A43700 | Datasheets for Ball Valves_IFD/IFC | 2025-11-11 | 2025-12-16 | 2025-11-06 | 2025-11-11 | 2
Datasheets for Double Block & Bleed Valves |  |  |  | 27-Jan-25 A | 22-Aug-25 A | 0
A43760 | Datasheets for Double Block & Bleed Valves_IFR |  |  | 27-Jan-25 A | 01-Aug-25 A | 0
A43770 | Datasheets for Double Block & Bleed Valves_RCC |  |  | 02-Aug-25 A | 10-Aug-25 A | 0
A43780 | Datasheets for Double Block & Bleed Valves_IFA |  |  | 11-Aug-25 A | 15-Aug-25 A | 0
A43790 | Datasheets for Double Block & Bleed Valves_RCA |  |  | 16-Aug-25 A | 20-Aug-25 A | 0
A43800 | Datasheets for Double Block & Bleed Valves_IFD/IFC |  |  | 21-Aug-25 A | 22-Aug-25 A | 0
Datasheets for Check Valves |  | 2025-10-20 | 2025-12-16 | 23-Jan-25 A | 2025-10-20 | 21
A43710 | Datasheets for Check Valves_IFR |  |  | 23-Jan-25 A | 14-May-25 A | 0
A43720 | Datasheets for Check Valves_RCC |  |  | 15-May-25 A | 21-Jun-25 A | 0
A43730 | Datasheets for Check Valves_IFA | 2025-09-24 | 2025-11-20 | 2025-09-19 | 2025-09-24 | 3
A43740 | Datasheets for Check Valves_RCA | 2025-10-16 | 2025-12-12 | 2025-09-24 | 2025-10-16 | 16
A43750 | Datasheets for Check Valves_IFD/IFC | 2025-10-20 | 2025-12-16 | 2025-10-16 | 2025-10-20 | 2
Datasheets for Butterfly Valves |  | 2025-11-11 | 2025-12-16 | 16-Jan-25 A | 2025-11-11 | 37
A43810 | Datasheets for Butterfly Valves_IFR |  |  | 16-Jan-25 A | 12-Jun-25 A | 0
A43820 | Datasheets for Butterfly Valves_RCC | 2025-10-10 | 2025-11-17 | 2025-09-19 | 2025-10-10 | 16
A43830 | Datasheets for Butterfly Valves_IFA | 2025-10-16 | 2025-11-20 | 2025-10-10 | 2025-10-16 | 3
A43840 | Datasheets for Butterfly Valves_RCA | 2025-11-06 | 2025-12-12 | 2025-10-16 | 2025-11-06 | 16
A43850 | Datasheets for Butterfly Valves_IFD/IFC | 2025-11-11 | 2025-12-16 | 2025-11-06 | 2025-11-11 | 2
Datasheets for Needle Valves |  |  |  | 01-Aug-25 A | 22-Aug-25 A | 0
A43860 | Datasheets for Needle Valves_IFR |  |  | 01-Aug-25 A | 05-Aug-25 A | 0
A43870 | Datasheets for Needle Valves_RCC |  |  | 06-Aug-25 A | 12-Aug-25 A | 0
A43880 | Datasheets for Needle Valves_IFA |  |  | 13-Aug-25 A | 15-Aug-25 A | 0
A43890 | Datasheets for Needle Valves_RCA |  |  | 16-Aug-25 A | 20-Aug-25 A | 0
A43900 | Datasheets for Needle Valves_IFD/IFC |  |  | 20-Aug-25 A | 22-Aug-25 A | 0
Datasheets for Insulating Gaskets |  | 2025-11-13 | 2026-02-23 | 2025-09-19 | 2025-11-13 | 39
A43910 | Datasheets for Insulating Gaskets_IFR | 2025-09-23 | 2025-12-31 | 2025-09-19 | 2025-09-23 | 2
A43920 | Datasheets for Insulating Gaskets_RCC | 2025-10-14 | 2026-01-21 | 2025-09-23 | 2025-10-14 | 16
A43930 | Datasheets for Insulating Gaskets_IFA | 2025-10-20 | 2026-01-27 | 2025-10-15 | 2025-10-20 | 3
A43940 | Datasheets for Insulating Gaskets_RCA | 2025-11-11 | 2026-02-19 | 2025-10-20 | 2025-11-11 | 16
A43950 | Datasheets for Insulating Gaskets_IFD/IFC | 2025-11-13 | 2026-02-23 | 2025-11-11 | 2025-11-13 | 2
Datasheets for Flame Arrestors |  | 2025-10-14 | 2027-01-20 | 20-Apr-25 A | 2025-10-14 | 18
A43960 | Datasheets for Flame Arrestors_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A43970 | Datasheets for Flame Arrestors_RCC |  |  | 12-May-25 A | 18-May-25 A | 0
A43980 | Datasheets for Flame Arrestors_IFA |  |  | 19-May-25 A | 25-May-25 A | 0
A43990 | Datasheets for Flame Arrestors_RCA | 2025-10-10 | 2027-01-18 | 26-May-25 A | 2025-10-10 | 16
A44000 | Datasheets for Flame Arrestors_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Datasheets for Flame Bird Screen |  | 2025-10-20 | 2027-01-20 | 15-Apr-25 A | 2025-10-20 | 21
A44010 | Datasheets for Flame Bird Screen_IFR |  |  | 15-Apr-25 A | 06-May-25 A | 0
A44020 | Datasheets for Flame Bird Screen_RCC |  |  | 07-May-25 A | 13-May-25 A | 0
A44030 | Datasheets for Flame Bird Screen_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A44040 | Datasheets for Flame Bird Screen_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A44050 | Datasheets for Flame Bird Screen_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Datasheets for Hose Coupling |  | 2025-11-11 | 2026-02-23 | 01-Jul-25 A | 2025-11-11 | 37
A44060 | Datasheets for Hose Coupling_IFR |  |  | 01-Jul-25 A | 12-Jul-25 A | 0
A44070 | Datasheets for Hose Coupling_RCC | 2025-10-10 | 2026-01-21 | 2025-09-19 | 2025-10-10 | 16
A44080 | Datasheets for Hose Coupling_IFA | 2025-10-16 | 2026-01-27 | 2025-10-10 | 2025-10-16 | 3
A44090 | Datasheets for Hose Coupling_RCA | 2025-11-06 | 2026-02-19 | 2025-10-16 | 2025-11-06 | 16
A44100 | Datasheets for Hose Coupling_IFD/IFC | 2025-11-11 | 2026-02-23 | 2025-11-06 | 2025-11-11 | 2
Datasheets for Strainers |  | 2025-09-23 | 2027-01-20 | 14-Apr-25 A | 2025-09-23 | 2
A44110 | Datasheets for Strainers_IFR |  |  | 14-Apr-25 A | 05-May-25 A | 0
A44120 | Datasheets for Strainers_RCC |  |  | 06-May-25 A | 12-May-25 A | 0
A44130 | Datasheets for Strainers_IFA |  |  | 13-May-25 A | 01-Sep-25 A | 0
A44140 | Datasheets for Strainers_RCA |  |  | 02-Sep-25 A | 08-Sep-25 A | 0
A44150 | Datasheets for Strainers_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Datasheets for Spring Hangers |  | 2025-10-20 | 2026-02-23 | 14-Apr-25 A | 2025-10-20 | 21
A44160 | Datasheets for Spring Hangers_IFR |  |  | 14-Apr-25 A | 20-Jun-25 A | 0
A44170 | Datasheets for Spring Hangers_RCC |  |  | 20-Jun-25 A | 25-Aug-25 A | 0
A44180 | Datasheets for Spring Hangers_IFA | 2025-09-24 | 2026-01-28 | 2025-09-19 | 2025-09-24 | 3
A44190 | Datasheets for Spring Hangers_RCA | 2025-10-16 | 2026-02-19 | 2025-09-24 | 2025-10-16 | 16
A44200 | Datasheets for Spring Hangers_IFD/IFC | 2025-10-20 | 2026-02-23 | 2025-10-16 | 2025-10-20 | 2
Datasheets for Rigid Struts |  | 2025-10-20 | 2026-02-23 | 15-Apr-25 A | 2025-10-20 | 21
A44210 | Datasheets for Rigid Struts_IFR |  |  | 15-Apr-25 A | 06-May-25 A | 0
A44220 | Datasheets for Rigid Struts_RCC |  |  | 07-May-25 A | 13-May-25 A | 0
A44230 | Datasheets for Rigid Struts_IFA | 2025-09-24 | 2026-01-27 | 2025-09-19 | 2025-09-24 | 3
A44240 | Datasheets for Rigid Struts_RCA | 2025-10-16 | 2026-02-19 | 2025-09-24 | 2025-10-16 | 16
A44250 | Datasheets for Rigid Struts_IFD/IFC | 2025-10-20 | 2026-02-23 | 2025-10-16 | 2025-10-20 | 2
Datasheet for Piping Speciality Items |  | 2025-10-20 | 2026-03-26 | 01-Sep-25 A | 2025-10-20 | 21
A54490 | Datasheet for Piping Speciality Items_IFR |  |  | 01-Sep-25 A | 12-Sep-25 A | 0
A54500 | Datasheet for Piping Speciality Items_RCC |  |  | 15-Sep-25 A | 19-Sep-25 A | 0
A54510 | Datasheet for Piping Speciality Items_IFA | 2025-09-24 | 2026-02-27 | 2025-09-19 | 2025-09-24 | 3
A54520 | Datasheet for Piping Speciality Items_RCA | 2025-10-16 | 2026-03-24 | 2025-09-24 | 2025-10-16 | 16
A54530 | Datasheet for Piping Speciality Items_IFD/IFC | 2025-10-20 | 2026-03-26 | 2025-10-16 | 2025-10-20 | 2
Material Requisition for Piping Bulk |  | 2025-11-18 | 2026-02-25 | 15-Apr-25 A | 2025-11-18 | 43
A44720 | Material Requisition for Piping Bulk_IFR |  |  | 15-Apr-25 A | 06-May-25 A | 0
A44730 | Material Requisition for Piping Bulk_RCC | 2025-10-10 | 2026-01-27 | 2025-09-19 | 2025-10-10 | 16
A44740 | Material Requisition for Piping Bulk_IFA | 2025-10-23 | 2026-01-30 | 2025-10-20 | 2025-10-23 | 3
A44750 | Material Requisition for Piping Bulk_RCA | 2025-11-14 | 2026-02-23 | 2025-10-23 | 2025-11-14 | 16
A44760 | Material Requisition for Piping Bulk_IFD/IFC | 2025-11-18 | 2026-02-25 | 2025-11-14 | 2025-11-18 | 2
Material Requisition for HDPE Piping Bulk |  | 2025-11-18 | 2026-02-25 | 2025-09-19 | 2025-11-18 | 43
A60050 | Material Requisition for HDPE Piping Bulk_IFR | 2025-09-26 | 2025-11-13 | 2025-09-19 | 2025-09-26 | 6
A60060 | Material Requisition for HDPE Piping Bulk_RCC | 2025-10-20 | 2026-01-27 | 2025-09-26 | 2025-10-20 | 16
A60070 | Material Requisition for HDPE Piping Bulk_IFA | 2025-10-23 | 2026-01-30 | 2025-10-20 | 2025-10-23 | 3
A60080 | Material Requisition for HDPE Piping Bulk_RCA | 2025-11-14 | 2026-02-23 | 2025-10-23 | 2025-11-14 | 16
A60090 | Material Requisition for HDPE Piping Bulk_IFD/IFC | 2025-11-18 | 2026-02-25 | 2025-11-14 | 2025-11-18 | 2
Material Requisition for Manual Valves |  | 2025-11-13 | 2025-12-18 | 01-Jul-25 A | 2025-11-13 | 39
A44770 | Material Requisition for Manual Valves_IFR |  |  | 01-Jul-25 A | 12-Jul-25 A | 0
A44780 | Material Requisition for Manual Valves_RCC | 2025-09-26 | 2025-11-21 | 2025-09-19 | 2025-09-26 | 6
A44790 | Material Requisition for Manual Valves_IFA | 2025-10-17 | 2025-11-24 | 2025-10-16 | 2025-10-17 | 1
A44800 | Material Requisition for Manual Valves_RCA | 2025-11-07 | 2025-12-16 | 2025-10-17 | 2025-11-07 | 16
A44810 | Material Requisition for Manual Valves_IFD/IFC | 2025-11-13 | 2025-12-18 | 2025-11-11 | 2025-11-13 | 2
Material Requisition for Piping Speciality Items |  | 2025-11-11 | 2026-03-30 | 15-Sep-25 A | 2025-11-11 | 37
A44820 | Material Requisition for Piping Speciality Items_IFR |  |  | 15-Sep-25 A | 16-Sep-25 A | 0
A44830 | Material Requisition for Piping Speciality Items_RCC | 2025-10-10 | 2026-02-27 | 2025-09-19 | 2025-10-10 | 16
A44840 | Material Requisition for Piping Speciality Items_IFA | 2025-10-16 | 2026-03-04 | 2025-10-10 | 2025-10-16 | 3
A44850 | Material Requisition for Piping Speciality Items_RCA | 2025-11-06 | 2026-03-26 | 2025-10-16 | 2025-11-06 | 16
A44860 | Material Requisition for Piping Speciality Items_IFD/IFC | 2025-11-11 | 2026-03-30 | 2025-11-06 | 2025-11-11 | 2
Material Requisition for Spring Hangers |  | 2025-10-22 | 2026-02-25 | 22-Apr-25 A | 2025-10-22 | 24
A44870 | Material Requisition for Spring Hangers_IFR |  |  | 22-Apr-25 A | 13-May-25 A | 0
A44880 | Material Requisition for Spring Hangers_RCC |  |  | 14-May-25 A | 20-May-25 A | 0
A44890 | Material Requisition for Spring Hangers_IFA | 2025-09-24 | 2026-01-30 | 2025-09-19 | 2025-09-24 | 3
A44900 | Material Requisition for Spring Hangers_RCA | 2025-10-16 | 2026-02-23 | 2025-09-24 | 2025-10-16 | 16
A44910 | Material Requisition for Spring Hangers_IFD/IFC | 2025-10-22 | 2026-02-25 | 2025-10-20 | 2025-10-22 | 2
Material Requisition for Rigid Struts |  | 2025-10-23 | 2026-02-25 | 22-Apr-25 A | 2025-10-23 | 21
A44920 | Material Requisition for Rigid Struts_IFR |  |  | 22-Apr-25 A | 13-May-25 A | 0
A44930 | Material Requisition for Rigid Struts_RCC |  |  | 14-May-25 A | 20-May-25 A | 0
A44940 | Material Requisition for Rigid Struts_IFA | 2025-09-29 | 2026-01-30 | 2025-09-24 | 2025-09-29 | 3
A44950 | Material Requisition for Rigid Struts_RCA | 2025-10-21 | 2026-02-23 | 2025-09-29 | 2025-10-21 | 16
A44960 | Material Requisition for Rigid Struts_IFD/IFC | 2025-10-23 | 2026-02-25 | 2025-10-21 | 2025-10-23 | 2
Utility Station Location Plan |  | 2025-11-11 | 2027-01-20 | 15-Apr-25 A | 2025-11-11 | 37
A43510 | Utility Station Location Plan_IFR |  |  | 15-Apr-25 A | 06-May-25 A | 0
A43520 | Utility Station Location Plan_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A43530 | Utility Station Location Plan_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A43540 | Utility Station Location Plan_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A43550 | Utility Station Location Plan_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
30% 3D Model Review Report |  |  |  | 25-Apr-25 A | 21-Aug-25 A | 0
A43560 | 30% 3D Model Review Report_IFR |  |  | 25-Apr-25 A | 16-May-25 A | 0
A43570 | 30% 3D Model Review Report_RCC |  |  | 17-May-25 A | 23-May-25 A | 0
A43580 | 30% 3D Model Review Report_IFA |  |  | 24-May-25 A | 10-Aug-25 A | 0
A43590 | 30% 3D Model Review Report_RCA |  |  | 11-Aug-25 A | 15-Aug-25 A | 0
A43600 | 30% 3D Model Review Report_IFD/IFC |  |  | 16-Aug-25 A | 21-Aug-25 A | 0
30% 3D Model Review Closeout Report |  | 2025-10-24 | 2026-02-24 | 01-Jul-25 A | 2025-10-24 | 26
A43610 | 30% 3D Model Review Closeout Report_IFR |  |  | 01-Jul-25 A | 12-Jul-25 A | 0
A43620 | 30% 3D Model Review Closeout Report_RCC | 2025-09-25 | 2026-01-26 | 27-Aug-25 A | 2025-09-25 | 5
A43630 | 30% 3D Model Review Closeout Report_IFA | 2025-09-30 | 2026-01-29 | 2025-09-25 | 2025-09-30 | 3
A43640 | 30% 3D Model Review Closeout Report_RCA | 2025-10-22 | 2026-02-20 | 2025-09-30 | 2025-10-22 | 16
A43650 | 30% 3D Model Review Closeout Report_IFD/IFC | 2025-10-24 | 2026-02-24 | 2025-10-22 | 2025-10-24 | 2
Plot Plan |  |  |  | 09-Mar-25 A | 27-Jun-25 A | 0
A45220 | Plot Plan_IFR |  |  | 14-Mar-25 A | 27-Apr-25 A | 0
A45230 | Plot Plan_RCC |  |  | 28-Apr-25 A | 17-May-25 A | 0
A45240 | Plot Plan_IFA |  |  | 19-May-25 A | 30-May-25 A | 0
A45250 | Plot Plan_RCA |  |  | 02-Jun-25 A | 13-Jun-25 A | 0
A45260 | Plot Plan_IFD/IFC |  |  | 16-Jun-25 A | 27-Jun-25 A | 0
A55670 | Plot Plan_Preliminary issuance for Plot plan workshop |  |  | 09-Mar-25 A | 12-Mar-25 A | 0
Plot Plan Review Report |  | 2025-09-23 | 2027-01-20 | 19-Apr-25 A | 2025-09-23 | 2
A43360 | Plot Plan Review Report_IFR |  |  | 19-Apr-25 A | 10-May-25 A | 0
A43370 | Plot Plan Review Report_RCC |  |  | 11-May-25 A | 17-May-25 A | 0
A43380 | Plot Plan Review Report_IFA |  |  | 18-May-25 A | 21-Jun-25 A | 0
A43390 | Plot Plan Review Report_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A43400 | Plot Plan Review Report_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
First Material Take Off |  |  |  | 02-Jun-25 A | 27-Jun-25 A | 0
A45270 | First Material Take Off_IFR |  |  | 02-Jun-25 A | 06-Jun-25 A | 0
A45280 | First Material Take Off_RCC |  |  | 09-Jun-25 A | 20-Jun-25 A | 0
A45290 | First Material Take Off_IFD/IFC |  |  | 23-Jun-25 A | 27-Jun-25 A | 0
Plot Plan Close Out Report |  | 2025-10-20 | 2027-01-20 | 19-Apr-25 A | 2025-10-20 | 21
A43410 | Plot Plan Close Out report_IFR |  |  | 19-Apr-25 A | 10-May-25 A | 0
A43420 | Plot Plan Close Out report_RCC |  |  | 11-May-25 A | 17-May-25 A | 0
A43430 | Plot Plan Close Out report_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A43440 | Plot Plan Close Out report_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A43450 | Plot Plan Close Out report_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Manual Valves List (Valves MTOs) |  | 2025-09-23 | 2027-01-20 | 25-Feb-25 A | 2025-09-23 | 2
A44690 | Manual Valves List (Valves MTOs)_IFR |  |  | 25-Feb-25 A | 10-Apr-25 A | 0
A44700 | Manual Valves List (Valves MTOs)_RCC |  |  | 11-Apr-25 A | 23-Apr-25 A | 0
A44710 | Manual Valves List (Valves MTOs)_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Technical Bid Evaluation (TBE) for Piping Bulk | [5 empty] | 0
Technical Bid Evaluation (TBE) for HDPE Piping Bulk | [5 empty] | 0
Technical Bid Evaluation (TBE) for Manual Valves | [5 empty] | 0
Technical Bid Evaluation (TBE) for Piping Speciality Items | [5 empty] | 0
Technical Bid Evaluation (TBE) for Spring Hangers | [5 empty] | 0
Technical Bid Evaluation (TBE) for Rigid Struts |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A45170 | Technical Bid Evaluation (TBE) for Rigid Struts_IFR | 2025-09-26 | 2025-12-05 | 2025-09-19 | 2025-09-26 | 6
A45180 | Technical Bid Evaluation (TBE) for Rigid Struts_RCC | 2025-10-20 | 2025-12-26 | 2025-09-26 | 2025-10-20 | 16
A45190 | Technical Bid Evaluation (TBE) for Rigid Struts_IFA | 2025-10-23 | 2026-01-01 | 2025-10-20 | 2025-10-23 | 3
A45200 | Technical Bid Evaluation (TBE) for Rigid Struts_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A45210 | Technical Bid Evaluation (TBE) for Rigid Struts_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
60% 3D Model Review Report |  | 2025-11-20 | 2027-01-20 | 2025-09-19 | 2025-11-20 | 45
A44260 | 60% 3D Model Review Report_IFR | 2025-09-26 | 2025-11-27 | 2025-09-19 | 2025-09-26 | 6
A44270 | 60% 3D Model Review Report_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A44280 | 60% 3D Model Review Report_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A44290 | 60% 3D Model Review Report_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A44300 | 60% 3D Model Review Report_IFD/IFC | 2025-11-20 | 2027-01-20 | 2025-11-18 | 2025-11-20 | 2
60% 3D Model Review Closeout Report |  | 2025-12-03 | 2027-01-20 | 2025-09-26 | 2025-12-03 | 48
A44310 | 60% 3D Model Review Closeout Report_IFR | 2025-10-13 | 2025-12-12 | 2025-09-26 | 2025-10-13 | 11
A44320 | 60% 3D Model Review Closeout Report_RCC | 2025-11-04 | 2026-04-03 | 2025-10-13 | 2025-11-04 | 16
A44330 | 60% 3D Model Review Closeout Report_IFA | 2025-11-07 | 2026-04-09 | 2025-11-04 | 2025-11-07 | 3
A44340 | 60% 3D Model Review Closeout Report_RCA | 2025-12-01 | 2027-01-18 | 2025-11-10 | 2025-12-01 | 16
A44350 | 60% 3D Model Review Closeout Report_IFD/IFC | 2025-12-03 | 2027-01-20 | 2025-12-01 | 2025-12-03 | 2
Piping Stress Analysis Reports |  | 2025-12-26 | 2027-01-20 | 18-Sep-25 A | 2025-12-26 | 71
A44640 | Piping Stress Analysis Reports_IFR | 2025-10-21 | 2026-11-13 | 18-Sep-25 A | 2025-10-21 | 23
A44650 | Piping Stress Analysis Reports_RCC | 2025-11-12 | 2026-12-07 | 2025-10-21 | 2025-11-12 | 16
A44660 | Piping Stress Analysis Reports_IFA | 2025-11-27 | 2026-12-22 | 2025-11-12 | 2025-11-27 | 11
A44670 | Piping Stress Analysis Reports_RCA | 2025-12-19 | 2027-01-13 | 2025-11-27 | 2025-12-19 | 16
A44680 | Piping Stress Analysis Reports_IFD/IFC | 2025-12-26 | 2027-01-20 | 2025-12-19 | 2025-12-26 | 6
Piping GA Drawings & Key Plan for Piping GADs |  | 2026-02-10 | 2027-01-20 | 2025-10-13 | 2026-02-10 | 86
A44540 | Piping GA Drawings & Key Plan for Piping GADs_IFR | 2025-12-03 | 2026-02-03 | 2025-10-13 | 2025-12-03 | 37
A44550 | Piping GA Drawings & Key Plan for Piping GADs_RCC | 2025-12-25 | 2026-02-25 | 2025-12-04 | 2025-12-25 | 16
A44560 | Piping GA Drawings & Key Plan for Piping GADs_IFA | 2026-01-09 | 2026-12-22 | 2025-12-25 | 2026-01-09 | 11
A44570 | Piping GA Drawings & Key Plan for Piping GADs_RCA | 2026-02-02 | 2027-01-13 | 2026-01-12 | 2026-02-02 | 16
A44580 | Piping GA Drawings & Key Plan for Piping GADs_IFD/IFC | 2026-02-10 | 2027-01-20 | 2026-02-02 | 2026-02-10 | 6
Piping Isometrics (large bore) |  | 2026-01-13 | 2026-03-12 | 2025-09-19 | 2026-01-13 | 82
A44360 | Piping Isometrics (large bore)_IFR | 2025-11-05 | 2026-01-05 | 2025-09-19 | 2025-11-05 | 34
A44370 | Piping Isometrics (large bore)_RCC | 2025-11-27 | 2026-01-27 | 2025-11-05 | 2025-11-27 | 16
A44380 | Piping Isometrics (large bore)_IFA | 2025-12-12 | 2026-02-11 | 2025-11-27 | 2025-12-12 | 11
A44390 | Piping Isometrics (large bore)_RCA | 2026-01-05 | 2026-03-05 | 2025-12-12 | 2026-01-05 | 16
A44400 | Piping Isometrics (large bore)_IFD/IFC | 2026-01-13 | 2026-03-12 | 2026-01-05 | 2026-01-13 | 6
Second Material Take Off |  | 2025-10-14 | 2026-03-05 | 01-Sep-25 A | 2025-10-14 | 18
A45300 | Second Material Take Off_IFR |  |  | 01-Sep-25 A | 08-Sep-25 A | 0
A45310 | Second Material Take Off_RCC | 2025-10-10 | 2026-03-02 | 2025-09-19 | 2025-10-10 | 16
A45320 | Second Material Take Off_IFD/IFC | 2025-10-14 | 2026-03-05 | 2025-10-10 | 2025-10-14 | 2
90% 3D Model Review Report |  | 2026-03-04 | 2026-06-26 | 2026-01-02 | 2026-03-04 | 43
A44410 | 90% 3D Model Review Report_IFR | 2026-01-09 | 2026-05-06 | 2026-01-02 | 2026-01-09 | 6
A44420 | 90% 3D Model Review Report_RCC | 2026-02-02 | 2026-05-28 | 2026-01-12 | 2026-02-02 | 16
A44430 | 90% 3D Model Review Report_IFA | 2026-02-06 | 2026-06-02 | 2026-02-02 | 2026-02-06 | 3
A44440 | 90% 3D Model Review Report_RCA | 2026-02-27 | 2026-06-24 | 2026-02-06 | 2026-02-27 | 16
A44450 | 90% 3D Model Review Report_IFD/IFC | 2026-03-04 | 2026-06-26 | 2026-02-27 | 2026-03-04 | 2
Piping Isometrics(Small Bore) |  | 2026-02-27 | 2026-06-24 | 2026-01-02 | 2026-02-27 | 41
A44510 | Piping Isometrics(Small Bore)_IFR | 2026-02-03 | 2026-05-29 | 2026-01-02 | 2026-02-03 | 23
A44520 | Piping Isometrics(Small Bore)_RCC | 2026-02-25 | 2026-06-22 | 2026-02-03 | 2026-02-25 | 16
A44530 | Piping Isometrics(Small Bore)_IFD/IFC | 2026-02-27 | 2026-06-24 | 2026-02-25 | 2026-02-27 | 2
Piping Tie-Ins Schedule |  | 2026-01-06 | 2026-10-15 | 2025-09-19 | 2026-01-06 | 78
A44590 | Piping Tie-Ins Schedule_IFR | 2025-09-26 | 2026-08-25 | 2025-09-19 | 2025-09-26 | 6
A44600 | Piping Tie-Ins Schedule_RCC | 2025-10-20 | 2026-09-16 | 2025-09-26 | 2025-10-20 | 16
A44610 | Piping Tie-Ins Schedule_IFA | 2025-10-23 | 2026-09-21 | 2025-10-20 | 2025-10-23 | 3
A44620 | Piping Tie-Ins Schedule_RCA | 2025-11-14 | 2026-10-13 | 2025-10-23 | 2025-11-14 | 16
A44630 | Piping Tie-Ins Schedule_IFD/IFC | 2026-01-06 | 2026-10-15 | 2026-01-02 | 2026-01-06 | 2
90% 3D Model Review Closeout Report |  | 2026-03-11 | 2027-01-20 | 2026-01-12 | 2026-03-11 | 43
A44460 | 90% 3D Model Review Closeout Report_IFR | 2026-01-19 | 2026-11-27 | 2026-01-12 | 2026-01-19 | 6
A44470 | 90% 3D Model Review Closeout Report_RCC | 2026-02-10 | 2026-12-22 | 2026-01-19 | 2026-02-10 | 16
A44480 | 90% 3D Model Review Closeout Report_IFA | 2026-02-13 | 2026-12-25 | 2026-02-10 | 2026-02-13 | 3
A44490 | 90% 3D Model Review Closeout Report_RCA | 2026-03-09 | 2027-01-18 | 2026-02-13 | 2026-03-09 | 16
A44500 | 90% 3D Model Review Closeout Report_IFD/IFC | 2026-03-11 | 2027-01-20 | 2026-03-09 | 2026-03-11 | 2
Final Material Take Off |  | 2025-10-22 | 2026-01-05 | 2025-09-19 | 2025-10-22 | 24
A45330 | Final Material Take Off_IFR | 2025-09-26 | 2025-12-10 | 2025-09-19 | 2025-09-26 | 6
A45340 | Final Material Take Off_RCC | 2025-10-20 | 2026-01-01 | 2025-09-26 | 2025-10-20 | 16
A45350 | Final Material Take Off_IFD/IFC | 2025-10-22 | 2026-01-05 | 2025-10-20 | 2025-10-22 | 2
Mechanical |  | 2025-11-11 | 2027-01-20 | 31-Dec-24 A | 2025-11-11 | 37
Mechanical Static |  | 2025-11-11 | 2027-01-20 | 31-Dec-24 A | 2025-11-11 | 37
Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705) |  |  |  | 31-Dec-24 A | 10-May-25 A | 0
A54590 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFR |  |  | 31-Dec-24 A | 06-Feb-25 A | 0
A54600 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCC |  |  | 07-Feb-25 A | 19-Apr-25 A | 0
A54610 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54620 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54630 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Suction Drum (Tag No. 13-Vv-705)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706) |  |  |  | 31-Dec-24 A | 10-May-25 A | 0
A54640 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFR |  |  | 31-Dec-24 A | 06-Feb-25 A | 0
A54650 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCC |  |  | 07-Feb-25 A | 19-Apr-25 A | 0
A54660 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54670 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54680 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-706)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707) |  |  |  | 31-Dec-24 A | 10-May-25 A | 0
A54690 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFR |  |  | 31-Dec-24 A | 06-Feb-25 A | 0
A54700 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCC |  |  | 07-Feb-25 A | 19-Apr-25 A | 0
A54710 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54720 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54730 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Suction Drum (Tag No. 13-Vv-707)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx) |  |  |  | 31-Dec-24 A | 05-Jul-25 A | 0
A54740 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFR |  |  | 31-Dec-24 A | 24-Jan-25 A | 0
A54750 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCC |  |  | 25-Jan-25 A | 19-Apr-25 A | 0
A54760 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFA |  |  | 20-Apr-25 A | 21-Jun-25 A | 0
A54770 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A54780 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Discharge Drum (Tag No. 13-Vv-Xxx)_IFD/IFC |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712) |  |  |  | 31-Dec-24 A | 10-May-25 A | 0
A54790 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFR |  |  | 31-Dec-24 A | 06-Feb-25 A | 0
A54800 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCC |  |  | 07-Feb-25 A | 19-Apr-25 A | 0
A54810 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54820 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54830 | Mechanical Datasheet For Psa2 Off Gas Buffer Drum (Tag No. 13-Vv-712)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713) |  |  |  | 31-Dec-24 A | 10-May-25 A | 0
A54840 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFR |  |  | 31-Dec-24 A | 06-Feb-25 A | 0
A54850 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCC |  |  | 07-Feb-25 A | 19-Apr-25 A | 0
A54860 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54870 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54880 | Mechanical Datasheet For Psa2 Off Gas Compressor 2Nd Stage Suction Drum (Tag No. 13-Vv-713)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415) |  |  |  | 01-Jan-25 A | 10-May-25 A | 0
A27210 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFR |  |  | 01-Jan-25 A | 06-Feb-25 A | 0
A27220 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCC |  |  | 07-Feb-25 A | 19-Apr-25 A | 0
A27230 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54890 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54900 | Mechanical Datasheet For Psa2 Slop Drum (Tag No. 70-Vv-1415)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703) |  |  |  | 07-Jan-25 A | 10-May-25 A | 0
A54910 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFR |  |  | 07-Jan-25 A | 06-Feb-25 A | 0
A54920 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCC |  |  | 07-Feb-25 A | 19-Apr-25 A | 0
A54930 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54940 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54950 | Mechanical Datasheet For Psa2 Feed Gas Compressor 1St Stage Cooler (Tag No. 13-He-703)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704) |  |  |  | 14-Feb-25 A | 03-May-25 A | 0
A54960 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFR |  |  | 14-Feb-25 A | 07-Mar-25 A | 0
A54970 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCC |  |  | 08-Mar-25 A | 14-Mar-25 A | 0
A54980 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFA |  |  | 15-Mar-25 A | 21-Mar-25 A | 0
A54990 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_RCA |  |  | 22-Mar-25 A | 30-Apr-25 A | 0
A55000 | Mechanical Datasheet For Psa2 Feed Gas Compressor 2Nd Stage Cooler (Tag No. 13-He-704)_IFD/IFC |  |  | 01-May-25 A | 03-May-25 A | 0
Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703) |  |  |  | 20-Jan-25 A | 14-Jun-25 A | 0
A55010 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFR |  |  | 20-Jan-25 A | 26-Feb-25 A | 0
A55020 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCC |  |  | 27-Feb-25 A | 19-Apr-25 A | 0
A55030 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A55040 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_RCA |  |  | 08-Jun-25 A | 10-Jun-25 A | 0
A55050 | Mechanical Datasheet For Psa2 Feed Gas Compressor 3Rd Stage Cooler (Tag No. 13-He-703)_IFD/IFC |  |  | 11-Jun-25 A | 14-Jun-25 A | 0
Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708) |  |  |  | 25-Feb-25 A | 09-May-25 A | 0
A27430 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFA |  |  | 05-Mar-25 A | 25-Apr-25 A | 0
A55060 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFR |  |  | 25-Feb-25 A | 26-Feb-25 A | 0
A55070 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCC |  |  | 27-Feb-25 A | 04-Mar-25 A | 0
A55080 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_RCA |  |  | 26-Apr-25 A | 02-May-25 A | 0
A55090 | Mechanical Datasheet For Psa2 Off Gas Compressor Interstage Cooler(Tag No. 13-He-708)_IFD/IFC |  |  | 03-May-25 A | 09-May-25 A | 0
Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709) |  |  |  | 25-Feb-25 A | 09-May-25 A | 0
A55100 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFR |  |  | 25-Feb-25 A | 26-Feb-25 A | 0
A55110 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCC |  |  | 27-Feb-25 A | 04-Mar-25 A | 0
A55120 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFA |  |  | 05-Mar-25 A | 25-Apr-25 A | 0
A55130 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_RCA |  |  | 26-Apr-25 A | 02-May-25 A | 0
A55140 | Mechanical Datasheet For Psa2 Off Gas Compressor Aftercooler(Tag No. 13-He-709)_IFD/IFC |  |  | 03-May-25 A | 09-May-25 A | 0
Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004 |  |  |  | 01-Jan-25 A | 10-May-25 A | 0
A27510 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFR |  |  | 01-Jan-25 A | 24-Jan-25 A | 0
A27520 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCC |  |  | 25-Jan-25 A | 19-Apr-25 A | 0
A55150 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A55160 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A55170 | Mechanical Datasheet For Psa2 Off Gas Compressor Discharge Dripleg -13-Sp-7004_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410) |  |  |  | 27-Feb-25 A | 10-May-25 A | 0
A55180 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFR |  |  | 27-Feb-25 A | 20-Mar-25 A | 0
A55190 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCC |  |  | 21-Mar-25 A | 19-Apr-25 A | 0
A55200 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A55210 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A55220 | Mechanical Datasheet For C4 Guard Adsorber Regeneration Gas Cooler(Tag No. 50-He-1410)_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A27610 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFR |  |  | 01-Jul-25 A | 12-Jul-25 A | 0
A55230 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A55240 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A55250 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A55260 | Mechanical Datasheet For Vhp Boiler Feed Water Preheater Dripleg_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Mechanical Datasheet For Off-Gas Compressor Coalescer |  |  |  | 13-Jan-25 A | 03-Mar-25 A | 0
A27700 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFD/IFC |  |  | 25-Feb-25 A | 03-Mar-25 A | 0
A55270 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFR |  |  | 13-Jan-25 A | 03-Feb-25 A | 0
A55280 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCC |  |  | 04-Feb-25 A | 10-Feb-25 A | 0
A55290 | Mechanical Datasheet For Off-Gas Compressor Coalescer_IFA |  |  | 11-Feb-25 A | 17-Feb-25 A | 0
A55300 | Mechanical Datasheet For Off-Gas Compressor Coalescer_RCA |  |  | 18-Feb-25 A | 24-Feb-25 A | 0
Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer |  |  |  | 06-Jan-25 A | 10-May-25 A | 0
A55310 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFR |  |  | 06-Jan-25 A | 14-Mar-25 A | 0
A55320 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCC |  |  | 15-Mar-25 A | 19-Apr-25 A | 0
A55330 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A55340 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A55350 | Mechanical Datasheet For Guard Adsorber Regeneration Gas Coalescer_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Datasheet For Tail Gas Silencer |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A27790 | Mechanical Datasheet For Tail Gas Silencer_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A55360 | Mechanical Datasheet For Tail Gas Silencer_IFR |  |  | 01-Jul-25 A | 12-Jul-25 A | 0
A55370 | Mechanical Datasheet For Tail Gas Silencer_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A55380 | Mechanical Datasheet For Tail Gas Silencer_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A55390 | Mechanical Datasheet For Tail Gas Silencer_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Material Requisiton for Coalscer |  |  |  | 28-Feb-25 A | 14-May-25 A | 0
A45410 | Material Requisiton for Coalscer_IFR |  |  | 28-Feb-25 A | 21-Mar-25 A | 0
A45420 | Material Requisiton for Coalscer_RCC |  |  | 22-Mar-25 A | 21-Apr-25 A | 0
A45430 | Material Requisiton for Coalscer_IFA |  |  | 22-Apr-25 A | 30-Apr-25 A | 0
A45440 | Material Requisiton for Coalscer_RCA |  |  | 01-May-25 A | 07-May-25 A | 0
A45450 | Material Requisiton for Coalscer_IFD/IFC |  |  | 08-May-25 A | 14-May-25 A | 0
Material Requisiton for Shell and Tube Heat Exchangers |  |  |  | 21-Feb-25 A | 20-Jun-25 A | 0
A45360 | Material Requisiton for Heat Exchangers_IFR |  |  | 21-Feb-25 A | 14-Mar-25 A | 0
A45370 | Material Requisiton for Heat Exchangers_RCC |  |  | 01-Jun-25 A | 05-Jun-25 A | 0
A45380 | Material Requisiton for Heat Exchangers_IFA |  |  | 06-Jun-25 A | 10-Jun-25 A | 0
A45390 | Material Requisiton for Heat Exchangers_RCA |  |  | 11-Jun-25 A | 15-Jun-25 A | 0
A45400 | Material Requisiton for Heat Exchangers_IFD/IFC |  |  | 16-Jun-25 A | 20-Jun-25 A | 0
Material Requisiton for Pressure Vessels & Internals |  |  |  | 17-Jan-25 A | 09-May-25 A | 0
A45910 | Material Requisiton for Pressure Vessels & Internals_IFR |  |  | 17-Jan-25 A | 07-Feb-25 A | 0
A45920 | Material Requisiton for Pressure Vessels & Internals_RCC |  |  | 08-Feb-25 A | 14-Feb-25 A | 0
A45930 | Material Requisiton for Pressure Vessels & Internals_IFA |  |  | 15-Feb-25 A | 25-Apr-25 A | 0
A45940 | Material Requisiton for Pressure Vessels & Internals_RCA |  |  | 26-Apr-25 A | 02-May-25 A | 0
A45950 | Material Requisiton for Pressure Vessels & Internals_IFD/IFC |  |  | 03-May-25 A | 09-May-25 A | 0
Technical Bid Evaluation for Coalscer | [5 empty] | 0
Technical Bid Evaluation for Shell and Tube Heat Exchangers | [5 empty] | 0
Technical Bid Evaluation for Pressure Vessels & Internals | [5 empty] | 0
Mechanical Rotating |  |  |  | 04-Jan-25 A | 28-Jun-25 A | 0
Mechanical Datasheet For Sanitary Water Collection Pump |  |  |  | 05-Feb-25 A | 10-May-25 A | 0
A54540 | Mechanical Datasheet For Sanitary Water Collection Pump_IFR |  |  | 05-Feb-25 A | 26-Feb-25 A | 0
A54550 | Mechanical Datasheet For Sanitary Water Collection Pump_RCC |  |  | 27-Feb-25 A | 19-Apr-25 A | 0
A54560 | Mechanical Datasheet For Sanitary Water Collection Pump_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A54570 | Mechanical Datasheet For Sanitary Water Collection Pump_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A54580 | Mechanical Datasheet For Sanitary Water Collection Pump_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Mechanical Data Sheet for EOT Crane for Feed Gas Compressor |  |  |  | 27-Jan-25 A | 28-Jun-25 A | 0
A45610 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFR |  |  | 27-Jan-25 A | 26-Feb-25 A | 0
A45620 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCC |  |  | 27-Feb-25 A | 19-Apr-25 A | 0
A45630 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFA |  |  | 20-Apr-25 A | 10-Jun-25 A | 0
A45640 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_RCA |  |  | 11-Jun-25 A | 21-Jun-25 A | 0
A45650 | Mechanical Data Sheet for EOT Crane for Feed Gas Compressor_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Mechanical Data Sheet EOT Crane for Off Gas Compressor |  |  |  | 27-Jan-25 A | 28-Jun-25 A | 0
A45660 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFR |  |  | 27-Jan-25 A | 26-Feb-25 A | 0
A45670 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCC |  |  | 27-Feb-25 A | 18-Mar-25 A | 0
A45680 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFA |  |  | 19-Mar-25 A | 10-Jun-25 A | 0
A45690 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_RCA |  |  | 11-Jun-25 A | 21-Jun-25 A | 0
A45700 | Mechanical Data Sheet EOT Crane for Off Gas Compressor_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Mechanical Datasheet for Water Collection Sump Pump |  |  |  | 04-Jan-25 A | 10-May-25 A | 0
A45560 | Mechanical Datasheet for Water Collection Sump Pump_IFR |  |  | 04-Jan-25 A | 25-Jan-25 A | 0
A45570 | Mechanical Datasheet for Water Collection Sump Pump_RCC |  |  | 26-Jan-25 A | 19-Apr-25 A | 0
A45580 | Mechanical Datasheet for Water Collection Sump Pump_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A45590 | Mechanical Datasheet for Water Collection Sump Pump_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A45600 | Mechanical Datasheet for Water Collection Sump Pump_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Material Requisiton for EOT Crane |  |  |  | 15-Apr-25 A | 13-Jun-25 A | 0
A45760 | Material Requisiton for EOT Crane_IFR |  |  | 15-Apr-25 A | 06-May-25 A | 0
A45770 | Material Requisiton for EOT Crane_RCC |  |  | 07-May-25 A | 13-May-25 A | 0
A45780 | Material Requisiton for EOT Crane_IFA |  |  | 14-May-25 A | 20-May-25 A | 0
A45790 | Material Requisiton for EOT Crane_RCA |  |  | 21-May-25 A | 02-Jun-25 A | 0
A45800 | Material Requisiton for EOT Crane_IFD/IFC |  |  | 03-Jun-25 A | 13-Jun-25 A | 0
Material Requisiton for Centrifugal Pump |  |  |  | 27-Jan-25 A | 21-Jun-25 A | 0
A45710 | Material Requisiton for Centrifugal Pump_IFR |  |  | 27-Jan-25 A | 21-Mar-25 A | 0
A45720 | Material Requisiton for Centrifugal Pump_RCC |  |  | 22-Mar-25 A | 19-Apr-25 A | 0
A45730 | Material Requisiton for Centrifugal Pump_IFA |  |  | 20-Apr-25 A | 01-May-25 A | 0
A45740 | Material Requisiton for Centrifugal Pump_RCA |  |  | 02-May-25 A | 26-May-25 A | 0
A45750 | Material Requisiton for Centrifugal Pump_IFD/IFC |  |  | 27-May-25 A | 21-Jun-25 A | 0
Technical Bid Evaluation for Centrifugal Pump | [5 empty] | 0
Technical Bid Evaluation for EOT Crane | [5 empty] | 0
Safety |  | 2026-03-20 | 2027-01-20 | 31-Dec-24 A | 2026-03-20 | 131
Engineering HSE Plan |  |  |  | 30-Jan-25 A | 19-May-25 A | 0
A46010 | Engineering HSE Plan_IFR |  |  | 30-Jan-25 A | 20-Feb-25 A | 0
A46020 | Engineering HSE Plan_RCC |  |  | 21-Feb-25 A | 27-Feb-25 A | 0
A46030 | Engineering HSE Plan_IFA |  |  | 28-Feb-25 A | 06-Mar-25 A | 0
A46040 | Engineering HSE Plan_RCA |  |  | 07-Mar-25 A | 12-May-25 A | 0
A46050 | Engineering HSE Plan_IFD/IFC |  |  | 13-May-25 A | 19-May-25 A | 0
Project HSE Philosophy |  |  |  | 31-Dec-24 A | 20-May-25 A | 0
A46060 | Project HSE Philosophy_IFR |  |  | 31-Dec-24 A | 23-Jan-25 A | 0
A46070 | Project HSE Philosophy_RCC |  |  | 24-Jan-25 A | 03-Mar-25 A | 0
A46080 | Project HSE Philosophy_IFA |  |  | 04-Mar-25 A | 10-Mar-25 A | 0
A46090 | Project HSE Philosophy_RCA |  |  | 11-Mar-25 A | 13-Mar-25 A | 0
A46100 | Project HSE Philosophy_IFD/IFC |  |  | 14-Mar-25 A | 20-May-25 A | 0
Fire Protection and Detection Philosophy |  | 2025-10-14 | 2027-01-20 | 07-Feb-25 A | 2025-10-14 | 18
A46110 | Fire Protection and Detection Philosophy_IFR |  |  | 07-Feb-25 A | 28-Feb-25 A | 0
A46120 | Fire Protection and Detection Philosophy_RCC |  |  | 01-Mar-25 A | 21-Jun-25 A | 0
A46130 | Fire Protection and Detection Philosophy_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A46140 | Fire Protection and Detection Philosophy_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46150 | Fire Protection and Detection Philosophy_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Hazardous Area Classification Schedule |  | 2025-10-14 | 2027-01-20 | 17-Jan-25 A | 2025-10-14 | 18
A46160 | Hazardous Area Classification Schedule_IFR |  |  | 17-Jan-25 A | 07-Feb-25 A | 0
A46170 | Hazardous Area Classification Schedule_RCC |  |  | 08-Feb-25 A | 06-May-25 A | 0
A46180 | Hazardous Area Classification Schedule_IFA |  |  | 07-May-25 A | 20-May-25 A | 0
A46190 | Hazardous Area Classification Schedule_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46200 | Hazardous Area Classification Schedule_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Fire Protection and Safety Equipment Layouts (Building) |  | 2025-09-23 | 2027-01-20 | 27-Feb-25 A | 2025-09-23 | 2
A46360 | Fire Protection and Safety Equipment Layouts (Building)_IFR |  |  | 27-Feb-25 A | 20-Mar-25 A | 0
A46370 | Fire Protection and Safety Equipment Layouts (Building)_RCC |  |  | 21-Mar-25 A | 21-Jun-25 A | 0
A46380 | Fire Protection and Safety Equipment Layouts (Building)_IFA |  |  | 22-Jun-25 A | 28-Jul-25 A | 0
A46390 | Fire Protection and Safety Equipment Layouts (Building)_RCA |  |  | 29-Jul-25 A | 27-Aug-25 A | 0
A46400 | Fire Protection and Safety Equipment Layouts (Building)_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Escape Route and Safety Signs Layouts (Building) |  | 2025-10-14 | 2027-01-20 | 27-Feb-25 A | 2025-10-14 | 18
A46460 | Escape Route and Safety Signs Layouts (Building)_IFR |  |  | 27-Feb-25 A | 20-Mar-25 A | 0
A46470 | Escape Route and Safety Signs Layouts (Building)_RCC |  |  | 21-Mar-25 A | 21-Jun-25 A | 0
A46480 | Escape Route and Safety Signs Layouts (Building)_IFA |  |  | 22-Jun-25 A | 16-Jul-25 A | 0
A46490 | Escape Route and Safety Signs Layouts (Building)_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46500 | Escape Route and Safety Signs Layouts (Building)_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Fire & Gas Detectors Layouts (Building) |  | 2025-10-14 | 2027-01-20 | 27-Feb-25 A | 2025-10-14 | 18
A46560 | Fire & Gas Detectors Layouts (Building)_IFR |  |  | 27-Feb-25 A | 20-Mar-25 A | 0
A46570 | Fire & Gas Detectors Layouts (Building)_RCC |  |  | 21-Mar-25 A | 21-Jun-25 A | 0
A46580 | Fire & Gas Detectors Layouts (Building)_IFA |  |  | 22-Jun-25 A | 16-Jul-25 A | 0
A46590 | Fire & Gas Detectors Layouts (Building)_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46600 | Fire & Gas Detectors Layouts (Building)_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
F&G Cause and Effects Matrix |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A46610 | F&G Cause and Effects Matrix_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A46620 | F&G Cause and Effects Matrix_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A46630 | F&G Cause and Effects Matrix_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A46640 | F&G Cause and Effects Matrix_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A46650 | F&G Cause and Effects Matrix_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Specification for Fire Protection and Safety Equipment |  | 2025-10-14 | 2027-01-20 | 07-Feb-25 A | 2025-10-14 | 18
A46760 | Specification for Fire Protection and Safety Equipment_IFR |  |  | 07-Feb-25 A | 28-Feb-25 A | 0
A46770 | Specification for Fire Protection and Safety Equipment_RCC |  |  | 01-Mar-25 A | 31-Jul-25 A | 0
A46780 | Specification for Fire Protection and Safety Equipment_IFA |  |  | 01-Aug-25 A | 14-Aug-25 A | 0
A46790 | Specification for Fire Protection and Safety Equipment_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46800 | Specification for Fire Protection and Safety Equipment_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Specification for Clean Agent System |  |  |  | 11-Feb-25 A | 18-Aug-25 A | 0
A46810 | Specification for Clean Agent System_IFR |  |  | 11-Feb-25 A | 04-Mar-25 A | 0
A46820 | Specification for Clean Agent System_RCC |  |  | 05-Mar-25 A | 21-Jun-25 A | 0
A46830 | Specification for Clean Agent System_IFA |  |  | 22-Jun-25 A | 11-Jul-25 A | 0
A46840 | Specification for Clean Agent System_RCA |  |  | 12-Jul-25 A | 30-Jul-25 A | 0
A46850 | Specification for Clean Agent System_IFD/IFC |  |  | 01-Aug-25 A | 18-Aug-25 A | 0
MR for Clean Agent System |  | 2025-09-23 | 2026-01-08 | 28-Feb-25 A | 2025-09-23 | 2
A47230 | MR for Clean Agent System_IFR |  |  | 28-Feb-25 A | 21-Mar-25 A | 0
A47240 | MR for Clean Agent System_RCC |  |  | 22-Mar-25 A | 21-Jun-25 A | 0
A47250 | MR for Clean Agent System_IFA |  |  | 22-Jun-25 A | 23-Aug-25 A | 0
A47260 | MR for Clean Agent System_RCA |  |  | 24-Aug-25 A | 30-Aug-25 A | 0
A47270 | MR for Clean Agent System_IFD/IFC | 2025-09-23 | 2026-01-08 | 2025-09-19 | 2025-09-23 | 2
Firewater Line List |  | 2025-11-14 | 2027-01-20 | 28-Feb-25 A | 2025-11-14 | 41
A47130 | Firewater Line List_IFR |  |  | 28-Feb-25 A | 21-Mar-25 A | 0
A47140 | Firewater Line List_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A47150 | Firewater Line List_IFA | 2025-10-21 | 2026-12-25 | 2025-10-16 | 2025-10-21 | 3
A47160 | Firewater Line List_RCA | 2025-11-12 | 2027-01-18 | 2025-10-21 | 2025-11-12 | 16
A47170 | Firewater Line List_IFD/IFC | 2025-11-14 | 2027-01-20 | 2025-11-12 | 2025-11-14 | 2
Passive Fire Protection schedule |  | 2025-10-14 | 2027-01-20 | 28-Feb-25 A | 2025-10-14 | 18
A46660 | Passive Fire Protection schedule_IFR |  |  | 28-Feb-25 A | 21-Mar-25 A | 0
A46670 | Passive Fire Protection schedule_RCC |  |  | 22-Mar-25 A | 21-Jun-25 A | 0
A46680 | Passive Fire Protection schedule_IFA |  |  | 22-Jun-25 A | 18-Jul-25 A | 0
A46690 | Passive Fire Protection schedule_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46700 | Passive Fire Protection schedule_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Firewater Demand Report |  | 2025-09-23 | 2027-01-20 | 17-Jan-25 A | 2025-09-23 | 2
A47070 | Firewater Demand Report_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
A9080 | Firewater Demand Report_IFR |  |  | 17-Jan-25 A | 11-Mar-25 A | 0
A9090 | Firewater Demand Report_RCC |  |  | 12-Mar-25 A | 21-Jul-25 A | 0
A9100 | Firewater Demand Report_IFA |  |  | 22-Jul-25 A | 06-Sep-25 A | 0
A9110 | Firewater Demand Report_RCA |  |  | 07-Sep-25 A | 13-Sep-25 A | 0
HAZID ENVID OHID Closeout Report |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A47330 | HAZID ENVID OHID Closeout Report_IFR | 2025-09-26 | 2026-02-16 | 2025-09-19 | 2025-09-26 | 6
A47340 | HAZID ENVID OHID Closeout Report_RCC | 2025-10-20 | 2026-11-09 | 2025-09-26 | 2025-10-20 | 16
A47350 | HAZID ENVID OHID Closeout Report_IFA | 2025-10-23 | 2026-11-12 | 2025-10-20 | 2025-10-23 | 3
A47360 | HAZID ENVID OHID Closeout Report_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A47370 | HAZID ENVID OHID Closeout Report_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Escape Route and Safety Signs Layouts (Plant) |  | 2025-09-23 | 2027-01-20 | 16-Apr-25 A | 2025-09-23 | 2
A46410 | Escape Route and Safety Signs Layouts (Plant)_IFR |  |  | 16-Apr-25 A | 07-May-25 A | 0
A46420 | Escape Route and Safety Signs Layouts (Plant)_RCC |  |  | 08-May-25 A | 21-Jun-25 A | 0
A46430 | Escape Route and Safety Signs Layouts (Plant)_IFA |  |  | 22-Jun-25 A | 28-Jul-25 A | 0
A46440 | Escape Route and Safety Signs Layouts (Plant)_RCA |  |  | 29-Jul-25 A | 30-Aug-25 A | 0
A46450 | Escape Route and Safety Signs Layouts (Plant)_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Fire & Gas Detectors Layouts (Plant) |  | 2025-10-14 | 2027-01-20 | 06-Apr-25 A | 2025-10-14 | 18
A46510 | Fire & Gas Detectors Layouts (Plant)_IFR |  |  | 06-Apr-25 A | 27-Apr-25 A | 0
A46520 | Fire & Gas Detectors Layouts (Plant)_RCC |  |  | 28-Apr-25 A | 21-Jun-25 A | 0
A46530 | Fire & Gas Detectors Layouts (Plant)_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A46540 | Fire & Gas Detectors Layouts (Plant)_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46550 | Fire & Gas Detectors Layouts (Plant)_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Passive Fire Protection Layouts |  | 2025-10-14 | 2027-01-20 | 08-Apr-25 A | 2025-10-14 | 18
A46710 | Passive Fire Protection Layouts_IFR |  |  | 08-Apr-25 A | 29-Apr-25 A | 0
A46720 | Passive Fire Protection Layouts_RCC |  |  | 30-Apr-25 A | 21-Jun-25 A | 0
A46730 | Passive Fire Protection Layouts_IFA |  |  | 22-Jun-25 A | 29-Jul-25 A | 0
A46740 | Passive Fire Protection Layouts_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46750 | Passive Fire Protection Layouts_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
HAZOP Closeout Report |  | 2025-11-11 | 2026-02-25 | 22-Aug-25 A | 2025-11-11 | 37
A47430 | HAZOP Closeout Report_IFR | 2025-09-19 | 2026-01-05 | 22-Aug-25 A | 2025-09-19 | 0
A47440 | HAZOP Closeout Report_RCC | 2025-10-10 | 2026-01-27 | 2025-09-19 | 2025-10-10 | 16
A47450 | HAZOP Closeout Report_IFA | 2025-10-16 | 2026-01-30 | 2025-10-10 | 2025-10-16 | 3
A47460 | HAZOP Closeout Report_RCA | 2025-11-06 | 2026-02-23 | 2025-10-16 | 2025-11-06 | 16
A47470 | HAZOP Closeout Report_IFD/IFC | 2025-11-11 | 2026-02-25 | 2025-11-06 | 2025-11-11 | 2
Fire Protection and Safety Equipment Layouts (Plant) |  | 2025-09-23 | 2027-01-20 | 28-Mar-25 A | 2025-09-23 | 2
A46310 | Fire Protection and Safety Equipment Layouts (Plant)_IFR |  |  | 28-Mar-25 A | 21-Apr-25 A | 0
A46320 | Fire Protection and Safety Equipment Layouts (Plant)_RCC |  |  | 22-Apr-25 A | 21-Jun-25 A | 0
A46330 | Fire Protection and Safety Equipment Layouts (Plant)_IFA |  |  | 22-Jun-25 A | 28-Jul-25 A | 0
A46340 | Fire Protection and Safety Equipment Layouts (Plant)_RCA |  |  | 29-Jul-25 A | 30-Aug-25 A | 0
A46350 | Fire Protection and Safety Equipment Layouts (Plant)_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Firewater Hydraulic Report |  | 2025-11-11 | 2027-01-20 | 02-Jul-25 A | 2025-11-11 | 37
A47080 | Firewater Hydraulic Report_IFR |  |  | 02-Jul-25 A | 20-Jul-25 A | 0
A47090 | Firewater Hydraulic Report_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A47100 | Firewater Hydraulic Report_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A47110 | Firewater Hydraulic Report_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A47120 | Firewater Hydraulic Report_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Datasheets for Fire Protection and Safety Equipment |  | 2025-10-14 | 2026-01-14 | 17-Apr-25 A | 2025-10-14 | 18
A46860 | Datasheets for Fire Protection and Safety Equipment_IFR |  |  | 17-Apr-25 A | 08-May-25 A | 0
A46870 | Datasheets for Fire Protection and Safety Equipment_RCC |  |  | 09-May-25 A | 21-Jun-25 A | 0
A46880 | Datasheets for Fire Protection and Safety Equipment_IFA |  |  | 22-Jun-25 A | 17-Jul-25 A | 0
A46890 | Datasheets for Fire Protection and Safety Equipment_RCA | 2025-10-10 | 2026-01-12 | 2025-09-19 | 2025-10-10 | 16
A46900 | Datasheets for Fire Protection and Safety Equipment_IFD/IFC | 2025-10-14 | 2026-01-14 | 2025-10-10 | 2025-10-14 | 2
Fire Zone Layout |  |  |  | 02-Apr-25 A | 10-Sep-25 A | 0
A46260 | Fire Zone Layout_IFR |  |  | 02-Apr-25 A | 23-Apr-25 A | 0
A46270 | Fire Zone Layout_RCC |  |  | 24-Apr-25 A | 12-Aug-25 A | 0
A46280 | Fire Zone Layout_IFA |  |  | 13-Aug-25 A | 15-Aug-25 A | 0
A46290 | Fire Zone Layout_RCA |  |  | 16-Aug-25 A | 07-Sep-25 A | 0
A46300 | Fire Zone Layout_IFD/IFC |  |  | 08-Sep-25 A | 10-Sep-25 A | 0
Hazardous Area Classification Layouts |  | 2025-10-14 | 2027-01-20 | 06-Apr-25 A | 2025-10-14 | 18
A46210 | Hazardous Area Classification Layouts_IFR |  |  | 06-Apr-25 A | 27-Apr-25 A | 0
A46220 | Hazardous Area Classification Layouts_RCC |  |  | 28-Apr-25 A | 21-Jun-25 A | 0
A46230 | Hazardous Area Classification Layouts_IFA |  |  | 22-Jun-25 A | 29-Aug-25 A | 0
A46240 | Hazardous Area Classification Layouts_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46250 | Hazardous Area Classification Layouts_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
MR for Fire Protection and Safety Equipment |  | 2025-10-20 | 2026-01-16 | 22-Apr-25 A | 2025-10-20 | 21
A47180 | MR for Fire Protection and Safety Equipment_IFR |  |  | 22-Apr-25 A | 13-May-25 A | 0
A47190 | MR for Fire Protection and Safety Equipment_RCC |  |  | 14-May-25 A | 21-Jun-25 A | 0
A47200 | MR for Fire Protection and Safety Equipment_IFA | 2025-09-24 | 2025-12-23 | 2025-09-19 | 2025-09-24 | 3
A47210 | MR for Fire Protection and Safety Equipment_RCA | 2025-10-16 | 2026-01-14 | 2025-09-24 | 2025-10-16 | 16
A47220 | MR for Fire Protection and Safety Equipment_IFD/IFC | 2025-10-20 | 2026-01-16 | 2025-10-16 | 2025-10-20 | 2
Fire Water Layout |  | 2025-10-14 | 2027-01-20 | 17-Apr-25 A | 2025-10-14 | 18
A46910 | Fire Water Layout_IFR |  |  | 17-Apr-25 A | 08-May-25 A | 0
A46920 | Fire Water Layout_RCC |  |  | 09-May-25 A | 21-Jun-25 A | 0
A46930 | Fire Water Layout_IFA |  |  | 22-Jun-25 A | 31-Jul-25 A | 0
A46940 | Fire Water Layout_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A46950 | Fire Water Layout_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
P&ID - Firewater Network |  | 2025-11-11 | 2027-01-18 | 21-Feb-25 A | 2025-11-11 | 37
A46960 | P&ID - Firewater Network_IFR |  |  | 21-Feb-25 A | 14-Mar-25 A | 0
A46970 | P&ID - Firewater Network_RCC | 2025-10-10 | 2026-12-17 | 2025-09-19 | 2025-10-10 | 16
A46980 | P&ID - Firewater Network_IFA | 2025-10-16 | 2026-12-22 | 2025-10-10 | 2025-10-16 | 3
A46990 | P&ID - Firewater Network_RCA | 2025-11-06 | 2027-01-14 | 2025-10-16 | 2025-11-06 | 16
A47000 | P&ID - Firewater Network_IFD/IFC | 2025-11-11 | 2027-01-18 | 2025-11-06 | 2025-11-11 | 2
P&ID - Deluge Spray System |  | 2025-11-11 | 2026-06-24 | 19-Apr-25 A | 2025-11-11 | 37
A47010 | P&ID - Deluge Spray System_IFR |  |  | 19-Apr-25 A | 10-May-25 A | 0
A47020 | P&ID - Deluge Spray System_RCC | 2025-10-10 | 2026-05-26 | 2025-09-19 | 2025-10-10 | 16
A47030 | P&ID - Deluge Spray System_IFA | 2025-10-16 | 2026-05-29 | 2025-10-10 | 2025-10-16 | 3
A47040 | P&ID - Deluge Spray System_RCA | 2025-11-06 | 2026-06-22 | 2025-10-16 | 2025-11-06 | 16
A47050 | P&ID - Deluge Spray System_IFD/IFC | 2025-11-11 | 2026-06-24 | 2025-11-06 | 2025-11-11 | 2
P&ID - Clean Agent System |  | 2025-11-11 | 2026-06-24 | 21-Feb-25 A | 2025-11-11 | 37
A47060 | P&ID - Clean Agent System_IFR |  |  | 21-Feb-25 A | 14-Mar-25 A | 0
A9040 | P&ID - Clean Agent System_RCC | 2025-10-10 | 2026-05-26 | 2025-09-19 | 2025-10-10 | 16
A9050 | P&ID - Clean Agent System_IFA | 2025-10-16 | 2026-05-29 | 2025-10-10 | 2025-10-16 | 3
A9060 | P&ID - Clean Agent System_RCA | 2025-11-06 | 2026-06-22 | 2025-10-16 | 2025-11-06 | 16
A9070 | P&ID - Clean Agent System_IFD/IFC | 2025-11-11 | 2026-06-24 | 2025-11-06 | 2025-11-11 | 2
ISD Closeout Report |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A47380 | ISD Closeout Report_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A47390 | ISD Closeout Report_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A47400 | ISD Closeout Report_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A47410 | ISD Closeout Report_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A47420 | ISD Closeout Report_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
PHSER 3 Closeout Report |  | 2026-03-12 | 2027-01-20 | 2026-01-13 | 2026-03-12 | 43
A47480 | PHSER 3 Closeout Report_IFR | 2026-01-20 | 2026-11-23 | 2026-01-13 | 2026-01-20 | 6
A47490 | PHSER 3 Closeout Report_RCC | 2026-02-11 | 2026-12-22 | 2026-01-20 | 2026-02-11 | 16
A47500 | PHSER 3 Closeout Report_IFA | 2026-02-16 | 2026-12-25 | 2026-02-11 | 2026-02-16 | 3
A47510 | PHSER 3 Closeout Report_RCA | 2026-03-10 | 2027-01-18 | 2026-02-16 | 2026-03-10 | 16
A47520 | PHSER 3 Closeout Report_IFD/IFC | 2026-03-12 | 2027-01-20 | 2026-03-10 | 2026-03-12 | 2
HSE Action Tracking Register |  | 2026-03-20 | 2027-01-20 | 2026-01-20 | 2026-03-20 | 43
A47280 | HSE Action Tracking Register_IFR | 2026-01-28 | 2026-11-30 | 2026-01-20 | 2026-01-28 | 6
A47290 | HSE Action Tracking Register_RCC | 2026-02-19 | 2026-12-22 | 2026-01-28 | 2026-02-19 | 16
A47300 | HSE Action Tracking Register_IFA | 2026-02-24 | 2026-12-25 | 2026-02-19 | 2026-02-24 | 3
A47310 | HSE Action Tracking Register_RCA | 2026-03-18 | 2027-01-18 | 2026-02-24 | 2026-03-18 | 16
A47320 | HSE Action Tracking Register_IFD/IFC | 2026-03-20 | 2027-01-20 | 2026-03-18 | 2026-03-20 | 2
Electrical |  | 2026-02-11 | 2027-01-20 | 13-Dec-24 A | 2026-02-11 | 100
Scope Of Work For Cathodic Protection |  | 2025-10-20 | 2027-01-20 | 08-Aug-25 A | 2025-10-20 | 21
A10630 | Scope Of Work For Cathodic Protection_IFR |  |  | 08-Aug-25 A | 14-Aug-25 A | 0
A10640 | Scope Of Work For Cathodic Protection_RCC |  |  | 15-Aug-25 A | 19-Sep-25 A | 0
A10650 | Scope Of Work For Cathodic Protection_IFA | 2025-09-24 | 2025-12-12 | 19-Sep-25 A | 2025-09-24 | 3
A10660 | Scope Of Work For Cathodic Protection_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A10670 | Scope Of Work For Cathodic Protection_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Electrical System Operating Philosophy |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A47530 | Electrical System Operating Philosophy_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A47540 | Electrical System Operating Philosophy_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A47550 | Electrical System Operating Philosophy_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A47560 | Electrical System Operating Philosophy_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A47570 | Electrical System Operating Philosophy_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Technical Data Sheet For Transformer (Power and Distribution) |  |  |  | 23-Dec-24 A | 03-Jul-25 A | 0
A47580 | Technical Data Sheet For Transformer (Power and Distribution)_IFR |  |  | 23-Dec-24 A | 13-Jan-25 A | 0
A47590 | Technical Data Sheet For Transformer (Power and Distribution)_RCC |  |  | 14-Jan-25 A | 06-May-25 A | 0
A47600 | Technical Data Sheet For Transformer (Power and Distribution)_IFA |  |  | 07-May-25 A | 19-Jun-25 A | 0
A47610 | Technical Data Sheet For Transformer (Power and Distribution)_RCA |  |  | 20-Jun-25 A | 26-Jun-25 A | 0
A47620 | Technical Data Sheet For Transformer (Power and Distribution)_IFD/IFC |  |  | 27-Jun-25 A | 03-Jul-25 A | 0
Technical Data Sheet For LV Motors |  |  |  | 01-Jan-25 A | 03-May-25 A | 0
A47630 | Technical Data Sheet For LV Motors_IFR |  |  | 01-Jan-25 A | 22-Jan-25 A | 0
A9840 | Technical Data Sheet For LV Motors_RCC |  |  | 23-Jan-25 A | 28-Feb-25 A | 0
A9850 | Technical Data Sheet For LV Motors_IFA |  |  | 01-Mar-25 A | 19-Apr-25 A | 0
A9860 | Technical Data Sheet For LV Motors_RCA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A9870 | Technical Data Sheet For LV Motors_IFD/IFC |  |  | 27-Apr-25 A | 03-May-25 A | 0
Technical Data Sheet For Emergency Diesel Generator |  |  |  | 09-Jan-25 A | 10-Sep-25 A | 0
A9880 | Technical Data Sheet For Emergency Diesel Generator_IFR |  |  | 09-Jan-25 A | 02-Mar-25 A | 0
A9890 | Technical Data Sheet For Emergency Diesel Generator_RCC |  |  | 03-Mar-25 A | 02-May-25 A | 0
A9900 | Technical Data Sheet For Emergency Diesel Generator_IFA |  |  | 03-May-25 A | 16-May-25 A | 0
A9910 | Technical Data Sheet For Emergency Diesel Generator_RCA |  |  | 19-Aug-25 A | 08-Sep-25 A | 0
A9920 | Technical Data Sheet For Emergency Diesel Generator_IFD/IFC |  |  | 09-Sep-25 A | 10-Sep-25 A | 0
Technical Data Sheet For Intergrated Protection Control Panel |  |  |  | 01-May-25 A | 06-Jun-25 A | 0
A58390 | Technical Data Sheet For IPCS_IFR |  |  | 01-May-25 A | 05-May-25 A | 0
A58400 | Technical Data Sheet For IPCS_RCC |  |  | 06-May-25 A | 16-May-25 A | 0
A58410 | Technical Data Sheet For IPCS_IFA |  |  | 19-May-25 A | 23-May-25 A | 0
A58420 | Technical Data Sheet For IPCS_RCA |  |  | 26-May-25 A | 30-May-25 A | 0
A58430 | Technical Data Sheet For IPCS_IFD/IFC |  |  | 02-Jun-25 A | 06-Jun-25 A | 0
Technical Data Sheet For SCMS |  |  |  | 05-May-25 A | 13-Jun-25 A | 0
A59900 | Technical Data Sheet For SCMS_IFR |  |  | 05-May-25 A | 09-May-25 A | 0
A59910 | Technical Data Sheet For SCMS_RCC |  |  | 12-May-25 A | 23-May-25 A | 0
A59920 | Technical Data Sheet For SCMS_IFA |  |  | 26-May-25 A | 30-May-25 A | 0
A59930 | Technical Data Sheet For SCMS_RCA |  |  | 02-Jun-25 A | 06-Jun-25 A | 0
A59940 | Technical Data Sheet For SCMS_IFD/IFC |  |  | 09-Jun-25 A | 13-Jun-25 A | 0
Technical Data Sheet For 11KV Switchgear |  |  |  | 19-Dec-24 A | 21-Jun-25 A | 0
A47640 | Technical Data Sheet For 11KV Switchgear_IFA |  |  | 15-Feb-25 A | 21-Mar-25 A | 0
A9930 | Technical Data Sheet For 11KV Switchgear_IFR |  |  | 19-Dec-24 A | 09-Jan-25 A | 0
A9940 | Technical Data Sheet For 11KV Switchgear_RCC |  |  | 10-Jan-25 A | 14-Feb-25 A | 0
A9960 | Technical Data Sheet For 11KV Switchgear_RCA |  |  | 22-Mar-25 A | 02-Jun-25 A | 0
A9970 | Technical Data Sheet For 11KV Switchgear_IFD/IFC |  |  | 03-Jun-25 A | 21-Jun-25 A | 0
Technical Data Sheet For LV Switchgear |  |  |  | 27-Dec-24 A | 11-May-25 A | 0
A10000 | Technical Data Sheet For LV Switchgear_IFA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A10010 | Technical Data Sheet For LV Switchgear_RCA |  |  | 28-Apr-25 A | 04-May-25 A | 0
A10020 | Technical Data Sheet For LV Switchgear_IFD/IFC |  |  | 06-May-25 A | 11-May-25 A | 0
A9980 | Technical Data Sheet For LV Switchgear_IFR |  |  | 27-Dec-24 A | 17-Jan-25 A | 0
A9990 | Technical Data Sheet For LV Switchgear_RCC |  |  | 18-Jan-25 A | 20-Apr-25 A | 0
Technical Data Sheet For LV Variable Frequency Drive |  |  |  | 31-Jan-25 A | 05-Jul-25 A | 0
A10030 | Technical Data Sheet For LV Variable Frequency Drive_IFR |  |  | 31-Jan-25 A | 21-Feb-25 A | 0
A10040 | Technical Data Sheet For LV Variable Frequency Drive_RCC |  |  | 22-Feb-25 A | 20-Apr-25 A | 0
A10050 | Technical Data Sheet For LV Variable Frequency Drive_IFA |  |  | 21-Apr-25 A | 21-Jun-25 A | 0
A10060 | Technical Data Sheet For LV Variable Frequency Drive_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A10070 | Technical Data Sheet For LV Variable Frequency Drive_IFD/IFC |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
Technical Data Sheet For Neutral Earthing Resistor |  |  |  | 19-Dec-24 A | 21-Jun-25 A | 0
A10080 | Technical Data Sheet For Neutral Earthing Resistor_IFR |  |  | 19-Dec-24 A | 09-Jan-25 A | 0
A10090 | Technical Data Sheet For Neutral Earthing Resistor_RCC |  |  | 10-Jan-25 A | 21-Feb-25 A | 0
A10100 | Technical Data Sheet For Neutral Earthing Resistor_IFA |  |  | 22-Feb-25 A | 06-Mar-25 A | 0
A10110 | Technical Data Sheet For Neutral Earthing Resistor_RCA |  |  | 07-Mar-25 A | 29-May-25 A | 0
A10120 | Technical Data Sheet For Neutral Earthing Resistor_IFD/IFC |  |  | 30-May-25 A | 21-Jun-25 A | 0
Technical Data Sheet For Interposting Relay Panel |  |  |  | 01-Aug-25 A | 17-Sep-25 A | 0
A58240 | Technical Data Sheet For Interpopsting Relay Panel _IFR |  |  | 01-Aug-25 A | 08-Aug-25 A | 0
A58250 | Technical Data Sheet For Interpopsting Relay Panel_RCC |  |  | 11-Aug-25 A | 22-Aug-25 A | 0
A58260 | Technical Data Sheet For Interpopsting Relay Panel_IFA |  |  | 25-Aug-25 A | 29-Aug-25 A | 0
A58270 | Technical Data Sheet For Interpopsting Relay Panel_RCA |  |  | 01-Sep-25 A | 12-Sep-25 A | 0
A58280 | Technical Data Sheet For Interpopsting Relay Panel_IFD/IFC |  |  | 15-Sep-25 A | 17-Sep-25 A | 0
Technical Data Sheet For Power, Control And Earthing Cables |  |  |  | 10-Jan-25 A | 05-Sep-25 A | 0
A10130 | Technical Data Sheet For Power, Control And Earthing Cables_IFR |  |  | 10-Jan-25 A | 20-Apr-25 A | 0
A10140 | Technical Data Sheet For Power, Control And Earthing Cables_RCC |  |  | 21-Apr-25 A | 19-May-25 A | 0
A10150 | Technical Data Sheet For Power, Control And Earthing Cables_IFA |  |  | 20-May-25 A | 11-Jun-25 A | 0
A10160 | Technical Data Sheet For Power, Control And Earthing Cables_RCA |  |  | 25-Aug-25 A | 29-Aug-25 A | 0
A10170 | Technical Data Sheet For Power, Control And Earthing Cables_IFD/IFC |  |  | 01-Sep-25 A | 05-Sep-25 A | 0
Technical Data Sheet For Direct Current UPS System |  |  |  | 01-Jan-25 A | 21-Jun-25 A | 0
A10180 | Technical Data Sheet For Direct Current UPS System_IFR |  |  | 01-Jan-25 A | 22-Jan-25 A | 0
A10190 | Technical Data Sheet For Direct Current UPS System_RCC |  |  | 23-Jan-25 A | 07-Mar-25 A | 0
A10200 | Technical Data Sheet For Direct Current UPS System_IFA |  |  | 08-Mar-25 A | 21-Mar-25 A | 0
A10210 | Technical Data Sheet For Direct Current UPS System_RCA |  |  | 22-Mar-25 A | 02-Jun-25 A | 0
A10220 | Technical Data Sheet For Direct Current UPS System_IFD/IFC |  |  | 03-Jun-25 A | 21-Jun-25 A | 0
Technical Data Sheet For Static AC UPS System |  |  |  | 27-Dec-24 A | 28-Jun-25 A | 0
A10230 | Technical Data Sheet For Static AC UPS System_IFR |  |  | 27-Dec-24 A | 17-Jan-25 A | 0
A10240 | Technical Data Sheet For Static AC UPS System_RCC |  |  | 18-Jan-25 A | 18-Feb-25 A | 0
A10250 | Technical Data Sheet For Static AC UPS System_IFA |  |  | 19-Feb-25 A | 12-Jun-25 A | 0
A10260 | Technical Data Sheet For Static AC UPS System_RCA |  |  | 13-Jun-25 A | 21-Jun-25 A | 0
A10270 | Technical Data Sheet For Static AC UPS System_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Technical Data Sheet For Power Factor Correction Capacitor |  |  |  | 20-Jan-25 A | 28-Aug-25 A | 0
A10280 | Technical Data Sheet For Power Factor Correction Capacitor_IFR |  |  | 20-Jan-25 A | 21-Feb-25 A | 0
A10290 | Technical Data Sheet For Power Factor Correction Capacitor_RCC |  |  | 19-Jul-25 A | 08-Aug-25 A | 0
A10300 | Technical Data Sheet For Power Factor Correction Capacitor_IFA |  |  | 09-Aug-25 A | 12-Aug-25 A | 0
A10310 | Technical Data Sheet For Power Factor Correction Capacitor_RCA |  |  | 12-Aug-25 A | 26-Aug-25 A | 0
A10320 | Technical Data Sheet For Power Factor Correction Capacitor_IFD/IFC |  |  | 26-Aug-25 A | 28-Aug-25 A | 0
Neutral Earthing Resistor Sizing Calculation |  |  |  | 13-Dec-24 A | 13-May-25 A | 0
A10380 | Neutral Earthing Resistor Sizing Calculation_IFR |  |  | 13-Dec-24 A | 09-Jan-25 A | 0
A10390 | Neutral Earthing Resistor Sizing Calculation_RCC |  |  | 10-Jan-25 A | 21-Feb-25 A | 0
A10400 | Neutral Earthing Resistor Sizing Calculation_IFA |  |  | 22-Feb-25 A | 12-Mar-25 A | 0
A10410 | Neutral Earthing Resistor Sizing Calculation_RCA |  |  | 13-Mar-25 A | 06-May-25 A | 0
A10420 | Neutral Earthing Resistor Sizing Calculation_IFD/IFC |  |  | 07-May-25 A | 13-May-25 A | 0
Interposting Relay Panel Sizing Calculation |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A58290 | Interpopsting Relay Panel Sizing Calculation_IFR | 2025-09-26 | 2025-12-11 | 2025-09-19 | 2025-09-26 | 6
A58300 | Interpopsting Relay Panel Sizing Calculation_RCC | 2025-10-20 | 2026-01-02 | 2025-09-26 | 2025-10-20 | 16
A58310 | Interpopsting Relay Panel Sizing Calculation_IFA | 2025-10-23 | 2026-01-07 | 2025-10-20 | 2025-10-23 | 3
A58320 | Interpopsting Relay Panel Sizing Calculation_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A58330 | Interpopsting Relay Panel Sizing Calculation_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Transformer Sizing Calculation |  |  |  | 19-Dec-24 A | 28-Jun-25 A | 0
A10680 | Transformer Sizing Calculation_IFR |  |  | 19-Dec-24 A | 09-Jan-25 A | 0
A10690 | Transformer Sizing Calculation_RCC |  |  | 10-Jan-25 A | 18-Feb-25 A | 0
A10700 | Transformer Sizing Calculation_IFA |  |  | 19-Feb-25 A | 20-Apr-25 A | 0
A10710 | Transformer Sizing Calculation_RCA |  |  | 21-Apr-25 A | 21-Jun-25 A | 0
A10720 | Transformer Sizing Calculation_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Electrical Load List - EU3 H2 Extraction Unit |  |  |  | 19-Dec-24 A | 30-Apr-25 A | 0
A10330 | Electrical Load List - EU3 H2 Extraction Unit_IFR |  |  | 19-Dec-24 A | 09-Jan-25 A | 0
A10340 | Electrical Load List - EU3 H2 Extraction Unit_RCC |  |  | 10-Jan-25 A | 18-Feb-25 A | 0
A10350 | Electrical Load List - EU3 H2 Extraction Unit_IFA |  |  | 25-Feb-25 A | 13-Mar-25 A | 0
A10360 | Electrical Load List - EU3 H2 Extraction Unit_RCA |  |  | 14-Mar-25 A | 29-Apr-25 A | 0
A10370 | Electrical Load List - EU3 H2 Extraction Unit_IFD/IFC |  |  | 30-Apr-25 A | 30-Apr-25 A | 0
Electrical Load Summary for Utilities & Offsites Area |  | 2025-11-11 | 2026-03-05 | 14-Feb-25 A | 2025-11-11 | 37
A28320 | Electrical Load Summary for Utilities & Offsites Area_IFD/IFC | 2025-11-11 | 2026-03-05 | 2025-11-06 | 2025-11-11 | 2
A55790 | Electrical Load Summary for Utilities & Offsites Area_IFR |  |  | 14-Feb-25 A | 20-Mar-25 A | 0
A55800 | Electrical Load Summary for Utilities & Offsites Area_RCC | 2025-10-10 | 2026-02-03 | 2025-09-19 | 2025-10-10 | 16
A55810 | Electrical Load Summary for Utilities & Offsites Area_IFA | 2025-10-16 | 2026-02-09 | 2025-10-10 | 2025-10-16 | 3
A55820 | Electrical Load Summary for Utilities & Offsites Area_RCA | 2025-11-06 | 2026-03-02 | 2025-10-16 | 2025-11-06 | 16
AC UPS Sizing Calculation |  | 2025-10-20 | 2027-01-20 | 26-Dec-24 A | 2025-10-20 | 21
A10930 | AC UPS Sizing Calculation_IFR |  |  | 26-Dec-24 A | 16-Jan-25 A | 0
A10940 | AC UPS Sizing Calculation_RCC |  |  | 17-Jan-25 A | 11-Feb-25 A | 0
A10950 | AC UPS Sizing Calculation_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A10960 | AC UPS Sizing Calculation_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A10970 | AC UPS Sizing Calculation_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
DC UPS Sizing Calculation |  | 2025-09-23 | 2027-01-20 | 27-Dec-24 A | 2025-09-23 | 2
A10980 | DC UPS Sizing Calculation_IFR |  |  | 27-Dec-24 A | 17-Jan-25 A | 0
A10990 | DC UPS Sizing Calculation_RCC |  |  | 18-Jan-25 A | 20-Apr-25 A | 0
A11000 | DC UPS Sizing Calculation_IFA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A11010 | DC UPS Sizing Calculation_RCA |  |  | 28-Apr-25 A | 21-Jun-25 A | 0
A11020 | DC UPS Sizing Calculation_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
EDG Sizing Calculation |  |  |  | 19-Dec-24 A | 28-Jun-25 A | 0
A11030 | EDG Sizing Calculation_IFR |  |  | 19-Dec-24 A | 09-Jan-25 A | 0
A11040 | EDG Sizing Calculation_RCC |  |  | 10-Jan-25 A | 20-Feb-25 A | 0
A11050 | EDG Sizing Calculation_IFA |  |  | 21-Feb-25 A | 20-Apr-25 A | 0
A11060 | EDG Sizing Calculation_RCA |  |  | 21-Apr-25 A | 21-Jun-25 A | 0
A11070 | EDG Sizing Calculation_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
IO List For IPCS |  |  |  | 28-Jan-25 A | 18-Sep-25 A | 0
A11080 | IO List For IPCS_IFR |  |  | 28-Jan-25 A | 18-Feb-25 A | 0
A11090 | IO List For IPCS_RCC |  |  | 19-Feb-25 A | 25-Feb-25 A | 0
A11100 | IO List For IPCS_IFA |  |  | 26-Feb-25 A | 20-Apr-25 A | 0
A11110 | IO List For IPCS_RCA |  |  | 21-Apr-25 A | 21-Jun-25 A | 0
A11120 | IO List For IPCS_IFD/IFC |  |  | 22-Jun-25 A | 18-Sep-25 A | 0
IO List For SCMS |  | 2025-09-23 | 2027-01-20 | 24-Jan-25 A | 2025-09-23 | 2
A11130 | IO List For SCMS_IFR |  |  | 24-Jan-25 A | 24-Feb-25 A | 0
A11140 | IO List For SCMS_RCC |  |  | 25-Feb-25 A | 20-Apr-25 A | 0
A11150 | IO List For SCMS_IFA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A11160 | IO List For SCMS_RCA |  |  | 21-Apr-25 A | 21-Jun-25 A | 0
A11170 | IO List For SCMS_IFD/IFC | 2025-09-23 | 2027-01-20 | 22-Jun-25 A | 2025-09-23 | 2
Power System Study Report - ARC Flash, Harmonics Resonance |  | 2025-11-11 | 2027-01-20 | 18-Jul-25 A | 2025-11-11 | 37
A11230 | Power System Study Report - ARC Flash, Harmonics Resonance_IFR |  |  | 18-Jul-25 A | 11-Aug-25 A | 0
A11240 | Power System Study Report - ARC Flash, Harmonics Resonance_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A11250 | Power System Study Report - ARC Flash, Harmonics Resonance_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A11260 | Power System Study Report - ARC Flash, Harmonics Resonance_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A11270 | Power System Study Report - ARC Flash, Harmonics Resonance_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Power System Study Report - Load Flow, Short Circuit and Motor Starting |  | 2025-11-11 | 2027-01-20 | 28-Apr-25 A | 2025-11-11 | 37
A11180 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFR |  |  | 28-Apr-25 A | 19-May-25 A | 0
A11190 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A11200 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A11210 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A11220 | Power System Study Report - Load Flow, Short Circuit and Motor Starting_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
PSCAD Study Report - Transient Stability And Insulation Coordination |  | 2025-11-11 | 2027-01-20 | 01-May-25 A | 2025-11-11 | 37
A11280 | Pscad Study Report - Transient Stability And Insulation Coordination_IFR |  |  | 01-May-25 A | 22-May-25 A | 0
A11290 | Pscad Study Report - Transient Stability And Insulation Coordination_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A11300 | Pscad Study Report - Transient Stability And Insulation Coordination_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A11310 | Pscad Study Report - Transient Stability And Insulation Coordination_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A11320 | Pscad Study Report - Transient Stability And Insulation Coordination_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Power System Study Report - Protection Coordination and Relay Setting |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A11330 | Power System Study Report - Protection Coordination and Relay Setting_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A11340 | Power System Study Report - Protection Coordination and Relay Setting_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A11350 | Power System Study Report - Protection Coordination and Relay Setting_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A11360 | Power System Study Report - Protection Coordination and Relay Setting_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A11370 | Power System Study Report - Protection Coordination and Relay Setting_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Material Requisition For Transformer (Power And Distribution) |  |  |  | 19-Dec-24 A | 28-Jun-25 A | 0
A12430 | Material Requisition For Transformer (Power And Distribution)_IFR |  |  | 19-Dec-24 A | 09-Jan-25 A | 0
A12440 | Material Requisition For Transformer (Power And Distribution)_RCC |  |  | 10-Jan-25 A | 18-Feb-25 A | 0
A12450 | Material Requisition For Transformer (Power And Distribution)_IFA |  |  | 19-Feb-25 A | 21-Mar-25 A | 0
A12460 | Material Requisition For Transformer (Power And Distribution)_RCA |  |  | 22-Mar-25 A | 21-Jun-25 A | 0
A12470 | Material Requisition For Transformer (Power And Distribution)_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Material Requisition For 11KV Switchgear |  |  |  | 13-Feb-25 A | 12-May-25 A | 0
A12480 | Material Requisition For 11KV Switchgear_IFR |  |  | 13-Feb-25 A | 06-Mar-25 A | 0
A12490 | Material Requisition For 11KV Switchgear_RCC |  |  | 07-Mar-25 A | 21-Apr-25 A | 0
A12500 | Material Requisition For 11KV Switchgear_IFA |  |  | 22-Apr-25 A | 28-Apr-25 A | 0
A12510 | Material Requisition For 11KV Switchgear_RCA |  |  | 29-Apr-25 A | 05-May-25 A | 0
A12520 | Material Requisition For 11KV Switchgear_IFD/IFC |  |  | 06-May-25 A | 12-May-25 A | 0
Material Requisition For LV Switchgear |  |  |  | 20-Jan-25 A | 11-Jul-25 A | 0
A12530 | Material Requisition For LV Switchgear_IFR |  |  | 20-Jan-25 A | 28-Feb-25 A | 0
A12540 | Material Requisition For LV Switchgear_RCC |  |  | 01-Mar-25 A | 06-May-25 A | 0
A12550 | Material Requisition For LV Switchgear_IFA |  |  | 07-May-25 A | 21-Jun-25 A | 0
A12560 | Material Requisition For LV Switchgear_RCA |  |  | 23-Jun-25 A | 04-Jul-25 A | 0
A12570 | Material Requisition For LV Switchgear_IFD/IFC |  |  | 07-Jul-25 A | 11-Jul-25 A | 0
Material Requisition For Capacitor Bank |  |  |  | 03-Mar-25 A | 04-Sep-25 A | 0
A12580 | Material Requisition For Capacitor Bank_IFR |  |  | 03-Mar-25 A | 27-Apr-25 A | 0
A12590 | Material Requisition For Capacitor Bank_RCC |  |  | 28-Apr-25 A | 04-May-25 A | 0
A12600 | Material Requisition For Capacitor Bank_IFA |  |  | 05-May-25 A | 21-Jun-25 A | 0
A12610 | Material Requisition For Capacitor Bank_RCA |  |  | 22-Jun-25 A | 28-Aug-25 A | 0
A12620 | Material Requisition For Capacitor Bank_IFD/IFC |  |  | 29-Aug-25 A | 04-Sep-25 A | 0
Material Requisition For Power, Control And Earthing Cables |  |  |  | 22-Apr-25 A | 19-Sep-25 A | 0
A12630 | Material Requisition For Power, Control And Earthing Cables_IFR |  |  | 22-Apr-25 A | 13-May-25 A | 0
A12640 | Material Requisition For Power, Control And Earthing Cables_RCC |  |  | 25-Aug-25 A | 05-Sep-25 A | 0
A12650 | Material Requisition For Power, Control And Earthing Cables_IFA |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
A12660 | Material Requisition For Power, Control And Earthing Cables_RCA |  |  | 15-Sep-25 A | 19-Sep-25 A | 0
A12670 | Material Requisition For Power, Control And Earthing Cables_IFD/IFC |  |  | 15-Sep-25 A | 19-Sep-25 A | 0
Material Requisition For Emergency Diesel Generator |  |  |  | 01-Jan-25 A | 28-Jun-25 A | 0
A12680 | Material Requisition For Emergency Diesel Generator_IFR |  |  | 01-Jan-25 A | 22-Jan-25 A | 0
A12690 | Material Requisition For Emergency Diesel Generator_RCC |  |  | 23-Jan-25 A | 07-Mar-25 A | 0
A12700 | Material Requisition For Emergency Diesel Generator_IFA |  |  | 08-Mar-25 A | 20-Apr-25 A | 0
A12710 | Material Requisition For Emergency Diesel Generator_RCA |  |  | 21-Apr-25 A | 21-Jun-25 A | 0
A12720 | Material Requisition For Emergency Diesel Generator_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Material Requisition For AC UPS |  |  |  | 01-Jan-25 A | 30-Apr-25 A | 0
A12730 | Material Requisition For AC UPS_IFR |  |  | 01-Jan-25 A | 22-Jan-25 A | 0
A12740 | Material Requisition For AC UPS_RCC |  |  | 25-Feb-25 A | 07-Mar-25 A | 0
A12750 | Material Requisition For AC UPS_IFA |  |  | 10-Mar-25 A | 21-Mar-25 A | 0
A12760 | Material Requisition For AC UPS_RCA |  |  | 24-Mar-25 A | 04-Apr-25 A | 0
A12770 | Material Requisition For AC UPS_IFD/IFC |  |  | 07-Apr-25 A | 30-Apr-25 A | 0
Material Requisition For DC UPS |  |  |  | 31-Jan-25 A | 28-Jun-25 A | 0
A12780 | Material Requisition For DC UPS_IFR |  |  | 31-Jan-25 A | 21-Feb-25 A | 0
A12790 | Material Requisition For DC UPS_RCC |  |  | 21-Feb-25 A | 14-Mar-25 A | 0
A12800 | Material Requisition For DC UPS_IFA |  |  | 13-Mar-25 A | 21-Mar-25 A | 0
A12810 | Material Requisition For DC UPS_RCA |  |  | 22-Mar-25 A | 21-Jun-25 A | 0
A12820 | Material Requisition For DC UPS_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Material Requisition For LV Variable Frequency Drive |  |  |  | 31-Jan-25 A | 12-Jul-25 A | 0
A12830 | Material Requisition For LV Variable Frequency Drive_IFR |  |  | 31-Jan-25 A | 21-Feb-25 A | 0
A12840 | Material Requisition For LV Variable Frequency Drive_RCC |  |  | 22-Feb-25 A | 21-Jun-25 A | 0
A12850 | Material Requisition For LV Variable Frequency Drive_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A12860 | Material Requisition For LV Variable Frequency Drive_RCA |  |  | 27-Jun-25 A | 05-Jul-25 A | 0
A12870 | Material Requisition For LV Variable Frequency Drive_IFD/IFC |  |  | 06-Jul-25 A | 12-Jul-25 A | 0
Material Requisition For Neutral Grounding Resistor |  |  |  | 13-Dec-24 A | 08-May-25 A | 0
A12880 | Material Requisition For Neutral Grounding Resistor_IFR |  |  | 13-Dec-24 A | 17-Jan-25 A | 0
A12890 | Material Requisition For Neutral Grounding Resistor_RCC |  |  | 08-Jan-25 A | 10-Feb-25 A | 0
A12900 | Material Requisition For Neutral Grounding Resistor_IFA |  |  | 11-Feb-25 A | 14-Mar-25 A | 0
A12910 | Material Requisition For Neutral Grounding Resistor_RCA |  |  | 15-Mar-25 A | 06-May-25 A | 0
A12920 | Material Requisition For Neutral Grounding Resistor_IFD/IFC |  |  | 07-May-25 A | 08-May-25 A | 0
Material Requisition For Interposting Relay Panel |  | 2025-11-24 | 2026-02-05 | 01-Sep-25 A | 2025-11-24 | 46
A58340 | Material Requisition For Interpopsting Relay Panel_IFR |  |  | 01-Sep-25 A | 05-Sep-25 A | 0
A58350 | Material Requisition For Interpopsting Relay Panel_RCC | 2025-10-10 | 2026-01-07 | 2025-09-19 | 2025-10-10 | 16
A58360 | Material Requisition For Interpopsting Relay Panel_IFA | 2025-10-29 | 2026-01-12 | 2025-10-23 | 2025-10-29 | 3
A58370 | Material Requisition For Interpopsting Relay Panel_RCA | 2025-11-19 | 2026-02-03 | 2025-10-29 | 2025-11-19 | 16
A58380 | Material Requisition For Interpopsting Relay Panel_IFD/IFC | 2025-11-24 | 2026-02-05 | 2025-11-19 | 2025-11-24 | 2
Material Requisition For Integrated Protection Control Panel |  |  |  | 19-Jul-25 A | 04-Sep-25 A | 0
A58140 | Material Requisition For IPCS_IFR |  |  | 19-Jul-25 A | 25-Jul-25 A | 0
A58150 | Material Requisition For IPCS_RCC |  |  | 26-Jul-25 A | 14-Aug-25 A | 0
A58160 | Material Requisition For IPCS_IFA |  |  | 14-Aug-25 A | 17-Aug-25 A | 0
A58170 | Material Requisition For IPCS_RCA |  |  | 17-Aug-25 A | 30-Aug-25 A | 0
A58180 | Material Requisition For IPCS_IFD/IFC |  |  | 30-Aug-25 A | 04-Sep-25 A | 0
Material Requisition For SCMS |  |  |  | 19-Jul-25 A | 04-Sep-25 A | 0
A59950 | Material Requisition For SCMS_IFR |  |  | 19-Jul-25 A | 25-Jul-25 A | 0
A59960 | Material Requisition For SCMS_RCC |  |  | 26-Jul-25 A | 14-Aug-25 A | 0
A59970 | Material Requisition For SCMS_IFA |  |  | 14-Aug-25 A | 17-Aug-25 A | 0
A59980 | Material Requisition For SCMS_RCA |  |  | 17-Aug-25 A | 30-Aug-25 A | 0
A59990 | Material Requisition For SCMS_IFD/IFC |  |  | 30-Aug-25 A | 04-Sep-25 A | 0
Key Single Line Diagram - Hydrogen Extraction Unit |  | 2025-10-14 | 2027-01-20 | 03-Jan-25 A | 2025-10-14 | 18
A11380 | Key Single Line Diagram - Hydrogen Extraction Unit_IFR |  |  | 03-Jan-25 A | 24-Jan-25 A | 0
A11390 | Key Single Line Diagram - Hydrogen Extraction Unit_RCC |  |  | 25-Jan-25 A | 06-May-25 A | 0
A11400 | Key Single Line Diagram - Hydrogen Extraction Unit_IFA |  |  | 07-May-25 A | 21-Jun-25 A | 0
A11410 | Key Single Line Diagram - Hydrogen Extraction Unit_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A11420 | Key Single Line Diagram - Hydrogen Extraction Unit_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Single Line Diagram For Integrated Protection Control Panel |  | 2025-11-11 | 2026-03-05 | 19-Aug-25 A | 2025-11-11 | 37
A58440 | Single Line Diagram For IPCS_IFR |  |  | 19-Aug-25 A | 25-Aug-25 A | 0
A58450 | Single Line Diagram For IPCS_RCC | 2025-10-10 | 2026-02-03 | 2025-09-19 | 2025-10-10 | 16
A58460 | Single Line Diagram For IPCS_IFA | 2025-10-16 | 2026-02-09 | 2025-10-10 | 2025-10-16 | 3
A58470 | Single Line Diagram For IPCS_RCA | 2025-11-06 | 2026-03-02 | 2025-10-16 | 2025-11-06 | 16
A58480 | Single Line Diagram For IPCS_IFD/IFC | 2025-11-11 | 2026-03-05 | 2025-11-06 | 2025-11-11 | 2
Single Line Diagram For SCMS |  | 2025-11-11 | 2026-03-05 | 19-Aug-25 A | 2025-11-11 | 37
A60000 | Single Line Diagram For SCMS_IFR |  |  | 19-Aug-25 A | 25-Aug-25 A | 0
A60010 | Single Line Diagram For SCMS_RCC | 2025-10-10 | 2026-02-03 | 2025-09-19 | 2025-10-10 | 16
A60020 | Single Line Diagram For SCMS_IFA | 2025-10-16 | 2026-02-09 | 2025-10-10 | 2025-10-16 | 3
A60030 | Single Line Diagram For SCMS_RCA | 2025-11-06 | 2026-03-02 | 2025-10-16 | 2025-11-06 | 16
A60040 | Single Line Diagram For SCMS_IFD/IFC | 2025-11-11 | 2026-03-05 | 2025-11-06 | 2025-11-11 | 2
Single Line Diagram For 11KV Switchgear |  |  |  | 31-Jan-25 A | 23-Aug-25 A | 0
A11530 | Single Line Diagram For 11KV Switchgear_IFR |  |  | 31-Jan-25 A | 21-Feb-25 A | 0
A11540 | Single Line Diagram For 11KV Switchgear_RCC |  |  | 22-Feb-25 A | 20-Apr-25 A | 0
A11550 | Single Line Diagram For 11KV Switchgear_IFA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A11560 | Single Line Diagram For 11KV Switchgear_RCA |  |  | 28-Apr-25 A | 21-Jun-25 A | 0
A11570 | Single Line Diagram For 11KV Switchgear_IFD/IFC |  |  | 22-Jun-25 A | 23-Aug-25 A | 0
Single Line Diagram For AC UPS |  | 2025-10-14 | 2026-03-02 | 26-Aug-25 A | 2025-10-14 | 18
A11580 | Single Line Diagram For AC UPS_IFR |  |  | 26-Aug-25 A | 02-Sep-25 A | 0
A11590 | Single Line Diagram For AC UPS_RCC |  |  | 02-Sep-25 A | 05-Sep-25 A | 0
A11600 | Single Line Diagram For AC UPS_IFA |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
A11610 | Single Line Diagram For AC UPS_RCA | 2025-10-10 | 2026-02-26 | 2025-09-19 | 2025-10-10 | 16
A11620 | Single Line Diagram For AC UPS_IFD/IFC | 2025-10-14 | 2026-03-02 | 2025-10-10 | 2025-10-14 | 2
Single Line Diagram For DC UPS |  | 2025-10-17 | 2026-03-05 | 03-Feb-25 A | 2025-10-17 | 2
A11630 | Single Line Diagram For DC UPS_IFR |  |  | 03-Feb-25 A | 24-Feb-25 A | 0
A11640 | Single Line Diagram For DC UPS_RCC |  |  | 25-Feb-25 A | 18-Mar-25 A | 0
A11650 | Single Line Diagram For DC UPS_IFA |  |  | 19-Mar-25 A | 29-Apr-25 A | 0
A11660 | Single Line Diagram For DC UPS_RCA |  |  | 30-Apr-25 A | 02-Jun-25 A | 0
A11670 | Single Line Diagram For DC UPS_IFD/IFC | 2025-10-17 | 2026-03-05 | 2025-10-15 | 2025-10-17 | 2
Single Line Diagram For LV Switchgear |  | 2025-10-15 | 2026-03-05 | 20-Jan-25 A | 2025-10-15 | 18
A11680 | Single Line Diagram For LV Switchgear_IFR |  |  | 20-Jan-25 A | 21-Feb-25 A | 0
A11690 | Single Line Diagram For LV Switchgear_RCC |  |  | 22-Feb-25 A | 06-May-25 A | 0
A11700 | Single Line Diagram For LV Switchgear_IFA |  |  | 07-May-25 A | 21-Jun-25 A | 0
A11710 | Single Line Diagram For LV Switchgear_RCA | 2025-10-10 | 2026-03-02 | 2025-09-19 | 2025-10-10 | 16
A11720 | Single Line Diagram For LV Switchgear_IFD/IFC | 2025-10-15 | 2026-03-05 | 2025-10-10 | 2025-10-15 | 2
Single Line Diagram For Lighting And Small Power |  | 2025-11-18 | 2026-03-05 | 2025-09-19 | 2025-11-18 | 43
A11730 | Single Line Diagram For Lighting And Small Power_IFR | 2025-09-26 | 2026-01-13 | 2025-09-19 | 2025-09-26 | 6
A11740 | Single Line Diagram For Lighting And Small Power_RCC | 2025-10-20 | 2026-02-03 | 2025-09-26 | 2025-10-20 | 16
A11750 | Single Line Diagram For Lighting And Small Power_IFA | 2025-10-23 | 2026-02-09 | 2025-10-20 | 2025-10-23 | 3
A11760 | Single Line Diagram For Lighting And Small Power_RCA | 2025-11-14 | 2026-03-02 | 2025-10-23 | 2025-11-14 | 16
A11770 | Single Line Diagram For Lighting And Small Power_IFD/IFC | 2025-11-18 | 2026-03-05 | 2025-11-14 | 2025-11-18 | 2
One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update |  |  |  | 25-Mar-25 A | 28-Jun-25 A | 0
A28330 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFR |  |  | 25-Mar-25 A | 28-Apr-25 A | 0
A55830 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCC |  |  | 29-Apr-25 A | 15-May-25 A | 0
A55840 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFA |  |  | 16-May-25 A | 04-Jun-25 A | 0
A55850 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_RCA |  |  | 05-Jun-25 A | 21-Jun-25 A | 0
A55860 | One Line Diagram 220/33 KV Main Substation (Unit No-80) - Update_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Upd |  | 2025-10-14 | 2027-01-20 | 18-Feb-25 A | 2025-10-14 | 18
A28410 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A28420 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
A55870 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFR |  |  | 18-Feb-25 A | 11-Mar-25 A | 0
A55880 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_RCC |  |  | 12-Mar-25 A | 15-May-25 A | 0
A55890 | Protection and Metering One Line Diagram 220/33 KV Main Substation 33 KV Switchgear 80-ES-1802 - Update_IFA |  |  | 16-May-25 A | 25-May-25 A | 0
Electrical Legend Sheet |  |  |  | 31-Jan-25 A | 28-Jun-25 A | 0
A12130 | Electrical Legend Sheet_IFR |  |  | 31-Jan-25 A | 21-Feb-25 A | 0
A12140 | Electrical Legend Sheet_RCC |  |  | 22-Feb-25 A | 13-Mar-25 A | 0
A12150 | Electrical Legend Sheet_IFA |  |  | 14-Apr-25 A | 20-Apr-25 A | 0
A12160 | Electrical Legend Sheet_RCA |  |  | 21-Apr-25 A | 21-Jun-25 A | 0
A12170 | Electrical Legend Sheet_IFD/IFC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Electrical Equipment And Motor List |  |  |  | 31-Jan-25 A | 04-May-25 A | 0
A12230 | Electrical Equipment And Motor List_IFR |  |  | 31-Jan-25 A | 21-Feb-25 A | 0
A12240 | Electrical Equipment And Motor List_RCC |  |  | 22-Feb-25 A | 13-Mar-25 A | 0
A12250 | Electrical Equipment And Motor List_IFA |  |  | 14-Mar-25 A | 20-Apr-25 A | 0
A12260 | Electrical Equipment And Motor List_RCA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A12270 | Electrical Equipment And Motor List_IFD/IFC |  |  | 28-Apr-25 A | 04-May-25 A | 0
System Architecture Diagram For IPCS |  | 2025-10-14 | 2027-01-20 | 12-Feb-25 A | 2025-10-14 | 18
A12280 | System Architecture Diagram For IPCS_IFR |  |  | 12-Feb-25 A | 05-Mar-25 A | 0
A12290 | System Architecture Diagram For IPCS_RCC |  |  | 06-Mar-25 A | 20-Apr-25 A | 0
A12300 | System Architecture Diagram For IPCS_IFA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A12310 | System Architecture Diagram For IPCS_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A12320 | System Architecture Diagram For IPCS_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
System Architecture Diagram For SCMS - Update |  |  |  | 01-Jul-25 A | 08-Sep-25 A | 0
A12330 | System Architecture Diagram For SCMS - Update_IFR |  |  | 01-Jul-25 A | 08-Jul-25 A | 0
A12340 | System Architecture Diagram For SCMS - Update_RCC |  |  | 09-Jul-25 A | 30-Jul-25 A | 0
A12350 | System Architecture Diagram For SCMS - Update_IFA |  |  | 31-Jul-25 A | 20-Aug-25 A | 0
A12360 | System Architecture Diagram For SCMS - Update_RCA |  |  | 21-Aug-25 A | 01-Sep-25 A | 0
A12370 | System Architecture Diagram For SCMS - Update_IFD/IFC |  |  | 02-Sep-25 A | 08-Sep-25 A | 0
Capacitor Bank Sizing Calculation |  | 2025-10-14 | 2027-01-20 | 28-Feb-25 A | 2025-10-14 | 18
A10780 | Capacitor Bank Sizing Calculation_IFR |  |  | 28-Feb-25 A | 21-Mar-25 A | 0
A10790 | Capacitor Bank Sizing Calculation_RCC |  |  | 22-Mar-25 A | 26-May-25 A | 0
A10800 | Capacitor Bank Sizing Calculation_IFA |  |  | 27-May-25 A | 21-Jun-25 A | 0
A10810 | Capacitor Bank Sizing Calculation_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A10820 | Capacitor Bank Sizing Calculation_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Technical Bid Evaluation For Transformer (Power And Distribution) | [5 empty] | 0
Technical Bid Evaluation For 11KV Switchgear |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A12980 | Technical Bid Evaluation For 11KV Switchgear_IFR |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A12990 | Technical Bid Evaluation For 11KV Switchgear_RCC | 2025-10-10 | 2025-12-26 | 2025-09-19 | 2025-10-10 | 16
A13000 | Technical Bid Evaluation For 11KV Switchgear_IFA | 2025-10-16 | 2026-01-01 | 2025-10-10 | 2025-10-16 | 3
A13010 | Technical Bid Evaluation For 11KV Switchgear_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A13020 | Technical Bid Evaluation For 11KV Switchgear_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Technical Bid Evaluation For LV Switchgear | [5 empty] | 0
Technical Bid Evaluation For AC UPS | [5 empty] | 0
Technical Bid Evaluation For DC UPS |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A13130 | Technical Bid Evaluation For DC UPS_IFR | 2025-09-26 | 2025-12-05 | 2025-09-19 | 2025-09-26 | 6
A13140 | Technical Bid Evaluation For DC UPS_RCC | 2025-10-20 | 2025-12-26 | 2025-09-26 | 2025-10-20 | 16
A13150 | Technical Bid Evaluation For DC UPS_IFA | 2025-10-23 | 2026-01-01 | 2025-10-20 | 2025-10-23 | 3
A13160 | Technical Bid Evaluation For DC UPS_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A13170 | Technical Bid Evaluation For DC UPS_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Technical Bid Evaluation For Capacitor Bank | [5 empty] | 0
Technical Bid Evaluation For Power, Control And Earthing Cables | [5 empty] | 0
Technical Bid Evaluation For Neutral Grounding Resistor | [5 empty] | 0
Technical Bid Evaluation For Emergency Diesel Generator Set | [5 empty] | 0
Technical Bid Evaluation For LV Variable Frequency Drive | [5 empty] | 0
Cable (MV and LV) Sizing Calculation |  | 2025-09-23 | 2027-01-20 | 19-Feb-25 A | 2025-09-23 | 2
A10730 | Cable (MV and LV) Sizing Calculation_IFR |  |  | 19-Feb-25 A | 12-Mar-25 A | 0
A10740 | Cable (MV and LV) Sizing Calculation_RCC |  |  | 13-Mar-25 A | 06-May-25 A | 0
A10750 | Cable (MV and LV) Sizing Calculation_IFA |  |  | 07-May-25 A | 19-Jun-25 A | 0
A10760 | Cable (MV and LV) Sizing Calculation_RCA |  |  | 20-Jun-25 A | 26-Jun-25 A | 0
A10770 | Cable (MV and LV) Sizing Calculation_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Lighting Design Calculation |  | 2025-11-11 | 2027-01-20 | 22-Apr-25 A | 2025-11-11 | 37
A10830 | Lighting Design Calculation_IFR |  |  | 22-Apr-25 A | 13-May-25 A | 0
A10840 | Lighting Design Calculation_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A10850 | Lighting Design Calculation_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A10860 | Lighting Design Calculation_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A10870 | Lighting Design Calculation_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Earthing and Lightning Protection Calculation |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A10880 | Earthing and Lightning Protection Calculation_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A10890 | Earthing and Lightning Protection Calculation_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A10900 | Earthing and Lightning Protection Calculation_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A10910 | Earthing and Lightning Protection Calculation_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A10920 | Earthing and Lightning Protection Calculation_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Power And Control Cable Schedule |  | 2025-11-11 | 2026-06-24 | 21-Apr-25 A | 2025-11-11 | 37
A12180 | Power And Control Cable Schedule_IFR |  |  | 21-Apr-25 A | 12-May-25 A | 0
A12190 | Power And Control Cable Schedule_RCC | 2025-10-10 | 2026-05-26 | 2025-09-19 | 2025-10-10 | 16
A12200 | Power And Control Cable Schedule_IFA | 2025-10-16 | 2026-05-29 | 2025-10-10 | 2025-10-16 | 3
A12210 | Power And Control Cable Schedule_RCA | 2025-11-06 | 2026-06-22 | 2025-10-16 | 2025-11-06 | 16
A12220 | Power And Control Cable Schedule_IFD/IFC | 2025-11-11 | 2026-06-24 | 2025-11-06 | 2025-11-11 | 2
Interconnection Schedule |  | 2025-11-18 | 2026-03-05 | 2025-09-19 | 2025-11-18 | 43
A12380 | Interconnection Schedule_IFR | 2025-09-26 | 2026-01-13 | 2025-09-19 | 2025-09-26 | 6
A12390 | Interconnection Schedule_RCC | 2025-10-20 | 2026-02-03 | 2025-09-26 | 2025-10-20 | 16
A12400 | Interconnection Schedule_IFA | 2025-10-23 | 2026-02-09 | 2025-10-20 | 2025-10-23 | 3
A12410 | Interconnection Schedule_RCA | 2025-11-14 | 2026-03-02 | 2025-10-23 | 2025-11-14 | 16
A12420 | Interconnection Schedule_IFD/IFC | 2025-11-18 | 2026-03-05 | 2025-11-14 | 2025-11-18 | 2
Electrical Substation Building Layout |  | 2025-09-30 | 2027-01-20 | 03-Jan-25 A | 2025-09-30 | 2
A11930 | Electrical Substation Building Layout_IFR |  |  | 03-Jan-25 A | 24-Jan-25 A | 0
A11940 | Electrical Substation Building Layout_RCC |  |  | 25-Jan-25 A | 15-May-25 A | 0
A11950 | Electrical Substation Building Layout_IFA |  |  | 16-May-25 A | 23-Aug-25 A | 0
A11960 | Electrical Substation Building Layout_RCA |  |  | 24-Aug-25 A | 30-Aug-25 A | 0
A11970 | Electrical Substation Building Layout_IFD/IFC | 2025-09-30 | 2027-01-20 | 2025-09-26 | 2025-09-30 | 2
Cable and Tray Routing Layout - Outdoor |  | 2026-02-11 | 2026-06-24 | 2025-10-13 | 2026-02-11 | 87
A11830 | Cable and Tray Routing Layout - Outdoor_IFR | 2025-10-21 | 2026-04-24 | 2025-10-13 | 2025-10-21 | 6
A11840 | Cable and Tray Routing Layout - Outdoor_RCC | 2025-11-12 | 2026-05-20 | 2025-10-21 | 2025-11-12 | 16
A11850 | Cable and Tray Routing Layout - Outdoor_IFA | 2025-11-17 | 2026-05-26 | 2025-11-12 | 2025-11-17 | 3
A11860 | Cable and Tray Routing Layout - Outdoor_RCA | 2025-12-09 | 2026-06-17 | 2025-11-17 | 2025-12-09 | 16
A11870 | Cable and Tray Routing Layout - Outdoor_IFD/IFC | 2026-02-11 | 2026-06-24 | 2026-02-03 | 2026-02-11 | 6
Underground 33KV Cable Routing Layout Overall - Update |  | 2026-02-11 | 2026-06-24 | 2025-10-21 | 2026-02-11 | 81
A55900 | Underground 33KV Cable Routing Layout Overall - Update_IFR | 2025-10-29 | 2026-05-04 | 2025-10-21 | 2025-10-29 | 6
A55910 | Underground 33KV Cable Routing Layout Overall - Update_RCC | 2025-11-19 | 2026-05-26 | 2025-10-29 | 2025-11-19 | 16
A55920 | Underground 33KV Cable Routing Layout Overall - Update_IFA | 2025-11-25 | 2026-05-29 | 2025-11-19 | 2025-11-25 | 3
A55930 | Underground 33KV Cable Routing Layout Overall - Update_RCA | 2025-12-16 | 2026-06-22 | 2025-11-25 | 2025-12-16 | 16
A55940 | Underground 33KV Cable Routing Layout Overall - Update_IFD/IFC | 2026-02-11 | 2026-06-24 | 2026-02-09 | 2026-02-11 | 2
Cable and Tray Routing Layout - Indoor |  | 2025-12-11 | 2026-06-24 | 2025-10-13 | 2025-12-11 | 43
A11880 | Cable and Tray Routing Layout - Indoor_IFR | 2025-10-21 | 2026-05-04 | 2025-10-13 | 2025-10-21 | 6
A11890 | Cable and Tray Routing Layout - Indoor_RCC | 2025-11-12 | 2026-05-26 | 2025-10-21 | 2025-11-12 | 16
A11900 | Cable and Tray Routing Layout - Indoor_IFA | 2025-11-17 | 2026-05-29 | 2025-11-12 | 2025-11-17 | 3
A11910 | Cable and Tray Routing Layout - Indoor_RCA | 2025-12-09 | 2026-06-22 | 2025-11-17 | 2025-12-09 | 16
A11920 | Cable and Tray Routing Layout - Indoor_IFD/IFC | 2025-12-11 | 2026-06-24 | 2025-12-09 | 2025-12-11 | 2
Overall Lighting & Small Power Layout |  | 2026-02-03 | 2026-06-24 | 23-Aug-25 A | 2026-02-03 | 98
A11980 | Overall Lighting & Small Power Layout_IFR |  |  | 23-Aug-25 A | 13-Sep-25 A | 0
A11990 | Overall Lighting & Small Power Layout_RCC | 2025-10-10 | 2026-05-20 | 2025-09-19 | 2025-10-10 | 16
A12000 | Overall Lighting & Small Power Layout_IFA | 2025-10-16 | 2026-05-26 | 2025-10-10 | 2025-10-16 | 3
A12010 | Overall Lighting & Small Power Layout_RCA | 2025-11-06 | 2026-06-17 | 2025-10-16 | 2025-11-06 | 16
A12020 | Overall Lighting & Small Power Layout_IFD/IFC | 2026-02-03 | 2026-06-24 | 2026-01-27 | 2026-02-03 | 6
Earthing And Lightning Protection System Layout |  | 2026-01-19 | 2026-06-24 | 2025-10-13 | 2026-01-19 | 70
A12030 | Earthing And Lightning Protection System Layout_IFR | 2025-10-21 | 2026-04-29 | 2025-10-13 | 2025-10-21 | 6
A12040 | Earthing And Lightning Protection System Layout_RCC | 2025-11-12 | 2026-05-20 | 2025-10-21 | 2025-11-12 | 16
A12050 | Earthing And Lightning Protection System Layout_IFA | 2025-11-17 | 2026-05-26 | 2025-11-12 | 2025-11-17 | 3
A12060 | Earthing And Lightning Protection System Layout_RCA | 2025-12-09 | 2026-06-17 | 2025-11-17 | 2025-12-09 | 16
A12070 | Earthing And Lightning Protection System Layout_IFD/IFC | 2026-01-19 | 2026-06-24 | 2026-01-12 | 2026-01-19 | 6
Updation of Earthing Layout Butene 1, EU3, B3/EU3 |  | 2026-01-27 | 2027-01-20 | 10-Sep-25 A | 2026-01-27 | 92
A12080 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFR |  |  | 10-Sep-25 A | 15-Sep-25 A | 0
A12090 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCC | 2025-10-10 | 2026-12-17 | 2025-09-19 | 2025-10-10 | 16
A12100 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFA | 2025-10-16 | 2026-12-22 | 2025-10-10 | 2025-10-16 | 3
A12110 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_RCA | 2025-11-06 | 2027-01-13 | 2025-10-16 | 2025-11-06 | 16
A12120 | Updation of Earthing Layout Butene 1, EU3, B3/EU3_IFD/IFC | 2026-01-27 | 2027-01-20 | 2026-01-19 | 2026-01-27 | 6
Electrical Bulk MTO |  |  |  | 20-Apr-25 A | 25-May-25 A | 0
A13430 | Electrical Bulk MTO_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A13440 | Electrical Bulk MTO_RCC |  |  | 12-May-25 A | 18-May-25 A | 0
A13470 | Electrical Bulk MTO_IFD/IFC |  |  | 19-May-25 A | 25-May-25 A | 0
Instrumentation |  | 2026-01-07 | 2027-01-20 | 31-Dec-24 A | 2026-01-07 | 75
Scope of Work for the ICSS System |  | 2025-11-11 | 2027-01-20 | 01-Mar-25 A | 2025-11-11 | 37
A14530 | Scope of Work for the ICSS System_IFR |  |  | 01-Mar-25 A | 10-Mar-25 A | 0
A14540 | Scope of Work for the ICSS System_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A14550 | Scope of Work for the ICSS System_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A14560 | Scope of Work for the ICSS System_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A14570 | Scope of Work for the ICSS System_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Scope of Work for the MCMS System |  | 2025-11-11 | 2027-01-20 | 01-Mar-25 A | 2025-11-11 | 37
A58490 | Scope of Work for the MCMS System_IFR |  |  | 01-Mar-25 A | 10-Mar-25 A | 0
A58500 | Scope of Work for the MCMS System_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A58510 | Scope of Work for the MCMS System_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A58520 | Scope of Work for the MCMSSystem_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A58530 | Scope of Work for the MCMS System_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Instrument Datasheet for ESD Valves |  | 2025-10-14 | 2026-02-23 | 13-Mar-25 A | 2025-10-14 | 18
A14430 | Instrument Datasheet for ESD Valves_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A14440 | Instrument Datasheet for ESD Valves_RCC |  |  | 28-Apr-25 A | 13-Jun-25 A | 0
A14450 | Instrument Datasheet for ESD Valves_IFA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A14460 | Instrument Datasheet for ESD Valves_RCA | 2025-10-10 | 2026-02-19 | 2025-09-19 | 2025-10-10 | 16
A14470 | Instrument Datasheet for ESD Valves_IFD/IFC | 2025-10-14 | 2026-02-23 | 2025-10-10 | 2025-10-14 | 2
Instrument Datasheet for Control Valves |  |  |  | 13-Mar-25 A | 10-Sep-25 A | 0
A14280 | Instrument Datasheet for Control Valves_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A14290 | Instrument Datasheet for Control Valves_RCC |  |  | 28-Apr-25 A | 21-Jun-25 A | 0
A14300 | Instrument Datasheet for Control Valves_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A14310 | Instrument Datasheet for Control Valves_RCA |  |  | 19-Aug-25 A | 08-Sep-25 A | 0
A14320 | Instrument Datasheet for Control Valves_IFD/IFC |  |  | 09-Sep-25 A | 10-Sep-25 A | 0
Instrument Datasheet for Motor Operated Valves |  |  |  | 13-Mar-25 A | 10-Sep-25 A | 0
A14330 | Instrument Datasheet for Motor Operated Valves_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A14340 | Instrument Datasheet for Motor Operated Valves_RCC |  |  | 28-Apr-25 A | 13-Jun-25 A | 0
A14350 | Instrument Datasheet for Motor Operated Valves_IFA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A14360 | Instrument Datasheet for Motor Operated Valves_RCA |  |  | 19-Aug-25 A | 08-Sep-25 A | 0
A14370 | Instrument Datasheet for Motor Operated Valves_IFD/IFC |  |  | 09-Sep-25 A | 10-Sep-25 A | 0
Instrument Datasheet for Analyzers |  | 2025-11-11 | 2026-02-23 | 01-Jul-25 A | 2025-11-11 | 37
A14130 | Instrument Datasheet for Analyzers_IFR |  |  | 01-Jul-25 A | 12-Jul-25 A | 0
A14140 | Instrument Datasheet for Analyzers_RCC | 2025-10-10 | 2026-01-21 | 2025-09-19 | 2025-10-10 | 16
A14150 | Instrument Datasheet for Analyzers_IFA | 2025-10-16 | 2026-01-27 | 2025-10-10 | 2025-10-16 | 3
A14160 | Instrument Datasheet for Analyzers_RCA | 2025-11-06 | 2026-02-19 | 2025-10-16 | 2025-11-06 | 16
A14170 | Instrument Datasheet for Analyzers_IFD/IFC | 2025-11-11 | 2026-02-23 | 2025-11-06 | 2025-11-11 | 2
Instrument Datasheet for Flow Element (Orifice Plate) |  | 2025-09-23 | 2027-01-18 | 07-Apr-25 A | 2025-09-23 | 2
A13830 | Instrument Datasheet for Flow Element (Orifice Plate)_IFR |  |  | 07-Apr-25 A | 28-Apr-25 A | 0
A13840 | Instrument Datasheet for Flow Element (Orifice Plate)_RCC |  |  | 29-Apr-25 A | 21-Jun-25 A | 0
A13850 | Instrument Datasheet for Flow Element (Orifice Plate)_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A13860 | Instrument Datasheet for Flow Element (Orifice Plate)_RCA |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
A13870 | Instrument Datasheet for Flow Element (Orifice Plate)_IFD/IFC | 2025-09-23 | 2027-01-18 | 2025-09-19 | 2025-09-23 | 2
Instrument Datasheet for Flow Element (Venturi Tube) |  |  |  | 13-Mar-25 A | 22-Aug-25 A | 0
A13880 | Instrument Datasheet for Flow Element (Venturi Tube)_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A13890 | Instrument Datasheet for Flow Element (Venturi Tube)_RCC |  |  | 28-Apr-25 A | 13-Jun-25 A | 0
A13900 | Instrument Datasheet for Flow Element (Venturi Tube)_IFA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A13910 | Instrument Datasheet for Flow Element (Venturi Tube)_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A13920 | Instrument Datasheet for Flow Element (Venturi Tube)_IFD/IFC |  |  | 19-Aug-25 A | 22-Aug-25 A | 0
Instrument Datasheet for Rotameter |  | 2025-09-23 | 2026-02-23 | 13-Mar-25 A | 2025-09-23 | 2
A14480 | Instrument Datasheet for Rotameter_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A14490 | Instrument Datasheet for Rotameter_RCC |  |  | 28-Apr-25 A | 13-Jun-25 A | 0
A14500 | Instrument Datasheet for Rotameter_IFA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A14510 | Instrument Datasheet for Rotameter_RCA |  |  | 22-Jun-25 A | 08-Sep-25 A | 0
A14520 | Instrument Datasheet for Rotameter_IFD/IFC | 2025-09-23 | 2026-02-23 | 2025-09-19 | 2025-09-23 | 2
Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP) |  | 2025-10-14 | 2026-02-23 | 26-Mar-25 A | 2025-10-14 | 18
A13680 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFR |  |  | 26-Mar-25 A | 16-Apr-25 A | 0
A13690 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCC |  |  | 17-Apr-25 A | 02-May-25 A | 0
A13700 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFA |  |  | 19-Jul-25 A | 23-Jul-25 A | 0
A13710 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_RCA | 2025-10-10 | 2026-02-19 | 2025-09-19 | 2025-10-10 | 16
A13720 | Instrument Datasheet for Electronic Transmitters (Pressure / Level / DP)_IFD/IFC | 2025-10-14 | 2026-02-23 | 2025-10-10 | 2025-10-14 | 2
Instrument Datasheet for Electronic Transmitters (Flow) |  | 2025-09-23 | 2026-02-23 | 13-Mar-25 A | 2025-09-23 | 2
A13730 | Instrument Datasheet for Electronic Transmitters (Flow)_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A13740 | Instrument Datasheet for Electronic Transmitters (Flow)_RCC |  |  | 28-Apr-25 A | 04-May-25 A | 0
A13750 | Instrument Datasheet for Electronic Transmitters (Flow)_IFA |  |  | 05-May-25 A | 21-Jun-25 A | 0
A13760 | Instrument Datasheet for Electronic Transmitters (Flow)_RCA |  |  | 22-Jun-25 A | 10-Sep-25 A | 0
A13770 | Instrument Datasheet for Electronic Transmitters (Flow)_IFD/IFC | 2025-09-23 | 2026-02-23 | 2025-09-19 | 2025-09-23 | 2
Instrument Datasheet for Temperature Transmitters (Head mounted) |  | 2025-09-23 | 2027-01-20 | 25-Mar-25 A | 2025-09-23 | 2
A14380 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFR |  |  | 25-Mar-25 A | 21-Jun-25 A | 0
A14390 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCC |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A14400 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFA |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
A14410 | Instrument Datasheet for Temperature Transmitters (Head mounted)_RCA |  |  | 06-Jul-25 A | 12-Jul-25 A | 0
A14420 | Instrument Datasheet for Temperature Transmitters (Head mounted)_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Instrument Datasheet for Level Transmitters (GWR type) |  | 2025-10-14 | 2026-02-23 | 13-Mar-25 A | 2025-10-14 | 18
A14080 | Instrument Datasheet for Level Transmitters (GWR type)_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A14090 | Instrument Datasheet for Level Transmitters (GWR type)_RCC |  |  | 28-Apr-25 A | 23-Jun-25 A | 0
A14100 | Instrument Datasheet for Level Transmitters (GWR type)_IFA |  |  | 19-Aug-25 A | 23-Aug-25 A | 0
A14110 | Instrument Datasheet for Level Transmitters (GWR type)_RCA | 2025-10-10 | 2026-02-19 | 2025-09-19 | 2025-10-10 | 16
A14120 | Instrument Datasheet for Level Transmitters (GWR type)_IFD/IFC | 2025-10-14 | 2026-02-23 | 2025-10-10 | 2025-10-14 | 2
Instrument Datasheet for Temperature Element / Thermowell |  | 2025-10-20 | 2026-02-23 | 25-Mar-25 A | 2025-10-20 | 21
A13930 | Instrument Datasheet for Temperature Element / Thermowell_IFR |  |  | 25-Mar-25 A | 25-Apr-25 A | 0
A13940 | Instrument Datasheet for Temperature Element / Thermowell_RCC |  |  | 26-Apr-25 A | 21-Jun-25 A | 0
A13950 | Instrument Datasheet for Temperature Element / Thermowell_IFA | 2025-09-24 | 2026-01-27 | 2025-09-19 | 2025-09-24 | 3
A13960 | Instrument Datasheet for Temperature Element / Thermowell_RCA | 2025-10-16 | 2026-02-19 | 2025-09-24 | 2025-10-16 | 16
A13970 | Instrument Datasheet for Temperature Element / Thermowell_IFD/IFC | 2025-10-20 | 2026-02-23 | 2025-10-16 | 2025-10-20 | 2
Instrument Datasheet for Temperature Gauges / Thermowell |  | 2025-10-20 | 2027-01-20 | 13-Mar-25 A | 2025-10-20 | 21
A14030 | Instrument Datasheet for Temperature Gauges / Thermowell_IFR |  |  | 13-Mar-25 A | 28-Apr-25 A | 0
A14040 | Instrument Datasheet for Temperature Gauges / Thermowell_RCC |  |  | 19-Apr-25 A | 13-Jun-25 A | 0
A14050 | Instrument Datasheet for Temperature Gauges / Thermowell_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A14060 | Instrument Datasheet for Temperature Gauges / Thermowell_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A14070 | Instrument Datasheet for Temperature Gauges / Thermowell_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Instrument Datasheet for Pressure Gauges |  | 2025-11-11 | 2026-02-23 | 13-Mar-25 A | 2025-11-11 | 37
A13980 | Instrument Datasheet for Pressure Gauges_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A13990 | Instrument Datasheet for Pressure Gauges_RCC | 2025-10-10 | 2026-01-21 | 2025-09-19 | 2025-10-10 | 16
A14000 | Instrument Datasheet for Pressure Gauges_IFA | 2025-10-16 | 2026-01-27 | 2025-10-10 | 2025-10-16 | 3
A14010 | Instrument Datasheet for Pressure Gauges_RCA | 2025-11-06 | 2026-02-19 | 2025-10-16 | 2025-11-06 | 16
A14020 | Instrument Datasheet for Pressure Gauges_IFD/IFC | 2025-11-11 | 2026-02-23 | 2025-11-06 | 2025-11-11 | 2
Instrument Datasheet for Level Gauges (Magnetic Type) |  |  |  | 13-Mar-25 A | 22-Aug-25 A | 0
A14180 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A14190 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCC |  |  | 24-Apr-25 A | 13-Jun-25 A | 0
A14200 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A14210 | Instrument Datasheet for Level Gauges (Magnetic Type)_RCA |  |  | 22-Jun-25 A | 26-Jun-25 A | 0
A14220 | Instrument Datasheet for Level Gauges (Magnetic Type)_IFD/IFC |  |  | 19-Aug-25 A | 22-Aug-25 A | 0
Instrument Datasheet for Fire & Gas Detectors |  | 2025-10-14 | 2026-01-23 | 26-May-25 A | 2025-10-14 | 18
A14230 | Instrument Datasheet for Fire & Gas Detectors_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A14240 | Instrument Datasheet for Fire & Gas Detectors_RCC |  |  | 07-Jul-25 A | 18-Jul-25 A | 0
A14250 | Instrument Datasheet for Fire & Gas Detectors_IFA |  |  | 21-Jul-25 A | 25-Jul-25 A | 0
A14260 | Instrument Datasheet for Fire & Gas Detectors_RCA | 2025-10-10 | 2026-01-21 | 2025-09-19 | 2025-10-10 | 16
A14270 | Instrument Datasheet for Fire & Gas Detectors_IFD/IFC | 2025-10-14 | 2026-01-23 | 2025-10-10 | 2025-10-14 | 2
Instrument Datasheet for Loop Powered Indicator |  |  |  | 07-Apr-25 A | 05-Jul-25 A | 0
A13780 | Instrument Datasheet for Loop Powered Indicator_IFR |  |  | 07-Apr-25 A | 28-Apr-25 A | 0
A13790 | Instrument Datasheet for Loop Powered Indicator_RCC |  |  | 29-Apr-25 A | 30-May-25 A | 0
A13800 | Instrument Datasheet for Loop Powered Indicator_IFA |  |  | 01-Jun-25 A | 21-Jun-25 A | 0
A13810 | Instrument Datasheet for Loop Powered Indicator_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A13820 | Instrument Datasheet for Loop Powered Indicator_IFD/IFC |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
Material Requisition for ESD Valves |  | 2025-10-17 | 2026-02-25 | 24-Mar-25 A | 2025-10-17 | 2
A15130 | Material Requisition for ESD Valves_IFR |  |  | 24-Mar-25 A | 30-Apr-25 A | 0
A15140 | Material Requisition for ESD Valves_RCC |  |  | 01-May-25 A | 21-Jun-25 A | 0
A15150 | Material Requisition for ESD Valves_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A15160 | Material Requisition for ESD Valves_RCA |  |  | 29-Jun-25 A | 27-Aug-25 A | 0
A15170 | Material Requisition for ESD Valves_IFD/IFC | 2025-10-17 | 2026-02-25 | 2025-10-15 | 2025-10-17 | 2
Material Requisition for Control Valves |  |  |  | 13-Mar-25 A | 19-Sep-25 A | 0
A14980 | Material Requisition for Control Valves_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A14990 | Material Requisition for Control Valves_RCC |  |  | 28-Apr-25 A | 21-Jun-25 A | 0
A15000 | Material Requisition for Control Valves_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A15010 | Material Requisition for Control Valves_RCA |  |  | 29-Jun-25 A | 02-Sep-25 A | 0
A15020 | Material Requisition for Control Valves_IFD/IFC |  |  | 10-Sep-25 A | 19-Sep-25 A | 0
Material Requisition for Motor Operated Valves |  |  |  | 24-Mar-25 A | 13-Sep-25 A | 0
A15080 | Material Requisition for Motor Operated Valves_IFR |  |  | 24-Mar-25 A | 27-Apr-25 A | 0
A15090 | Material Requisition for Motor Operated Valves_RCC |  |  | 28-Apr-25 A | 13-Jun-25 A | 0
A15100 | Material Requisition for Motor Operated Valves_IFA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A15110 | Material Requisition for Motor Operated Valves_RCA |  |  | 22-Jun-25 A | 08-Sep-25 A | 0
A15120 | Material Requisition for Motor Operated Valves_IFD/IFC |  |  | 11-Sep-25 A | 13-Sep-25 A | 0
Material Requisition for Analyzers |  | 2025-11-14 | 2026-02-25 | 01-Jul-25 A | 2025-11-14 | 41
A14830 | Material Requisition for Analyzers_IFR |  |  | 01-Jul-25 A | 15-Jul-25 A | 0
A14840 | Material Requisition for Analyzers_RCC | 2025-10-10 | 2026-01-27 | 2025-09-19 | 2025-10-10 | 16
A14850 | Material Requisition for Analyzers_IFA | 2025-10-21 | 2026-01-30 | 2025-10-16 | 2025-10-21 | 3
A14860 | Material Requisition for Analyzers_RCA | 2025-11-12 | 2026-02-23 | 2025-10-21 | 2025-11-12 | 16
A14870 | Material Requisition for Analyzers_IFD/IFC | 2025-11-14 | 2026-02-25 | 2025-11-12 | 2025-11-14 | 2
Material Requisition for Flow Element (Orifice Plate) |  | 2025-09-25 | 2027-01-20 | 14-Mar-25 A | 2025-09-25 | 2
A14630 | Material Requisition for Flow Element (Orifice Plate)_IFR |  |  | 14-Mar-25 A | 29-Apr-25 A | 0
A14640 | Material Requisition for Flow Element (Orifice Plate)_RCC |  |  | 30-Apr-25 A | 21-Jun-25 A | 0
A14650 | Material Requisition for Flow Element (Orifice Plate)_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A14660 | Material Requisition for Flow Element (Orifice Plate)_RCA |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
A14670 | Material Requisition for Flow Element (Orifice Plate)_IFD/IFC | 2025-09-25 | 2027-01-20 | 2025-09-23 | 2025-09-25 | 2
Material Requisition for Flow Element (Venturi Tube) |  |  |  | 13-Mar-25 A | 15-Sep-25 A | 0
A14680 | Material Requisition for Flow Element (Venturi Tube)_IFR |  |  | 13-Mar-25 A | 30-Apr-25 A | 0
A14690 | Material Requisition for Flow Element (Venturi Tube)_RCC |  |  | 01-May-25 A | 21-Jun-25 A | 0
A14700 | Material Requisition for Flow Element (Venturi Tube)_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A14710 | Material Requisition for Flow Element (Venturi Tube)_RCA |  |  | 22-Aug-25 A | 11-Sep-25 A | 0
A14720 | Material Requisition for Flow Element (Venturi Tube)_IFD/IFC |  |  | 12-Sep-25 A | 15-Sep-25 A | 0
Material Requisition for Rotameter |  | 2025-09-25 | 2026-02-25 | 25-Mar-25 A | 2025-09-25 | 2
A15180 | Material Requisition for Rotameter_IFR |  |  | 25-Mar-25 A | 01-May-25 A | 0
A15190 | Material Requisition for Rotameter_RCC |  |  | 02-May-25 A | 13-Jun-25 A | 0
A15200 | Material Requisition for Rotameter_IFA |  |  | 14-Jun-25 A | 21-Jun-25 A | 0
A15210 | Material Requisition for Rotameter_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A15220 | Material Requisition for Rotameter_IFD/IFC | 2025-09-25 | 2026-02-25 | 2025-09-23 | 2025-09-25 | 2
Material Requisition for Electronic Transmitters |  | 2025-10-17 | 2026-02-25 | 25-Mar-25 A | 2025-10-17 | 2
A14580 | Material Requisition for Electronic Transmitters_IFR |  |  | 25-Mar-25 A | 28-Apr-25 A | 0
A14590 | Material Requisition for Electronic Transmitters_RCC |  |  | 29-Apr-25 A | 30-Jul-25 A | 0
A14600 | Material Requisition for Electronic Transmitters_IFA |  |  | 31-Jul-25 A | 23-Aug-25 A | 0
A14610 | Material Requisition for Electronic Transmitters_RCA |  |  | 24-Aug-25 A | 06-Sep-25 A | 0
A14620 | Material Requisition for Electronic Transmitters_IFD/IFC | 2025-10-17 | 2026-02-25 | 2025-10-15 | 2025-10-17 | 2
Material Requisition for Level Transmitters (GWR type) |  | 2025-10-17 | 2026-02-25 | 26-Mar-25 A | 2025-10-17 | 20
A14880 | Material Requisition for Level Transmitters (GWR type)_IFR |  |  | 26-Mar-25 A | 28-Apr-25 A | 0
A14890 | Material Requisition for Level Transmitters (GWR type)_RCC |  |  | 19-Aug-25 A | 08-Sep-25 A | 0
A14900 | Material Requisition for Level Transmitters (GWR type)_IFA |  |  | 09-Sep-25 A | 12-Sep-25 A | 0
A14910 | Material Requisition for Level Transmitters (GWR type)_RCA | 2025-10-10 | 2026-02-23 | 2025-09-19 | 2025-10-10 | 16
A14920 | Material Requisition for Level Transmitters (GWR type)_IFD/IFC | 2025-10-17 | 2026-02-25 | 2025-10-15 | 2025-10-17 | 2
Material Requisition for Temperature Element / Thermowell |  | 2025-11-11 | 2026-02-25 | 13-Mar-25 A | 2025-11-11 | 37
A14730 | Material Requisition for Temperature Element / Thermowell_IFR |  |  | 13-Mar-25 A | 07-May-25 A | 0
A14740 | Material Requisition for Temperature Element / Thermowell_RCC | 2025-10-10 | 2026-01-27 | 2025-09-19 | 2025-10-10 | 16
A14750 | Material Requisition for Temperature Element / Thermowell_IFA | 2025-10-16 | 2026-01-30 | 2025-10-10 | 2025-10-16 | 3
A14760 | Material Requisition for Temperature Element / Thermowell_RCA | 2025-11-06 | 2026-02-23 | 2025-10-16 | 2025-11-06 | 16
A14770 | Material Requisition for Temperature Element / Thermowell_IFD/IFC | 2025-11-11 | 2026-02-25 | 2025-11-06 | 2025-11-11 | 2
Material Requisition for Temperature Gauges / Pressure Gauges |  | 2025-11-14 | 2026-02-25 | 25-Mar-25 A | 2025-11-14 | 21
A14780 | Material Requisition for Temperature Gauges / Pressure Gauges_IFR |  |  | 25-Mar-25 A | 30-Apr-25 A | 0
A14790 | Material Requisition for Temperature Gauges / Pressure Gauges_RCC |  |  | 01-May-25 A | 21-Jun-25 A | 0
A14800 | Material Requisition for Temperature Gauges / Pressure Gauges_IFA | 2025-10-21 | 2026-01-30 | 2025-10-16 | 2025-10-21 | 3
A14810 | Material Requisition for Temperature Gauges / Pressure Gauges_RCA | 2025-11-12 | 2026-02-23 | 2025-10-21 | 2025-11-12 | 16
A14820 | Material Requisition for Temperature Gauges / Pressure Gauges_IFD/IFC | 2025-11-14 | 2026-02-25 | 2025-11-12 | 2025-11-14 | 2
Material Requisition for Level Gauges (Magnetic Type) |  |  |  | 25-Mar-25 A | 09-Sep-25 A | 0
A14930 | Material Requisition for Level Gauges (Magnetic Type)_IFR |  |  | 25-Mar-25 A | 23-Apr-25 A | 0
A14940 | Material Requisition for Level Gauges (Magnetic Type)_RCC |  |  | 24-Apr-25 A | 30-Jul-25 A | 0
A14950 | Material Requisition for Level Gauges (Magnetic Type)_IFA |  |  | 31-Jul-25 A | 26-Aug-25 A | 0
A14960 | Material Requisition for Level Gauges (Magnetic Type)_RCA |  |  | 27-Aug-25 A | 02-Sep-25 A | 0
A14970 | Material Requisition for Level Gauges (Magnetic Type)_IFD/IFC |  |  | 03-Sep-25 A | 09-Sep-25 A | 0
Material Requisition for Fire & Gas Detectors |  | 2025-11-04 | 2026-01-27 | 27-May-25 A | 2025-11-04 | 33
A15030 | Material Requisition for Fire & Gas Detectors_IFR |  |  | 27-May-25 A | 05-Jul-25 A | 0
A15040 | Material Requisition for Fire & Gas Detectors_RCC | 2025-10-10 | 2026-01-05 | 2025-09-19 | 2025-10-10 | 16
A15050 | Material Requisition for Fire & Gas Detectors_IFA | 2025-10-16 | 2026-01-08 | 2025-10-10 | 2025-10-16 | 3
A15060 | Material Requisition for Fire & Gas Detectors_RCA | 2025-10-31 | 2026-01-23 | 2025-10-16 | 2025-10-31 | 11
A15070 | Material Requisition for Fire & Gas Detectors_IFD/IFC | 2025-11-04 | 2026-01-27 | 2025-10-31 | 2025-11-04 | 2
Material Requisition for Instrument Cables |  |  |  | 27-May-25 A | 08-Aug-25 A | 0
A15230 | Material Requisition for Instrument Cables_IFR |  |  | 27-May-25 A | 05-Jul-25 A | 0
A47650 | Material Requisition for Instrument Cables_RCC |  |  | 07-Jul-25 A | 18-Jul-25 A | 0
A47660 | Material Requisition for Instrument Cables_IFA |  |  | 02-Jun-25 A | 06-Jun-25 A | 0
A47670 | Material Requisition for Instrument Cables_RCA |  |  | 21-Jul-25 A | 01-Aug-25 A | 0
A47680 | Material Requisition for Instrument Cables_IFD/IFC |  |  | 04-Aug-25 A | 08-Aug-25 A | 0
Material Requisition for Junction Boxes |  | 2025-11-11 | 2026-02-25 | 27-May-25 A | 2025-11-11 | 37
A47690 | Material Requisition for Junction Boxes_IFR |  |  | 27-May-25 A | 05-Jul-25 A | 0
A47700 | Material Requisition for Junction Boxes_RCC | 2025-10-10 | 2026-01-27 | 2025-09-19 | 2025-10-10 | 16
A47710 | Material Requisition for Junction Boxes_IFA | 2025-10-16 | 2026-01-30 | 2025-10-10 | 2025-10-16 | 3
A47720 | Material Requisition for Junction Boxes_RCA | 2025-11-06 | 2026-02-23 | 2025-10-16 | 2025-11-06 | 16
A47730 | Material Requisition for Junction Boxes_IFD/IFC | 2025-11-11 | 2026-02-25 | 2025-11-06 | 2025-11-11 | 2
Material Requisition for ICSS System |  |  |  | 31-Dec-24 A | 14-Aug-25 A | 0
A15370 | Material Requisition for ICSS System_IFD/IFC |  |  | 04-Aug-25 A | 14-Aug-25 A | 0
A47740 | Material Requisition for ICSS System_IFR |  |  | 31-Dec-24 A | 23-Jan-25 A | 0
A47750 | Material Requisition for ICSS System_RCC |  |  | 24-Jan-25 A | 25-Feb-25 A | 0
A47760 | Material Requisition for ICSS System_IFA |  |  | 26-Feb-25 A | 21-Jun-25 A | 0
A47770 | Material Requisition for ICSS System_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
Material Requisition for MCMS System |  |  |  | 20-Apr-25 A | 07-May-25 A | 0
A58190 | Material Requisition for MCMS System_IFR |  |  | 20-Apr-25 A | 24-Apr-25 A | 0
A58200 | Material Requisition for MCMS System_RCC |  |  | 25-Apr-25 A | 27-Apr-25 A | 0
A58210 | Material Requisition for MCMS System_IFA |  |  | 28-Apr-25 A | 01-May-25 A | 0
A58220 | Material Requisition for MCMS System_RCA |  |  | 02-May-25 A | 05-May-25 A | 0
A58230 | Material Requisition for MCMS System_IFD/IFC |  |  | 05-May-25 A | 07-May-25 A | 0
Technical Bid Evaluation for ESD Valves |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A16680 | Technical Bid Evaluation for ESD Valves_IFR | 2025-09-26 | 2025-12-05 | 2025-09-19 | 2025-09-26 | 6
A16700 | Technical Bid Evaluation for ESD Valves_IFA | 2025-10-23 | 2026-01-01 | 2025-10-20 | 2025-10-23 | 3
A16710 | Technical Bid Evaluation for ESD Valves_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A16720 | Technical Bid Evaluation for ESD Valves_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
A48240 | Technical Bid Evaluation for ESD Valves_RCC | 2025-10-20 | 2025-12-26 | 2025-09-26 | 2025-10-20 | 16
Technical Bid Evaluation for Control Valves | [5 empty] | 0
Technical Bid Evaluation for Motor Operated Valves | [5 empty] | 0
Technical Bid Evaluation for Analyzers | [5 empty] | 0
Technical Bid Evaluation for Flow Element (Orifice Plate) | [5 empty] | 0
Technical Bid Evaluation for Flow Element (Venturi Tube) | [5 empty] | 0
Technical Bid Evaluation for Rotameter |  | 2025-11-18 | 2026-02-02 | 2025-09-19 | 2025-11-18 | 43
A16730 | Technical Bid Evaluation for Rotameter_IFR | 2025-09-26 | 2025-12-05 | 2025-09-19 | 2025-09-26 | 6
A16740 | Technical Bid Evaluation for Rotameter_RCC | 2025-10-20 | 2025-12-26 | 2025-09-26 | 2025-10-20 | 16
A16760 | Technical Bid Evaluation for Rotameter_RCA | 2025-11-14 | 2026-01-29 | 2025-10-23 | 2025-11-14 | 16
A16770 | Technical Bid Evaluation for Rotameter_IFD/IFC | 2025-11-18 | 2026-02-02 | 2025-11-14 | 2025-11-18 | 2
A48250 | Technical Bid Evaluation for Rotameter_IFA | 2025-10-23 | 2026-01-01 | 2025-10-20 | 2025-10-23 | 3
Technical Bid Evaluation for Electronic Transmitters | [5 empty] | 0
Technical Bid Evaluation for Level Transmitters (GWR type) |  | 2025-11-11 | 2026-02-02 | 23-Aug-25 A | 2025-11-11 | 37
A16580 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFR |  |  | 23-Aug-25 A | 18-Sep-25 A | 0
A16590 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCC | 2025-10-10 | 2025-12-26 | 2025-09-19 | 2025-10-10 | 16
A16600 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFA | 2025-10-16 | 2026-01-01 | 2025-10-10 | 2025-10-16 | 3
A16610 | Technical Bid Evaluation for Level Transmitters (GWR type)_RCA | 2025-11-06 | 2026-01-29 | 2025-10-16 | 2025-11-06 | 16
A16620 | Technical Bid Evaluation for Level Transmitters (GWR type)_IFD/IFC | 2025-11-11 | 2026-02-02 | 2025-11-06 | 2025-11-11 | 2
Technical Bid Evaluation for Temperature Element / Thermowell |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A16280 | Technical Bid Evaluation for Temperature Element / Thermowell_IFR | 2025-09-26 | 2025-12-05 | 2025-09-19 | 2025-09-26 | 6
A16290 | Technical Bid Evaluation for Temperature Element / Thermowell_RCC | 2025-10-20 | 2025-12-26 | 2025-09-26 | 2025-10-20 | 16
A16300 | Technical Bid Evaluation for Temperature Element / Thermowell_IFA | 2025-10-23 | 2026-01-01 | 2025-10-20 | 2025-10-23 | 3
A16310 | Technical Bid Evaluation for Temperature Element / Thermowell_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A16320 | Technical Bid Evaluation for Temperature Element / Thermowell_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Technical Bid Evaluation for Temperature Gauges / Pressure Gauges | [5 empty] | 0
Technical Bid Evaluation for Level Gauges (Magnetic Type) | [5 empty] | 0
Technical Bid Evaluation for Fire & Gas Detectors | [5 empty] | 0
Technical Bid Evaluation for Instrument Cables | [5 empty] | 0
Technical Bid Evaluation for Junction Boxes | [5 empty] | 0
Technical Bid Evaluation for ICSS System | [5 empty] | 0
SIL/LOPA CLoseout Report |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A13480 | SIL/LOPA Closeout Report_IFR | 2025-09-26 | 2026-11-12 | 2025-09-19 | 2025-09-26 | 6
A13490 | SIL/LOPA Closeout Report_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A13500 | SIL/LOPA Closeout Report_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A13510 | SIL/LOPA Closeout Report_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A13520 | SIL/LOPA Closeout Report_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Overall Control System Architecture Drawing |  | 2025-10-03 | 2027-01-20 | 09-Jun-25 A | 2025-10-03 | 2
A15430 | Overall Control System Architecture Drawing_IFR |  |  | 09-Jun-25 A | 05-Jul-25 A | 0
A15440 | Overall Control System Architecture Drawing_RCC |  |  | 06-Jul-25 A | 30-Jul-25 A | 0
A15450 | Overall Control System Architecture Drawing_IFA |  |  | 31-Jul-25 A | 09-Sep-25 A | 0
A15460 | Overall Control System Architecture Drawing_RCA |  |  | 10-Sep-25 A | 16-Sep-25 A | 0
A15470 | Overall Control System Architecture Drawing_IFD/IFC | 2025-10-03 | 2027-01-20 | 2025-09-30 | 2025-10-03 | 2
Instrument Index |  | 2025-11-11 | 2027-01-20 | 10-Jun-25 A | 2025-11-11 | 37
A15480 | Instrument Index_IFR |  |  | 10-Jun-25 A | 05-Jul-25 A | 0
A15490 | Instrument Index_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A15500 | Instrument Index_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A15510 | Instrument Index_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A15520 | Instrument Index_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Instrument & F&G I/O list |  | 2025-09-23 | 2027-01-20 | 26-May-25 A | 2025-09-23 | 2
A15530 | Instrument & F&G I/O list_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A15540 | Instrument & F&G I/O list_RCC |  |  | 06-Jul-25 A | 10-Aug-25 A | 0
A47820 | Instrument & F&G I/O list_IFA |  |  | 11-Aug-25 A | 20-Aug-25 A | 0
A47830 | Instrument & F&G I/O list_RCA |  |  | 21-Aug-25 A | 01-Sep-25 A | 0
A47840 | Instrument & F&G I/O list_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Cable Block Diagram |  | 2025-09-23 | 2027-01-20 | 08-May-25 A | 2025-09-23 | 2
A15580 | Cable Block Diagram_IFR |  |  | 08-May-25 A | 06-Aug-25 A | 0
A15590 | Cable Block Diagram_RCC |  |  | 07-Aug-25 A | 13-Sep-25 A | 0
A15600 | Cable Block Diagram_IFA |  |  | 14-Aug-25 A | 20-Aug-25 A | 0
A15620 | Cable Block Diagram_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
A47850 | Cable Block Diagram_RCA |  |  | 21-Aug-25 A | 01-Sep-25 A | 0
Process & Pneumatic Hookup Drawings |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A15630 | Process & Pneumatic Hookup Drawings_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A47860 | Process & Pneumatic Hookup Drawings_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A47870 | Process & Pneumatic Hookup Drawings_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A47880 | Process & Pneumatic Hookup Drawings_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A47890 | Process & Pneumatic Hookup Drawings_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Junction Box Schedule |  | 2025-11-11 | 2027-01-20 | 26-May-25 A | 2025-11-11 | 37
A15680 | Junction Box Schedule_IFR |  |  | 26-May-25 A | 07-Jul-25 A | 0
A47900 | Junction Box Schedule_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A47910 | Junction Box Schedule_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A47920 | Junction Box Schedule_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A47930 | Junction Box Schedule_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Instrument Cable Schedule |  | 2025-11-18 | 2026-06-08 | 14-Jul-25 A | 2025-11-18 | 43
A47940 | Instrument Cable Schedule_IFR | 2025-09-26 | 2026-04-16 | 14-Jul-25 A | 2025-09-26 | 6
A47950 | Instrument Cable Schedule_RCC | 2025-10-20 | 2026-05-08 | 2025-09-26 | 2025-10-20 | 16
A47960 | Instrument Cable Schedule_IFA | 2025-10-23 | 2026-05-13 | 2025-10-20 | 2025-10-23 | 3
A47970 | Instrument Cable Schedule_RCA | 2025-11-14 | 2026-06-04 | 2025-10-23 | 2025-11-14 | 16
A47980 | Instrument Cable Schedule_IFD/IFC | 2025-11-18 | 2026-06-08 | 2025-11-14 | 2025-11-18 | 2
SIS Building Equipment Layout |  |  |  | 08-Apr-25 A | 27-Jun-25 A | 0
A48040 | SIS Building Equipment Layout_IFR |  |  | 08-Apr-25 A | 29-Apr-25 A | 0
A48050 | SIS Building Equipment Layout_RCC |  |  | 30-Apr-25 A | 30-May-25 A | 0
A48060 | SIS Building Equipment Layout_IFA |  |  | 02-Jun-25 A | 06-Jun-25 A | 0
A48070 | SIS Building Equipment Layout_RCA |  |  | 09-Jun-25 A | 20-Jun-25 A | 0
A48080 | SIS Building Equipment Layout_IFD/IFC |  |  | 23-Jun-25 A | 27-Jun-25 A | 0
Instrument & JB Wiring Diagram |  | 2025-12-11 | 2026-06-08 | 2025-10-13 | 2025-12-11 | 43
A47990 | Instrument & JB wiring Diagram_IFR | 2025-10-21 | 2026-04-16 | 2025-10-13 | 2025-10-21 | 6
A48000 | Instrument & JB wiring Diagram_RCC | 2025-11-12 | 2026-05-08 | 2025-10-21 | 2025-11-12 | 16
A48010 | Instrument & JB wiring Diagram_IFA | 2025-11-17 | 2026-05-13 | 2025-11-12 | 2025-11-17 | 3
A48020 | Instrument & JB wiring Diagram_RCA | 2025-12-09 | 2026-06-04 | 2025-11-17 | 2025-12-09 | 16
A48030 | Instrument & JB wiring Diagram_IFD/IFC | 2025-12-11 | 2026-06-08 | 2025-12-09 | 2025-12-11 | 2
Instrument Loop Diagram |  | 2025-12-11 | 2026-03-05 | 2025-10-13 | 2025-12-11 | 43
A16080 | Instrument Loop Diagram_IFR | 2025-10-21 | 2026-01-13 | 2025-10-13 | 2025-10-21 | 6
A16100 | Instrument Loop Diagram_IFA | 2025-11-17 | 2026-02-09 | 2025-11-12 | 2025-11-17 | 3
A16110 | Instrument Loop Diagram_RCA | 2025-12-09 | 2026-03-02 | 2025-11-17 | 2025-12-09 | 16
A16120 | Instrument Loop Diagram_IFD/IFC | 2025-12-11 | 2026-03-05 | 2025-12-09 | 2025-12-11 | 2
A48140 | Instrument Loop Diagram_RCC | 2025-11-12 | 2026-02-03 | 2025-10-21 | 2025-11-12 | 16
Instrument Location Layout |  | 2026-01-07 | 2026-06-08 | 2025-11-10 | 2026-01-07 | 43
A15900 | Instrument Location Layout_IFA | 2025-12-12 | 2026-05-13 | 2025-12-09 | 2025-12-12 | 3
A15920 | Instrument Location Layout_IFD/IFC | 2026-01-07 | 2026-06-08 | 2026-01-05 | 2026-01-07 | 2
A48090 | Instrument Location Layout_IFR | 2025-11-17 | 2026-04-16 | 2025-11-10 | 2025-11-17 | 6
A48100 | Instrument Location Layout_RCC | 2025-12-09 | 2026-05-08 | 2025-11-17 | 2025-12-09 | 16
A48110 | Instrument Location Layout_RCA | 2026-01-05 | 2026-06-04 | 2025-12-12 | 2026-01-05 | 16
Instrument Cable & trench routing layout |  | 2026-01-07 | 2026-06-08 | 2025-11-10 | 2026-01-07 | 43
A15930 | Instrument Cable & trench routing layout_IFR | 2025-11-17 | 2026-04-16 | 2025-11-10 | 2025-11-17 | 6
A15940 | Instrument Cable & trench routing layout_RCC | 2025-12-09 | 2026-05-08 | 2025-11-17 | 2025-12-09 | 16
A15950 | Instrument Cable & trench routing layout_IFA | 2025-12-12 | 2026-05-13 | 2025-12-09 | 2025-12-12 | 3
A15960 | Instrument Cable & trench routing layout_RCA | 2026-01-05 | 2026-06-04 | 2025-12-12 | 2026-01-05 | 16
A48120 | Instrument Cable & trench routing layout_IFD/IFC | 2026-01-07 | 2026-06-08 | 2026-01-05 | 2026-01-07 | 2
MCT Installation Drawing |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A15980 | MCT Installation Drawing_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A15990 | MCT Installation Drawing_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A16000 | MCT Installation Drawing_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A16010 | MCT Installation Drawing_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A16020 | MCT Installation Drawing_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Instrumentation & Control Material Take Off |  | 2025-10-30 | 2027-01-20 | 2025-09-26 | 2025-10-30 | 24
A16040 | Instrumentation & Control Material Take Off_RCC | 2025-10-27 | 2027-01-18 | 2025-10-06 | 2025-10-27 | 16
A16070 | Instrumentation & Control Material Take Off_IFD/IFC | 2025-10-30 | 2027-01-20 | 2025-10-28 | 2025-10-30 | 2
A48130 | Instrumentation & Control Material Take Off_IFR | 2025-10-06 | 2026-03-20 | 2025-09-26 | 2025-10-06 | 6
SPI |  | 2025-11-11 | 2027-01-20 | 25-Mar-25 A | 2025-11-11 | 37
SPI Execution Philoshpy |  | 2025-11-11 | 2027-01-20 | 25-Mar-25 A | 2025-11-11 | 37
A28050 | SPI Execution Philoshpy_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
A55560 | SPI Execution Philoshpy_IFR |  |  | 25-Mar-25 A | 28-Apr-25 A | 0
A55570 | SPI Execution Philoshpy_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A55580 | SPI Execution Philoshpy_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A55590 | SPI Execution Philoshpy_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
SPI Extraction Procedure |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A28060 | SPI Extraction Procedure_IFR |  |  | 01-Jul-25 A | 12-Jul-25 A | 0
A55600 | SPI Extraction Procedure_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A55610 | SPI Extraction Procedure_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A55620 | SPI Extraction Procedure_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A55630 | SPI Extraction Procedure_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Civil/Structural/Architectural |  | 2026-01-19 | 2027-01-20 | 16-Jan-25 A | 2026-01-19 | 87
Structure & Foundation design - Piperack & other pipe supports |  | 2026-01-19 | 2027-01-20 | 21-Apr-25 A | 2026-01-19 | 87
Structural GA, Section and Details - Pipe Rack SR8001 |  |  |  | 02-Jun-25 A | 08-Aug-25 A | 0
A18000 | Structural GA, Section and Details - Pipe Rack SR8001_IFA |  |  | 07-Jul-25 A | 18-Jul-25 A | 0
A48510 | Structural GA, Section and Details - Pipe Rack SR8001_IFR |  |  | 02-Jun-25 A | 20-Jun-25 A | 0
A48520 | Structural GA, Section and Details - Pipe Rack SR8001_RCC |  |  | 23-Jun-25 A | 04-Jul-25 A | 0
A48530 | Structural GA, Section and Details - Pipe Rack SR8001_RCA |  |  | 21-Jul-25 A | 01-Aug-25 A | 0
A48540 | Structural GA, Section and Details - Pipe Rack SR8001_IFD/IFC |  |  | 04-Aug-25 A | 08-Aug-25 A | 0
Design Calculation Report for Structural Steel - Pipe Rack SR8001 |  |  |  | 02-Jun-25 A | 01-Aug-25 A | 0
A18050 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFA |  |  | 30-Jun-25 A | 11-Jul-25 A | 0
A18060 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCA |  |  | 14-Jul-25 A | 25-Jul-25 A | 0
A18070 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFD/IFC |  |  | 28-Jul-25 A | 01-Aug-25 A | 0
A48550 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_IFR |  |  | 02-Jun-25 A | 13-Jun-25 A | 0
A48560 | Design Calculation Report for Structural Steel - Pipe Rack SR8001_RCC |  |  | 16-Jun-25 A | 27-Jun-25 A | 0
Foundation layout, Section and Details - Pipe Rack SR8001 |  | 2025-11-11 | 2026-01-05 | 25-Jun-25 A | 2025-11-11 | 37
A18110 | Foundation layout, Section and Details - Pipe Rack SR8001_RCA | 2025-11-06 | 2026-01-01 | 2025-10-16 | 2025-11-06 | 16
A18120 | Foundation layout, Section and Details - Pipe Rack SR8001_IFD/IFC | 2025-11-11 | 2026-01-05 | 2025-11-06 | 2025-11-11 | 2
A48570 | Foundation layout, Section and Details - Pipe Rack SR8001_IFR |  |  | 25-Jun-25 A | 05-Jul-25 A | 0
A48580 | Foundation layout, Section and Details - Pipe Rack SR8001_RCC | 2025-10-10 | 2025-12-05 | 2025-09-19 | 2025-10-10 | 16
A48590 | Foundation layout, Section and Details - Pipe Rack SR8001_IFA | 2025-10-16 | 2025-12-10 | 2025-10-10 | 2025-10-16 | 3
Design Calculation Report for Foundations - Pipe Rack SR8001 |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A18130 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFR |  |  | 01-Jul-25 A | 07-Jul-25 A | 0
A18170 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
A48600 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A48610 | Design Calculation Report for Foundations - Pipe Rack SR8001_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A48620 | Design Calculation Report for Foundations - Pipe Rack SR8001_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
Structural GA, Section and Details - Pipe Rack 13-I-08001 |  |  |  | 23-Jun-25 A | 29-Aug-25 A | 0
A18180 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFR |  |  | 23-Jun-25 A | 04-Jul-25 A | 0
A18190 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCC |  |  | 07-Jul-25 A | 18-Jul-25 A | 0
A48630 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFA |  |  | 21-Jul-25 A | 01-Aug-25 A | 0
A48640 | Structural GA, Section and Details - Pipe Rack 13-I-08001_RCA |  |  | 04-Aug-25 A | 22-Aug-25 A | 0
A48650 | Structural GA, Section and Details - Pipe Rack 13-I-08001_IFD/IFC |  |  | 25-Aug-25 A | 29-Aug-25 A | 0
Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001 |  |  |  | 07-Jul-25 A | 12-Sep-25 A | 0
A18230 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFR |  |  | 07-Jul-25 A | 18-Jul-25 A | 0
A18240 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCC |  |  | 21-Jul-25 A | 08-Aug-25 A | 0
A18250 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFA |  |  | 11-Aug-25 A | 19-Aug-25 A | 0
A48660 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_RCA |  |  | 20-Aug-25 A | 05-Sep-25 A | 0
A48670 | Design Calculation Report for Structural Steel - Pipe Rack 13-I-08001_IFD/IFC |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
Foundation layout, Section and Details - Pipe Rack 13-I-08001 |  | 2025-11-11 | 2026-01-05 | 30-Jun-25 A | 2025-11-11 | 37
A18290 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCC | 2025-10-10 | 2025-12-05 | 2025-09-19 | 2025-10-10 | 16
A18300 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFA | 2025-10-16 | 2025-12-10 | 2025-10-10 | 2025-10-16 | 3
A18310 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_RCA | 2025-11-06 | 2026-01-01 | 2025-10-16 | 2025-11-06 | 16
A48680 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFR |  |  | 30-Jun-25 A | 15-Jul-25 A | 0
A48690 | Foundation layout, Section and Details - Pipe Rack 13-I-08001_IFD/IFC | 2025-11-11 | 2026-01-05 | 2025-11-06 | 2025-11-11 | 2
Design Calculation Report for Foundations - Pipe Rack 13-I-08001 |  | 2025-11-11 | 2026-01-05 | 02-Jul-25 A | 2025-11-11 | 37
A18350 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFA | 2025-10-16 | 2025-12-10 | 2025-10-10 | 2025-10-16 | 3
A48700 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFR |  |  | 02-Jul-25 A | 18-Jul-25 A | 0
A48710 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCC | 2025-10-10 | 2025-12-05 | 2025-09-19 | 2025-10-10 | 16
A48720 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_RCA | 2025-11-06 | 2026-01-01 | 2025-10-16 | 2025-11-06 | 16
A48730 | Design Calculation Report for Foundations - Pipe Rack 13-I-08001_IFD/IFC | 2025-11-11 | 2026-01-05 | 2025-11-06 | 2025-11-11 | 2
Structral steel GA and details Field Supports SF8200 |  | 2026-01-06 | 2026-06-24 | 03-Jul-25 A | 2026-01-06 | 78
A20980 | Structral steel GA and details Field Supports SF8200_IFR |  |  | 03-Jul-25 A | 20-Jul-25 A | 0
A20990 | Structral steel GA and details Field Supports SF8200_RCC | 2025-10-10 | 2026-05-26 | 2025-09-19 | 2025-10-10 | 16
A21000 | Structral steel GA and details Field Supports SF8200_IFA | 2025-10-16 | 2026-05-29 | 2025-10-10 | 2025-10-16 | 3
A21010 | Structral steel GA and details Field Supports SF8200_RCA | 2025-11-06 | 2026-06-22 | 2025-10-16 | 2025-11-06 | 16
A21020 | Structral steel GA and details Field Supports SF8200_IFD/IFC | 2026-01-06 | 2026-06-24 | 2026-01-02 | 2026-01-06 | 2
Design Calculation Report for structural steel Field Supports SF8200 |  | 2026-01-06 | 2026-06-15 | 19-Aug-25 A | 2026-01-06 | 78
A21070 | Design Calculation Report for structural steel Field Supports SF8200_IFD/IFC | 2026-01-06 | 2026-06-15 | 2026-01-02 | 2026-01-06 | 2
A49960 | Design Calculation Report for structural steel Field Supports SF8200_IFR |  |  | 19-Aug-25 A | 25-Aug-25 A | 0
A49970 | Design Calculation Report for structural steel Field Supports SF8200_RCC | 2025-10-10 | 2026-05-12 | 2025-09-19 | 2025-10-10 | 16
A49980 | Design Calculation Report for structural steel Field Supports SF8200_IFA | 2025-10-16 | 2026-05-15 | 2025-10-10 | 2025-10-16 | 3
A49990 | Design Calculation Report for structural steel Field Supports SF8200_RCA | 2025-11-06 | 2026-06-11 | 2025-10-16 | 2025-11-06 | 16
Foundation Layout, Section and details Field Supports SF8200 |  | 2026-01-08 | 2027-01-20 | 2025-09-19 | 2026-01-08 | 80
A21080 | Foundation Layout, Section and details Field Supports SF8200_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A21090 | Foundation Layout, Section and details Field Supports SF8200_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A21100 | Foundation Layout, Section and details Field Supports SF8200_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A50000 | Foundation Layout, Section and details Field Supports SF8200_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A50010 | Foundation Layout, Section and details Field Supports SF8200_IFD/IFC | 2026-01-08 | 2027-01-20 | 2026-01-06 | 2026-01-08 | 2
Design Calculation Report for Foundations Field Supports SF8200 |  | 2026-01-08 | 2027-01-20 | 2025-09-19 | 2026-01-08 | 80
A21150 | Design Calculation Report for Foundations Field Supports SF8200_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A21160 | Design Calculation Report for Foundations Field Supports SF8200_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A21170 | Design Calculation Report for Foundations Field Supports SF8200_IFD/IFC | 2026-01-08 | 2027-01-20 | 2026-01-06 | 2026-01-08 | 2
A50020 | Design Calculation Report for Foundations Field Supports SF8200_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A50030 | Design Calculation Report for Foundations Field Supports SF8200_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
Structural GA and Details, Field supports in CA37 |  | 2026-01-08 | 2026-06-18 | 2025-09-19 | 2026-01-08 | 80
A21900 | Structural GA and Details, Field supports in CA37_IFA | 2025-10-23 | 2026-05-20 | 2025-10-20 | 2025-10-23 | 3
A50430 | Structural GA and Details, Field supports in CA37_IFR | 2025-09-26 | 2026-04-17 | 2025-09-19 | 2025-09-26 | 6
A50440 | Structural GA and Details, Field supports in CA37_RCC | 2025-10-20 | 2026-05-15 | 2025-09-26 | 2025-10-20 | 16
A50450 | Structural GA and Details, Field supports in CA37_RCA | 2025-11-14 | 2026-06-15 | 2025-10-23 | 2025-11-14 | 16
A50460 | Structural GA and Details, Field supports in CA37_IFD/IFC | 2026-01-08 | 2026-06-18 | 2026-01-06 | 2026-01-08 | 2
Design Calculation report of structural steel Field supports CA37 |  | 2026-01-08 | 2026-06-18 | 2025-09-19 | 2026-01-08 | 80
A21990 | Design Calculation report of structural steel Field supports CA37_RCC | 2025-10-20 | 2026-05-15 | 2025-09-26 | 2025-10-20 | 16
A22020 | Design Calculation report of structural steel Field supports CA37_IFD/IFC | 2026-01-08 | 2026-06-18 | 2026-01-06 | 2026-01-08 | 2
A50500 | Design Calculation report of structural steel Field supports CA37_IFR | 2025-09-26 | 2026-04-17 | 2025-09-19 | 2025-09-26 | 6
A50510 | Design Calculation report of structural steel Field supports CA37_IFA | 2025-10-23 | 2026-05-20 | 2025-10-20 | 2025-10-23 | 3
A50520 | Design Calculation report of structural steel Field supports CA37_RCA | 2025-11-14 | 2026-06-15 | 2025-10-23 | 2025-11-14 | 16
Design Calculation report of Foundations Field supports CA37 |  | 2026-01-13 | 2027-01-20 | 2025-09-26 | 2026-01-13 | 77
A22060 | Design Calculation report of Foundations Field supports CA37_RCA | 2025-11-24 | 2027-01-18 | 2025-10-31 | 2025-11-24 | 16
A50530 | Design Calculation report of Foundations Field supports CA37_IFR | 2025-10-06 | 2026-11-30 | 2025-09-26 | 2025-10-06 | 6
A50540 | Design Calculation report of Foundations Field supports CA37_RCC | 2025-10-27 | 2026-12-22 | 2025-10-06 | 2025-10-27 | 16
A50550 | Design Calculation report of Foundations Field supports CA37_IFA | 2025-10-31 | 2026-12-25 | 2025-10-28 | 2025-10-31 | 3
A50560 | Design Calculation report of Foundations Field supports CA37_IFD/IFC | 2026-01-13 | 2027-01-20 | 2026-01-08 | 2026-01-13 | 2
Foundation layout and details, Field supports in CA37 |  | 2026-01-13 | 2027-01-20 | 2025-09-26 | 2026-01-13 | 77
A21950 | Foundation layout and details, Field supports in CA37_IFA | 2025-10-31 | 2026-12-25 | 2025-10-28 | 2025-10-31 | 3
A21960 | Foundation layout and details, Field supports in CA37_RCA | 2025-11-24 | 2027-01-18 | 2025-10-31 | 2025-11-24 | 16
A50470 | Foundation layout and details, Field supports in CA37_IFR | 2025-10-06 | 2026-11-30 | 2025-09-26 | 2025-10-06 | 6
A50480 | Foundation layout and details, Field supports in CA37_RCC | 2025-10-27 | 2026-12-22 | 2025-10-06 | 2025-10-27 | 16
A50490 | Foundation layout and details, Field supports in CA37_IFD/IFC | 2026-01-13 | 2027-01-20 | 2026-01-08 | 2026-01-13 | 2
Structural GA, Section and Details - Pipe Bridge SR81 |  |  |  | 23-Jun-25 A | 14-Aug-25 A | 0
A18390 | Structural GA, Section and Details - Pipe Bridge SR81_RCC |  |  | 03-Jul-25 A | 18-Jul-25 A | 0
A18400 | Structural GA, Section and Details - Pipe Bridge SR81_IFA |  |  | 21-Jul-25 A | 25-Jul-25 A | 0
A18410 | Structural GA, Section and Details - Pipe Bridge SR81_RCA |  |  | 28-Jul-25 A | 08-Aug-25 A | 0
A48740 | Structural GA, Section and Details - Pipe Bridge SR81_IFR |  |  | 23-Jun-25 A | 02-Jul-25 A | 0
A48750 | Structural GA, Section and Details - Pipe Bridge SR81_IFD/IFC |  |  | 11-Aug-25 A | 14-Aug-25 A | 0
Design Calculation Report for Structural Steel - Pipe Bridge SR81 |  |  |  | 03-Jul-25 A | 12-Sep-25 A | 0
A18440 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCC |  |  | 21-Jul-25 A | 08-Aug-25 A | 0
A18450 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFA |  |  | 11-Aug-25 A | 15-Aug-25 A | 0
A18470 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFD/IFC |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
A48760 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_IFR |  |  | 03-Jul-25 A | 20-Jul-25 A | 0
A48770 | Design Calculation Report for Structural Steel - Pipe Bridge SR81_RCA |  |  | 18-Aug-25 A | 05-Sep-25 A | 0
Design Calculation Report for Foundations - Pipe Bridge SR81 |  |  |  | 21-Apr-25 A | 17-Jul-25 A | 0
A48830 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFR |  |  | 21-Apr-25 A | 12-May-25 A | 0
A48840 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCC |  |  | 13-May-25 A | 19-May-25 A | 0
A48850 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFA |  |  | 20-May-25 A | 20-Jun-25 A | 0
A48860 | Design Calculation Report for Foundations - Pipe Bridge SR81_RCA |  |  | 23-Jun-25 A | 11-Jul-25 A | 0
A48870 | Design Calculation Report for Foundations - Pipe Bridge SR81_IFD/IFC |  |  | 14-Jul-25 A | 17-Jul-25 A | 0
Foundation layout, Section and Details - Pipe Bridge SR81 |  | 2025-09-23 | 2026-01-05 | 21-Apr-25 A | 2025-09-23 | 2
A48780 | Foundation layout, Section and Details - Pipe Bridge SR81_IFR |  |  | 21-Apr-25 A | 12-May-25 A | 0
A48790 | Foundation layout, Section and Details - Pipe Bridge SR81_RCC |  |  | 13-May-25 A | 19-May-25 A | 0
A48800 | Foundation layout, Section and Details - Pipe Bridge SR81_IFA |  |  | 20-May-25 A | 20-Jun-25 A | 0
A48810 | Foundation layout, Section and Details - Pipe Bridge SR81_RCA |  |  | 21-Jun-25 A | 06-Sep-25 A | 0
A48820 | Foundation layout, Section and Details - Pipe Bridge SR81_IFD/IFC | 2025-09-23 | 2026-01-05 | 2025-09-19 | 2025-09-23 | 2
Structral steel GA and details Field Supports SF8300 |  | 2026-01-13 | 2026-06-22 | 2025-09-26 | 2026-01-13 | 77
A21180 | Structral steel GA and details Field Supports SF8300_IFR | 2025-10-06 | 2026-04-24 | 2025-09-26 | 2025-10-06 | 6
A50040 | Structral steel GA and details Field Supports SF8300_RCC | 2025-10-27 | 2026-05-20 | 2025-10-06 | 2025-10-27 | 16
A50050 | Structral steel GA and details Field Supports SF8300_IFA | 2025-10-31 | 2026-05-26 | 2025-10-28 | 2025-10-31 | 3
A50060 | Structral steel GA and details Field Supports SF8300_RCA | 2025-11-24 | 2026-06-18 | 2025-10-31 | 2025-11-24 | 16
A50070 | Structral steel GA and details Field Supports SF8300_IFD/IFC | 2026-01-13 | 2026-06-22 | 2026-01-08 | 2026-01-13 | 2
Design Calculation Report for structural steel Field Supports SF8300 |  | 2026-01-13 | 2027-01-20 | 2025-09-26 | 2026-01-13 | 77
A21230 | Design Calculation Report for structural steel Field Supports SF8300_IFR | 2025-10-06 | 2026-11-30 | 2025-09-26 | 2025-10-06 | 6
A21240 | Design Calculation Report for structural steel Field Supports SF8300_RCC | 2025-10-27 | 2026-12-22 | 2025-10-06 | 2025-10-27 | 16
A21250 | Design Calculation Report for structural steel Field Supports SF8300_IFA | 2025-10-31 | 2026-12-25 | 2025-10-28 | 2025-10-31 | 3
A21260 | Design Calculation Report for structural steel Field Supports SF8300_RCA | 2025-11-24 | 2027-01-18 | 2025-10-31 | 2025-11-24 | 16
A50080 | Design Calculation Report for structural steel Field Supports SF8300_IFD/IFC | 2026-01-13 | 2027-01-20 | 2026-01-08 | 2026-01-13 | 2
Design Calculation Report for Foundations Field Supports SF8300 |  | 2026-01-15 | 2027-01-20 | 2025-10-06 | 2026-01-15 | 73
A21330 | Design Calculation Report for Foundations Field Supports SF8300_IFR | 2025-10-13 | 2026-11-30 | 2025-10-06 | 2025-10-13 | 6
A21340 | Design Calculation Report for Foundations Field Supports SF8300_RCC | 2025-11-04 | 2026-12-22 | 2025-10-13 | 2025-11-04 | 16
A50120 | Design Calculation Report for Foundations Field Supports SF8300_IFA | 2025-11-07 | 2026-12-25 | 2025-11-04 | 2025-11-07 | 3
A50130 | Design Calculation Report for Foundations Field Supports SF8300_RCA | 2025-12-01 | 2027-01-18 | 2025-11-10 | 2025-12-01 | 16
A50140 | Design Calculation Report for Foundations Field Supports SF8300_IFD/IFC | 2026-01-15 | 2027-01-20 | 2026-01-13 | 2026-01-15 | 2
Foundation Layout, Section and details Field Supports SF8300 |  | 2026-01-15 | 2027-01-20 | 2025-10-06 | 2026-01-15 | 73
A21310 | Foundation Layout, Section and details Field Supports SF8300_RCA | 2025-12-01 | 2027-01-18 | 2025-11-10 | 2025-12-01 | 16
A21320 | Foundation Layout, Section and details Field Supports SF8300_IFD/IFC | 2026-01-15 | 2027-01-20 | 2026-01-13 | 2026-01-15 | 2
A50090 | Foundation Layout, Section and details Field Supports SF8300_IFR | 2025-10-13 | 2026-11-30 | 2025-10-06 | 2025-10-13 | 6
A50100 | Foundation Layout, Section and details Field Supports SF8300_RCC | 2025-11-04 | 2026-12-22 | 2025-10-13 | 2025-11-04 | 16
A50110 | Foundation Layout, Section and details Field Supports SF8300_IFA | 2025-11-07 | 2026-12-25 | 2025-11-04 | 2025-11-07 | 3
Structral steel GA and details Field Supports SF8100 |  | 2026-01-15 | 2026-06-24 | 2025-10-06 | 2026-01-15 | 73
A20780 | Structral steel GA and details Field Supports SF8100_IFR | 2025-10-13 | 2026-05-04 | 2025-10-06 | 2025-10-13 | 6
A49900 | Structral steel GA and details Field Supports SF8100_RCC | 2025-11-04 | 2026-05-26 | 2025-10-13 | 2025-11-04 | 16
A49910 | Structral steel GA and details Field Supports SF8100_IFA | 2025-11-07 | 2026-05-29 | 2025-11-04 | 2025-11-07 | 3
A49920 | Structral steel GA and details Field Supports SF8100_RCA | 2025-12-01 | 2026-06-22 | 2025-11-10 | 2025-12-01 | 16
A49930 | Structral steel GA and details Field Supports SF8100_IFD/IFC | 2026-01-15 | 2026-06-24 | 2026-01-13 | 2026-01-15 | 2
Design Calculation Report for structural steel Field Supports SF8100 |  | 2026-01-15 | 2027-01-18 | 2025-10-06 | 2026-01-15 | 73
A20830 | Design Calculation Report for structural steel Field Supports SF8100_IFR | 2025-10-13 | 2026-11-23 | 2025-10-06 | 2025-10-13 | 6
A20840 | Design Calculation Report for structural steel Field Supports SF8100_RCC | 2025-11-04 | 2026-12-17 | 2025-10-13 | 2025-11-04 | 16
A20850 | Design Calculation Report for structural steel Field Supports SF8100_IFA | 2025-11-07 | 2026-12-22 | 2025-11-04 | 2025-11-07 | 3
A20860 | Design Calculation Report for structural steel Field Supports SF8100_RCA | 2025-12-01 | 2027-01-14 | 2025-11-10 | 2025-12-01 | 16
A20870 | Design Calculation Report for structural steel Field Supports SF8100_IFD/IFC | 2026-01-15 | 2027-01-18 | 2026-01-13 | 2026-01-15 | 2
Design Calculation Report for Foundations Field Supports SF8100 |  | 2026-01-19 | 2027-01-20 | 2025-10-13 | 2026-01-19 | 70
A20930 | Design Calculation Report for Foundations Field Supports SF8100_IFR | 2025-10-21 | 2026-11-30 | 2025-10-13 | 2025-10-21 | 6
A20940 | Design Calculation Report for Foundations Field Supports SF8100_RCC | 2025-11-12 | 2026-12-22 | 2025-10-21 | 2025-11-12 | 16
A20970 | Design Calculation Report for Foundations Field Supports SF8100_IFD/IFC | 2026-01-19 | 2027-01-20 | 2026-01-15 | 2026-01-19 | 2
A49940 | Design Calculation Report for Foundations Field Supports SF8100_IFA | 2025-11-17 | 2026-12-25 | 2025-11-12 | 2025-11-17 | 3
A49950 | Design Calculation Report for Foundations Field Supports SF8100_RCA | 2025-12-09 | 2027-01-18 | 2025-11-17 | 2025-12-09 | 16
Foundation Layout, Section and details Field Supports SF8100 |  | 2026-01-19 | 2027-01-20 | 2025-10-13 | 2026-01-19 | 70
A20880 | Foundation Layout, Section and details Field Supports SF8100_IFR | 2025-10-21 | 2026-11-30 | 2025-10-13 | 2025-10-21 | 6
A20890 | Foundation Layout, Section and details Field Supports SF8100_RCC | 2025-11-12 | 2026-12-22 | 2025-10-21 | 2025-11-12 | 16
A20900 | Foundation Layout, Section and details Field Supports SF8100_IFA | 2025-11-17 | 2026-12-25 | 2025-11-12 | 2025-11-17 | 3
A20910 | Foundation Layout, Section and details Field Supports SF8100_RCA | 2025-12-09 | 2027-01-18 | 2025-11-17 | 2025-12-09 | 16
A20920 | Foundation Layout, Section and details Field Supports SF8100_IFD/IFC | 2026-01-19 | 2027-01-20 | 2026-01-15 | 2026-01-19 | 2
Adequacy check of Pipe rack SR70 |  | 2025-12-24 | 2026-06-15 | 2025-10-24 | 2025-12-24 | 43
A22130 | Adequacy check of Pipe rack SR70_IFR | 2025-11-03 | 2026-04-09 | 2025-10-24 | 2025-11-03 | 6
A22140 | Adequacy check of Pipe rack SR70_RCC | 2025-11-25 | 2026-05-12 | 2025-11-03 | 2025-11-25 | 16
A50610 | Adequacy check of Pipe rack SR70_IFA | 2025-11-28 | 2026-05-15 | 2025-11-25 | 2025-11-28 | 3
A50620 | Adequacy check of Pipe rack SR70_RCA | 2025-12-22 | 2026-06-10 | 2025-11-28 | 2025-12-22 | 16
A50630 | Adequacy check of Pipe rack SR70_IFD/IFC | 2025-12-24 | 2026-06-15 | 2025-12-22 | 2025-12-24 | 2
Structural GA and Details, Pipe Rack SR70 |  | 2026-01-01 | 2026-06-17 | 2025-11-03 | 2026-01-01 | 43
A22120 | Structural GA and Details, Pipe Rack SR70_IFD/IFC | 2026-01-01 | 2026-06-17 | 2025-12-30 | 2026-01-01 | 2
A50570 | Structural GA and Details, Pipe Rack SR70_IFR | 2025-11-11 | 2026-04-27 | 2025-11-03 | 2025-11-11 | 6
A50580 | Structural GA and Details, Pipe Rack SR70_RCC | 2025-12-02 | 2026-05-19 | 2025-11-11 | 2025-12-02 | 16
A50590 | Structural GA and Details, Pipe Rack SR70_IFA | 2025-12-08 | 2026-05-22 | 2025-12-02 | 2025-12-08 | 3
A50600 | Structural GA and Details, Pipe Rack SR70_RCA | 2025-12-29 | 2026-06-15 | 2025-12-08 | 2025-12-29 | 16
Adequacy check of Pipe rack SR73 |  | 2026-01-01 | 2026-06-18 | 2025-11-03 | 2026-01-01 | 43
A22240 | Adequacy check of Pipe rack SR73_RCC | 2025-12-02 | 2026-05-15 | 2025-11-11 | 2025-12-02 | 16
A22250 | Adequacy check of Pipe rack SR73_IFA | 2025-12-08 | 2026-05-20 | 2025-12-02 | 2025-12-08 | 3
A22260 | Adequacy check of Pipe rack SR73_RCA | 2025-12-29 | 2026-06-15 | 2025-12-08 | 2025-12-29 | 16
A50660 | Adequacy check of Pipe rack SR73_IFR | 2025-11-11 | 2026-04-17 | 2025-11-03 | 2025-11-11 | 6
A50670 | Adequacy check of Pipe rack SR73_IFD/IFC | 2026-01-01 | 2026-06-18 | 2025-12-30 | 2026-01-01 | 2
Structural GA and Details, Pipe Rack SR73 |  | 2026-01-16 | 2026-06-24 | 2025-11-18 | 2026-01-16 | 43
A22180 | Structural GA and Details, Pipe Rack SR73_IFR | 2025-11-26 | 2026-05-04 | 2025-11-18 | 2025-11-26 | 6
A22190 | Structural GA and Details, Pipe Rack SR73_RCC | 2025-12-18 | 2026-05-26 | 2025-11-26 | 2025-12-18 | 16
A22200 | Structural GA and Details, Pipe Rack SR73_IFA | 2025-12-23 | 2026-05-29 | 2025-12-18 | 2025-12-23 | 3
A50640 | Structural GA and Details, Pipe Rack SR73_RCA | 2026-01-14 | 2026-06-22 | 2025-12-23 | 2026-01-14 | 16
A50650 | Structural GA and Details, Pipe Rack SR73_IFD/IFC | 2026-01-16 | 2026-06-24 | 2026-01-14 | 2026-01-16 | 2
Adequacy check of U&O Rack SR37 |  | 2026-01-08 | 2026-06-22 | 2025-11-11 | 2026-01-08 | 43
A22360 | Adequacy check of U&O Rack SR37_RCA | 2026-01-06 | 2026-06-18 | 2025-12-15 | 2026-01-06 | 16
A22370 | Adequacy check of U&O Rack SR37_IFD/IFC | 2026-01-08 | 2026-06-22 | 2026-01-06 | 2026-01-08 | 2
A50700 | Adequacy check of U&O Rack SR37_IFR | 2025-11-18 | 2026-04-24 | 2025-11-11 | 2025-11-18 | 6
A50710 | Adequacy check of U&O Rack SR37_RCC | 2025-12-10 | 2026-05-20 | 2025-11-18 | 2025-12-10 | 16
A50720 | Adequacy check of U&O Rack SR37_IFA | 2025-12-15 | 2026-05-26 | 2025-12-10 | 2025-12-15 | 3
Structural GA and Details, U&O Rack SR37 |  | 2026-01-16 | 2026-06-24 | 2025-11-18 | 2026-01-16 | 43
A22300 | Structural GA and Details, U&O Rack SR37_IFA | 2025-12-23 | 2026-05-29 | 2025-12-18 | 2025-12-23 | 3
A22310 | Structural GA and Details, U&O Rack SR37_RCA | 2026-01-14 | 2026-06-22 | 2025-12-23 | 2026-01-14 | 16
A22320 | Structural GA and Details, U&O Rack SR37_IFD/IFC | 2026-01-16 | 2026-06-24 | 2026-01-14 | 2026-01-16 | 2
A50680 | Structural GA and Details, U&O Rack SR37_IFR | 2025-11-26 | 2026-05-04 | 2025-11-18 | 2025-11-26 | 6
A50690 | Structural GA and Details, U&O Rack SR37_RCC | 2025-12-18 | 2026-05-26 | 2025-11-26 | 2025-12-18 | 16
Structure & Foundation design - Mechanical |  | 2025-11-26 | 2027-01-20 | 10-Apr-25 A | 2025-11-26 | 48
Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor |  | 2025-10-14 | 2026-04-03 | 12-Apr-25 A | 2025-10-14 | 18
A18980 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFR |  |  | 12-Apr-25 A | 03-May-25 A | 0
A18990 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCC |  |  | 04-May-25 A | 10-May-25 A | 0
A19000 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFA |  |  | 11-May-25 A | 21-Jun-25 A | 0
A19010 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 2025-10-10 | 2026-04-01 | 2025-09-19 | 2025-10-10 | 16
A19020 | Foundation Drawing- Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 2025-10-14 | 2026-04-03 | 2025-10-10 | 2025-10-14 | 2
Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor |  | 2025-10-14 | 2027-01-20 | 13-Apr-25 A | 2025-10-14 | 18
A19030 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFR |  |  | 13-Apr-25 A | 03-May-25 A | 0
A19040 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCC |  |  | 04-May-25 A | 10-May-25 A | 0
A19050 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFA |  |  | 11-May-25 A | 21-Jun-25 A | 0
A19060 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A19070 | Design Calculation report for foundation of Lube Oil unit for PSA-2 FeedGas Compressor_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor |  | 2025-11-11 | 2026-04-03 | 26-May-25 A | 2025-11-11 | 37
A19080 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A19090 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCC | 2025-10-10 | 2026-03-05 | 2025-09-19 | 2025-10-10 | 16
A19100 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFA | 2025-10-16 | 2026-03-10 | 2025-10-10 | 2025-10-16 | 3
A49150 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_RCA | 2025-11-06 | 2026-04-01 | 2025-10-16 | 2025-11-06 | 16
A49160 | Foundation Drawing- Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 2025-11-11 | 2026-04-03 | 2025-11-06 | 2025-11-11 | 2
Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor |  | 2025-11-11 | 2027-01-20 | 26-May-25 A | 2025-11-11 | 37
A19140 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A19150 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A19160 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A49170 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A49180 | Design Calculation report for foundation of Lube Oil unit for PSA-2 OffGas Compressor_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Foundation drawing PSA-2 FeedGas Compressor 13-KC-701 |  | 2025-11-11 | 2026-04-03 | 19-Apr-25 A | 2025-11-11 | 37
A18800 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFA | 2025-10-16 | 2026-03-10 | 2025-10-10 | 2025-10-16 | 3
A49020 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFR |  |  | 19-Apr-25 A | 02-Sep-25 A | 0
A49030 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCC | 2025-10-10 | 2026-03-05 | 2025-09-19 | 2025-10-10 | 16
A49040 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_RCA | 2025-11-06 | 2026-04-01 | 2025-10-16 | 2025-11-06 | 16
A49050 | Foundation drawing PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2025-11-11 | 2026-04-03 | 2025-11-06 | 2025-11-11 | 2
Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701 |  | 2025-11-11 | 2027-01-20 | 12-Apr-25 A | 2025-11-11 | 21
A49060 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFR |  |  | 12-Apr-25 A | 27-Jul-25 A | 0
A49070 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCC |  |  | 28-Jul-25 A | 15-Aug-25 A | 0
A49080 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A49090 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A49100 | Design Calculation Report PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Foundation drawing PSA-2 OffGas Compressor 13-KC-702 |  |  |  | 30-Jun-25 A | 05-Sep-25 A | 0
A18880 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFR |  |  | 30-Jun-25 A | 10-Jul-25 A | 0
A49110 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCC |  |  | 11-Jul-25 A | 15-Aug-25 A | 0
A49120 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFA |  |  | 16-Aug-25 A | 22-Aug-25 A | 0
A49130 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_RCA |  |  | 23-Aug-25 A | 29-Aug-25 A | 0
A49140 | Foundation drawing PSA-2 OffGas Compressor 13-KC-702_IFD/IFC |  |  | 30-Aug-25 A | 05-Sep-25 A | 0
Design Calculation Report PSA-2 OffGas Compressor 13-KC-702 |  | 2025-11-26 | 2027-01-20 | 2025-09-19 | 2025-11-26 | 48
A18930 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFR | 2025-10-06 | 2026-11-30 | 2025-09-19 | 2025-10-06 | 11
A18940 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCC | 2025-10-27 | 2026-12-22 | 2025-10-06 | 2025-10-27 | 16
A18950 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFA | 2025-10-31 | 2026-12-25 | 2025-10-28 | 2025-10-31 | 3
A18960 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_RCA | 2025-11-24 | 2027-01-18 | 2025-10-31 | 2025-11-24 | 16
A18970 | Design Calculation Report PSA-2 OffGas Compressor 13-KC-702_IFD/IFC | 2025-11-26 | 2027-01-20 | 2025-11-24 | 2025-11-26 | 2
Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 2025-11-18 | 2026-04-03 | 14-Jul-25 A | 2025-11-18 | 43
A20200 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 2025-10-23 | 2026-03-10 | 2025-10-20 | 2025-10-23 | 3
A20210 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 2025-11-14 | 2026-04-01 | 2025-10-23 | 2025-11-14 | 16
A20220 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2025-11-18 | 2026-04-03 | 2025-11-14 | 2025-11-18 | 2
A49600 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR | 2025-09-26 | 2025-06-02 | 14-Jul-25 A | 2025-09-26 | 6
A49610 | Foundation Drawing PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 2025-10-20 | 2026-03-05 | 2025-09-26 | 2025-10-20 | 16
Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710 |  | 2025-11-18 | 2027-01-20 | 26-May-25 A | 2025-11-18 | 43
A20260 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A20270 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
A49620 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR |  |  | 26-May-25 A | 07-Jul-25 A | 0
A49630 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A49640 | Design Calculation Report for foundation of PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
Foundation drawing for Equipment 50-HE-1410 |  | 2025-10-20 | 2026-04-03 | 02-May-25 A | 2025-10-20 | 21
A50340 | Foundation drawing for Equipment 50-HE-1410_IFR |  |  | 02-May-25 A | 23-May-25 A | 0
A50350 | Foundation drawing for Equipment 50-HE-1410_RCC |  |  | 24-May-25 A | 29-May-25 A | 0
A50360 | Foundation drawing for Equipment 50-HE-1410_IFA | 2025-09-24 | 2026-03-10 | 2025-09-19 | 2025-09-24 | 3
A50370 | Foundation drawing for Equipment 50-HE-1410_RCA | 2025-10-16 | 2026-04-01 | 2025-09-24 | 2025-10-16 | 16
A50380 | Foundation drawing for Equipment 50-HE-1410_IFD/IFC | 2025-10-20 | 2026-04-03 | 2025-10-16 | 2025-10-20 | 2
Design calculation for foundation of Equipment 50-HE-1410 |  | 2025-10-20 | 2027-01-20 | 02-May-25 A | 2025-10-20 | 21
A21870 | Design calculation for foundation of Equipment 50-HE-1410_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
A50390 | Design calculation for foundation of Equipment 50-HE-1410_IFR |  |  | 02-May-25 A | 23-May-25 A | 0
A50400 | Design calculation for foundation of Equipment 50-HE-1410_RCC |  |  | 24-May-25 A | 21-Jun-25 A | 0
A50410 | Design calculation for foundation of Equipment 50-HE-1410_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A50420 | Design calculation for foundation of Equipment 50-HE-1410_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  | 2025-10-14 | 2026-04-03 | 01-May-25 A | 2025-10-14 | 18
A20080 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR |  |  | 01-May-25 A | 15-May-25 A | 0
A20090 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC |  |  | 16-May-25 A | 22-May-25 A | 0
A20100 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA |  |  | 23-May-25 A | 21-Jun-25 A | 0
A49560 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 2025-10-10 | 2026-04-01 | 2025-09-19 | 2025-10-10 | 16
A49570 | Foundation Drawing PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 2025-10-14 | 2026-04-03 | 2025-10-10 | 2025-10-14 | 2
Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708 |  | 2025-10-14 | 2027-01-20 | 28-Apr-25 A | 2025-10-14 | 18
A20140 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCC |  |  | 20-May-25 A | 21-Jun-25 A | 0
A20150 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A20160 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A49580 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFR |  |  | 28-Apr-25 A | 19-May-25 A | 0
A49590 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Interstage Cooler 13-HE-708_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  |  |  | 28-Apr-25 A | 25-Jul-25 A | 0
A19280 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR |  |  | 28-Apr-25 A | 19-May-25 A | 0
A19290 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC |  |  | 20-May-25 A | 21-Jun-25 A | 0
A19300 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A19310 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA |  |  | 30-Jun-25 A | 18-Jul-25 A | 0
A19320 | Foundation Drawing PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC |  |  | 21-Jul-25 A | 25-Jul-25 A | 0
Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704 |  |  |  | 28-Apr-25 A | 08-Sep-25 A | 0
A19330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFR |  |  | 28-Apr-25 A | 03-May-25 A | 0
A19340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCC |  |  | 04-May-25 A | 19-May-25 A | 0
A49240 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFA |  |  | 20-May-25 A | 21-Jun-25 A | 0
A49250 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A49260 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor AfterCooler 13-HE-704_IFD/IFC |  |  | 29-Jun-25 A | 08-Sep-25 A | 0
Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  |  |  | 24-Apr-25 A | 15-Sep-25 A | 0
A19500 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA |  |  | 23-May-25 A | 01-Sep-25 A | 0
A19510 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA |  |  | 02-Sep-25 A | 08-Sep-25 A | 0
A19520 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC |  |  | 09-Sep-25 A | 15-Sep-25 A | 0
A49310 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR |  |  | 24-Apr-25 A | 15-May-25 A | 0
A49320 | Foundation Drawing PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC |  |  | 16-May-25 A | 22-May-25 A | 0
Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703 |  |  |  | 24-Apr-25 A | 15-Sep-25 A | 0
A19560 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCA |  |  | 02-Sep-25 A | 09-Sep-25 A | 0
A19570 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFD/IFC |  |  | 10-Sep-25 A | 15-Sep-25 A | 0
A49330 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFR |  |  | 24-Apr-25 A | 15-May-25 A | 0
A49340 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_RCC |  |  | 16-May-25 A | 22-May-25 A | 0
A49350 | Design Calculation Report for foundation of PSA-2 Feed Gas Compressor Interstage Cooler 13-HE-703_IFA |  |  | 23-May-25 A | 01-Sep-25 A | 0
Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  |  |  | 28-Apr-25 A | 25-Jul-25 A | 0
A19790 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC |  |  | 20-May-25 A | 21-Jun-25 A | 0
A19800 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A19810 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA |  |  | 30-Jun-25 A | 18-Jul-25 A | 0
A19820 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC |  |  | 21-Jul-25 A | 25-Jul-25 A | 0
A49430 | Foundation Drawing PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR |  |  | 28-Apr-25 A | 19-May-25 A | 0
Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709 |  |  |  | 28-Apr-25 A | 15-Sep-25 A | 0
A19830 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFR |  |  | 28-Apr-25 A | 19-May-25 A | 0
A19840 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCC |  |  | 20-May-25 A | 21-Jun-25 A | 0
A19850 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A19860 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_RCA |  |  | 29-Jun-25 A | 08-Sep-25 A | 0
A49440 | Design Calculation Report for foundation of PSA-2 OffGas Compressor AfterCooler 13-HE-709_IFD/IFC |  |  | 09-Sep-25 A | 15-Sep-25 A | 0
Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  |  |  | 16-Apr-25 A | 04-Sep-25 A | 0
A19980 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR |  |  | 16-Apr-25 A | 07-May-25 A | 0
A20020 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC |  |  | 22-Jun-25 A | 04-Sep-25 A | 0
A49500 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC |  |  | 08-May-25 A | 14-May-25 A | 0
A49510 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA |  |  | 15-May-25 A | 03-Jun-25 A | 0
A49520 | Foundation Drawing PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA |  |  | 04-Jun-25 A | 21-Jun-25 A | 0
Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004 |  | 2025-09-23 | 2027-01-20 | 16-Apr-25 A | 2025-09-23 | 2
A20030 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFR |  |  | 16-Apr-25 A | 07-May-25 A | 0
A20040 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCC |  |  | 08-May-25 A | 14-May-25 A | 0
A49530 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFA |  |  | 15-May-25 A | 03-Jun-25 A | 0
A49540 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_RCA |  |  | 04-Jun-25 A | 21-Jun-25 A | 0
A49550 | Design Calculation Report for foundation of PSA-2 OffGas Compressor Discharge Dripleg 13-SP-7004_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Foundation Drawing PSA-2 Slop Drum 70-VV-1415 |  | 2025-10-20 | 2026-03-25 | 24-Apr-25 A | 2025-10-20 | 21
A20280 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFR |  |  | 24-Apr-25 A | 15-May-25 A | 0
A20320 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 2025-10-20 | 2026-03-25 | 2025-10-16 | 2025-10-20 | 2
A49650 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCC |  |  | 16-May-25 A | 22-May-25 A | 0
A49660 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_IFA | 2025-09-24 | 2026-02-27 | 2025-09-19 | 2025-09-24 | 3
A49670 | Foundation Drawing PSA-2 Slop Drum 70-VV-1415_RCA | 2025-10-16 | 2026-03-23 | 2025-09-24 | 2025-10-16 | 16
Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415 |  | 2025-11-11 | 2027-01-20 | 01-Aug-25 A | 2025-11-11 | 37
A20330 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFR |  |  | 01-Aug-25 A | 22-Aug-25 A | 0
A20340 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A49680 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A49690 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A49700 | Design Calculation Report for foundation of PSA-2 Slop Drum 70-VV-1415_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707 |  | 2025-10-14 | 2026-04-03 | 20-Apr-25 A | 2025-10-14 | 18
A19200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFA |  |  | 19-May-25 A | 11-Jun-25 A | 0
A19210 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCA | 2025-10-10 | 2026-04-01 | 2025-09-19 | 2025-10-10 | 16
A19220 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFD/IFC | 2025-10-14 | 2026-04-03 | 2025-10-10 | 2025-10-14 | 2
A49190 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A49200 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Discharge Drum 13-VV-707_RCC |  |  | 12-May-25 A | 18-May-25 A | 0
Design Calculation Report-Foundation of PSA-2 FeedGas Compressor 2ndStage DischargeDrum 13-VV-707 |  | 2025-10-14 | 2027-01-20 | 20-Apr-25 A | 2025-10-14 | 18
A19260 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A19270 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
A49210 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A49220 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_RCC |  |  | 12-May-25 A | 18-May-25 A | 0
A49230 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE DISCHARGE DRUM 13-VV-707_IFA |  |  | 19-May-25 A | 11-Jun-25 A | 0
Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706 |  |  |  | 16-Apr-25 A | 16-Sep-25 A | 0
A19380 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFR |  |  | 16-Apr-25 A | 03-May-25 A | 0
A19390 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCC |  |  | 04-May-25 A | 10-May-25 A | 0
A19400 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFA |  |  | 11-May-25 A | 11-Jun-25 A | 0
A49270 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_RCA |  |  | 12-Jun-25 A | 01-Sep-25 A | 0
A49280 | Foundation Drawing PSA-2 Feed Gas Compressor 2nd Stage Suction Drum 13-VV-706_IFD/IFC |  |  | 02-Sep-25 A | 16-Sep-25 A | 0
Design Calculation Report Foundation of PSA-2 FeedGas Compressor 2ndStage Suction Drum 13-VV-706 |  |  |  | 16-Apr-25 A | 08-Sep-25 A | 0
A19440 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCC |  |  | 04-May-25 A | 10-May-25 A | 0
A19450 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFA |  |  | 11-May-25 A | 11-Jun-25 A | 0
A19460 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_RCA |  |  | 12-Jun-25 A | 21-Jun-25 A | 0
A49290 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFR |  |  | 16-Apr-25 A | 03-May-25 A | 0
A49300 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-706_IFD/IFC |  |  | 22-Jun-25 A | 08-Sep-25 A | 0
Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705 |  | 2025-09-23 | 2026-04-03 | 24-Apr-25 A | 2025-09-23 | 2
A19580 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFR |  |  | 24-Apr-25 A | 15-May-25 A | 0
A19620 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFD/IFC | 2025-09-23 | 2026-04-03 | 2025-09-19 | 2025-09-23 | 2
A49360 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCC |  |  | 16-May-25 A | 22-May-25 A | 0
A49370 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_IFA |  |  | 23-May-25 A | 04-Jun-25 A | 0
A49380 | Foundation Drawing PSA-2 Feed Gas Compressor 1st Stage Suction Drum 13-VV-705_RCA |  |  | 05-Jun-25 A | 21-Jun-25 A | 0
Design Calculation Report Foundation of PSA-2 FeedGas Compressor 1stStage Suction Drum 13-VV-705 |  | 2025-09-23 | 2027-01-20 | 24-Apr-25 A | 2025-09-23 | 2
A19630 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFR |  |  | 24-Apr-25 A | 15-May-25 A | 0
A19640 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCC |  |  | 16-May-25 A | 22-May-25 A | 0
A49390 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFA |  |  | 23-May-25 A | 03-Jun-25 A | 0
A49400 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_RCA |  |  | 04-Jun-25 A | 21-Jun-25 A | 0
A49410 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 FEED GAS COMPRESSOR 1ST STAGE SUCTION DRUM 13-VV-705_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713 |  |  |  | 15-Apr-25 A | 11-Sep-25 A | 0
A19680 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFR |  |  | 15-Apr-25 A | 06-May-25 A | 0
A19690 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCC |  |  | 07-May-25 A | 13-May-25 A | 0
A19700 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFA |  |  | 14-May-25 A | 21-Jun-25 A | 0
A19710 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_RCA |  |  | 22-Jun-25 A | 04-Sep-25 A | 0
A19720 | Foundation Drawing PSA-2 OffGas Compressor 2nd Stage Suction Drum 13-VV-713_IFD/IFC |  |  | 05-Sep-25 A | 11-Sep-25 A | 0
Design Calculation Report Foundation of PSA-2 OffGas Compressor 2ndStage Suction Drum 13-VV-713 |  | 2025-10-14 | 2027-01-20 | 20-Apr-25 A | 2025-10-14 | 18
A19730 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A19740 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCC |  |  | 12-May-25 A | 21-Jun-25 A | 0
A19750 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A19760 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_RCA | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A49420 | DESIGN CALCULATION REPORT FOR FOUNDATION OF PSA-2 OFFGAS COMPRESSOR 2ND STAGE SUCTION DRUM 13-VV-713_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712 |  | 2025-09-23 | 2026-04-03 | 22-Apr-25 A | 2025-09-23 | 2
A19900 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFA |  |  | 30-May-25 A | 21-Jun-25 A | 0
A19910 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCA |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A19920 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2025-09-23 | 2026-04-03 | 2025-09-19 | 2025-09-23 | 2
A49450 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_IFR |  |  | 22-Apr-25 A | 13-May-25 A | 0
A49460 | Foundation Drawing PSA-2 OffGas Buffer Drum 13-VV-712_RCC |  |  | 14-May-25 A | 29-May-25 A | 0
Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712 |  | 2025-09-23 | 2027-01-20 | 22-Apr-25 A | 2025-09-23 | 2
A19960 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCA |  |  | 22-Jun-25 A | 06-Sep-25 A | 0
A19970 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
A49470 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFR |  |  | 22-Apr-25 A | 13-May-25 A | 0
A49480 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_RCC |  |  | 14-May-25 A | 03-Jun-25 A | 0
A49490 | Design Calculation Report for foundation of PSA-2 OffGas Buffer Drum 13-VV-712_IFA |  |  | 04-Jun-25 A | 21-Jun-25 A | 0
Pile Layout Compressor Shelter & SR8001 |  |  |  | 01-Jul-25 A | 10-Jul-25 A | 0
A17630 | Pile Layout Compressor Shelter & SR8001_IFR |  |  | 01-Jul-25 A | 10-Jul-25 A | 0
A17640 | Pile Layout Compressor Shelter & SR8001_RCC |  |  | 01-Jul-25 A | 10-Jul-25 A | 0
A17650 | Pile Layout Compressor Shelter & SR8001_IFA |  |  | 01-Jul-25 A | 10-Jul-25 A | 0
A17660 | Pile Layout Compressor Shelter & SR8001_RCA |  |  | 01-Jul-25 A | 10-Jul-25 A | 0
A17670 | Pile Layout Compressor Shelter & SR8001_IFD/IFC |  |  | 01-Jul-25 A | 10-Jul-25 A | 0
Pile Reinforcement Drawing |  |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17480 | Pile Reinforcement Drawing_IFR |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17490 | Pile Reinforcement Drawing_RCC |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17500 | Pile Reinforcement Drawing_IFA |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17510 | Pile Reinforcement Drawing_RCA |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17520 | Pile Reinforcement Drawing_IFD/IFC |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
Pile Layout PSA-2 FeedGas Compressor 13-KC-701 |  |  |  | 10-Apr-25 A | 16-Sep-25 A | 0
A17530 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFR |  |  | 10-Apr-25 A | 15-Aug-25 A | 0
A17550 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFA |  |  | 22-Aug-25 A | 26-Aug-25 A | 0
A17560 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCA |  |  | 27-Aug-25 A | 16-Sep-25 A | 0
A17570 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_IFD/IFC |  |  | 02-Jun-25 A | 13-Jun-25 A | 0
A48320 | Pile Layout PSA-2 FeedGas Compressor 13-KC-701_RCC |  |  | 16-Aug-25 A | 22-Aug-25 A | 0
Pile Layout PSA-2 OffGas Compressor 13-KC-702 |  |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17580 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFR |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17590 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCC |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17600 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFA |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17610 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_RCA |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
A17620 | Pile Layout PSA-2 OffGas Compressor 13-KC-702_IFD/IFC |  |  | 01-Jul-25 A | 18-Jul-25 A | 0
Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710 |  |  |  | 30-Jun-25 A | 10-Jul-25 A | 0
A48330 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFR |  |  | 30-Jun-25 A | 10-Jul-25 A | 0
A48340 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCC |  |  | 30-Jun-25 A | 10-Jul-25 A | 0
A48350 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFA |  |  | 30-Jun-25 A | 10-Jul-25 A | 0
A48360 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_RCA |  |  | 30-Jun-25 A | 10-Jul-25 A | 0
A48370 | Pile Layout PSA-2 Unit - Hydrogen Purification 13-XA-710_IFD/IFC |  |  | 30-Jun-25 A | 10-Jul-25 A | 0
Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712 |  |  |  | 22-Apr-25 A | 20-May-25 A | 0
A17680 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFR |  |  | 22-Apr-25 A | 20-May-25 A | 0
A17690 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCC |  |  | 22-Apr-25 A | 20-May-25 A | 0
A17700 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFA |  |  | 22-Apr-25 A | 20-May-25 A | 0
A17710 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_RCA |  |  | 22-Apr-25 A | 20-May-25 A | 0
A17720 | Pile Layout PSA-2 OffGas Buffer Drum 13-VV-712_IFD/IFC |  |  | 22-Apr-25 A | 20-May-25 A | 0
Structure & Foundation design - Buildings/Shelters/Electrical |  | 2026-01-02 | 2027-01-20 | 05-Feb-25 A | 2026-01-02 | 76
Structural GA, Section and Details - Compressor Shelter |  | 2025-12-31 | 2026-05-08 | 2025-10-01 | 2025-12-31 | 65
A48880 | Structural GA, Section and Details - Compressor Shelter_IFR | 2025-10-24 | 2026-03-03 | 2025-10-01 | 2025-10-24 | 17
A48890 | Structural GA, Section and Details - Compressor Shelter_RCC | 2025-11-17 | 2026-03-25 | 2025-10-24 | 2025-11-17 | 16
A48900 | Structural GA, Section and Details - Compressor Shelter_IFA | 2025-12-02 | 2026-04-09 | 2025-11-17 | 2025-12-02 | 11
A48910 | Structural GA, Section and Details - Compressor Shelter_RCA | 2025-12-24 | 2026-05-01 | 2025-12-02 | 2025-12-24 | 16
A48920 | Structural GA, Section and Details - Compressor Shelter_IFD/IFC | 2025-12-31 | 2026-05-08 | 2025-12-24 | 2025-12-31 | 6
Design Calculation Report for structural steel- Compressor Shelter |  | 2025-12-31 | 2027-01-20 | 2025-10-01 | 2025-12-31 | 65
A18690 | Design Calculation Report for structural steel- Compressor Shelter_RCC | 2025-11-17 | 2026-12-07 | 2025-10-24 | 2025-11-17 | 16
A18700 | Design Calculation Report for structural steel- Compressor Shelter_IFA | 2025-12-02 | 2026-12-22 | 2025-11-17 | 2025-12-02 | 11
A18710 | Design Calculation Report for structural steel- Compressor Shelter_RCA | 2025-12-24 | 2027-01-13 | 2025-12-02 | 2025-12-24 | 16
A48950 | Design Calculation Report for structural steel- Compressor Shelter_IFR | 2025-10-24 | 2026-11-13 | 2025-10-01 | 2025-10-24 | 17
A48960 | Design Calculation Report for structural steel- Compressor Shelter_IFD/IFC | 2025-12-31 | 2027-01-20 | 2025-12-24 | 2025-12-31 | 6
Foundation Drawing- Compressor Shelter |  | 2026-01-02 | 2027-01-20 | 01-Jul-25 A | 2026-01-02 | 76
A18630 | Foundation Drawing- Compressor Shelter_IFR |  |  | 01-Jul-25 A | 20-Jul-25 A | 0
A18640 | Foundation Drawing- Compressor Shelter_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A18650 | Foundation Drawing- Compressor Shelter_IFA | 2025-12-05 | 2026-12-25 | 2025-12-02 | 2025-12-05 | 3
A48930 | Foundation Drawing- Compressor Shelter_RCA | 2025-12-29 | 2027-01-18 | 2025-12-05 | 2025-12-29 | 16
A48940 | Foundation Drawing- Compressor Shelter_IFD/IFC | 2026-01-02 | 2027-01-20 | 2025-12-31 | 2026-01-02 | 2
Design Calculation Report for Foundations- Compressor Shelter |  | 2026-01-02 | 2027-01-20 | 28-Jun-25 A | 2026-01-02 | 76
A48970 | Design Calculation Report for Foundations- Compressor Shelter_IFR |  |  | 28-Jun-25 A | 15-Jul-25 A | 0
A48980 | Design Calculation Report for Foundations- Compressor Shelter_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A48990 | Design Calculation Report for Foundations- Compressor Shelter_IFA | 2025-12-05 | 2026-12-25 | 2025-12-02 | 2025-12-05 | 3
A49000 | Design Calculation Report for Foundations- Compressor Shelter_RCA | 2025-12-29 | 2027-01-18 | 2025-12-05 | 2025-12-29 | 16
A49010 | Design Calculation Report for Foundations- Compressor Shelter_IFD/IFC | 2026-01-02 | 2027-01-20 | 2025-12-31 | 2026-01-02 | 2
Architectural Drawing- Substation, SIS Building |  |  |  | 05-Feb-25 A | 18-Sep-25 A | 0
A17790 | Architectural Drawing- Substation, SIS Building_RCC |  |  | 12-Mar-25 A | 20-Apr-25 A | 0
A48380 | Architectural Drawing- Substation, SIS Building_IFR |  |  | 05-Feb-25 A | 11-Mar-25 A | 0
A48390 | Architectural Drawing- Substation, SIS Building_IFA |  |  | 21-Apr-25 A | 19-Jun-25 A | 0
A48400 | Architectural Drawing- Substation, SIS Building_RCA |  |  | 20-Jun-25 A | 04-Sep-25 A | 0
A48410 | Architectural Drawing- Substation, SIS Building_IFD/IFC |  |  | 08-Sep-25 A | 18-Sep-25 A | 0
Structural Concrete GA, Section and Details- Substation, SIS Building |  |  |  | 21-Apr-25 A | 11-Jul-25 A | 0
A17880 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFR |  |  | 21-Apr-25 A | 12-May-25 A | 0
A48430 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCC |  |  | 13-May-25 A | 03-Jun-25 A | 0
A48440 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFA |  |  | 04-Jun-25 A | 13-Jun-25 A | 0
A48450 | Structural Concrete GA, Section and Details- Substation, SIS Building_RCA |  |  | 16-Jun-25 A | 04-Jul-25 A | 0
A48460 | Structural Concrete GA, Section and Details- Substation, SIS Building_IFD/IFC |  |  | 07-Jul-25 A | 11-Jul-25 A | 0
Design Calculation report for Substation, SIS Building |  | 2025-10-22 | 2025-12-24 | 20-Apr-25 A | 2025-10-22 | 24
A17940 | Design Calculation report for Substation, SIS Building_RCC |  |  | 12-May-25 A | 05-Jun-25 A | 0
A48470 | Design Calculation report for Substation, SIS Building_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A48480 | Design Calculation report for Substation, SIS Building_IFA | 2025-09-26 | 2025-11-28 | 2025-09-19 | 2025-09-26 | 6
A48490 | Design Calculation report for Substation, SIS Building_RCA | 2025-10-20 | 2025-12-22 | 2025-09-26 | 2025-10-20 | 16
A48500 | Design Calculation report for Substation, SIS Building_IFD/IFC | 2025-10-22 | 2025-12-24 | 2025-10-20 | 2025-10-22 | 2
Foundation Layout, Section and Details- Substation, SIS Building |  | 2025-10-24 | 2025-12-26 | 21-Apr-25 A | 2025-10-24 | 26
A17840 | Foundation Layout, Section and Details- Substation, SIS Building_RCC |  |  | 13-May-25 A | 29-May-25 A | 0
A17850 | Foundation Layout, Section and Details- Substation, SIS Building_IFA |  |  | 30-May-25 A | 21-Jun-25 A | 0
A17860 | Foundation Layout, Section and Details- Substation, SIS Building_RCA | 2025-10-10 | 2025-12-24 | 23-Jun-25 A | 2025-10-10 | 16
A17870 | Foundation Layout, Section and Details- Substation, SIS Building_IFD/IFC | 2025-10-24 | 2025-12-26 | 2025-10-22 | 2025-10-24 | 2
A48420 | Foundation Layout, Section and Details- Substation, SIS Building_IFR |  |  | 21-Apr-25 A | 12-May-25 A | 0
Structure design - U/G facilities |  | 2025-11-26 | 2027-01-20 | 10-Jun-25 A | 2025-11-26 | 48
Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407 |  | 2025-11-11 | 2026-03-17 | 22-Aug-25 A | 2025-11-11 | 37
A20380 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFR |  |  | 22-Aug-25 A | 28-Aug-25 A | 0
A20390 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCC | 2025-10-10 | 2026-02-16 | 2025-09-19 | 2025-10-10 | 16
A20400 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFA | 2025-10-16 | 2026-02-19 | 2025-10-10 | 2025-10-16 | 3
A49710 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_RCA | 2025-11-06 | 2026-03-13 | 2025-10-16 | 2025-11-06 | 16
A49720 | Sump Pit plan and details Accidentally Oil contaminated water collection 70-TD-1407_IFD/IFC | 2025-11-11 | 2026-03-17 | 2025-11-06 | 2025-11-11 | 2
Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407 |  | 2025-11-11 | 2026-03-17 | 23-Aug-25 A | 2025-11-11 | 37
A20440 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCC | 2025-10-10 | 2026-02-16 | 2025-09-19 | 2025-10-10 | 16
A20450 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFA | 2025-10-16 | 2026-02-19 | 2025-10-10 | 2025-10-16 | 3
A20460 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_RCA | 2025-11-06 | 2026-03-13 | 2025-10-16 | 2025-11-06 | 16
A49730 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFR |  |  | 23-Aug-25 A | 13-Sep-25 A | 0
A49740 | Design Calculation Report for Accidentally Oil contaminated water collection Sump Pit 70-TD-1407_IFD/IFC | 2025-11-11 | 2026-03-17 | 2025-11-06 | 2025-11-11 | 2
Sump Pit plan and details Oily Water 70-TD-1408 |  | 2025-11-11 | 2026-04-02 | 01-Aug-25 A | 2025-11-11 | 21
A20500 | Sump Pit plan and details Oily Water 70-TD-1408_IFA | 2025-10-16 | 2026-03-09 | 2025-10-10 | 2025-10-16 | 3
A20510 | Sump Pit plan and details Oily Water 70-TD-1408_RCA | 2025-11-06 | 2026-03-31 | 2025-10-16 | 2025-11-06 | 16
A20520 | Sump Pit plan and details Oily Water 70-TD-1408_IFD/IFC | 2025-11-11 | 2026-04-02 | 2025-11-06 | 2025-11-11 | 2
A49750 | Sump Pit plan and details Oily Water 70-TD-1408_IFR |  |  | 01-Aug-25 A | 22-Aug-25 A | 0
A49760 | Sump Pit plan and details Oily Water 70-TD-1408_RCC |  |  | 23-Aug-25 A | 26-Aug-25 A | 0
Design Calculation Report for Oily Water Sump Pit 70-TD-1408 |  | 2025-11-11 | 2026-04-02 | 23-Aug-25 A | 2025-11-11 | 37
A20560 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCA | 2025-11-06 | 2026-03-31 | 2025-10-16 | 2025-11-06 | 16
A20570 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFD/IFC | 2025-11-11 | 2026-04-02 | 2025-11-06 | 2025-11-11 | 2
A49770 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFR |  |  | 23-Aug-25 A | 13-Sep-25 A | 0
A49780 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_RCC | 2025-10-10 | 2026-03-04 | 2025-09-19 | 2025-10-10 | 16
A49790 | Design Calculation Report for Oily Water Sump Pit 70-TD-1408_IFA | 2025-10-16 | 2026-03-09 | 2025-10-10 | 2025-10-16 | 3
Sump Pit plan and details Sanitary Waste Water 70-TD-1409 |  | 2025-11-11 | 2026-10-14 | 23-Aug-25 A | 2025-11-11 | 37
A20580 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFR |  |  | 23-Aug-25 A | 13-Sep-25 A | 0
A20620 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFD/IFC | 2025-11-11 | 2026-10-14 | 2025-11-06 | 2025-11-11 | 2
A49800 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCC | 2025-10-10 | 2026-09-14 | 2025-09-19 | 2025-10-10 | 16
A49810 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_IFA | 2025-10-16 | 2026-09-18 | 2025-10-10 | 2025-10-16 | 3
A49820 | Sump Pit plan and details Sanitary Waste Water 70-TD-1409_RCA | 2025-11-06 | 2026-10-12 | 2025-10-16 | 2025-11-06 | 16
Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409 |  | 2025-11-11 | 2026-10-14 | 23-Aug-25 A | 2025-11-11 | 37
A20630 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFR |  |  | 23-Aug-25 A | 13-Sep-25 A | 0
A20640 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCC | 2025-10-10 | 2026-09-14 | 2025-09-19 | 2025-10-10 | 16
A49830 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFA | 2025-10-16 | 2026-09-18 | 2025-10-10 | 2025-10-16 | 3
A49840 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_RCA | 2025-11-06 | 2026-10-12 | 2025-10-16 | 2025-11-06 | 16
A49850 | Design Calculation Report for Sanitary Waste Water Sump Pit 70-TD-1409_IFD/IFC | 2025-11-11 | 2026-10-14 | 2025-11-06 | 2025-11-11 | 2
Transformer Foundation Drawing for Bay-A to Bay-E |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A20680 | Transformer Foundation Drawing for Bay-A to Bay-E_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A20690 | Transformer Foundation Drawing for Bay-A to Bay-E_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A20700 | Transformer Foundation Drawing for Bay-A to Bay-E_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A49860 | Transformer Foundation Drawing for Bay-A to Bay-E_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A49870 | Transformer Foundation Drawing for Bay-A to Bay-E_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A20750 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A20760 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A20770 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
A49880 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A49890 | Design Calculation Report for Foundation- Transformer for Bay-A to Bay-E_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
Firewater Valve Pit Plan, Section and Details |  | 2025-11-18 | 2026-02-27 | 2025-09-19 | 2025-11-18 | 43
A21380 | Firewater Valve Pit Plan, Section and Details_IFR | 2025-09-26 | 2026-01-07 | 2025-09-19 | 2025-09-26 | 6
A21390 | Firewater Valve Pit Plan, Section and Details_RCC | 2025-10-20 | 2026-01-29 | 2025-09-26 | 2025-10-20 | 16
A21400 | Firewater Valve Pit Plan, Section and Details_IFA | 2025-10-23 | 2026-02-03 | 2025-10-20 | 2025-10-23 | 3
A50150 | Firewater Valve Pit Plan, Section and Details_RCA | 2025-11-14 | 2026-02-25 | 2025-10-23 | 2025-11-14 | 16
A50160 | Firewater Valve Pit Plan, Section and Details_IFD/IFC | 2025-11-18 | 2026-02-27 | 2025-11-14 | 2025-11-18 | 2
Cooling water Valve Pit Plan, Section and Details |  | 2025-11-18 | 2026-04-01 | 2025-09-19 | 2025-11-18 | 43
A21440 | Cooling water Valve Pit Plan, Section and Details_RCC | 2025-10-20 | 2026-03-03 | 2025-09-26 | 2025-10-20 | 16
A21450 | Cooling water Valve Pit Plan, Section and Details_IFA | 2025-10-23 | 2026-03-06 | 2025-10-20 | 2025-10-23 | 3
A21460 | Cooling water Valve Pit Plan, Section and Details_RCA | 2025-11-14 | 2026-03-30 | 2025-10-23 | 2025-11-14 | 16
A50170 | Cooling water Valve Pit Plan, Section and Details_IFR | 2025-09-26 | 2026-02-09 | 2025-09-19 | 2025-09-26 | 6
A50180 | Cooling water Valve Pit Plan, Section and Details_IFD/IFC | 2025-11-18 | 2026-04-01 | 2025-11-14 | 2025-11-18 | 2
Underground Layout |  | 2025-11-11 | 2026-03-05 | 10-Jun-25 A | 2025-11-11 | 37
A21570 | Underground Layout_IFD/IFC | 2025-11-11 | 2026-03-05 | 2025-11-06 | 2025-11-11 | 2
A50210 | Underground Layout_IFR |  |  | 10-Jun-25 A | 08-Jul-25 A | 0
A50220 | Underground Layout_RCC | 2025-10-10 | 2026-02-03 | 2025-09-19 | 2025-10-10 | 16
A50230 | Underground Layout_IFA | 2025-10-16 | 2026-02-09 | 2025-10-10 | 2025-10-16 | 3
A50240 | Underground Layout_RCA | 2025-11-06 | 2026-03-02 | 2025-10-16 | 2025-11-06 | 16
Composite Underground drawing |  | 2025-11-26 | 2026-04-17 | 2025-09-26 | 2025-11-26 | 43
A21580 | Composite Underground drawing_IFR | 2025-10-06 | 2026-02-25 | 2025-09-26 | 2025-10-06 | 6
A21590 | Composite Underground drawing_RCC | 2025-10-27 | 2026-03-19 | 2025-10-06 | 2025-10-27 | 16
A21600 | Composite Underground drawing_IFA | 2025-10-31 | 2026-03-24 | 2025-10-28 | 2025-10-31 | 3
A50250 | Composite Underground drawing_RCA | 2025-11-24 | 2026-04-15 | 2025-10-31 | 2025-11-24 | 16
A50260 | Composite Underground drawing_IFD/IFC | 2025-11-26 | 2026-04-17 | 2025-11-24 | 2025-11-26 | 2
Underground Trench Layout drawing and details |  | 2025-11-18 | 2026-02-27 | 2025-09-19 | 2025-11-18 | 43
A21650 | Underground Trench Layout drawing and details_IFA | 2025-10-23 | 2026-02-03 | 2025-10-20 | 2025-10-23 | 3
A21660 | Underground Trench Layout drawing and details_RCA | 2025-11-14 | 2026-02-25 | 2025-10-23 | 2025-11-14 | 16
A21670 | Underground Trench Layout drawing and details_IFD/IFC | 2025-11-18 | 2026-02-27 | 2025-11-14 | 2025-11-18 | 2
A50270 | Underground Trench Layout drawing and details_IFR | 2025-09-26 | 2026-01-07 | 2025-09-19 | 2025-09-26 | 6
A50280 | Underground Trench Layout drawing and details_RCC | 2025-10-20 | 2026-01-28 | 2025-09-26 | 2025-10-20 | 16
Design Calculation for Concrete Trenches and Duct Banks (If Required) |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A21680 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A50290 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A50300 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A50310 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A50320 | Design Calculation for Concrete Trenches and Duct Banks (If Required)_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Calculation for UG Hydraulics |  | 2025-11-14 | 2027-01-20 | 10-Jun-25 A | 2025-11-14 | 41
A21730 | Calculation for UG Hydraulics_IFR |  |  | 10-Jun-25 A | 02-Jul-25 A | 0
A21740 | Calculation for UG Hydraulics_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A21750 | Calculation for UG Hydraulics_IFA | 2025-10-21 | 2026-12-25 | 2025-10-16 | 2025-10-21 | 3
A21760 | Calculation for UG Hydraulics_RCA | 2025-11-12 | 2027-01-18 | 2025-10-21 | 2025-11-12 | 16
A50330 | Calculation for UG Hydraulics_IFD/IFC | 2025-11-14 | 2027-01-20 | 2025-11-12 | 2025-11-14 | 2
Other Civil deliverables |  | 2026-01-06 | 2027-01-20 | 16-Jan-25 A | 2026-01-06 | 78
General notes for Civil and Concrete Works |  |  |  | 30-Jan-25 A | 10-May-25 A | 0
A17180 | General notes for Civil and Concrete Works_IFR |  |  | 30-Jan-25 A | 20-Feb-25 A | 0
A17190 | General notes for Civil and Concrete Works_RCC |  |  | 21-Feb-25 A | 19-Apr-25 A | 0
A17200 | General notes for Civil and Concrete Works_IFA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A17210 | General notes for Civil and Concrete Works_RCA |  |  | 27-Apr-25 A | 03-May-25 A | 0
A17220 | General notes for Civil and Concrete Works_IFD/IFC |  |  | 04-May-25 A | 10-May-25 A | 0
Standard details for stair and ladder foundation |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A17280 | Standard details for stair and ladder foundation_IFR |  |  | 01-Jul-25 A | 10-Jul-25 A | 0
A17300 | Standard details for stair and ladder foundation_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A17310 | Standard details for stair and ladder foundation_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A17320 | Standard details for stair and ladder foundation_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
A48280 | Standard details for stair and ladder foundation_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
Site Grading Layout |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A17430 | Site Grading Layout_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A17440 | Site Grading Layout_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A17450 | Site Grading Layout_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A17460 | Site Grading Layout_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A48310 | Site Grading Layout_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
General notes for Structural steel Works |  |  |  | 16-Jan-25 A | 03-May-25 A | 0
A17240 | General notes for Structural steel Works_RCC |  |  | 21-Feb-25 A | 13-Mar-25 A | 0
A17250 | General notes for Structural steel Works_IFA |  |  | 14-Mar-25 A | 19-Apr-25 A | 0
A17260 | General notes for Structural steel Works_RCA |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A17270 | General notes for Structural steel Works_IFD/IFC |  |  | 27-Apr-25 A | 03-May-25 A | 0
A48270 | General notes for Structural steel Works_IFR |  |  | 16-Jan-25 A | 20-Feb-25 A | 0
Typical Road Details |  | 2025-11-11 | 2027-01-20 | 02-Jul-25 A | 2025-11-11 | 37
A17330 | Typical Road Details_IFR |  |  | 02-Jul-25 A | 09-Jul-25 A | 0
A17340 | Typical Road Details_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A17360 | Typical Road Details_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A17370 | Typical Road Details_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
A48290 | Typical Road Details_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
MTO for Civil Works |  |  |  | 05-May-25 A | 10-Jun-25 A | 0
A22430 | MTO for Civil Works_IFR |  |  | 05-May-25 A | 16-May-25 A | 0
A22440 | MTO for Civil Works_RCC |  |  | 19-May-25 A | 05-Jun-25 A | 0
A50770 | MTO for Civil Works_IFD/IFC |  |  | 08-Jun-25 A | 10-Jun-25 A | 0
MTO for Structural Steel |  |  |  | 25-Aug-25 A | 12-Sep-25 A | 0
A50780 | MTO for Structural Steel_IFR |  |  | 25-Aug-25 A | 29-Aug-25 A | 0
A50790 | MTO for Structural Steel_RCC |  |  | 01-Sep-25 A | 05-Sep-25 A | 0
A50800 | MTO for Structural Steel_IFD/IFC |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
Tie-in Manhole modification drawing |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A22380 | Tie-in Manhole modification drawing_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A50730 | Tie-in Manhole modification drawing_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A50740 | Tie-in Manhole modification drawing_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A50750 | Tie-in Manhole modification drawing_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A50760 | Tie-in Manhole modification drawing_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Fence and Gate Layout |  | 2026-01-06 | 2027-01-20 | 01-May-25 A | 2026-01-06 | 2
A17380 | Fence and Gate Layout_IFR |  |  | 01-May-25 A | 22-May-25 A | 0
A17390 | Fence and Gate Layout_RCC |  |  | 23-May-25 A | 17-Jun-25 A | 0
A17400 | Fence and Gate Layout_IFA |  |  | 18-Jun-25 A | 24-Jun-25 A | 0
A17420 | Fence and Gate Layout_IFD/IFC | 2026-01-06 | 2027-01-20 | 2026-01-02 | 2026-01-06 | 2
A48300 | Fence and Gate Layout_RCA |  |  | 25-Jun-25 A | 16-Sep-25 A | 0
Road and Paving Layout |  | 2025-11-11 | 2026-07-28 | 02-Jun-25 A | 2025-11-11 | 37
A21520 | Road and Paving Layout_IFD/IFC | 2025-11-11 | 2026-07-28 | 2025-11-06 | 2025-11-11 | 2
A50190 | Road and Paving Layout_IFR |  |  | 02-Jun-25 A | 06-Jul-25 A | 0
A50200 | Road and Paving Layout_RCC | 2025-10-10 | 2026-06-29 | 2025-09-19 | 2025-10-10 | 16
A56270 | Road and Paving Layout_IFA | 2025-10-16 | 2026-07-02 | 2025-10-10 | 2025-10-16 | 3
A56280 | Road and Paving Layout_RCA | 2025-11-06 | 2026-07-24 | 2025-10-16 | 2025-11-06 | 16
Telecom |  | 2026-01-06 | 2027-01-20 | 30-Dec-24 A | 2026-01-06 | 74
Block Diagram For Process CCTV |  |  |  | 30-Dec-24 A | 19-Sep-25 A | 0
A51060 | Block Diagram For Process CCTV_IFR |  |  | 30-Dec-24 A | 20-Jan-25 A | 0
A51070 | Block Diagram For Process CCTV_RCC |  |  | 21-Jan-25 A | 14-Feb-25 A | 0
A51080 | Block Diagram For Process CCTV_IFA |  |  | 15-Feb-25 A | 22-Apr-25 A | 0
A51090 | Block Diagram For Process CCTV_RCA |  |  | 23-Apr-25 A | 12-Sep-25 A | 0
A51100 | Block Diagram For Process CCTV_IFD/IFC |  |  | 13-Sep-25 A | 19-Sep-25 A | 0
Block Diagram For PAGA |  | 2025-09-23 | 2027-01-20 | 30-Dec-24 A | 2025-09-23 | 2
A51110 | Block Diagram For PAGA_IFR |  |  | 30-Dec-24 A | 20-Jan-25 A | 0
A51120 | Block Diagram For PAGA_RCC |  |  | 21-Jan-25 A | 14-Feb-25 A | 0
A51130 | Block Diagram For PAGA_IFA |  |  | 15-Feb-25 A | 22-Apr-25 A | 0
A51140 | Block Diagram For PAGA_RCA |  |  | 23-Apr-25 A | 10-Sep-25 A | 0
A51150 | Block Diagram For PAGA_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Block Diagram For Digital Network And Telephone System |  | 2025-09-23 | 2027-01-20 | 30-Dec-24 A | 2025-09-23 | 2
A51160 | Block Diagram For Digital Network And Telephone System_IFR |  |  | 30-Dec-24 A | 20-Jan-25 A | 0
A51170 | Block Diagram For Digital Network And Telephone System_RCC |  |  | 21-Jan-25 A | 14-Feb-25 A | 0
A51180 | Block Diagram For Digital Network And Telephone System_IFA |  |  | 15-Feb-25 A | 24-Apr-25 A | 0
A51190 | Block Diagram For Digital Network And Telephone System_RCA |  |  | 25-Apr-25 A | 10-Sep-25 A | 0
A51200 | Block Diagram For Digital Network And Telephone System_IFD/IFC | 2025-09-23 | 2027-01-20 | 2025-09-19 | 2025-09-23 | 2
Block Diagram For Access Control System |  |  |  | 30-Dec-24 A | 19-Sep-25 A | 0
A51210 | Block Diagram For Access Control System_IFR |  |  | 30-Dec-24 A | 20-Jan-25 A | 0
A51220 | Block Diagram For Access Control System_RCC |  |  | 21-Jan-25 A | 14-Feb-25 A | 0
A51230 | Block Diagram For Access Control System_IFA |  |  | 15-Feb-25 A | 22-Apr-25 A | 0
A51240 | Block Diagram For Access Control System_RCA |  |  | 23-Apr-25 A | 21-Jun-25 A | 0
A51250 | Block Diagram For Access Control System_IFD/IFC |  |  | 22-Jun-25 A | 19-Sep-25 A | 0
Overall Telecom System Block Diagram |  | 2025-11-11 | 2027-01-20 | 25-Jan-25 A | 2025-11-11 | 37
A51260 | Overall Telecom System Block Diagram_IFR |  |  | 25-Jan-25 A | 27-Apr-25 A | 0
A51270 | Overall Telecom System Block Diagram_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A51280 | Overall Telecom System Block Diagram_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A51290 | Overall Telecom System Block Diagram_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A51300 | Overall Telecom System Block Diagram_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Telecom Tie-In Schedule |  |  |  | 13-Mar-25 A | 01-Sep-25 A | 0
A23660 | Telecom Tie-In Schedule_RCA |  |  | 12-May-25 A | 25-Aug-25 A | 0
A51800 | Telecom Tie-In Schedule_IFR |  |  | 13-Mar-25 A | 27-Apr-25 A | 0
A51810 | Telecom Tie-In Schedule_RCC |  |  | 28-Apr-25 A | 04-May-25 A | 0
A51820 | Telecom Tie-In Schedule_IFA |  |  | 05-May-25 A | 11-May-25 A | 0
A51830 | Telecom Tie-In Schedule_IFD/IFC |  |  | 26-Aug-25 A | 01-Sep-25 A | 0
Datasheet For Fiber Optic Cable |  |  |  | 30-Jan-25 A | 11-May-25 A | 0
A50810 | Datasheet For Fiber Optic Cable_IFR |  |  | 30-Jan-25 A | 20-Feb-25 A | 0
A50820 | Datasheet For Fiber Optic Cable_RCC |  |  | 21-Feb-25 A | 20-Apr-25 A | 0
A50830 | Datasheet For Fiber Optic Cable_IFA |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A50840 | Datasheet For Fiber Optic Cable_RCA |  |  | 28-Apr-25 A | 04-May-25 A | 0
A50850 | Datasheet For Fiber Optic Cable_IFD/IFC |  |  | 05-May-25 A | 11-May-25 A | 0
Datasheet For Process CCTV |  | 2025-11-11 | 2025-12-29 | 07-Jan-25 A | 2025-11-11 | 37
A50860 | Datasheet For Process CCTV_IFR |  |  | 07-Jan-25 A | 28-Jan-25 A | 0
A50870 | Datasheet For Process CCTV_RCC | 2025-10-10 | 2025-11-27 | 2025-09-19 | 2025-10-10 | 16
A50880 | Datasheet For Process CCTV_IFA | 2025-10-16 | 2025-12-02 | 2025-10-10 | 2025-10-16 | 3
A50890 | Datasheet For Process CCTV_RCA | 2025-11-06 | 2025-12-25 | 2025-10-16 | 2025-11-06 | 16
A50900 | Datasheet For Process CCTV_IFD/IFC | 2025-11-11 | 2025-12-29 | 2025-11-06 | 2025-11-11 | 2
Datasheet For PAGA |  | 2025-09-23 | 2025-12-29 | 10-Jan-25 A | 2025-09-23 | 2
A50910 | Datasheet For PAGA_IFR |  |  | 10-Jan-25 A | 20-Mar-25 A | 0
A50920 | Datasheet For PAGA_RCC |  |  | 21-Mar-25 A | 20-Apr-25 A | 0
A50930 | Datasheet For PAGA_IFA |  |  | 21-Apr-25 A | 30-May-25 A | 0
A50940 | Datasheet For PAGA_RCA |  |  | 01-Jun-25 A | 21-Jun-25 A | 0
A50950 | Datasheet For PAGA_IFD/IFC | 2025-09-23 | 2025-12-29 | 2025-09-19 | 2025-09-23 | 2
Datasheet For Access Control System |  | 2025-09-23 | 2025-12-29 | 15-Jan-25 A | 2025-09-23 | 2
A50960 | Datasheet For Access Control System_IFR |  |  | 15-Jan-25 A | 27-Apr-25 A | 0
A50970 | Datasheet For Access Control System_RCC |  |  | 28-Apr-25 A | 04-May-25 A | 0
A50980 | Datasheet For Access Control System_IFA |  |  | 05-May-25 A | 09-Jun-25 A | 0
A50990 | Datasheet For Access Control System_RCA |  |  | 10-Jun-25 A | 19-Sep-25 A | 0
A51000 | Datasheet For Access Control System_IFD/IFC | 2025-09-23 | 2025-12-29 | 2025-09-19 | 2025-09-23 | 2
Datasheet For Digital Network And Telephone System |  | 2025-09-23 | 2025-12-29 | 15-Jan-25 A | 2025-09-23 | 2
A51010 | Datasheet For Digital Network And Telephone System_IFR |  |  | 15-Jan-25 A | 27-Apr-25 A | 0
A51020 | Datasheet For Digital Network And Telephone System_RCC |  |  | 28-Apr-25 A | 04-May-25 A | 0
A51030 | Datasheet For Digital Network And Telephone System_IFA |  |  | 05-May-25 A | 10-Jun-25 A | 0
A51040 | Datasheet For Digital Network And Telephone System_RCA |  |  | 11-Jun-25 A | 28-Aug-25 A | 0
A51050 | Datasheet For Digital Network And Telephone System_IFD/IFC | 2025-09-23 | 2025-12-29 | 2025-09-19 | 2025-09-23 | 2
Wiring Diagram For Process Cctv |  | 2025-10-20 | 2027-01-20 | 08-Jan-25 A | 2025-10-20 | 21
A51310 | Wiring Diagram For Process Cctv_IFR |  |  | 08-Jan-25 A | 12-Feb-25 A | 0
A51320 | Wiring Diagram For Process Cctv_RCC |  |  | 13-Feb-25 A | 13-Mar-25 A | 0
A51330 | Wiring Diagram For Process Cctv_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A51340 | Wiring Diagram For Process Cctv_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A51350 | Wiring Diagram For Process Cctv_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Wiring Diagram For Paga |  | 2025-10-20 | 2027-01-20 | 09-Jan-25 A | 2025-10-20 | 21
A51360 | Wiring Diagram For Paga_IFR |  |  | 09-Jan-25 A | 12-Feb-25 A | 0
A51370 | Wiring Diagram For Paga_RCC |  |  | 13-Feb-25 A | 13-Mar-25 A | 0
A51380 | Wiring Diagram For Paga_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A51390 | Wiring Diagram For Paga_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A51400 | Wiring Diagram For Paga_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Wiring Diagram For Digital Network And Telephone System |  | 2025-11-18 | 2027-01-20 | 22-Jan-25 A | 2025-11-18 | 43
A51410 | Wiring Diagram For Digital Network And Telephone System_IFR | 2025-09-26 | 2026-11-30 | 22-Jan-25 A | 2025-09-26 | 6
A51420 | Wiring Diagram For Digital Network And Telephone System_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A51430 | Wiring Diagram For Digital Network And Telephone System_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A51440 | Wiring Diagram For Digital Network And Telephone System_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A51450 | Wiring Diagram For Digital Network And Telephone System_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Wiring Diagram For Access Control System |  | 2025-11-18 | 2027-01-20 | 22-Jan-25 A | 2025-11-18 | 43
A51460 | Wiring Diagram For Access Control System_IFR | 2025-09-26 | 2026-11-30 | 22-Jan-25 A | 2025-09-26 | 6
A51470 | Wiring Diagram For Access Control System_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A51480 | Wiring Diagram For Access Control System_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A51490 | Wiring Diagram For Access Control System_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A51500 | Wiring Diagram For Access Control System_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
Material Requisitions For Telecom System (Paga, CCTV, ACS, Telephone & LAN System) |  | 2025-11-14 | 2025-12-31 | 14-Mar-25 A | 2025-11-14 | 41
A23780 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFR |  |  | 14-Mar-25 A | 26-Apr-25 A | 0
A23790 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCC | 2025-10-10 | 2025-12-02 | 2025-09-19 | 2025-10-10 | 16
A23800 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFA | 2025-10-21 | 2025-12-05 | 2025-10-16 | 2025-10-21 | 3
A23810 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_RCA | 2025-11-12 | 2025-12-29 | 2025-10-21 | 2025-11-12 | 16
A51910 | Material Requisitions For Telecom System (Paga, Cctv, Acs, Telephone & Lan System)_IFD/IFC | 2025-11-14 | 2025-12-31 | 2025-11-12 | 2025-11-14 | 2
Material Requisitions For Telecom Cables |  | 2025-11-11 | 2027-01-20 | 01-May-25 A | 2025-11-11 | 37
A23860 | Material Requisitions For Telecom Cables_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A23870 | Material Requisitions For Telecom Cables_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
A51920 | Material Requisitions For Telecom Cables_IFR |  |  | 01-May-25 A | 22-May-25 A | 0
A51930 | Material Requisitions For Telecom Cables_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A51940 | Material Requisitions For Telecom Cables_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
Telecom Equipment List |  | 2025-10-20 | 2027-01-20 | 10-Mar-25 A | 2025-10-20 | 21
A23580 | Telecom Equipment List_IFR |  |  | 10-Mar-25 A | 27-Apr-25 A | 0
A51760 | Telecom Equipment List_RCC |  |  | 28-Apr-25 A | 04-May-25 A | 0
A51770 | Telecom Equipment List_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A51780 | Telecom Equipment List_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A51790 | Telecom Equipment List_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Telecom Cable Schedule |  | 2025-11-11 | 2027-01-20 | 14-Apr-25 A | 2025-11-11 | 37
A51640 | Telecom Cable Schedule_IFR |  |  | 14-Apr-25 A | 05-May-25 A | 0
A51650 | Telecom Cable Schedule_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A51660 | Telecom Cable Schedule_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A51670 | Telecom Cable Schedule_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A51680 | Telecom Cable Schedule_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Telecom Junction Box Schedule |  | 2025-10-20 | 2027-01-20 | 20-Apr-25 A | 2025-10-20 | 21
A23520 | Telecom Junction Box Schedule_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
A51690 | Telecom Junction Box Schedule_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A51700 | Telecom Junction Box Schedule_RCC |  |  | 12-May-25 A | 18-May-25 A | 0
A51710 | Telecom Junction Box Schedule_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A51720 | Telecom Junction Box Schedule_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
Voltage Drop Calculation For Paga System |  | 2025-12-12 | 2027-01-20 | 2025-10-06 | 2025-12-12 | 50
A23550 | Voltage Drop Calculation For Paga System_IFA | 2025-11-18 | 2026-12-25 | 2025-11-13 | 2025-11-18 | 3
A23570 | Voltage Drop Calculation For Paga System_IFD/IFC | 2025-12-12 | 2027-01-20 | 2025-12-10 | 2025-12-12 | 2
A51730 | Voltage Drop Calculation For Paga System_IFR | 2025-10-13 | 2026-11-30 | 2025-10-06 | 2025-10-13 | 6
A51740 | Voltage Drop Calculation For Paga System_RCC | 2025-11-04 | 2026-12-22 | 2025-10-13 | 2025-11-04 | 16
A51750 | Voltage Drop Calculation For Paga System_RCA | 2025-12-10 | 2027-01-18 | 2025-11-18 | 2025-12-10 | 16
Technical Bid Evaluation For Telecom Cables |  | 2025-11-18 | 2026-02-02 | 2025-09-19 | 2025-11-18 | 43
A51980 | Technical Bid Evaluation For Telecom Cables_IFR | 2025-09-26 | 2025-12-05 | 2025-09-19 | 2025-09-26 | 6
A51990 | Technical Bid Evaluation For Telecom Cables_RCC | 2025-10-20 | 2025-12-26 | 2025-09-26 | 2025-10-20 | 16
A52000 | Technical Bid Evaluation For Telecom Cables_IFA | 2025-10-23 | 2026-01-01 | 2025-10-20 | 2025-10-23 | 3
A52010 | Technical Bid Evaluation For Telecom Cables_RCA | 2025-11-14 | 2026-01-29 | 2025-10-23 | 2025-11-14 | 16
A52020 | Technical Bid Evaluation For Telecom Cables_IFD/IFC | 2025-11-18 | 2026-02-02 | 2025-11-14 | 2025-11-18 | 2
Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System) | [5 empty] | 0
Central Control Room Equipment Layout For Telecom |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A51840 | Central Control Room Equipment Layout For Telecom_IFR |  |  | 01-Jul-25 A | 13-Jul-25 A | 0
A51850 | Central Control Room Equipment Layout For Telecom_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A51860 | Central Control Room Equipment Layout For Telecom_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A51870 | Central Control Room Equipment Layout For Telecom_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A51880 | Central Control Room Equipment Layout For Telecom_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Telecommunication Core Allocation Drawing For Fiber Optic Cable |  | 2026-01-06 | 2027-01-20 | 2025-09-26 | 2026-01-06 | 72
A23750 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFA | 2025-10-31 | 2026-12-25 | 2025-10-28 | 2025-10-31 | 3
A23760 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCA | 2025-11-24 | 2027-01-18 | 2025-10-31 | 2025-11-24 | 16
A23770 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFD/IFC | 2026-01-06 | 2027-01-20 | 2026-01-02 | 2026-01-06 | 2
A51890 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_IFR | 2025-10-06 | 2026-11-30 | 2025-09-26 | 2025-10-06 | 6
A51900 | Telecommunication Core Allocation Drawing For Fiber Optic Cable_RCC | 2025-10-27 | 2026-12-22 | 2025-10-06 | 2025-10-27 | 16
Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit |  | 2026-01-06 | 2027-01-20 | 2025-09-19 | 2026-01-06 | 78
A51560 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFR | 2025-10-06 | 2026-11-23 | 2025-09-19 | 2025-10-06 | 11
A51570 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCC | 2025-10-27 | 2026-12-17 | 2025-10-06 | 2025-10-27 | 16
A51580 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFA | 2025-11-13 | 2026-12-22 | 2025-11-10 | 2025-11-13 | 3
A51590 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_RCA | 2025-12-05 | 2027-01-18 | 2025-11-13 | 2025-12-05 | 16
A51600 | Overall Telecom Cable Routing Layout Drawing For H2 Extraction Unit_IFD/IFC | 2026-01-06 | 2027-01-20 | 2026-01-02 | 2026-01-06 | 2
Overall Telecom Equipment Layout Drawing For H2 Extraction Unit |  | 2026-01-06 | 2027-01-20 | 2025-09-19 | 2026-01-06 | 78
A51510 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFR | 2025-10-06 | 2026-11-23 | 2025-09-19 | 2025-10-06 | 11
A51520 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCC | 2025-10-27 | 2026-12-17 | 2025-10-06 | 2025-10-27 | 16
A51530 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFA | 2025-11-13 | 2026-12-22 | 2025-11-10 | 2025-11-13 | 3
A51540 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_RCA | 2025-12-05 | 2027-01-18 | 2025-11-13 | 2025-12-05 | 16
A51550 | Overall Telecom Equipment Layout Drawing For H2 Extraction Unit_IFD/IFC | 2026-01-06 | 2027-01-20 | 2026-01-02 | 2026-01-06 | 2
Telecom System Material Take Off |  | 2025-10-14 | 2027-01-20 | 02-Jul-25 A | 2025-10-14 | 18
A51610 | Telecom System Material Take Off_IFR |  |  | 02-Jul-25 A | 17-Jul-25 A | 0
A51620 | Telecom System Material Take Off_RCC | 2025-10-10 | 2027-01-18 | 2025-09-19 | 2025-10-10 | 16
A51630 | Telecom System Material Take Off_IFD/IFC | 2025-10-14 | 2027-01-20 | 2025-10-10 | 2025-10-14 | 2
Material/Corrosion |  | 2025-10-20 | 2027-01-20 | 15-Apr-25 A | 2025-10-20 | 21
Material Selection & Corrosion Control Report |  | 2025-10-20 | 2027-01-20 | 15-Apr-25 A | 2025-10-20 | 21
A24040 | Material Selection & Corrosion Control Report_RCC |  |  | 08-May-25 A | 03-Jun-25 A | 0
A24050 | Material Selection & Corrosion Control Report_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A52070 | Material Selection & Corrosion Control Report_IFR |  |  | 15-Apr-25 A | 07-May-25 A | 0
A52080 | Material Selection & Corrosion Control Report_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A52090 | Material Selection & Corrosion Control Report_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Material Selection Diagrams (MSD) |  | 2025-10-20 | 2027-01-20 | 16-Apr-25 A | 2025-10-20 | 21
A24020 | Material Selection Diagrams (MSD)_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
A52030 | Material Selection Diagrams (MSD)_IFR |  |  | 16-Apr-25 A | 25-Jul-25 A | 0
A52040 | Material Selection Diagrams (MSD)_RCC |  |  | 25-Jul-25 A | 01-Aug-25 A | 0
A52050 | Material Selection Diagrams (MSD)_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A52060 | Material Selection Diagrams (MSD)_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
HVAC |  | 2025-11-18 | 2027-01-20 | 13-Mar-25 A | 2025-11-18 | 43
HVAC Design Basis |  |  |  | 13-Mar-25 A | 24-May-25 A | 0
A52100 | HVAC Design Basis_IFR |  |  | 13-Mar-25 A | 26-Apr-25 A | 0
A52110 | HVAC Design Basis_RCC |  |  | 27-Apr-25 A | 03-May-25 A | 0
A52120 | HVAC Design Basis_IFA |  |  | 04-May-25 A | 10-May-25 A | 0
A52130 | HVAC Design Basis_RCA |  |  | 11-May-25 A | 18-May-25 A | 0
A52140 | HVAC Design Basis_IFD/IFC |  |  | 19-May-25 A | 24-May-25 A | 0
HVAC Equipment And Accessories Specifications |  |  |  | 23-Mar-25 A | 19-May-25 A | 0
A52150 | HVAC Equipment And Accessories Specifications_IFR |  |  | 23-Mar-25 A | 13-Apr-25 A | 0
A52160 | HVAC Equipment And Accessories Specifications_RCC |  |  | 14-Apr-25 A | 22-Apr-25 A | 0
A52170 | HVAC Equipment And Accessories Specifications_IFA |  |  | 23-Apr-25 A | 05-May-25 A | 0
A52180 | HVAC Equipment And Accessories Specifications_RCA |  |  | 06-May-25 A | 12-May-25 A | 0
A52190 | HVAC Equipment And Accessories Specifications_IFD/IFC |  |  | 13-May-25 A | 19-May-25 A | 0
HVAC Cooling Load Calculation And Equipment Sizing |  |  |  | 20-Apr-25 A | 03-Jun-25 A | 0
A24210 | HVAC Cooling Load Calculation And Equipment Sizing_RCA |  |  | 26-May-25 A | 31-May-25 A | 0
A24220 | HVAC Cooling Load Calculation And Equipment Sizing_IFD/IFC |  |  | 01-Jun-25 A | 03-Jun-25 A | 0
A52200 | HVAC Cooling Load Calculation And Equipment Sizing_IFR |  |  | 20-Apr-25 A | 11-May-25 A | 0
A52210 | HVAC Cooling Load Calculation And Equipment Sizing_RCC |  |  | 12-May-25 A | 18-May-25 A | 0
A52220 | HVAC Cooling Load Calculation And Equipment Sizing_IFA |  |  | 23-May-25 A | 25-May-25 A | 0
HVAC Airflow Schematic Diagrams |  |  |  | 25-Apr-25 A | 03-Jun-25 A | 0
A52540 | HVAC Airflow Schematic Diagrams_IFR |  |  | 25-Apr-25 A | 16-May-25 A | 0
A52550 | HVAC Airflow Schematic Diagrams_RCC |  |  | 17-May-25 A | 20-May-25 A | 0
A52560 | HVAC Airflow Schematic Diagrams_IFA |  |  | 21-May-25 A | 25-May-25 A | 0
A52570 | HVAC Airflow Schematic Diagrams_RCA |  |  | 26-May-25 A | 31-May-25 A | 0
A52580 | HVAC Airflow Schematic Diagrams_IFD/IFC |  |  | 01-Jun-25 A | 03-Jun-25 A | 0
HVAC Chilled Water Piping Schematic Diagrams |  | 2025-11-11 | 2027-01-20 | 20-Jun-25 A | 2025-11-11 | 37
A52590 | HVAC Chilled Water Piping Schematic Diagrams_IFR |  |  | 20-Jun-25 A | 05-Jul-25 A | 0
A52600 | HVAC Chilled Water Piping Schematic Diagrams_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A52610 | HVAC Chilled Water Piping Schematic Diagrams_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A52620 | HVAC Chilled Water Piping Schematic Diagrams_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A52630 | HVAC Chilled Water Piping Schematic Diagrams_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
HVAC Chilled Water Piping And Instrumentation Diagrams |  | 2025-11-11 | 2027-01-20 | 02-Jun-25 A | 2025-11-11 | 37
A52840 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFR |  |  | 02-Jun-25 A | 05-Jul-25 A | 0
A52850 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A52860 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFH | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A52870 | HVAC Chilled Water Piping And Instrumentation Diagrams_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A52880 | HVAC Chilled Water Piping And Instrumentation Diagrams_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
HVAC Ducting and Instrumentation Diagrams |  | 2025-11-11 | 2027-01-20 | 17-Jun-25 A | 2025-11-11 | 37
A52790 | HVAC Ducting and Instrumentation Diagrams_IFR |  |  | 17-Jun-25 A | 08-Jul-25 A | 0
A52800 | HVAC Ducting and Instrumentation Diagrams_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A52810 | HVAC Ducting and Instrumentation Diagrams_IFH | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A52820 | HVAC Ducting and Instrumentation Diagrams_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A52830 | HVAC Ducting and Instrumentation Diagrams_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
HVAC Equipment Schedules |  | 2025-10-20 | 2027-01-20 | 09-Jun-25 A | 2025-10-20 | 21
A52890 | HVAC Equipment Schedules_IFR |  |  | 09-Jun-25 A | 16-Jun-25 A | 0
A52900 | HVAC Equipment Schedules_RCC |  |  | 17-Jun-25 A | 07-Jul-25 A | 0
A52910 | HVAC Equipment Schedules_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A52920 | HVAC Equipment Schedules_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A52930 | HVAC Equipment Schedules_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
HVAC System Cause & Effect |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A52990 | HVAC System Cause & Effect_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A53000 | HVAC System Cause & Effect_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A53010 | HVAC System Cause & Effect_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A53020 | HVAC System Cause & Effect_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A53030 | HVAC System Cause & Effect_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
HVAC Chilled Water Pump Head Calculation |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A53090 | HVAC Chilled Water Pump Head Calculation_IFR |  |  | 01-Jul-25 A | 09-Jul-25 A | 0
A53100 | HVAC Chilled Water Pump Head Calculation_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A53110 | HVAC Chilled Water Pump Head Calculation_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A53120 | HVAC Chilled Water Pump Head Calculation_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A53130 | HVAC Chilled Water Pump Head Calculation_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
HVAC Technical Data Sheet For Air Handling Unit |  | 2025-09-23 | 2026-02-23 | 01-May-25 A | 2025-09-23 | 2
A52240 | HVAC Technical Data Sheet For Air Handling Unit_IFR |  |  | 01-May-25 A | 22-May-25 A | 0
A52250 | HVAC Technical Data Sheet For Air Handling Unit_RCC |  |  | 23-May-25 A | 10-Jun-25 A | 0
A52260 | HVAC Technical Data Sheet For Air Handling Unit_IFA |  |  | 11-Jun-25 A | 26-Jun-25 A | 0
A52270 | HVAC Technical Data Sheet For Air Handling Unit_RCA |  |  | 27-Jun-25 A | 10-Sep-25 A | 0
A52280 | HVAC Technical Data Sheet For Air Handling Unit_IFD/IFC | 2025-09-23 | 2026-02-23 | 2025-09-19 | 2025-09-23 | 2
HVAC Technical Data Sheet For Air Cooled Chiller |  |  |  | 26-May-25 A | 10-Jun-25 A | 0
A24230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFR |  |  | 26-May-25 A | 28-May-25 A | 0
A24240 | HVAC Technical Data Sheet For Air Cooled Chiller_RCC |  |  | 29-May-25 A | 31-May-25 A | 0
A24250 | HVAC Technical Data Sheet For Air Cooled Chiller_IFA |  |  | 01-Jun-25 A | 04-Jun-25 A | 0
A24260 | HVAC Technical Data Sheet For Air Cooled Chiller_RCA |  |  | 05-Jun-25 A | 07-Jun-25 A | 0
A52230 | HVAC Technical Data Sheet For Air Cooled Chiller_IFD/IFC |  |  | 08-Jun-25 A | 10-Jun-25 A | 0
HVAC Technical Data Sheet For Chilled Water Pump |  | 2025-09-23 | 2026-02-23 | 26-May-25 A | 2025-09-23 | 2
A52290 | HVAC Technical Data Sheet For Chilled Water Pump_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A52300 | HVAC Technical Data Sheet For Chilled Water Pump_RCC |  |  | 06-Jul-25 A | 01-Aug-25 A | 0
A52310 | HVAC Technical Data Sheet For Chilled Water Pump_IFA |  |  | 02-Aug-25 A | 27-Aug-25 A | 0
A52320 | HVAC Technical Data Sheet For Chilled Water Pump_RCA |  |  | 28-Aug-25 A | 10-Sep-25 A | 0
A52330 | HVAC Technical Data Sheet For Chilled Water Pump_IFD/IFC | 2025-09-23 | 2026-02-23 | 2025-09-19 | 2025-09-23 | 2
HVAC Technical Data Sheet For Chemical Filter Unit |  | 2025-09-23 | 2026-02-23 | 26-May-25 A | 2025-09-23 | 2
A52340 | HVAC Technical Data Sheet For Chemical Filter Unit_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A52350 | HVAC Technical Data Sheet For Chemical Filter Unit_RCC |  |  | 06-Jul-25 A | 01-Aug-25 A | 0
A52360 | HVAC Technical Data Sheet For Chemical Filter Unit_IFA |  |  | 02-Aug-25 A | 29-Aug-25 A | 0
A52370 | HVAC Technical Data Sheet For Chemical Filter Unit_RCA |  |  | 30-Aug-25 A | 12-Sep-25 A | 0
A52380 | HVAC Technical Data Sheet For Chemical Filter Unit_IFD/IFC | 2025-09-23 | 2026-02-23 | 2025-09-19 | 2025-09-23 | 2
HVAC Technical Data Sheet For Inertia Filter With Bleed Fan |  | 2025-09-23 | 2026-02-23 | 26-May-25 A | 2025-09-23 | 2
A52390 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A52400 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCC |  |  | 06-Jul-25 A | 30-Jul-25 A | 0
A52410 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFA |  |  | 31-Jul-25 A | 22-Aug-25 A | 0
A52420 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_RCA |  |  | 23-Aug-25 A | 10-Sep-25 A | 0
A52430 | HVAC Technical Data Sheet For Inertia Filter With Bleed Fan_IFD/IFC | 2025-09-23 | 2026-02-23 | 2025-09-19 | 2025-09-23 | 2
HVAC Technical Data Sheet For Exhaust Air Fans |  |  |  | 26-May-25 A | 15-Sep-25 A | 0
A52440 | HVAC Technical Data Sheet For Exhaust Air Fans_IFR |  |  | 26-May-25 A | 05-Jul-25 A | 0
A52450 | HVAC Technical Data Sheet For Exhaust Air Fans_RCC |  |  | 06-Jul-25 A | 01-Aug-25 A | 0
A52460 | HVAC Technical Data Sheet For Exhaust Air Fans_IFA |  |  | 02-Aug-25 A | 01-Sep-25 A | 0
A52470 | HVAC Technical Data Sheet For Exhaust Air Fans_RCA |  |  | 02-Sep-25 A | 08-Sep-25 A | 0
A52480 | HVAC Technical Data Sheet For Exhaust Air Fans_IFD/IFC |  |  | 09-Sep-25 A | 15-Sep-25 A | 0
HVAC Technical Data Sheet For Electric Duct Heater |  |  |  | 26-May-25 A | 15-Sep-25 A | 0
A52490 | HVAC Technical Data Sheet For Electric Duct Heater_IFR |  |  | 26-May-25 A | 01-Jun-25 A | 0
A52500 | HVAC Technical Data Sheet For Electric Duct Heater_RCC |  |  | 02-Jun-25 A | 15-Jun-25 A | 0
A52510 | HVAC Technical Data Sheet For Electric Duct Heater_IFA |  |  | 16-Jun-25 A | 20-Jun-25 A | 0
A52520 | HVAC Technical Data Sheet For Electric Duct Heater_RCA |  |  | 21-Jun-25 A | 08-Sep-25 A | 0
A52530 | HVAC Technical Data Sheet For Electric Duct Heater_IFD/IFC |  |  | 09-Sep-25 A | 15-Sep-25 A | 0
HVAC Chilled Water Piping Layouts & Sections |  | 2025-11-18 | 2027-01-20 | 10-Jul-25 A | 2025-11-18 | 43
A52740 | HVAC Chilled Water Piping Layouts & Sections_IFR | 2025-09-26 | 2026-11-30 | 10-Jul-25 A | 2025-09-26 | 6
A52750 | HVAC Chilled Water Piping Layouts & Sections_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A52760 | HVAC Chilled Water Piping Layouts & Sections_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A52770 | HVAC Chilled Water Piping Layouts & Sections_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A52780 | HVAC Chilled Water Piping Layouts & Sections_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
HVAC System Sequence Of Operation And Control Philosophy |  | 2025-11-11 | 2027-01-20 | 01-Jul-25 A | 2025-11-11 | 37
A52940 | HVAC System Sequence Of Operation And Control Philosophy_IFR |  |  | 01-Jul-25 A | 16-Jul-25 A | 0
A52950 | HVAC System Sequence Of Operation And Control Philosophy_RCC | 2025-10-10 | 2026-12-22 | 2025-09-19 | 2025-10-10 | 16
A52960 | HVAC System Sequence Of Operation And Control Philosophy_IFA | 2025-10-16 | 2026-12-25 | 2025-10-10 | 2025-10-16 | 3
A52970 | HVAC System Sequence Of Operation And Control Philosophy_RCA | 2025-11-06 | 2027-01-18 | 2025-10-16 | 2025-11-06 | 16
A52980 | HVAC System Sequence Of Operation And Control Philosophy_IFD/IFC | 2025-11-11 | 2027-01-20 | 2025-11-06 | 2025-11-11 | 2
Material Requisition For HVAC Equipments |  | 2025-10-14 | 2026-02-25 | 02-Jun-25 A | 2025-10-14 | 18
A53190 | Material Requisition For HVAC Equipments_IFR |  |  | 02-Jun-25 A | 03-Jun-25 A | 0
A53200 | Material Requisition For HVAC Equipments_RCC |  |  | 03-Jun-25 A | 05-Jun-25 A | 0
A53210 | Material Requisition For HVAC Equipments_IFA |  |  | 06-Jun-25 A | 10-Jun-25 A | 0
A53220 | Material Requisition For HVAC Equipments_RCA | 2025-10-10 | 2026-02-23 | 2025-09-19 | 2025-10-10 | 16
A53230 | Material Requisition For HVAC Equipments_IFD/IFC | 2025-10-14 | 2026-02-25 | 2025-10-10 | 2025-10-14 | 2
Material Requisition for Fire Detection System & LFCP |  | 2025-10-17 | 2026-02-25 | 09-Jun-25 A | 2025-10-17 | 2
A15420 | Material Requisition for Fire Detection System & LFCP_IFD/IFC | 2025-10-17 | 2026-02-25 | 2025-10-15 | 2025-10-17 | 2
A47780 | Material Requisition for Fire Detection System & LFCP_IFR |  |  | 09-Jun-25 A | 12-Jun-25 A | 0
A47790 | Material Requisition for Fire Detection System & LFCP_RCC |  |  | 13-Jun-25 A | 18-Jun-25 A | 0
A47800 | Material Requisition for Fire Detection System & LFCP_IFA |  |  | 18-Jun-25 A | 20-Jun-25 A | 0
A47810 | Material Requisition for Fire Detection System & LFCP_RCA |  |  | 21-Jun-25 A | 10-Sep-25 A | 0
HVAC Equipment And Ducting Layouts |  | 2025-11-11 | 2026-10-30 | 29-Jun-25 A | 2025-11-11 | 37
A52640 | HVAC Equipment And Ducting Layouts_IFR |  |  | 29-Jun-25 A | 18-Jul-25 A | 0
A52650 | HVAC Equipment And Ducting Layouts_RCC | 2025-10-10 | 2026-10-01 | 2025-09-19 | 2025-10-10 | 16
A52660 | HVAC Equipment And Ducting Layouts_IFA | 2025-10-16 | 2026-10-06 | 2025-10-10 | 2025-10-16 | 3
A52670 | HVAC Equipment And Ducting Layouts_RCA | 2025-11-06 | 2026-10-28 | 2025-10-16 | 2025-11-06 | 16
A52680 | HVAC Equipment And Ducting Layouts_IFD/IFC | 2025-11-11 | 2026-10-30 | 2025-11-06 | 2025-11-11 | 2
HVAC Ducting Section Layout |  | 2025-10-20 | 2027-01-20 | 03-Aug-25 A | 2025-10-20 | 21
A52690 | HVAC Ducting Section Layout_IFR |  |  | 03-Aug-25 A | 18-Aug-25 A | 0
A52700 | HVAC Ducting Section Layout_RCC |  |  | 19-Aug-25 A | 22-Aug-25 A | 0
A52710 | HVAC Ducting Section Layout_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A52720 | HVAC Ducting Section Layout_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A52730 | HVAC Ducting Section Layout_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
HVAC External Static Pressure Calculation |  | 2025-11-18 | 2027-01-20 | 2025-09-19 | 2025-11-18 | 43
A53040 | HVAC External Static Pressure Calculation_IFR | 2025-09-26 | 2026-11-30 | 2025-09-19 | 2025-09-26 | 6
A53050 | HVAC External Static Pressure Calculation_RCC | 2025-10-20 | 2026-12-22 | 2025-09-26 | 2025-10-20 | 16
A53060 | HVAC External Static Pressure Calculation_IFA | 2025-10-23 | 2026-12-25 | 2025-10-20 | 2025-10-23 | 3
A53070 | HVAC External Static Pressure Calculation_RCA | 2025-11-14 | 2027-01-18 | 2025-10-23 | 2025-11-14 | 16
A53080 | HVAC External Static Pressure Calculation_IFD/IFC | 2025-11-18 | 2027-01-20 | 2025-11-14 | 2025-11-18 | 2
HVAC Standard Installation Details |  | 2025-10-20 | 2027-01-20 | 25-Apr-25 A | 2025-10-20 | 21
A53140 | HVAC Standard Installation Details_IFR |  |  | 25-Apr-25 A | 16-May-25 A | 0
A53150 | HVAC Standard Installation Details_RCC |  |  | 17-May-25 A | 10-Jun-25 A | 0
A53160 | HVAC Standard Installation Details_IFA | 2025-09-24 | 2026-12-25 | 2025-09-19 | 2025-09-24 | 3
A53170 | HVAC Standard Installation Details_RCA | 2025-10-16 | 2027-01-18 | 2025-09-24 | 2025-10-16 | 16
A53180 | HVAC Standard Installation Details_IFD/IFC | 2025-10-20 | 2027-01-20 | 2025-10-16 | 2025-10-20 | 2
Technical Bid Evaluation For HVAC Equipments | [5 empty] | 0
Technical Bid Evaluation for Fire Detection System & LFCP |  | 2025-11-12 | 2027-01-20 | 2025-09-19 | 2025-11-12 | 38
A16940 | Technical Bid Evaluation for Fire Detection System & LFCP_RCC | 2025-10-13 | 2025-12-26 | 2025-09-26 | 2025-10-13 | 11
A16950 | Technical Bid Evaluation for Fire Detection System & LFCP_IFA | 2025-10-17 | 2026-01-01 | 2025-10-13 | 2025-10-17 | 3
A16960 | Technical Bid Evaluation for Fire Detection System & LFCP_RCA | 2025-11-07 | 2027-01-18 | 2025-10-17 | 2025-11-07 | 16
A16970 | Technical Bid Evaluation for Fire Detection System & LFCP_IFD/IFC | 2025-11-12 | 2027-01-20 | 2025-11-10 | 2025-11-12 | 2
A48260 | Technical Bid Evaluation for Fire Detection System & LFCP_IFR | 2025-09-26 | 2025-12-11 | 2025-09-19 | 2025-09-26 | 6
Procurement - HO Services |  | 2026-03-25 | 2027-01-20 | 01-Jan-25 A | 2026-03-25 | 134
Equipment Packages |  |  |  | 01-Jan-25 A | 18-Sep-25 A | 0
Vessels |  |  |  | 01-Jan-25 A | 20-Jun-25 A | 0
C4 Guard Adsorber Cooler - (BF) |  |  |  | 01-Jan-25 A | 20-Jun-25 A | 0
A57190 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 28-Apr-25 A | 03-May-25 A | 0
A57200 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 04-May-25 A | 03-Jun-25 A | 0
A57210 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 04-Jun-25 A | 08-Jun-25 A | 0
A57220 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 09-Jun-25 A | 14-Jun-25 A | 0
A57230 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 15-Jun-25 A | 20-Jun-25 A | 0
A8310 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 14-Jan-25 A | 0
A8340 | Issue Purchase Order to Vendor |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
Vessel's Internals (05 Dimister pads) |  |  |  | 01-Jan-25 A | 20-Jun-25 A | 0
A15970 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 14-Jan-25 A | 0
A18020 | Issue Purchase Order to Vendor |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A18040 | Commercial Bid Evaluation(Completion) |  |  | 15-Jun-25 A | 20-Jun-25 A | 0
A56540 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 28-Apr-25 A | 03-May-25 A | 0
A56550 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 04-May-25 A | 03-Jun-25 A | 0
A56560 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 04-Jun-25 A | 08-Jun-25 A | 0
A56570 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 09-Jun-25 A | 14-Jun-25 A | 0
A56580 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 09-Jun-25 A | 14-Jun-25 A | 0
Vessels/Drums |  |  |  | 01-Jan-25 A | 20-Jun-25 A | 0
FG Comp. 2nd Stage Suc. Drum (13-VV-706) |  |  |  | 01-Jan-25 A | 20-Jun-25 A | 0
A35900 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 14-Jan-25 A | 0
A35920 | Commercial Bid Evaluation(Completion) |  |  | 15-Jun-25 A | 20-Jun-25 A | 0
A35930 | Issue Purchase Order to Vendor |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A45960 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 28-Apr-25 A | 03-May-25 A | 0
A45970 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 25-Mar-25 A | 27-Mar-25 A | 0
A45980 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 28-Mar-25 A | 29-Mar-25 A | 0
A45990 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 30-Mar-25 A | 31-Mar-25 A | 0
A46000 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 31-Mar-25 A | 01-Apr-25 A | 0
FG Comp.1st Stage Suc. Drum (13-VV-705) |  |  |  | 01-Jan-25 A | 07-Apr-25 A | 0
A17540 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 14-Jan-25 A | 0
A56290 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 23-Mar-25 A | 24-Mar-25 A | 0
A56300 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 25-Mar-25 A | 27-Mar-25 A | 0
A56310 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 28-Mar-25 A | 29-Mar-25 A | 0
A56320 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 30-Mar-25 A | 31-Mar-25 A | 0
A56330 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 01-Apr-25 A | 02-Apr-25 A | 0
A9200 | Issue Purchase Order to Vendor |  |  | 04-Apr-25 A | 07-Apr-25 A | 0
A9220 | Commercial Bid Evaluation(Completion) |  |  | 03-Apr-25 A | 04-Apr-25 A | 0
PSA2 Slop Drum (70-VV-1415) |  |  |  | 01-Jan-25 A | 12-Apr-25 A | 0
A35940 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 14-Jan-25 A | 0
A35960 | Commercial Bid Evaluation(Completion) |  |  | 02-Apr-25 A | 03-Apr-25 A | 0
A35970 | Issue Purchase Order to Vendor |  |  | 04-Apr-25 A | 12-Apr-25 A | 0
A56340 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 23-Mar-25 A | 24-Mar-25 A | 0
A56350 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 25-Mar-25 A | 27-Mar-25 A | 0
A56360 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 28-Mar-25 A | 29-Mar-25 A | 0
A56370 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 30-Mar-25 A | 31-Mar-25 A | 0
A56380 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 31-Mar-25 A | 01-Apr-25 A | 0
OG Comp. 2nd Stage Suc. Drum (13-VV-713) |  |  |  | 01-Jan-25 A | 12-Apr-25 A | 0
A35980 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 14-Jan-25 A | 0
A36000 | Commercial Bid Evaluation(Completion) |  |  | 02-Apr-25 A | 03-Apr-25 A | 0
A36010 | Issue Purchase Order to Vendor |  |  | 04-Apr-25 A | 12-Apr-25 A | 0
A56390 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 23-Mar-25 A | 24-Mar-25 A | 0
A56400 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 25-Mar-25 A | 27-Mar-25 A | 0
A56410 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 28-Mar-25 A | 29-Mar-25 A | 0
A56420 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 30-Mar-25 A | 31-Mar-25 A | 0
A56430 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 31-Mar-25 A | 01-Apr-25 A | 0
FG Comp. 2nd Stage Dis. Drum (13-VV-707) |  |  |  | 01-Jan-25 A | 12-Apr-25 A | 0
A36020 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 14-Jan-25 A | 0
A36040 | Commercial Bid Evaluation(Completion) |  |  | 02-Apr-25 A | 03-Apr-25 A | 0
A36050 | Issue Purchase Order to Vendor |  |  | 04-Apr-25 A | 12-Apr-25 A | 0
A56440 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 23-Mar-25 A | 24-Mar-25 A | 0
A56450 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 25-Mar-25 A | 27-Mar-25 A | 0
A56460 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 28-Mar-25 A | 29-Mar-25 A | 0
A56470 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 30-Mar-25 A | 31-Mar-25 A | 0
A56480 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 31-Mar-25 A | 01-Apr-25 A | 0
OG Buffer Drum (13-VV-712) |  |  |  | 01-Jan-25 A | 12-Apr-25 A | 0
A36060 | Issue RFQ to Bidders |  |  | 01-Jan-25 A | 22-Mar-25 A | 0
A36080 | Commercial Bid Evaluation(Completion) |  |  | 02-Apr-25 A | 03-Apr-25 A | 0
A36090 | Issue Purchase Order to Vendor |  |  | 04-Apr-25 A | 12-Apr-25 A | 0
A56490 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 23-Mar-25 A | 24-Mar-25 A | 0
A56500 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 25-Mar-25 A | 27-Mar-25 A | 0
A56510 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 28-Mar-25 A | 29-Mar-25 A | 0
A56520 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 30-Mar-25 A | 31-Mar-25 A | 0
A56530 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 31-Mar-25 A | 01-Apr-25 A | 0
Water Collection & Sanitary Wastewater Pumps |  |  |  | 01-Apr-25 A | 17-Sep-25 A | 0
Sanitary Waste Water Sump Pump |  |  |  | 01-Apr-25 A | 17-Sep-25 A | 0
A19470 | Issue Purchase Order to Vendor |  |  | 15-Sep-25 A | 17-Sep-25 A | 0
A19490 | Commercial Bid Evaluation(Completion) |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
A45810 | Technical Bid Evaluation for Centrifugal Pump_IFR |  |  | 10-Jun-25 A | 12-Jun-25 A | 0
A45820 | Technical Bid Evaluation for Centrifugal Pump_RCC |  |  | 13-Jun-25 A | 18-Jun-25 A | 0
A45830 | Technical Bid Evaluation for Centrifugal Pump_IFA |  |  | 04-Jul-25 A | 23-Aug-25 A | 0
A45840 | Technical Bid Evaluation for Centrifugal Pump_RCA |  |  | 24-Aug-25 A | 30-Aug-25 A | 0
A45850 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC |  |  | 01-Sep-25 A | 05-Sep-25 A | 0
A8430 | RFQs to Bid Receipt |  |  | 01-Apr-25 A | 10-Apr-25 A | 0
Water Collection Sump Pump ll |  |  |  | 01-Apr-25 A | 05-Aug-25 A | 0
A19410 | Issue Purchase Order to Vendor |  |  | 30-Jul-25 A | 05-Aug-25 A | 0
A19430 | Commercial Bid Evaluation(Completion) |  |  | 18-Jul-25 A | 29-Jul-25 A | 0
A56890 | Technical Bid Evaluation for Centrifugal Pump_IFR |  |  | 10-Jun-25 A | 12-Jun-25 A | 0
A56900 | Technical Bid Evaluation for Centrifugal Pump_RCC |  |  | 13-Jun-25 A | 18-Jun-25 A | 0
A56910 | Technical Bid Evaluation for Centrifugal Pump_IFA |  |  | 19-Jun-25 A | 23-Jun-25 A | 0
A56920 | Technical Bid Evaluation for Centrifugal Pump_RCA |  |  | 24-Jun-25 A | 29-Jun-25 A | 0
A56930 | Technical Bid Evaluation for Centrifugal Pump_IFD/IFC |  |  | 30-Jun-25 A | 03-Jul-25 A | 0
A8490 | RFQs to Bid Receipt |  |  | 01-Apr-25 A | 10-Apr-25 A | 0
EOT Cranes |  |  |  | 01-May-25 A | 18-Sep-25 A | 0
EOT Crane for FG Compressor (1 = 60 Ton) |  |  |  | 01-May-25 A | 13-Aug-25 A | 0
A20470 | Issue Purchase Order to Vendor |  |  | 07-Aug-25 A | 13-Aug-25 A | 0
A20490 | Commercial Bid Evaluation(Completion) |  |  | 23-Jul-25 A | 06-Aug-25 A | 0
A45860 | Technical Bid Evaluation for EOT Crane_IFR |  |  | 20-Jun-25 A | 24-Jun-25 A | 0
A45870 | Technical Bid Evaluation for EOT Crane_RCC |  |  | 25-Jun-25 A | 30-Jun-25 A | 0
A45880 | Technical Bid Evaluation for EOT Crane_IFA |  |  | 30-Jun-25 A | 06-Jul-25 A | 0
A45890 | Technical Bid Evaluation for EOT Crane_RCA |  |  | 06-Jul-25 A | 12-Jul-25 A | 0
A45900 | Technical Bid Evaluation for EOT Crane_IFD/IFC |  |  | 13-Jul-25 A | 22-Jul-25 A | 0
A8370 | Issue RFQ to Bidders |  |  | 01-May-25 A | 15-May-25 A | 0
EOT Crane for OG Compressor (1 = 25 Ton) |  |  |  | 01-May-25 A | 18-Sep-25 A | 0
A20530 | Issue Purchase Order to Vendor |  |  | 17-Sep-25 A | 18-Sep-25 A | 0
A20550 | Commercial Bid Evaluation(Completion) |  |  | 15-Sep-25 A | 17-Sep-25 A | 0
A56940 | Technical Bid Evaluation for EOT Crane_IFR |  |  | 20-Jun-25 A | 15-Aug-25 A | 0
A56950 | Technical Bid Evaluation for EOT Crane_RCC |  |  | 16-Aug-25 A | 22-Aug-25 A | 0
A56960 | Technical Bid Evaluation for EOT Crane_IFA |  |  | 23-Aug-25 A | 30-Aug-25 A | 0
A56970 | Technical Bid Evaluation for EOT Crane_RCA |  |  | 01-Sep-25 A | 05-Sep-25 A | 0
A56980 | Technical Bid Evaluation for EOT Crane_IFD/IFC |  |  | 01-Sep-25 A | 12-Sep-25 A | 0
A8250 | Issue RFQ to Bidders |  |  | 01-May-25 A | 20-Jun-25 A | 0
Heat Exchangers |  |  |  | 01-Jun-25 A | 02-Jul-25 A | 0
Heat Exchanger (Type S & T = 06 Nos) |  |  |  | 01-Jun-25 A | 02-Jul-25 A | 0
FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  |  |  | 01-Jun-25 A | 27-Jun-25 A | 0
A36100 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 03-Jun-25 A | 0
A36120 | Commercial Bid Evaluation(Completion) |  |  | 20-Jun-25 A | 24-Jun-25 A | 0
A36130 | Issue Purchase Order to Vendor |  |  | 25-Jun-25 A | 27-Jun-25 A | 0
A45460 | Technical Bid Evaluation for Heat Exchangers_IFR |  |  | 04-Jun-25 A | 07-Jun-25 A | 0
A45470 | Technical Bid Evaluation for Heat Exchangers_RCC |  |  | 08-Jun-25 A | 11-Jun-25 A | 0
A45480 | Technical Bid Evaluation for Heat Exchangers_IFA |  |  | 12-Jun-25 A | 14-Jun-25 A | 0
A45490 | Technical Bid Evaluation for Heat Exchangers_RCA |  |  | 15-Jun-25 A | 17-Jun-25 A | 0
A45500 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  |  | 18-Jun-25 A | 20-Jun-25 A | 0
OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  |  |  | 01-Jun-25 A | 27-Jun-25 A | 0
A36140 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 03-Jun-25 A | 0
A36160 | Commercial Bid Evaluation(Completion) |  |  | 20-Jun-25 A | 24-Jun-25 A | 0
A36170 | Issue Purchase Order to Vendor |  |  | 25-Jun-25 A | 27-Jun-25 A | 0
A56640 | Technical Bid Evaluation for Heat Exchangers_IFR |  |  | 04-Jun-25 A | 07-Jun-25 A | 0
A56650 | Technical Bid Evaluation for Heat Exchangers_RCC |  |  | 08-Jun-25 A | 11-Jun-25 A | 0
A56660 | Technical Bid Evaluation for Heat Exchangers_IFA |  |  | 12-Jun-25 A | 14-Jun-25 A | 0
A56670 | Technical Bid Evaluation for Heat Exchangers_RCA |  |  | 15-Jun-25 A | 17-Jun-25 A | 0
A56680 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  |  | 18-Jun-25 A | 20-Jun-25 A | 0
FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  |  |  | 01-Jun-25 A | 27-Jun-25 A | 0
A36950 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 03-Jun-25 A | 0
A36970 | Commercial Bid Evaluation(Completion) |  |  | 20-Jun-25 A | 24-Jun-25 A | 0
A36980 | Issue Purchase Order to Vendor |  |  | 25-Jun-25 A | 27-Jun-25 A | 0
A56690 | Technical Bid Evaluation for Heat Exchangers_IFR |  |  | 04-Jun-25 A | 07-Jun-25 A | 0
A56700 | Technical Bid Evaluation for Heat Exchangers_RCC |  |  | 08-Jun-25 A | 11-Jun-25 A | 0
A56710 | Technical Bid Evaluation for Heat Exchangers_IFA |  |  | 12-Jun-25 A | 14-Jun-25 A | 0
A56720 | Technical Bid Evaluation for Heat Exchangers_RCA |  |  | 15-Jun-25 A | 17-Jun-25 A | 0
A56730 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  |  | 18-Jun-25 A | 20-Jun-25 A | 0
OG Comp. Interstage Cooler (BEU) (13-HE-708) |  |  |  | 01-Jun-25 A | 27-Jun-25 A | 0
A36990 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 03-Jun-25 A | 0
A37010 | Commercial Bid Evaluation(Completion) |  |  | 20-Jun-25 A | 24-Jun-25 A | 0
A37020 | Issue Purchase Order to Vendor |  |  | 25-Jun-25 A | 27-Jun-25 A | 0
A56740 | Technical Bid Evaluation for Heat Exchangers_IFR |  |  | 04-Jun-25 A | 07-Jun-25 A | 0
A56750 | Technical Bid Evaluation for Heat Exchangers_RCC |  |  | 08-Jun-25 A | 11-Jun-25 A | 0
A56760 | Technical Bid Evaluation for Heat Exchangers_IFA |  |  | 12-Jun-25 A | 14-Jun-25 A | 0
A56770 | Technical Bid Evaluation for Heat Exchangers_RCA |  |  | 15-Jun-25 A | 17-Jun-25 A | 0
A56780 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  |  | 18-Jun-25 A | 20-Jun-25 A | 0
C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  |  |  | 01-Jun-25 A | 02-Jul-25 A | 0
A37030 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 03-Jun-25 A | 0
A37050 | Commercial Bid Evaluation(Completion) |  |  | 20-Jun-25 A | 27-Jun-25 A | 0
A37060 | Issue Purchase Order to Vendor |  |  | 30-Jun-25 A | 02-Jul-25 A | 0
A56790 | Technical Bid Evaluation for Heat Exchangers_IFR |  |  | 04-Jun-25 A | 07-Jun-25 A | 0
A56800 | Technical Bid Evaluation for Heat Exchangers_RCC |  |  | 08-Jun-25 A | 11-Jun-25 A | 0
A56810 | Technical Bid Evaluation for Heat Exchangers_IFA |  |  | 12-Jun-25 A | 14-Jun-25 A | 0
A56820 | Technical Bid Evaluation for Heat Exchangers_RCA |  |  | 15-Jun-25 A | 17-Jun-25 A | 0
A56830 | Technical Bid Evaluation for Heat Exchangers_IFD/IFC |  |  | 18-Jun-25 A | 20-Jun-25 A | 0
HVAC |  |  |  | 25-May-25 A | 29-Aug-25 A | 0
HVAC |  |  |  | 25-May-25 A | 29-Aug-25 A | 0
A16510 | Issue RFQ to Bidders |  |  | 25-May-25 A | 03-Jun-25 A | 0
A19870 | Issue Purchase Order to Vendor |  |  | 20-Aug-25 A | 29-Aug-25 A | 0
A19890 | Commercial Bid Evaluation(Completion) |  |  | 15-Jul-25 A | 31-Jul-25 A | 0
A25290 | Technical Bid Evaluation For HVAC Equipments_RCC |  |  | 20-Jun-25 A | 25-Jun-25 A | 0
A25300 | Technical Bid Evaluation For HVAC Equipments_IFA |  |  | 26-Jun-25 A | 02-Jul-25 A | 0
A25310 | Technical Bid Evaluation For HVAC Equipments_RCA |  |  | 03-Jul-25 A | 08-Jul-25 A | 0
A25320 | Technical Bid Evaluation For HVAC Equipments_IFD/IFC |  |  | 09-Jul-25 A | 14-Jul-25 A | 0
A53240 | Technical Bid Evaluation For HVAC Equipments_IFR |  |  | 04-Jun-25 A | 19-Jun-25 A | 0
Bulk Materials |  | 2026-03-25 | 2027-01-20 | 15-Jan-25 A | 2026-03-25 | 134
Drip Leg |  |  |  | 01-Aug-25 A | 09-Sep-25 A | 0
OG Comp. Dis. Drip leg (02 Nos) |  |  |  | 01-Aug-25 A | 09-Sep-25 A | 0
A19350 | Issue Purchase Order to Vendor |  |  | 04-Sep-25 A | 09-Sep-25 A | 0
A19370 | Commercial Bid Evaluation(Completion) |  |  | 30-Aug-25 A | 03-Sep-25 A | 0
A56840 | Technical Bid Evaluation for Pressure Vessels & Internals_IFR |  |  | 06-Aug-25 A | 07-Aug-25 A | 0
A56850 | Technical Bid Evaluation for Pressure Vessels & Internals_RCC |  |  | 08-Aug-25 A | 13-Aug-25 A | 0
A56860 | Technical Bid Evaluation for Pressure Vessels & Internals_IFA |  |  | 14-Aug-25 A | 19-Aug-25 A | 0
A56870 | Technical Bid Evaluation for Pressure Vessels & Internals_RCA |  |  | 20-Aug-25 A | 25-Aug-25 A | 0
A56880 | Technical Bid Evaluation for Pressure Vessels & Internals_IFD/IFC |  |  | 26-Aug-25 A | 29-Aug-25 A | 0
A8790 | Issue RFQ to Bidders |  |  | 01-Aug-25 A | 05-Aug-25 A | 0
Fire Fighting Equipment |  | 2025-11-13 | 2026-01-23 | 11-Feb-25 A | 2025-11-13 | 40
TA_Fire Alarm System Modification - SAFCO |  |  |  | 11-Feb-25 A | 31-Mar-25 A | 0
A37120 | Issue RFQ to Bidders |  |  | 11-Feb-25 A | 28-Feb-25 A | 0
A37150 | Issue Purchase Order to Vendor |  |  | 03-Mar-25 A | 21-Mar-25 A | 0
A57240 | TBE for ICT System Modification_Free Issue Material |  |  | 24-Mar-25 A | 31-Mar-25 A | 0
VESDA (Very Early Smoke Detection Apparatus) |  | 2025-09-19 | 2026-01-09 | 01-May-25 A | 2025-09-19 | 1
A20710 | Issue RFQ to Bidders |  |  | 01-May-25 A | 20-Jun-25 A | 0
A20720 | Issue Purchase Order to Vendor for VESDA | 2025-09-19 | 2026-01-09 | 15-Sep-25 A | 2025-09-19 | 1
A20730 | Bid Evaluation(Completion) |  |  | 25-Aug-25 A | 29-Aug-25 A | 0
A20740 | Commercial Bid Evaluation(Completion) |  |  | 01-Sep-25 A | 12-Sep-25 A | 0
Fire Fighting Equipment |  | 2025-11-13 | 2026-01-23 | 2025-09-19 | 2025-11-13 | 40
A17470 | Issue RFQ to Bidders | 2025-09-25 | 2025-12-05 | 2025-09-19 | 2025-09-25 | 5
A18080 | Issue Purchase Order to Vendor for Fire Fighting Equipment | 2025-11-13 | 2026-01-23 | 2025-11-07 | 2025-11-13 | 5
A18090 | Bid Evaluation(Completion) | 2025-10-16 | 2025-12-26 | 2025-09-26 | 2025-10-16 | 15
A18100 | Commercial Bid Evaluation(Completion) | 2025-11-06 | 2026-01-16 | 2025-10-17 | 2025-11-06 | 15
Tail Gas Filter/Silencer/Colesor |  | 2025-10-16 | 2025-12-26 | 01-Apr-25 A | 2025-10-16 | 20
Coalescer - (BF) |  | 2025-10-16 | 2025-12-26 | 01-Apr-25 A | 2025-10-16 | 20
A45510 | Technical Bid Evaluation for Coalscer_IFR | 2025-09-24 | 2025-12-04 | 2025-09-19 | 2025-09-24 | 3
A45520 | Technical Bid Evaluation for Coalscer_RCC | 2025-09-29 | 2025-12-09 | 2025-09-24 | 2025-09-29 | 3
A45530 | Technical Bid Evaluation for Coalscer_IFA | 2025-10-03 | 2025-12-15 | 2025-09-29 | 2025-10-03 | 3
A45540 | Technical Bid Evaluation for Coalscer_RCA | 2025-10-08 | 2025-12-18 | 2025-10-03 | 2025-10-08 | 3
A45550 | Technical Bid Evaluation for Coalscer_IFD/IFC | 2025-10-13 | 2025-12-23 | 2025-10-08 | 2025-10-13 | 3
A8130 | Issue RFQ to Bidders |  |  | 01-Apr-25 A | 10-Apr-25 A | 0
A8160 | Issue Purchase Order to Vendor | 2025-10-16 | 2025-12-26 | 2025-10-13 | 2025-10-16 | 3
Steel Structure (material +sandwitch Panel) |  | 2025-10-13 | 2026-04-22 | 01-Mar-25 A | 2025-10-13 | 17
Civil Bulk Material |  |  |  | 16-May-25 A | 10-Jul-25 A | 0
A9550 | Issue RFQ to Bidders |  |  | 16-May-25 A | 01-Jun-25 A | 0
A9560 | Vendor Quote Received |  |  | 02-Jun-25 A | 01-Jul-25 A | 0
A9570 | Technical Bid Evaluation |  |  | 02-Jul-25 A | 10-Jul-25 A | 0
A9580 | Issue Purchase Order to Vendor |  |  | 09-Jun-25 A | 20-Jun-25 A | 0
TA_Steel Structure (Additional Steel Structure required for BFW) |  |  |  | 01-Mar-25 A | 20-Mar-25 A | 0
A21910 | Issue RFQs to Bidders (Remaining Steel Structure for TA) |  |  | 01-Mar-25 A | 05-Mar-25 A | 0
A21920 | Vendor Quote Received |  |  | 05-Mar-25 A | 10-Mar-25 A | 0
A21930 | Issue Purchase Order to Vendor |  |  | 16-Mar-25 A | 20-Mar-25 A | 0
A21940 | TBE for Steel Structure (TA) |  |  | 11-Mar-25 A | 15-Mar-25 A | 0
Steel Structure - Post TA |  | 2025-10-02 | 2026-04-22 | 01-Jun-25 A | 2025-10-02 | 10
122 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 25-Jul-25 A | 0
A34530 | Bid Evaluation(Completion) |  |  | 25-Aug-25 A | 05-Sep-25 A | 0
A34540 | Commercial Bid Evaluation(Completion) |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
A34550 | Issue Purchase Order to Vendor | 2025-10-02 | 2026-04-22 | 2025-09-19 | 2025-10-02 | 10
Structural Steel |  | 2025-10-13 | 2026-01-23 | 01-Jun-25 A | 2025-10-13 | 17
A23620 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 25-Jul-25 A | 0
A23630 | Vendor Quote Received |  |  | 25-Aug-25 A | 05-Sep-25 A | 0
A23640 | Issue Purchase Order to Vendor | 2025-10-10 | 2025-11-07 | 2025-09-26 | 2025-10-10 | 10
A57960 | Technical Bid Evaluation for Structural Steel_IFR |  |  | 08-Sep-25 A | 12-Sep-25 A | 0
A57970 | Technical Bid Evaluation for Structural Steel_RCC |  |  | 15-Sep-25 A | 19-Sep-25 A | 0
A57980 | Technical Bid Evaluation for Structural Steel_IFA | 2025-09-26 | 2025-10-24 | 19-Sep-25 A | 2025-09-26 | 6
A57990 | Technical Bid Evaluation for Structural Steel_RCA | 2025-10-06 | 2026-01-16 | 2025-09-26 | 2025-10-06 | 6
A58000 | Technical Bid Evaluation for Structural Steel_IFD/IFC | 2025-10-13 | 2026-01-23 | 2025-10-06 | 2025-10-13 | 6
Turbing Material [SS tubes, Connectors, unions, plugs etc.] |  | 2025-12-15 | 2026-05-29 | 2025-10-06 | 2025-12-15 | 50
Turbing Material [SS tubes, Connectors, unions, plugs etc] |  | 2025-12-15 | 2026-05-29 | 2025-10-06 | 2025-12-15 | 50
A17410 | Issue RFQ to Bidders | 2025-10-27 | 2026-04-10 | 2025-10-06 | 2025-10-27 | 15
A18200 | Issue Purchase Order to Vendor | 2025-12-15 | 2026-05-29 | 2025-12-01 | 2025-12-15 | 10
A18210 | Bid Evaluation(Completion) | 2025-11-17 | 2026-05-01 | 2025-10-27 | 2025-11-17 | 15
A18220 | Commercial Bid Evaluation(Completion) | 2025-12-01 | 2026-05-15 | 2025-11-17 | 2025-12-01 | 10
Telecom (ACS+LAN +CCTV+PAGA) |  | 2025-11-19 | 2026-02-04 | 11-Mar-25 A | 2025-11-19 | 44
Acess Control System |  | 2025-11-19 | 2026-01-05 | 2025-09-19 | 2025-11-19 | 44
A18720 | RFQs to Bid Receipt | 2025-09-23 | 2025-12-05 | 2025-09-19 | 2025-09-23 | 3
A22340 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2025-12-31 | 2025-10-15 | 2025-10-17 | 3
A22350 | Issue Purchase Order to Vendor for ACS | 2025-11-19 | 2026-01-05 | 2025-11-14 | 2025-11-19 | 3
A23880 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 2025-09-26 | 2025-12-10 | 2025-09-24 | 2025-09-26 | 3
A23890 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 2025-10-01 | 2025-12-15 | 2025-09-29 | 2025-10-01 | 3
A51950 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 2025-10-06 | 2025-12-18 | 2025-10-02 | 2025-10-06 | 3
A51960 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2025-10-09 | 2025-12-23 | 2025-10-07 | 2025-10-09 | 3
A51970 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2025-10-14 | 2025-12-26 | 2025-10-10 | 2025-10-14 | 3
TA_LAN System Modification - CISCO |  |  |  | 11-Mar-25 A | 10-Apr-25 A | 0
A37200 | Issue RFQ to Bidders |  |  | 11-Mar-25 A | 27-Mar-25 A | 0
A37230 | Issue Purchase Order to Vendor |  |  | 03-Apr-25 A | 10-Apr-25 A | 0
A57480 | TBE for Electrical System Modification_Free Issue Material |  |  | 28-Mar-25 A | 03-Apr-25 A | 0
PAGA + Telephone |  | 2025-11-19 | 2026-01-30 | 2025-09-19 | 2025-11-19 | 44
A18810 | RFQs to Bid Receipt | 2025-09-23 | 2025-12-19 | 2025-09-19 | 2025-09-23 | 3
A19110 | Issue Purchase Order to Vendor for PAGA + Telephone | 2025-11-19 | 2026-01-30 | 2025-11-14 | 2025-11-19 | 3
A19130 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2026-01-27 | 2025-10-15 | 2025-10-17 | 3
A56990 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 2025-09-26 | 2025-12-24 | 2025-09-24 | 2025-09-26 | 3
A57000 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 2025-10-01 | 2025-12-29 | 2025-09-29 | 2025-10-01 | 3
A57010 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 2025-10-06 | 2026-01-01 | 2025-10-02 | 2025-10-06 | 3
A57020 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2025-10-09 | 2026-01-19 | 2025-10-07 | 2025-10-09 | 3
A57030 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2025-10-14 | 2026-01-22 | 2025-10-10 | 2025-10-14 | 3
CCTV |  | 2025-11-19 | 2026-01-16 | 2025-09-19 | 2025-11-19 | 44
A18900 | RFQs to Bid Receipt | 2025-09-23 | 2025-12-18 | 2025-09-19 | 2025-09-23 | 3
A19170 | Issue Purchase Order to Vendor for CCTV | 2025-11-19 | 2026-01-16 | 2025-11-14 | 2025-11-19 | 3
A19190 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2026-01-13 | 2025-10-15 | 2025-10-17 | 3
A57040 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFR | 2025-09-26 | 2025-12-23 | 2025-09-24 | 2025-09-26 | 3
A57050 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCC | 2025-10-01 | 2025-12-26 | 2025-09-29 | 2025-10-01 | 3
A57060 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFA | 2025-10-06 | 2025-12-31 | 2025-10-02 | 2025-10-06 | 3
A57070 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_RCA | 2025-10-09 | 2026-01-05 | 2025-10-07 | 2025-10-09 | 3
A57080 | Technical Bid Evaluation For Telecom System (PAGA, CCTV, ACS, Telephone & LAN System)_IFD/IFC | 2025-10-14 | 2026-01-08 | 2025-10-10 | 2025-10-14 | 3
Telecom (ACS + CCTV + PAGA) Integration |  | 2025-11-19 | 2026-02-04 | 2025-09-19 | 2025-11-19 | 44
A16990 | Issue RFQ to Bidders | 2025-09-23 | 2026-01-22 | 2025-09-19 | 2025-09-23 | 3
A22270 | Bid Evaluation(Completion) | 2025-09-26 | 2026-01-27 | 2025-09-24 | 2025-09-26 | 3
A22280 | Commercial Bid Evaluation(Completion) | 2025-10-01 | 2026-01-30 | 2025-09-29 | 2025-10-01 | 3
A22290 | Issue Purchase Order to Vendor for Telecom (ACS+CCTV+PAGA) Integration | 2025-11-19 | 2026-02-04 | 2025-11-14 | 2025-11-19 | 3
Lighting Fixtures |  | 2026-02-24 | 2026-07-03 | 2025-09-19 | 2026-02-24 | 113
Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 2026-02-24 | 2026-07-03 | 2025-09-19 | 2026-02-24 | 113
A16390 | Issue RFQ to Bidders | 2025-10-17 | 2026-02-25 | 2025-09-19 | 2025-10-17 | 21
A19590 | Issue Purchase Order to Vendor for Lighting Fixtures | 2026-02-24 | 2026-07-03 | 2026-01-27 | 2026-02-24 | 21
A19600 | Bid Evaluation(Completion) | 2025-12-26 | 2026-05-06 | 2025-10-20 | 2025-12-26 | 50
A19610 | Commercial Bid Evaluation(Completion) | 2026-01-26 | 2026-06-04 | 2025-12-29 | 2026-01-26 | 21
Manual Valve |  | 2025-12-12 | 2026-01-16 | 20-May-25 A | 2025-12-12 | 60
Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  | 2025-12-12 | 2026-01-16 | 20-May-25 A | 2025-12-12 | 60
A18140 | Issue Purchase Order to Vendor for Manual Valves | 2025-12-12 | 2026-01-16 | 2025-11-13 | 2025-12-12 | 21
A18160 | Commercial Bid Evaluation(Completion) | 2025-11-05 | 2025-12-18 | 2025-10-29 | 2025-11-05 | 6
A45020 | Technical Bid Evaluation (TBE) for Manual Valves_IFR | 2025-09-26 | 2025-11-10 | 2025-09-19 | 2025-09-26 | 6
A45030 | Technical Bid Evaluation (TBE) for Manual Valves_RCC | 2025-10-06 | 2025-11-18 | 2025-09-26 | 2025-10-06 | 6
A45040 | Technical Bid Evaluation (TBE) for Manual Valves_IFA | 2025-10-13 | 2025-11-26 | 2025-10-06 | 2025-10-13 | 6
A45050 | Technical Bid Evaluation (TBE) for Manual Valves_RCA | 2025-10-21 | 2025-12-03 | 2025-10-13 | 2025-10-21 | 6
A45060 | Technical Bid Evaluation (TBE) for Manual Valves_IFD/IFC | 2025-10-29 | 2025-12-11 | 2025-10-21 | 2025-10-29 | 6
A9270 | Issue RFQ to Bidders |  |  | 20-May-25 A | 04-Jun-25 A | 0
Piping Bulk |  | 2026-02-20 | 2027-01-20 | 01-Jul-25 A | 2026-02-20 | 111
Piping Lot for Post TA |  | 2025-10-29 | 2025-12-05 | 01-Jul-25 A | 2025-10-29 | 28
112 | Issue RFQ to Bidders |  |  | 01-Jul-25 A | 21-Jul-25 A | 0
A23680 | Issue Purchase Order to Vendor | 2025-10-27 | 2025-12-05 | 2025-10-17 | 2025-10-27 | 6
A23700 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2025-11-27 | 2025-10-09 | 2025-10-17 | 6
A57090 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR |  |  | 22-Jul-25 A | 15-Sep-25 A | 0
A57100 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 2025-09-30 | 2025-11-07 | 15-Sep-25 A | 2025-09-30 | 8
A57110 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 2025-10-09 | 2025-11-18 | 2025-09-30 | 2025-10-09 | 7
A57120 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 2025-10-21 | 2025-11-28 | 2025-10-09 | 2025-10-21 | 8
A57130 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 2025-10-29 | 2025-12-05 | 2025-10-21 | 2025-10-29 | 6
Piping Supports (Swing Hangers) for Post TA |  | 2026-01-13 | 2026-04-29 | 2025-09-19 | 2026-01-13 | 83
A23710 | Issue RFQ to Bidders | 2025-10-16 | 2025-11-24 | 2025-09-19 | 2025-10-16 | 20
A23720 | Issue Purchase Order to Vendor | 2026-01-13 | 2026-02-18 | 2026-01-02 | 2026-01-13 | 7
A23740 | Commercial Bid Evaluation(Completion) | 2026-01-02 | 2026-02-09 | 2025-12-04 | 2026-01-02 | 21
A57140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 2025-11-03 | 2025-12-09 | 2025-10-17 | 2025-11-03 | 11
A57150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 2025-11-24 | 2025-12-31 | 2025-11-03 | 2025-11-24 | 16
A57160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 2025-12-04 | 2026-01-09 | 2025-11-25 | 2025-12-04 | 8
A57170 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 2025-12-26 | 2026-04-20 | 2025-12-04 | 2025-12-26 | 16
A57180 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 2026-01-07 | 2026-04-29 | 2025-12-26 | 2026-01-07 | 8
Piping 1st Lot for GF |  | 2025-10-10 | 2027-01-20 | 01-Jul-25 A | 2025-10-10 | 16
100 | Issue RFQ to Bidders |  |  | 01-Jul-25 A | 21-Jul-25 A | 0
A21350 | Issue Purchase Order to Vendor |  |  | 08-Sep-25 A | 19-Sep-25 A | 0
A21370 | Commercial Bid Evaluation(Completion) |  |  | 25-Aug-25 A | 05-Sep-25 A | 0
A44970 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR |  |  | 19-Aug-25 A | 29-Aug-25 A | 0
A44980 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC |  |  | 30-Aug-25 A | 08-Sep-25 A | 0
A44990 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA |  |  | 09-Sep-25 A | 16-Sep-25 A | 0
A45000 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 2025-09-30 | 2027-01-11 | 2025-09-19 | 2025-09-30 | 8
A45010 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 2025-10-10 | 2027-01-20 | 2025-09-30 | 2025-10-10 | 8
Piping 2nd Lot for GF (CS Material) |  | 2025-10-16 | 2025-11-07 | 09-Sep-25 A | 2025-10-16 | 20
101 | Issue RFQ to Bidders |  |  | 09-Sep-25 A | 17-Sep-25 A | 0
A21410 | Issue Purchase Order to Vendor | 2025-10-16 | 2025-11-07 | 2025-10-10 | 2025-10-16 | 5
A21420 | Bid Evaluation(Completion) | 2025-10-02 | 2025-10-24 | 18-Sep-25 A | 2025-10-02 | 10
A21430 | Commercial Bid Evaluation(Completion) | 2025-10-09 | 2025-10-31 | 2025-10-03 | 2025-10-09 | 5
Piping 3rd Lot GF (CS Material) |  | 2025-12-30 | 2026-03-13 | 2025-10-22 | 2025-12-30 | 49
102 | Issue RFQ to Bidders | 2025-11-05 | 2026-01-19 | 2025-10-22 | 2025-11-05 | 10
A21470 | Issue Purchase Order to Vendor | 2025-12-30 | 2026-03-13 | 2025-12-10 | 2025-12-30 | 14
A21480 | Bid Evaluation(Completion) | 2025-11-19 | 2026-02-02 | 2025-11-05 | 2025-11-19 | 10
A21490 | Commercial Bid Evaluation(Completion) | 2025-12-10 | 2026-02-23 | 2025-11-19 | 2025-12-10 | 15
Piping Supports (Swing Hangers) for GF |  | 2026-02-20 | 2026-06-26 | 2025-09-19 | 2026-02-20 | 111
A21610 | Issue RFQ to Bidders | 2025-09-25 | 2026-01-30 | 2025-09-19 | 2025-09-25 | 5
A21620 | Issue Purchase Order to Vendor | 2026-02-20 | 2026-06-26 | 2026-02-02 | 2026-02-20 | 14
A21640 | Commercial Bid Evaluation(Completion) | 2026-02-02 | 2026-06-08 | 2025-12-22 | 2026-02-02 | 30
A45120 | Technical Bid Evaluation (TBE) for Spring Hangers_IFR | 2025-10-13 | 2026-02-16 | 2025-09-26 | 2025-10-13 | 11
A45130 | Technical Bid Evaluation (TBE) for Spring Hangers_RCC | 2025-11-03 | 2026-03-10 | 2025-10-13 | 2025-11-03 | 16
A45140 | Technical Bid Evaluation (TBE) for Spring Hangers_IFA | 2025-11-19 | 2026-03-25 | 2025-11-04 | 2025-11-19 | 11
A45150 | Technical Bid Evaluation (TBE) for Spring Hangers_RCA | 2025-12-10 | 2026-04-16 | 2025-11-19 | 2025-12-10 | 16
A45160 | Technical Bid Evaluation (TBE) for Spring Hangers_IFD/IFC | 2025-12-22 | 2026-04-27 | 2025-12-11 | 2025-12-22 | 8
HDPE Piping |  | 2026-01-07 | 2026-05-18 | 2025-09-26 | 2026-01-07 | 73
HDPE Piping GF (Fire Water Lines) |  | 2026-01-07 | 2026-05-18 | 2025-09-26 | 2026-01-07 | 73
A21530 | Issue RFQ to Bidders | 2025-10-10 | 2025-11-27 | 2025-09-26 | 2025-10-10 | 10
A21540 | Issue Purchase Order to Vendor | 2026-01-07 | 2026-02-23 | 2025-12-24 | 2026-01-07 | 10
A21560 | Commercial Bid Evaluation(Completion) | 2025-12-24 | 2026-02-09 | 2025-11-25 | 2025-12-24 | 21
A60270 | Technical Bid Evaluation (TBE) for Piping Bulk_IFR | 2025-10-22 | 2025-12-09 | 2025-10-10 | 2025-10-22 | 8
A60280 | Technical Bid Evaluation (TBE) for Piping Bulk_RCC | 2025-11-13 | 2025-12-31 | 2025-10-22 | 2025-11-13 | 16
A60290 | Technical Bid Evaluation (TBE) for Piping Bulk_IFA | 2025-11-25 | 2026-01-09 | 2025-11-13 | 2025-11-25 | 8
A60300 | Technical Bid Evaluation (TBE) for Piping Bulk_RCA | 2025-12-04 | 2026-05-07 | 2025-11-25 | 2025-12-04 | 8
A60310 | Technical Bid Evaluation (TBE) for Piping Bulk_IFD/IFC | 2025-12-16 | 2026-05-18 | 2025-12-05 | 2025-12-16 | 8
Piping SP Items (strainer, filters) |  | 2026-03-25 | 2026-05-07 | 2025-09-19 | 2026-03-25 | 134
Specialized Items (Orifice Flanges) CS 300# 1" - 6" = 08 Nos |  | 2025-11-18 | 2026-04-06 | 2025-09-19 | 2025-11-18 | 42
A18340 | Issue RFQ to Bidders | 2025-09-25 | 2026-02-19 | 2025-09-19 | 2025-09-25 | 5
A18360 | Issue Purchase Order to Vendor | 2025-11-18 | 2026-04-06 | 2025-11-11 | 2025-11-18 | 5
A18380 | Commercial Bid Evaluation(Completion) | 2025-11-04 | 2026-03-30 | 2025-10-28 | 2025-11-04 | 5
A45070 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 2025-10-02 | 2026-02-25 | 2025-09-26 | 2025-10-02 | 5
A45080 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 2025-10-08 | 2026-03-04 | 2025-10-02 | 2025-10-08 | 5
A45090 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 2025-10-15 | 2026-03-10 | 2025-10-09 | 2025-10-15 | 5
A45100 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 2025-10-21 | 2026-03-17 | 2025-10-15 | 2025-10-21 | 5
A45110 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 2025-10-28 | 2026-03-23 | 2025-10-22 | 2025-10-28 | 5
Specialized Items (Strainer/Filter) CS & SS 150 # -300# 2" - 26" = 08 Nos |  | 2026-03-25 | 2026-05-07 | 2025-09-19 | 2026-03-25 | 134
A15910 | Issue RFQ to Bidders | 2025-10-17 | 2025-12-02 | 2025-09-19 | 2025-10-17 | 21
A18260 | Issue Purchase Order to Vendor | 2026-03-25 | 2026-05-07 | 2026-02-24 | 2026-03-25 | 21
A18280 | Commercial Bid Evaluation(Completion) | 2026-02-24 | 2026-04-08 | 2026-01-13 | 2026-02-24 | 30
A56590 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFR | 2025-11-04 | 2025-12-17 | 2025-10-20 | 2025-11-04 | 11
A56600 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCC | 2025-11-25 | 2026-01-08 | 2025-11-04 | 2025-11-25 | 16
A56610 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFA | 2025-12-11 | 2026-01-23 | 2025-11-26 | 2025-12-11 | 11
A56620 | Technical Bid Evaluation (TBE) for Piping Speciality Items_RCA | 2026-01-01 | 2026-02-16 | 2025-12-11 | 2026-01-01 | 16
A56630 | Technical Bid Evaluation (TBE) for Piping Speciality Items_IFD/IFC | 2026-01-13 | 2026-02-25 | 2026-01-02 | 2026-01-13 | 8
Pressure / Temperature / Level Instruments, Flowmeters |  | 2025-11-25 | 2026-03-26 | 18-Apr-25 A | 2025-11-25 | 48
Gauges (PG, TG, PDG) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 2025-11-25 | 2026-03-09 | 2025-09-19 | 2025-11-25 | 48
A16340 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCC | 2025-10-08 | 2025-12-24 | 2025-09-30 | 2025-10-08 | 6
A16350 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFA | 2025-10-15 | 2026-01-01 | 2025-10-08 | 2025-10-15 | 6
A16360 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_RCA | 2025-10-23 | 2026-02-04 | 2025-10-15 | 2025-10-23 | 6
A16370 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFD/IFC | 2025-10-31 | 2026-02-12 | 2025-10-23 | 2025-10-31 | 6
A17290 | RFQs to Bid Receipt | 2025-09-22 | 2025-12-09 | 2025-09-19 | 2025-09-22 | 2
A19230 | Issue Purchase Order to Vendor Guages (PG, TG, PDG) | 2025-11-25 | 2026-03-09 | 2025-11-07 | 2025-11-25 | 12
A19250 | Commercial Bid Evaluation(Completion) | 2025-11-07 | 2026-02-19 | 2025-10-31 | 2025-11-07 | 6
A48180 | Technical Bid Evaluation for Temperature Gauges / Pressure Gauges_IFR | 2025-09-30 | 2025-12-16 | 2025-09-23 | 2025-09-30 | 6
Flow Elements Venturi |  | 2025-11-25 | 2026-01-15 | 01-Jun-25 A | 2025-11-25 | 47
A16230 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFR | 2025-09-30 | 2025-11-21 | 2025-09-19 | 2025-09-30 | 8
A16240 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCC | 2025-10-10 | 2025-12-03 | 2025-09-30 | 2025-10-10 | 8
A16250 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFA | 2025-10-22 | 2025-12-15 | 2025-10-10 | 2025-10-22 | 8
A16260 | Technical Bid Evaluation for Flow Element (Venturi Tube)_RCA | 2025-11-13 | 2026-01-06 | 2025-10-22 | 2025-11-13 | 16
A48170 | Technical Bid Evaluation for Flow Element (Venturi Tube)_IFD/IFC | 2025-11-25 | 2026-01-15 | 2025-11-13 | 2025-11-25 | 8
A57610 | Issue RFQ to Bidders |  |  | 01-Jun-25 A | 22-Jun-25 A | 0
A57630 | Commercial Bid Evaluation | 2025-11-05 | 2026-01-01 | 2025-10-22 | 2025-11-05 | 10
A57640 | Issue Purchase Order to Vendor | 2025-11-19 | 2026-01-15 | 2025-11-05 | 2025-11-19 | 10
Flow Elements Orifice |  | 2025-11-18 | 2026-01-30 | 01-May-25 A | 2025-11-18 | 43
A16180 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFR | 2025-09-24 | 2025-12-08 | 01-Sep-25 A | 2025-09-24 | 3
A16190 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCC | 2025-10-06 | 2025-12-18 | 2025-09-24 | 2025-10-06 | 8
A16200 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFA | 2025-10-16 | 2025-12-30 | 2025-10-06 | 2025-10-16 | 8
A16220 | Technical Bid Evaluation for Flow Element (Orifice Plate)_IFD/IFC | 2025-11-18 | 2026-01-30 | 2025-11-06 | 2025-11-18 | 8
A48160 | Technical Bid Evaluation for Flow Element (Orifice Plate)_RCA | 2025-11-06 | 2026-01-21 | 2025-10-16 | 2025-11-06 | 16
A57920 | Issue RFQ to Bidders |  |  | 01-May-25 A | 15-May-25 A | 0
A57930 | Issue Purchase Order to Vendor | 2025-11-13 | 2026-01-30 | 2025-10-30 | 2025-11-13 | 10
A57950 | Commercial Bid Evaluation | 2025-10-30 | 2026-01-16 | 2025-10-16 | 2025-10-30 | 10
PT, TT & DPT [PT 50 Nos, TT 33 Nos, DPT 20 Nos] |  | 2025-10-29 | 2026-03-26 | 18-Apr-25 A | 2025-10-29 | 28
A16130 | Technical Bid Evaluation for Electronic Transmitters_IFR | 2025-09-24 | 2025-12-23 | 2025-09-19 | 2025-09-24 | 3
A16140 | Technical Bid Evaluation for Electronic Transmitters_RCC | 2025-09-29 | 2025-12-26 | 2025-09-24 | 2025-09-29 | 3
A16160 | Technical Bid Evaluation for Electronic Transmitters_RCA | 2025-10-08 | 2026-03-06 | 2025-10-03 | 2025-10-08 | 3
A16170 | Technical Bid Evaluation for Electronic Transmitters_IFD/IFC | 2025-10-13 | 2026-03-11 | 2025-10-08 | 2025-10-13 | 3
A21030 | Issue RFQ to Bidders |  |  | 18-Apr-25 A | 09-May-25 A | 0
A21040 | Issue Purchase Order to Vendor | 2025-10-29 | 2026-03-26 | 2025-10-17 | 2025-10-29 | 8
A21060 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2026-03-16 | 2025-10-13 | 2025-10-17 | 3
A48150 | Technical Bid Evaluation for Electronic Transmitters_IFA | 2025-10-03 | 2026-01-01 | 2025-09-29 | 2025-10-03 | 3
Instrument Bulk Material |  | 2025-11-13 | 2026-03-11 | 01-Feb-25 A | 2025-11-13 | 40
TA_Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  |  |  | 01-Feb-25 A | 19-Mar-25 A | 0
A22030 | Issue RFQs to Bidders |  |  | 01-Feb-25 A | 11-Feb-25 A | 0
A22040 | Vendor Quote Received |  |  | 24-Feb-25 A | 04-Mar-25 A | 0
A22050 | TBE for Instrument Bulk Material (TA) |  |  | 12-Feb-25 A | 21-Feb-25 A | 0
A22070 | Issue Purchase Order to Vendor |  |  | 05-Mar-25 A | 19-Mar-25 A | 0
Analyzer |  |  |  | 01-May-25 A | 08-Jun-25 A | 0
A16380 | Technical Bid Evaluation for Analyzers_IFR |  |  | 01-May-25 A | 25-May-25 A | 0
A16400 | Technical Bid Evaluation for Analyzers_IFA |  |  | 01-May-25 A | 23-May-25 A | 0
A16410 | Technical Bid Evaluation for Analyzers_RCA |  |  | 01-May-25 A | 23-May-25 A | 0
A16420 | Technical Bid Evaluation for Analyzers_IFD/IFC |  |  | 01-May-25 A | 23-May-25 A | 0
A48190 | Technical Bid Evaluation for Analyzers_RCC |  |  | 01-May-25 A | 23-May-25 A | 0
A57570 | Issue RFQ to Bidders |  |  | 01-May-25 A | 25-May-25 A | 0
A57590 | Commercial Bid Evaluation |  |  | 25-May-25 A | 01-Jun-25 A | 0
A57600 | Issue Purchase Order to Vendor |  |  | 02-Jun-25 A | 08-Jun-25 A | 0
Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty = 5982 Mtrs, JBs = 73 Nos) |  | 2025-11-13 | 2026-03-11 | 20-Jul-25 A | 2025-11-13 | 40
A16830 | Technical Bid Evaluation for Junction Boxes_IFR | 2025-10-02 | 2025-12-18 | 2025-09-26 | 2025-10-02 | 5
A16840 | Technical Bid Evaluation for Junction Boxes_RCC | 2025-10-09 | 2025-12-25 | 2025-10-03 | 2025-10-09 | 5
A16850 | Technical Bid Evaluation for Junction Boxes_IFA | 2025-10-16 | 2026-01-01 | 2025-10-10 | 2025-10-16 | 5
A16860 | Technical Bid Evaluation for Junction Boxes_RCA | 2025-10-23 | 2026-02-18 | 2025-10-17 | 2025-10-23 | 5
A16870 | Technical Bid Evaluation for Junction Boxes_IFD/IFC | 2025-10-30 | 2026-02-25 | 2025-10-24 | 2025-10-30 | 5
A17230 | Issue RFQ to Bidders | 2025-09-25 | 2025-12-11 | 20-Jul-25 A | 2025-09-25 | 5
A20050 | Issue Purchase Order to Vendor | 2025-11-13 | 2026-03-11 | 2025-11-07 | 2025-11-13 | 5
A20070 | Commercial Bid Evaluation(Completion) | 2025-11-06 | 2026-03-04 | 2025-10-31 | 2025-11-06 | 5
Magnetic Level Gauge ( 09 Nos) |  | 2025-10-21 | 2026-02-12 | 18-Jul-25 A | 2025-10-21 | 23
A16430 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFR | 2025-09-23 | 2025-12-24 | 2025-09-19 | 2025-09-23 | 3
A16440 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCC | 2025-09-26 | 2025-12-29 | 2025-09-24 | 2025-09-26 | 3
A16460 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_RCA | 2025-10-06 | 2026-01-28 | 2025-10-02 | 2025-10-06 | 3
A16470 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFD/IFC | 2025-10-09 | 2026-02-02 | 2025-10-07 | 2025-10-09 | 3
A21270 | Issue RFQ to Bidders |  |  | 18-Jul-25 A | 06-Aug-25 A | 0
A21280 | Issue Purchase Order to Vendor | 2025-10-21 | 2026-02-12 | 2025-10-15 | 2025-10-21 | 5
A21300 | Commercial Bid Evaluation(Completion) | 2025-10-14 | 2026-02-05 | 2025-10-10 | 2025-10-14 | 3
A48200 | Technical Bid Evaluation for Level Gauges (Magnetic Type)_IFA | 2025-10-01 | 2026-01-01 | 2025-09-29 | 2025-10-01 | 3
Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  |  |  | 01-Jun-25 A | 18-Aug-25 A | 0
A17170 | RFQs to Bid receipt |  |  | 01-Jun-25 A | 21-Jun-25 A | 0
A18660 | Issue Purchase Order to Vendor |  |  | 09-Aug-25 A | 18-Aug-25 A | 0
A18680 | Commercial Bid Evaluation(Completion) |  |  | 01-Aug-25 A | 08-Aug-25 A | 0
A57510 | Technical Bid Evaluation for Instrument Cables_IFR |  |  | 30-Jul-25 A | 31-Jul-25 A | 0
A57520 | Technical Bid Evaluation for Instrument Cables_RCC |  |  | 30-Jul-25 A | 31-Jul-25 A | 0
A57530 | Technical Bid Evaluation for Instrument Cables_IFA |  |  | 30-Jul-25 A | 31-Jul-25 A | 0
A57540 | Technical Bid Evaluation for Instrument Cables_RCA |  |  | 30-Jul-25 A | 31-Jul-25 A | 0
A57550 | Technical Bid Evaluation for Instrument Cables_IFD/IFC |  |  | 30-Jul-25 A | 31-Jul-25 A | 0
Earthing & Power Cables |  | 2025-12-24 | 2026-07-13 | 18-Jul-25 A | 2025-12-24 | 69
Power Cables ( 11kV & 33kV) |  | 2025-12-24 | 2026-07-13 | 01-Aug-25 A | 2025-12-24 | 69
A58690 | Issue RFQ to Bidders |  |  | 01-Aug-25 A | 20-Aug-25 A | 0
A58700 | Bid Evaluation(Completion) | 2025-10-30 | 2026-05-19 | 2025-09-19 | 2025-10-30 | 30
A58710 | Commercial Bid Evaluation(Completion) | 2025-12-04 | 2026-06-23 | 2025-10-31 | 2025-12-04 | 25
A58720 | Issue Purchase Order to Vendor | 2025-12-24 | 2026-07-13 | 2025-12-05 | 2025-12-24 | 14
Earthing and Power Cables |  | 2025-10-22 | 2026-01-20 | 18-Jul-25 A | 2025-10-22 | 24
A13230 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFR | 2025-09-24 | 2025-12-23 | 2025-09-19 | 2025-09-24 | 3
A13240 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCC | 2025-09-29 | 2025-12-26 | 2025-09-24 | 2025-09-29 | 3
A13250 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFA | 2025-10-03 | 2026-01-01 | 2025-09-29 | 2025-10-03 | 3
A13260 | Technical Bid Evaluation For Power, Control And Earthing Cables_RCA | 2025-10-08 | 2026-01-06 | 2025-10-03 | 2025-10-08 | 3
A13270 | Technical Bid Evaluation For Power, Control And Earthing Cables_IFD/IFC | 2025-10-13 | 2026-01-12 | 2025-10-08 | 2025-10-13 | 3
A16450 | Issue RFQ to Bidders |  |  | 18-Jul-25 A | 20-Aug-25 A | 0
A20590 | Issue Purchase Order to Vendor | 2025-10-22 | 2026-01-20 | 2025-10-17 | 2025-10-22 | 3
A20610 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2026-01-15 | 2025-10-13 | 2025-10-17 | 3
Electrical Bulk |  | 2026-01-29 | 2026-07-13 | 15-Jan-25 A | 2026-01-29 | 95
TA_Electrical Bulk Material (Earthing ,FO, Power Cables) |  |  |  | 15-Jan-25 A | 09-Mar-25 A | 0
A17890 | Issue RFQ to Bidders |  |  | 15-Jan-25 A | 08-Feb-25 A | 0
A17900 | Vendor Quote Received |  |  | 10-Feb-25 A | 19-Feb-25 A | 0
A17910 | Negotiations and PO Placement (33 KVA) |  |  | 03-Mar-25 A | 09-Mar-25 A | 0
A17920 | TBE |  |  | 20-Feb-25 A | 28-Feb-25 A | 0
Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 2026-01-28 | 2026-06-26 | 2025-09-19 | 2026-01-28 | 94
A20650 | Issue Purchase Order to Vendor | 2026-01-28 | 2026-06-26 | 2026-01-09 | 2026-01-28 | 14
A20660 | Bid Evaluation(Completion) | 2025-12-11 | 2026-05-11 | 2025-10-17 | 2025-12-11 | 40
A20670 | Commercial Bid Evaluation(Completion) | 2026-01-08 | 2026-06-08 | 2025-12-12 | 2026-01-08 | 20
A9450 | Issue RFQ to Bidders | 2025-10-16 | 2026-03-16 | 2025-09-19 | 2025-10-16 | 20
LCS & Snap Switches |  | 2026-01-29 | 2026-07-13 | 2025-09-19 | 2026-01-29 | 95
A21690 | Issue RFQ to Bidders | 2025-10-17 | 2026-03-31 | 2025-09-19 | 2025-10-17 | 21
A21700 | Issue Purchase Order to Vendor | 2026-01-29 | 2026-07-13 | 2026-01-12 | 2026-01-29 | 14
A21710 | Bid Evaluation(Completion) | 2025-12-05 | 2026-05-19 | 2025-10-20 | 2025-12-05 | 35
A21720 | Commercial Bid Evaluation(Completion) | 2026-01-09 | 2026-06-23 | 2025-12-08 | 2026-01-09 | 25
Main Automation Equipment |  | 2025-12-16 | 2026-03-06 | 01-Feb-25 A | 2025-12-16 | 63
On Off Valve / Control Valves |  | 2025-12-01 | 2026-02-24 | 21-Apr-25 A | 2025-12-01 | 52
ESD Valve |  | 2025-12-01 | 2026-02-24 | 01-Sep-25 A | 2025-12-01 | 52
A59730 | Issue RFQ to Bidders |  |  | 01-Sep-25 A | 17-Sep-25 A | 0
A59740 | Issue Purchase Order to Vendor for ESD | 2025-11-18 | 2026-01-08 | 2025-10-21 | 2025-11-18 | 21
A59750 | Commercial Bid Evaluation(Completion) | 2025-11-07 | 2025-12-30 | 2025-10-10 | 2025-11-07 | 21
A59760 | Technical Bid Evaluation for ESD_IFR | 2025-09-22 | 2025-11-11 | 18-Sep-25 A | 2025-09-22 | 1
A59770 | Technical Bid Evaluation for ESD_RCC | 2025-10-13 | 2025-12-03 | 2025-09-22 | 2025-10-13 | 16
A59780 | Technical Bid Evaluation for ESD_IFA | 2025-10-29 | 2025-12-18 | 2025-10-13 | 2025-10-29 | 11
A59790 | Technical Bid Evaluation for ESD_RCA | 2025-11-19 | 2026-02-12 | 2025-10-29 | 2025-11-19 | 16
A59800 | Technical Bid Evaluation for ESD_IFD/IFC | 2025-12-01 | 2026-02-24 | 2025-11-19 | 2025-12-01 | 8
Control Valves (1" - 24" Rating 150, 300 & 2500 = 32 Nos) + SDV |  | 2025-11-17 | 2026-01-16 | 21-Apr-25 A | 2025-11-17 | 42
A16480 | Technical Bid Evaluation for Control Valves_IFR |  |  | 23-Aug-25 A | 18-Sep-25 A | 0
A16490 | Technical Bid Evaluation for Control Valves_RCC |  |  | 23-Aug-25 A | 18-Sep-25 A | 0
A16500 | Technical Bid Evaluation for Control Valves_IFA |  |  | 23-Aug-25 A | 18-Sep-25 A | 0
A16520 | Technical Bid Evaluation for Control Valves_IFD/IFC |  |  | 23-Aug-25 A | 18-Sep-25 A | 0
A16750 | Issue RFQ to Bidders |  |  | 21-Apr-25 A | 15-May-25 A | 0
A22100 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2025-12-18 | 18-Sep-25 A | 2025-10-17 | 21
A22110 | Issue Purchase Order to Vendor for Control Valves | 2025-11-17 | 2026-01-16 | 2025-10-20 | 2025-11-17 | 21
A48210 | Technical Bid Evaluation for Control Valves_RCA |  |  | 23-Aug-25 A | 18-Sep-25 A | 0
MOVs |  |  |  | 21-Apr-25 A | 10-Sep-25 A | 0
MOVs [Ball Type 24" 150# = 01 No] |  |  |  | 21-Apr-25 A | 10-Sep-25 A | 0
A16640 | Technical Bid Evaluation for Motor Operated Valves_RCC |  |  | 22-Aug-25 A | 02-Sep-25 A | 0
A16650 | Technical Bid Evaluation for Motor Operated Valves_IFA |  |  | 19-Aug-25 A | 29-Aug-25 A | 0
A16660 | Technical Bid Evaluation for Motor Operated Valves_RCA |  |  | 30-Aug-25 A | 06-Sep-25 A | 0
A16670 | Technical Bid Evaluation for Motor Operated Valves_IFD/IFC |  |  | 07-Sep-25 A | 10-Sep-25 A | 0
A17050 | RFQs to Bid Receipt |  |  | 21-Apr-25 A | 15-May-25 A | 0
A18600 | Issue Purchase Order to Vendor for MOVs |  |  | 26-Aug-25 A | 02-Sep-25 A | 0
A18620 | Commercial Bid Evaluation(Completion) |  |  | 19-Aug-25 A | 01-Sep-25 A | 0
A48230 | Technical Bid Evaluation for Motor Operated Valves_IFR |  |  | 16-May-25 A | 22-Aug-25 A | 0
Machine Condition Monitoring System (MCMS) |  |  |  | 01-Feb-25 A | 01-Jun-25 A | 0
TA_MCMS System Modification - Bently Nevada |  |  |  | 01-Feb-25 A | 15-Mar-25 A | 0
A37160 | Issue RFQ to Bidders |  |  | 01-Feb-25 A | 22-Feb-25 A | 0
A37190 | Issue Purchase Order to Vendor |  |  | 10-Mar-25 A | 15-Mar-25 A | 0
A57450 | TBE for ICT System Modification_Free Issue Material |  |  | 23-Feb-25 A | 09-Mar-25 A | 0
Machine Condition Monitoring System |  |  |  | 01-Apr-25 A | 01-Jun-25 A | 0
A17110 | Issue RFQ to Bidders |  |  | 01-Apr-25 A | 20-Apr-25 A | 0
A19930 | Issue Purchase Order to Vendor for MCMS |  |  | 08-May-25 A | 15-May-25 A | 0
A19950 | Commercial Bid Evaluation(Completion) |  |  | 26-May-25 A | 01-Jun-25 A | 0
A58590 | Technical Bid Evaluation for MCMS System_IFR |  |  | 01-May-25 A | 15-May-25 A | 0
A58600 | Technical Bid Evaluation for MCMS System_RCC |  |  | 16-May-25 A | 19-May-25 A | 0
A58610 | Technical Bid Evaluation for MCMSSystem_IFA |  |  | 16-May-25 A | 19-May-25 A | 0
A58620 | Technical Bid Evaluation for MCMS System_RCA |  |  | 16-May-25 A | 19-May-25 A | 0
A58630 | Technical Bid Evaluation for MCMS System_IFD/IFC |  |  | 20-May-25 A | 25-May-25 A | 0
IPCS Modification (ABB) |  |  |  | 01-Feb-25 A | 25-Jul-25 A | 0
TA_Integrated Protection and Control System - ABB/Hitachi |  |  |  | 01-Feb-25 A | 18-Mar-25 A | 0
A20950 | Issue RFQ to Bidders |  |  | 01-Feb-25 A | 25-Feb-25 A | 0
A20960 | Issue Purchase Order to Vendor |  |  | 10-Mar-25 A | 18-Mar-25 A | 0
A57390 | TBE for Electrical System Modification_ Free Issue Material |  |  | 26-Feb-25 A | 09-Mar-25 A | 0
Integrated Protection and Control System |  |  |  | 10-Apr-25 A | 25-Jul-25 A | 0
A23820 | Issue RFQ to Bidders |  |  | 10-Apr-25 A | 01-May-25 A | 0
A23830 | Issue Purchase Order to Vendor for IPCS |  |  | 17-Jul-25 A | 25-Jul-25 A | 0
A23850 | Commercial Bid Evaluation(Completion) |  |  | 07-Jul-25 A | 16-Jul-25 A | 0
A58540 | Technical Bid Evaluation for IPCS_IFR |  |  | 02-May-25 A | 10-May-25 A | 0
A58550 | Technical Bid Evaluation for IPCS_RCC |  |  | 11-May-25 A | 20-May-25 A | 0
A58560 | Technical Bid Evaluation for IPCS_IFA |  |  | 21-May-25 A | 26-May-25 A | 0
A58570 | Technical Bid Evaluation for IPCS_RCA |  |  | 27-May-25 A | 31-May-25 A | 0
A58580 | Technical Bid Evaluation for IPCS_IFD/IFC |  |  | 01-Jun-25 A | 04-Jun-25 A | 0
OTS |  |  |  | 01-Feb-25 A | 20-Aug-25 A | 0
TA_SCMS Modification - Siemens |  |  |  | 01-Feb-25 A | 03-Mar-25 A | 0
A24190 | Issue RFQ to Bidders |  |  | 01-Feb-25 A | 10-Feb-25 A | 0
A24200 | Issue Purchase Order to Vendor |  |  | 25-Feb-25 A | 03-Mar-25 A | 0
A57360 | TBE for Electrical System Modification_ Free Issue Material |  |  | 11-Feb-25 A | 24-Feb-25 A | 0
SCMS |  |  |  | 19-Mar-25 A | 20-Aug-25 A | 0
A60190 | Issue RFQ to Bidders |  |  | 19-Mar-25 A | 20-May-25 A | 0
A60200 | Issue Purchase Order to Vendor for SCMS |  |  | 16-Jul-25 A | 20-Aug-25 A | 0
A60210 | Commercial Bid Evaluation(Completion) |  |  | 04-Jul-25 A | 15-Jul-25 A | 0
A60220 | Technical Bid Evaluation for SCMS_IFR |  |  | 21-May-25 A | 01-Jun-25 A | 0
A60230 | Technical Bid Evaluation for SCMS_RCC |  |  | 02-Jun-25 A | 12-Jun-25 A | 0
A60240 | Technical Bid Evaluation for SCMS_IFA |  |  | 13-Jun-25 A | 19-Jun-25 A | 0
A60250 | Technical Bid Evaluation for SCMS_RCA |  |  | 20-Jun-25 A | 26-Jun-25 A | 0
A60260 | Technical Bid Evaluation for SCMS_IFD/IFC |  |  | 27-Jun-25 A | 03-Jul-25 A | 0
ICSS (Integrated Control and Safety System) including sys. Modifications |  |  |  | 07-Feb-25 A | 20-Jun-25 A | 0
Integrated Control and Safety System GF |  |  |  | 15-May-25 A | 20-Jun-25 A | 0
A16880 | Technical Bid Evaluation for ICSS System_IFR |  |  | 26-May-25 A | 28-May-25 A | 0
A16890 | Technical Bid Evaluation for ICSS System_RCC |  |  | 29-May-25 A | 30-May-25 A | 0
A16900 | Technical Bid Evaluation for ICSS System_IFA |  |  | 30-May-25 A | 31-May-25 A | 0
A16910 | Technical Bid Evaluation for ICSS System_RCA |  |  | 31-May-25 A | 01-Jun-25 A | 0
A16920 | Technical Bid Evaluation for ICSS System_IFD/IFC |  |  | 01-Jun-25 A | 06-Jun-25 A | 0
A23940 | Issue RFQ to Bidders |  |  | 15-May-25 A | 30-May-25 A | 0
A23950 | Issue Purchase Order to Vendor for ICSS |  |  | 14-Jun-25 A | 20-Jun-25 A | 0
A23970 | Commercial Bid Evaluation(Completion) |  |  | 07-Jun-25 A | 13-Jun-25 A | 0
TA_Integrated Control & Safety System BF - Honeywell |  |  |  | 07-Feb-25 A | 10-Mar-25 A | 0
A19770 | Issue RFQ to Bidders |  |  | 07-Feb-25 A | 17-Feb-25 A | 0
A19780 | Issue Purchase Order to Vendor |  |  | 01-Mar-25 A | 10-Mar-25 A | 0
A56210 | TBE for ICT System Modification_Free Issue Material |  |  | 18-Feb-25 A | 28-Feb-25 A | 0
Instrument Cables |  | 2025-11-13 | 2026-03-06 | 2025-09-19 | 2025-11-13 | 40
Instrument Cable (Single & Multicore = Approx. 78,130 Mtr) |  | 2025-11-13 | 2026-03-06 | 2025-09-19 | 2025-11-13 | 40
A16780 | Technical Bid Evaluation for Instrument Cables_IFR | 2025-10-02 | 2025-12-18 | 2025-09-26 | 2025-10-02 | 5
A16790 | Technical Bid Evaluation for Instrument Cables_RCC | 2025-10-09 | 2025-12-25 | 2025-10-03 | 2025-10-09 | 5
A16800 | Technical Bid Evaluation for Instrument Cables_IFA | 2025-10-16 | 2026-01-01 | 2025-10-10 | 2025-10-16 | 5
A16810 | Technical Bid Evaluation for Instrument Cables_RCA | 2025-10-23 | 2026-02-13 | 2025-10-17 | 2025-10-23 | 5
A16820 | Technical Bid Evaluation for Instrument Cables_IFD/IFC | 2025-10-30 | 2026-02-20 | 2025-10-24 | 2025-10-30 | 5
A21190 | Issue RFQ to Bidders | 2025-09-25 | 2025-12-11 | 2025-09-19 | 2025-09-25 | 5
A21200 | Issue Purchase Order to Vendor | 2025-11-13 | 2026-03-06 | 2025-11-07 | 2025-11-13 | 5
A21220 | Commercial Bid Evaluation(Completion) | 2025-11-06 | 2026-02-27 | 2025-10-31 | 2025-11-06 | 5
Local Fire Control Panel including F & G Detectors |  | 2025-11-12 | 2026-01-16 | 20-Jun-25 A | 2025-11-12 | 39
Fire Detection Alarm System and Local Fire Control Panel (Clean Agent Unit) |  | 2025-11-12 | 2026-01-16 | 20-Jun-25 A | 2025-11-12 | 39
A16930 | Issue RFQ to Bidders |  |  | 20-Jun-25 A | 14-Aug-25 A | 0
A19650 | Issue Purchase Order to Vendor for Fire Detection, Local Fire Control and Clean Agent | 2025-11-12 | 2026-01-16 | 2025-11-05 | 2025-11-12 | 6
A19660 | Bid Evaluation(Completion) | 2025-10-09 | 2025-12-15 | 2025-09-19 | 2025-10-09 | 15
A19670 | Commercial Bid Evaluation(Completion) | 2025-11-04 | 2026-01-08 | 2025-10-10 | 2025-11-04 | 18
PSVs |  | 2025-11-06 | 2026-01-15 | 2025-09-19 | 2025-11-06 | 35
PSVs (1"x2" upto 8"x10" - CS Rating 150/150, 300/150 = 22 Nos) |  | 2025-11-06 | 2026-01-15 | 2025-09-19 | 2025-11-06 | 35
A21110 | Issue RFQ to Bidders | 2025-09-25 | 2025-12-04 | 2025-09-19 | 2025-09-25 | 5
A21120 | Issue Purchase Order to Vendor | 2025-11-06 | 2026-01-15 | 2025-10-24 | 2025-11-06 | 10
A21130 | Bid Evaluation(Completion) | 2025-10-09 | 2025-12-18 | 2025-09-26 | 2025-10-09 | 10
A21140 | Commercial Bid Evaluation(Completion) | 2025-10-23 | 2026-01-01 | 2025-10-10 | 2025-10-23 | 10
Sampling System |  |  |  | 12-Feb-25 A | 18-Mar-25 A | 0
TA_CGC Turbine Software Upgrade - HMI |  |  |  | 15-Feb-25 A | 18-Mar-25 A | 0
A37240 | Issue RFQ to Bidders |  |  | 15-Feb-25 A | 25-Feb-25 A | 0
A37270 | Issue Purchase Order to Vendor |  |  | 08-Mar-25 A | 18-Mar-25 A | 0
A57300 | TBE for ICT System Modification_Free Issue Material |  |  | 26-Feb-25 A | 07-Mar-25 A | 0
TA_SGM Replacement (Additional Item) |  |  |  | 12-Feb-25 A | 15-Mar-25 A | 0
A37400 | Issue RFQ to Bidders |  |  | 12-Feb-25 A | 22-Feb-25 A | 0
A37410 | Issue Purchase Order to Vendor |  |  | 05-Mar-25 A | 15-Mar-25 A | 0
A57330 | TBE for ICT System Modification_Free Issue Material |  |  | 23-Feb-25 A | 04-Mar-25 A | 0
F&G [324 Nos] Flame Detectors, MCP, Beacon, etc. |  | 2025-12-16 | 2026-02-12 | 18-Jul-25 A | 2025-12-16 | 63
F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 2025-12-16 | 2026-02-12 | 18-Jul-25 A | 2025-12-16 | 63
A16530 | Technical Bid Evaluation for Fire & Gas Detectors_IFR | 2025-10-08 | 2025-12-05 | 2025-09-19 | 2025-10-08 | 14
A16540 | Technical Bid Evaluation for Fire & Gas Detectors_RCC | 2025-10-20 | 2025-12-17 | 2025-10-08 | 2025-10-20 | 8
A16550 | Technical Bid Evaluation for Fire & Gas Detectors_IFA | 2025-10-27 | 2025-12-25 | 2025-10-20 | 2025-10-27 | 6
A16560 | Technical Bid Evaluation for Fire & Gas Detectors_RCA | 2025-11-04 | 2026-01-02 | 2025-10-28 | 2025-11-04 | 6
A17350 | Issue RFQ to Bidders |  |  | 18-Jul-25 A | 14-Aug-25 A | 0
A20110 | Issue Purchase Order to Vendor F&G Flames Detectors, MCP, Beacon (nos 324) | 2025-12-16 | 2026-02-12 | 2025-11-28 | 2025-12-16 | 12
A20130 | Commercial Bid Evaluation(Completion) | 2025-11-28 | 2026-01-27 | 2025-11-14 | 2025-11-28 | 10
A48220 | Technical Bid Evaluation for Fire & Gas Detectors_IFD/IFC | 2025-11-14 | 2026-01-13 | 2025-11-04 | 2025-11-14 | 8
Main Electrical Equipment |  | 2026-02-25 | 2026-07-13 | 20-Jan-25 A | 2026-02-25 | 113
DG Set (750 KVA) |  |  |  | 01-Feb-25 A | 22-Aug-25 A | 0
DG Set |  |  |  | 01-Feb-25 A | 22-Aug-25 A | 0
A13330 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFR |  |  | 08-Feb-25 A | 13-Feb-25 A | 0
A13340 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCC |  |  | 14-Feb-25 A | 20-Feb-25 A | 0
A13350 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFA |  |  | 21-Feb-25 A | 25-Feb-25 A | 0
A13360 | Technical Bid Evaluation For Emergency Diesel Generator Set_RCA |  |  | 26-Feb-25 A | 03-Mar-25 A | 0
A13370 | Technical Bid Evaluation For Emergency Diesel Generator Set_IFD/IFC |  |  | 04-Mar-25 A | 15-Jun-25 A | 0
A16030 | Issue RFQ to Bidders |  |  | 01-Feb-25 A | 07-Feb-25 A | 0
A20410 | Issue Purchase Order to Vendor for DG Set |  |  | 09-Aug-25 A | 22-Aug-25 A | 0
A20430 | Commercial Bid Evaluation(Completion) |  |  | 18-Jul-25 A | 08-Aug-25 A | 0
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) |  | 2025-11-28 | 2026-03-06 | 20-Jan-25 A | 2025-11-28 | 51
TA_UPS Modification (Additional Item) - Chloride Technology |  |  |  | 12-Feb-25 A | 15-Mar-25 A | 0
A37080 | Issue RFQs to Bidders |  |  | 12-Feb-25 A | 22-Feb-25 A | 0
A37090 | Issue Purchase Order to Vendor |  |  | 05-Mar-25 A | 15-Mar-25 A | 0
A57420 | TBE for Electrical System Modification_ Free Issue Material |  |  | 23-Feb-25 A | 04-Mar-25 A | 0
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 2025-11-28 | 2026-03-06 | 20-Jan-25 A | 2025-11-28 | 51
A13080 | Technical Bid Evaluation For AC UPS_IFR | 2025-10-06 | 2025-12-16 | 2025-09-19 | 2025-10-06 | 11
A13090 | Technical Bid Evaluation For AC UPS_RCC | 2025-10-13 | 2025-12-24 | 2025-10-06 | 2025-10-13 | 6
A13100 | Technical Bid Evaluation For AC UPS_IFA | 2025-10-21 | 2026-01-01 | 2025-10-13 | 2025-10-21 | 6
A13110 | Technical Bid Evaluation For AC UPS_RCA | 2025-10-29 | 2026-02-04 | 2025-10-21 | 2025-10-29 | 6
A13120 | Technical Bid Evaluation For AC UPS_IFD/IFC | 2025-11-13 | 2026-02-19 | 2025-10-29 | 2025-11-13 | 11
A16090 | Issue RFQ to Bidders |  |  | 20-Jan-25 A | 06-Feb-25 A | 0
A19530 | Issue Purchase Order to Vendor for UPS (GF) | 2025-11-28 | 2026-03-06 | 2025-11-21 | 2025-11-28 | 6
A19550 | Commercial Bid Evaluation(Completion) | 2025-11-20 | 2026-02-26 | 2025-11-13 | 2025-11-20 | 6
Power Transformer |  |  |  | 15-May-25 A | 29-Jul-25 A | 0
Power Transformers (Qty 05) |  |  |  | 15-May-25 A | 29-Jul-25 A | 0
A12930 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFR |  |  | 15-May-25 A | 25-May-25 A | 0
A12940 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCC |  |  | 15-May-25 A | 25-May-25 A | 0
A12950 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFA |  |  | 15-May-25 A | 25-May-25 A | 0
A12960 | Technical Bid Evaluation For Transformer (Power And Distribution)_RCA |  |  | 15-May-25 A | 25-May-25 A | 0
A12970 | Technical Bid Evaluation For Transformer (Power And Distribution)_IFD/IFC |  |  | 25-May-25 A | 01-Jun-25 A | 0
A16150 | Issue RFQ to Bidders |  |  | 15-May-25 A | 25-May-25 A | 0
A20170 | Issue Purchase Order to Vendor for Power Transformers |  |  | 09-Jun-25 A | 29-Jul-25 A | 0
A20190 | Commercial Bid Evaluation(Completion) |  |  | 02-Jun-25 A | 08-Jun-25 A | 0
Electrical Heat Tracing |  | 2026-01-16 | 2026-07-13 | 2025-09-19 | 2026-01-16 | 86
Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 2026-01-16 | 2026-07-13 | 2025-09-19 | 2026-01-16 | 86
A16270 | Issue RFQ to Bidders | 2025-10-17 | 2026-04-13 | 2025-09-19 | 2025-10-17 | 21
A22210 | Bid Evaluation(Completion) | 2025-11-28 | 2026-05-25 | 2025-10-20 | 2025-11-28 | 30
A22220 | Commercial Bid Evaluation(Completion) | 2025-12-29 | 2026-06-23 | 2025-12-01 | 2025-12-29 | 21
A22230 | Issue Purchase Order to Vendor | 2026-01-16 | 2026-07-13 | 2025-12-30 | 2026-01-16 | 14
CP |  | 2026-02-25 | 2026-05-15 | 2025-09-24 | 2026-02-25 | 110
Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 2026-02-25 | 2026-05-15 | 2025-09-24 | 2026-02-25 | 110
A16210 | Issue RFQ to Bidders | 2025-10-22 | 2026-01-09 | 2025-09-24 | 2025-10-22 | 20
A22150 | Bid Evaluation(Completion) | 2025-12-24 | 2026-03-13 | 2025-10-22 | 2025-12-24 | 45
A22160 | Commercial Bid Evaluation(Completion) | 2026-01-14 | 2026-04-03 | 2025-12-24 | 2026-01-14 | 15
A22170 | Issue Purchase Order to Vendor | 2026-02-25 | 2026-05-15 | 2026-01-14 | 2026-02-25 | 30
LV & MV Switchgears |  |  |  | 18-Mar-25 A | 10-Sep-25 A | 0
Switchgear (LV, MV) |  |  |  | 18-Mar-25 A | 10-Sep-25 A | 0
A13030 | Technical Bid Evaluation For LV Switchgear_IFR |  |  | 15-Apr-25 A | 20-Apr-25 A | 0
A13040 | Technical Bid Evaluation For LV Switchgear_RCC |  |  | 21-Apr-25 A | 25-Apr-25 A | 0
A13050 | Technical Bid Evaluation For LV Switchgear_IFA |  |  | 28-Apr-25 A | 01-May-25 A | 0
A13060 | Technical Bid Evaluation For LV Switchgear_RCA |  |  | 02-May-25 A | 10-May-25 A | 0
A13070 | Technical Bid Evaluation For LV Switchgear_IFD/IFC |  |  | 11-May-25 A | 18-Jul-25 A | 0
A16330 | Issue RFQ to Bidders |  |  | 18-Mar-25 A | 14-Apr-25 A | 0
A20230 | Issue Purchase Order to Vendor for switchgear (LV, MV) |  |  | 19-Aug-25 A | 10-Sep-25 A | 0
A20250 | Commercial Bid Evaluation(Completion) |  |  | 19-Jul-25 A | 29-Jul-25 A | 0
Switch Gear Modification (Siemens) |  |  |  | 20-Feb-25 A | 18-Mar-25 A | 0
TA_Switchgear (MV Switchgear Modifications) - Siemens |  |  |  | 20-Feb-25 A | 18-Mar-25 A | 0
A22400 | Issue RFQ to Bidders |  |  | 20-Feb-25 A | 25-Feb-25 A | 0
A22420 | Issue Purchase Order to Vendor |  |  | 10-Mar-25 A | 18-Mar-25 A | 0
A56240 | TBE for Electrical System Modification_Free Issue Material |  |  | 26-Feb-25 A | 09-Mar-25 A | 0
MV & LV VFD's |  |  |  | 18-Jul-25 A | 12-Aug-25 A | 0
Variable Fequency Drives (VFDs) LV Qty = 03 |  |  |  | 18-Jul-25 A | 12-Aug-25 A | 0
A13380 | Technical Bid Evaluation For LV Variable Frequency Drive_IFR |  |  | 21-Jul-25 A | 23-Jul-25 A | 0
A13390 | Technical Bid Evaluation For LV Variable Frequency Drive_RCC |  |  | 24-Jul-25 A | 25-Jul-25 A | 0
A13400 | Technical Bid Evaluation For LV Variable Frequency Drive_IFA |  |  | 28-Jul-25 A | 30-Jul-25 A | 0
A13410 | Technical Bid Evaluation For LV Variable Frequency Drive_RCA |  |  | 31-Jul-25 A | 01-Aug-25 A | 0
A13420 | Technical Bid Evaluation For LV Variable Frequency Drive_IFD/IFC |  |  | 04-Aug-25 A | 06-Aug-25 A | 0
A20790 | Issue RFQ to Bidders |  |  | 18-Jul-25 A | 20-Jul-25 A | 0
A20800 | Issue Purchase Order to Vendor for VFDs |  |  | 11-Aug-25 A | 12-Aug-25 A | 0
A20820 | Commercial Bid Evaluation(Completion) |  |  | 07-Aug-25 A | 08-Aug-25 A | 0
HV Capacitor Bay |  | 2025-10-22 | 2026-04-01 | 15-Apr-25 A | 2025-10-22 | 24
HV Capacitor Bay |  | 2025-10-22 | 2026-04-01 | 15-Apr-25 A | 2025-10-22 | 24
A13180 | Technical Bid Evaluation For Capacitor Bank_IFR | 2025-09-24 | 2025-12-23 | 2025-09-19 | 2025-09-24 | 3
A13190 | Technical Bid Evaluation For Capacitor Bank_RCC | 2025-09-29 | 2025-12-26 | 2025-09-24 | 2025-09-29 | 3
A13200 | Technical Bid Evaluation For Capacitor Bank_IFA | 2025-10-03 | 2026-01-01 | 2025-09-29 | 2025-10-03 | 3
A13210 | Technical Bid Evaluation For Capacitor Bank_RCA | 2025-10-08 | 2026-03-18 | 2025-10-03 | 2025-10-08 | 3
A13220 | Technical Bid Evaluation For Capacitor Bank_IFD/IFC | 2025-10-13 | 2026-03-24 | 2025-10-08 | 2025-10-13 | 3
A16570 | Issue RFQ to Bidders |  |  | 15-Apr-25 A | 06-May-25 A | 0
A19990 | Issue Purchase Order to Vendor for HV Capacitor Bay | 2025-10-22 | 2026-04-01 | 2025-10-17 | 2025-10-22 | 3
A20010 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2026-03-27 | 2025-10-13 | 2025-10-17 | 3
Power Distribution Panel and LCS, Battery & Safety Switch, Resister Bank |  |  |  | 10-Apr-25 A | 20-Jun-25 A | 0
NGR Panel Qty 02 |  |  |  | 10-Apr-25 A | 20-Jun-25 A | 0
A13280 | Technical Bid Evaluation For Neutral Grounding Resistor_IFR |  |  | 02-May-25 A | 13-May-25 A | 0
A13290 | Technical Bid Evaluation For Neutral Grounding Resistor_RCC |  |  | 14-May-25 A | 15-May-25 A | 0
A13300 | Technical Bid Evaluation For Neutral Grounding Resistor_IFA |  |  | 14-May-25 A | 15-May-25 A | 0
A13310 | Technical Bid Evaluation For Neutral Grounding Resistor_RCA |  |  | 14-May-25 A | 15-May-25 A | 0
A13320 | Technical Bid Evaluation For Neutral Grounding Resistor_IFD/IFC |  |  | 15-May-25 A | 20-May-25 A | 0
A16630 | Issue RFQ to Bidders |  |  | 10-Apr-25 A | 01-May-25 A | 0
A20290 | Issue Purchase Order to Vendor for NGR Panel |  |  | 14-Jun-25 A | 20-Jun-25 A | 0
A20310 | Commercial Bid Evaluation(Completion) |  |  | 21-May-25 A | 13-Jun-25 A | 0
Interposing Relay Panel (IRP) |  | 2025-11-28 | 2026-02-11 | 2025-09-19 | 2025-11-28 | 50
Interposing Relay Panel |  | 2025-11-28 | 2026-02-11 | 2025-09-19 | 2025-11-28 | 50
A16690 | Issue RFQ to Bidders | 2025-09-23 | 2026-01-12 | 2025-09-19 | 2025-09-23 | 3
A20350 | Issue Purchase Order to Vendor for Interposing Relay Panel | 2025-11-28 | 2026-02-11 | 2025-11-24 | 2025-11-28 | 4
A20370 | Commercial Bid Evaluation(Completion) | 2025-10-17 | 2026-02-05 | 2025-10-15 | 2025-10-17 | 3
A58640 | Technical Bid Evaluation for Interposting Relay Panel_IFR | 2025-09-26 | 2026-01-15 | 2025-09-24 | 2025-09-26 | 3
A58650 | Technical Bid Evaluation for Interposting Relay Panel_RCC | 2025-10-01 | 2026-01-20 | 2025-09-29 | 2025-10-01 | 3
A58660 | Technical Bid Evaluation for Interposting Relay Panel_IFA | 2025-10-06 | 2026-01-23 | 2025-10-02 | 2025-10-06 | 3
A58670 | Technical Bid Evaluation for Interposting Relay Panel_RCA | 2025-10-09 | 2026-01-28 | 2025-10-07 | 2025-10-09 | 3
A58680 | Technical Bid Evaluation for Interposting Relay Panel_IFD/IFC | 2025-10-14 | 2026-02-02 | 2025-10-10 | 2025-10-14 | 3
Subcontract Services |  |  |  | 14-Nov-24 A | 11-Jun-25 A | 0
Detail Engineering Subcontract |  |  |  | 14-Nov-24 A | 06-Dec-24 A | 0
A61090 | Issue RFQ to CONTRACTORs |  |  | 14-Nov-24 A | 15-Nov-24 A | 0
A61100 | Technical Bid analysis and clarifications |  |  | 19-Nov-24 A | 22-Nov-24 A | 0
A61110 | Bid analysis and clarifications |  |  | 23-Nov-24 A | 29-Nov-24 A | 0
A61120 | Subcontract Awarded/Signed |  |  | 29-Nov-24 A | 06-Dec-24 A | 0
TA Construction |  |  |  | 09-Dec-24 A | 07-Mar-25 A | 0
A61130 | Issue RFQ to CONTRACTORs |  |  | 09-Dec-24 A | 09-Dec-24 A | 0
A61140 | Technical Bid analysis and clarifications |  |  | 08-Jan-25 A | 08-Jan-25 A | 0
A61150 | Bid analysis and clarifications |  |  | 06-Feb-25 A | 06-Feb-25 A | 0
A61160 | Subcontract Awarded/Signed |  |  | 07-Mar-25 A | 07-Mar-25 A | 0
Main Construction |  |  |  | 09-Dec-24 A | 10-Mar-25 A | 0
A61170 | Issue RFQ to CONTRACTORs |  |  | 09-Dec-24 A | 01-Feb-25 A | 0
A61180 | Technical Bid analysis and clarifications |  |  | 02-Feb-25 A | 15-Feb-25 A | 0
A61190 | Bid analysis and clarifications |  |  | 16-Feb-25 A | 25-Feb-25 A | 0
A61200 | Subcontract Awarded/Signed |  |  | 07-Mar-25 A | 10-Mar-25 A | 0
Topgraphic |  |  |  | 01-Jan-25 A | 20-Mar-25 A | 0
A61210 | Issue RFQ to CONTRACTORs |  |  | 01-Jan-25 A | 03-Jan-25 A | 0
A61220 | Technical Bid analysis and clarifications |  |  | 04-Jan-25 A | 03-Feb-25 A | 0
A61230 | Bid analysis and clarifications |  |  | 04-Feb-25 A | 01-Mar-25 A | 0
A61240 | Subcontract Awarded/Signed |  |  | 02-Mar-25 A | 20-Mar-25 A | 0
Piling |  |  |  | 01-Apr-25 A | 11-May-25 A | 0
A61250 | Issue RFQ to CONTRACTORs |  |  | 01-Apr-25 A | 20-Apr-25 A | 0
A61260 | Technical Bid analysis and clarifications |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A61270 | Bid analysis and clarifications |  |  | 28-Apr-25 A | 04-May-25 A | 0
A61280 | Subcontract Awarded/Signed |  |  | 05-May-25 A | 11-May-25 A | 0
HSE Studies |  |  |  | 10-Feb-25 A | 11-Jun-25 A | 0
A61290 | Issue RFQ to CONTRACTORs |  |  | 10-Feb-25 A | 01-Mar-25 A | 0
A61300 | Technical Bid analysis and clarifications |  |  | 02-Mar-25 A | 15-Mar-25 A | 0
A61310 | Bid analysis and clarifications |  |  | 16-Mar-25 A | 18-Apr-25 A | 0
A61320 | Subcontract Awarded/Signed |  |  | 19-Apr-25 A | 11-Jun-25 A | 0
VSM Services Agreements |  |  |  | 01-Feb-25 A | 08-Mar-25 A | 0
A61330 | Issue RFQ to CONTRACTORs |  |  | 01-Feb-25 A | 15-Feb-25 A | 0
A61340 | Technical Bid analysis and clarifications |  |  | 16-Feb-25 A | 22-Feb-25 A | 0
A61350 | Bid analysis and clarifications |  |  | 23-Feb-25 A | 01-Mar-25 A | 0
A61360 | Subcontract Awarded/Signed |  |  | 02-Mar-25 A | 08-Mar-25 A | 0
As-Built & Package handover |  | 2027-07-14 | 2027-07-20 | 01-Jun-25 A | 2027-07-14 | 60
TA |  |  |  | 01-Jun-25 A | 15-Jul-25 A | 0
A61430 | TA As-Built |  |  | 01-Jun-25 A | 15-Jul-25 A | 0
Main Scope |  | 2027-07-14 | 2027-07-20 | 2027-04-22 | 2027-07-14 | 60
A61440 | Main Scope As-Built | 2027-07-14 | 2027-07-20 | 2027-04-22 | 2027-07-14 | 60
Manufacturing and Delivery |  | 2026-09-25 | 2027-01-31 | 25-Feb-25 A | 2026-09-25 | 253
51.C | Issue purchase orders for all remaining Mechanical / Rotating EQT. & EQT. Pkgs | 2025-09-19 | 2026-04-15 |  | 2025-09-19 | 0
52.C | Issue purchase orders for all major Electrical Equipments | 2026-02-24 | 2027-01-01 |  | 2026-02-24 | 0
54.C | Issue purchase order for all major Instruments Control System | 2025-12-16 | 2027-01-01 |  | 2025-12-16 | 0
79.D | All major electrical Equipment delivered to Site | 2026-07-23 | 2027-01-03 |  | 2026-07-23 | 0
Equipment Packages |  | 2026-08-27 | 2026-12-17 | 20-Jun-25 A | 2026-08-27 | 232
Vessels |  | 2026-06-23 | 2026-10-25 | 20-Jun-25 A | 2026-06-23 | 186
Vessels / Drums (by Linde) |  | 2026-06-23 | 2026-10-18 | 20-Jun-25 A | 2026-06-23 | 186
FG Comp. 2nd Stage Dis. Drum (13-VV-707) |  | 2026-06-12 | 2026-07-31 | 20-Jun-25 A | 2026-06-12 | 180
A35200 | Start Production (13-VV-707) |  |  | 20-Jun-25 A |  | 0
A35210 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2025-12-18 | 20-Jun-25 A | 2025-10-30 | 30
A35220 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2025-12-25 | 2025-10-30 | 2025-11-06 | 5
A35230 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-02-05 | 2025-11-06 | 2025-12-18 | 30
A35240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-19 | 2026-02-06 | 2025-12-18 | 2025-12-19 | 1
A35250 | Manufacturing / Ex Works (India/UAE) | 2026-04-08 | 2026-05-27 | 2025-12-19 | 2026-04-08 | 110
A35260 | Complete Manufacturing & ready for Final Inspection | 2026-04-17 | 2026-06-05 | 2026-04-08 | 2026-04-17 | 7
A35270 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-07 | 2026-06-25 | 2026-04-20 | 2026-05-07 | 14
A35320 | Delivery of FG Comp. 2nd Stage Dis. Drum Tag# 13-VV-707 | 2026-06-12 | 2026-07-31 | 2026-05-16 | 2026-06-12 | 28
OG Comp. 2nd Stage Suc. Drum (13-VV-713) |  | 2026-06-09 | 2026-08-06 | 20-Jun-25 A | 2026-06-09 | 177
A35060 | Start Production (13-VV-713) |  |  | 20-Jun-25 A |  | 0
A35070 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2025-12-26 | 20-Jun-25 A | 2025-10-30 | 30
A35080 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-01-02 | 2025-10-30 | 2025-11-06 | 5
A35090 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-02-13 | 2025-11-06 | 2025-12-18 | 30
A35100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-19 | 2026-02-15 | 2025-12-18 | 2025-12-19 | 1
A35110 | Manufacturing / Ex Works (India/UAE) | 2026-04-08 | 2026-06-05 | 2025-12-19 | 2026-04-08 | 110
A35120 | Complete Manufacturing & ready for Final Inspection | 2026-04-15 | 2026-06-12 | 2026-04-08 | 2026-04-15 | 5
A35130 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-05 | 2026-07-02 | 2026-04-15 | 2026-05-05 | 14
A35170 | Delivery of OG Comp. 2nd Stage Suc. Drum Tag# 13-VV-713 | 2026-06-09 | 2026-08-06 | 2026-05-12 | 2026-06-09 | 28
OG Buffer Drum (13-VV-712) |  | 2026-06-16 | 2026-09-10 | 20-Jun-25 A | 2026-06-16 | 181
A35340 | Start Production (13-VV-712) |  |  | 20-Jun-25 A |  | 0
A35350 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2026-01-23 | 20-Jun-25 A | 2025-10-30 | 30
A35360 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-01-30 | 2025-10-30 | 2025-11-06 | 5
A35370 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-03-13 | 2025-11-06 | 2025-12-18 | 30
A35380 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-19 | 2026-03-15 | 2025-12-18 | 2025-12-19 | 1
A35390 | Manufacturing / Ex Works (India/UAE) | 2026-04-08 | 2026-07-03 | 2025-12-19 | 2026-04-08 | 110
A35400 | Complete Manufacturing & ready for Final Inspection | 2026-04-15 | 2026-07-10 | 2026-04-08 | 2026-04-15 | 5
A35410 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-05 | 2026-07-30 | 2026-04-15 | 2026-05-05 | 14
A35470 | Delivery of OG Buffer Drum - Tag# 13-VV-712 | 2026-06-16 | 2026-09-10 | 2026-05-19 | 2026-06-16 | 28
PSA2 Slop Drum (70-VV-1415) |  | 2026-06-09 | 2026-10-18 | 20-Jun-25 A | 2026-06-09 | 177
A35480 | Start Production (70-VV-1415) |  |  | 20-Jun-25 A |  | 0
A35490 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2026-03-10 | 20-Jun-25 A | 2025-10-30 | 30
A35500 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-03-17 | 2025-10-30 | 2025-11-06 | 5
A35510 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-04-28 | 2025-11-06 | 2025-12-18 | 30
A35520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-19 | 2026-04-30 | 2025-12-18 | 2025-12-19 | 1
A35530 | Manufacturing / Ex Works (India/UAE) | 2026-04-08 | 2026-08-18 | 2025-12-19 | 2026-04-08 | 110
A35540 | Complete Manufacturing & ready for Final Inspection | 2026-04-15 | 2026-08-24 | 2026-04-08 | 2026-04-15 | 5
A35550 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-06 | 2026-09-14 | 2026-04-15 | 2026-05-06 | 15
A35580 | Delivery of PSA2 Slop Drum Tag# 70-VV-1415 | 2026-06-09 | 2026-10-18 | 2026-05-12 | 2026-06-09 | 28
FG Comp. 2nd Stage Suc. Drum (13-VV-706) |  | 2026-05-28 | 2026-07-28 | 20-Jun-25 A | 2026-05-28 | 170
A35620 | Start Production (13-VV-706) |  |  | 20-Jun-25 A |  | 0
A35630 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2025-12-30 | 20-Jun-25 A | 2025-10-30 | 30
A35640 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-01-06 | 2025-10-30 | 2025-11-06 | 5
A35650 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-02-17 | 2025-11-06 | 2025-12-18 | 30
A35660 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-19 | 2026-02-18 | 2025-12-18 | 2025-12-19 | 1
A35670 | Manufacturing / Ex Works (India/UAE) | 2026-04-08 | 2026-06-08 | 2025-12-19 | 2026-04-08 | 110
A35680 | Complete Manufacturing & ready for Final Inspection | 2026-04-17 | 2026-06-17 | 2026-04-08 | 2026-04-17 | 7
A35690 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-07 | 2026-07-07 | 2026-04-17 | 2026-05-07 | 14
A35710 | Delivery of FG Comp. 2nd Stage Suc. Drum Tag# 13-VV-706 | 2026-05-28 | 2026-07-28 | 2026-05-07 | 2026-05-28 | 21
FG Comp.1st Stage Suc. Drum (13-VV-705) |  | 2026-06-23 | 2026-08-15 | 20-Jun-25 A | 2026-06-23 | 186
A35760 | Start Production (13-VV-705) |  |  | 20-Jun-25 A |  | 0
A35770 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2025-12-23 | 20-Jun-25 A | 2025-10-30 | 30
A35780 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2025-12-30 | 2025-10-30 | 2025-11-06 | 5
A35790 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-02-10 | 2025-11-06 | 2025-12-18 | 30
A35800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-08 | 2026-03-04 | 2025-12-18 | 2026-01-08 | 21
A35810 | Manufacturing / Ex Works (India/UAE) | 2026-04-28 | 2026-06-22 | 2026-01-08 | 2026-04-28 | 110
A35820 | Complete Manufacturing & ready for Final Inspection | 2026-05-06 | 2026-06-29 | 2026-04-28 | 2026-05-06 | 6
A35830 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-26 | 2026-07-17 | 2026-05-06 | 2026-05-26 | 14
A35840 | Delivery of FG Comp.1st Stage Suc. Drum (13-VV-705) | 2026-06-23 | 2026-08-15 | 2026-05-26 | 2026-06-23 | 28
Vessel's Internals (05 Dimister pads) |  | 2026-05-27 | 2026-08-24 | 20-Jun-25 A | 2026-05-27 | 170
A29960 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2026-01-27 | 20-Jun-25 A | 2025-10-30 | 30
A29970 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-02-03 | 2025-10-30 | 2025-11-06 | 5
A29980 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-04 | 2026-03-03 | 2025-11-06 | 2025-12-04 | 20
A29990 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-05 | 2026-03-04 | 2025-12-04 | 2025-12-05 | 1
A30000 | Manufacturing / Ex Works (India/UAE) | 2026-03-25 | 2026-06-22 | 2025-12-05 | 2026-03-25 | 110
A30010 | Complete Manufacturing & ready for Final Inspection | 2026-04-08 | 2026-07-06 | 2026-03-25 | 2026-04-08 | 10
A30020 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-15 | 2026-07-13 | 2026-04-08 | 2026-04-15 | 5
A33660 | Start Production |  |  | 20-Jun-25 A |  | 0
A33670 | Delivery of Vessel's Internals (05 Dimister Pads) in Warehouse | 2026-05-27 | 2026-08-24 | 2026-04-15 | 2026-05-27 | 42
C4 Guard Adsorber Cooler Dripleg - (BF) |  | 2026-06-10 | 2026-10-25 | 20-Jun-25 A | 2026-06-10 | 178
A28160 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-04-13 | 20-Jun-25 A | 2025-11-27 | 50
A28170 | Purchase Order for Major Sub-ordered Materials | 2026-01-08 | 2026-05-25 | 2025-11-27 | 2026-01-08 | 30
A28180 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-06 | 2026-06-23 | 2026-01-08 | 2026-02-06 | 21
A28190 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-13 | 2026-07-01 | 2026-02-06 | 2026-02-13 | 7
A28200 | Manufacturing / Ex Works (India/UAE) | 2026-05-14 | 2026-09-29 | 2026-02-13 | 2026-05-14 | 90
A28210 | Complete Manufacturing & ready for Final Inspection | 2026-05-25 | 2026-10-07 | 2026-05-14 | 2026-05-25 | 7
A28220 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-03 | 2026-10-16 | 2026-05-25 | 2026-06-03 | 7
A34660 | Start Production |  |  | 20-Jun-25 A |  | 0
A34670 | Delivery of C4 Guard Absorber Cooler Dripleg (Post - TA) | 2026-06-10 | 2026-10-25 | 2026-06-03 | 2026-06-10 | 7
Water Collection & Sanitary Waste Water Pumps |  | 2026-07-28 | 2026-10-06 | 10-Aug-25 A | 2026-07-28 | 211
Sanitary Waste Water Sump Pump |  | 2026-07-27 | 2026-09-24 | 10-Sep-25 A | 2026-07-27 | 210
A30680 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2025-12-30 | 2025-09-19 | 2025-10-30 | 30
A30690 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-01-06 | 2025-10-30 | 2025-11-06 | 5
A30700 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-01 | 2026-03-03 | 2025-11-06 | 2026-01-01 | 40
A30710 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-02 | 2026-03-04 | 2026-01-01 | 2026-01-02 | 1
A30720 | Manufacturing / Ex Works (India/UAE) | 2026-05-22 | 2026-07-22 | 2026-01-02 | 2026-05-22 | 140
A30730 | Complete Manufacturing & ready for Final Inspection | 2026-06-03 | 2026-08-03 | 2026-05-22 | 2026-06-03 | 8
A30740 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-15 | 2026-08-13 | 2026-06-03 | 2026-06-15 | 8
A33850 | Start Production |  |  | 10-Sep-25 A |  | 0
A33860 | Delivery of Sanitary Waste Water Sump Pump (01) | 2026-07-27 | 2026-09-24 | 2026-06-15 | 2026-07-27 | 42
Water Collection Sump Pump ll |  | 2026-07-28 | 2026-10-06 | 10-Aug-25 A | 2026-07-28 | 211
A30770 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2026-01-08 | 2025-09-19 | 2025-10-30 | 30
A30780 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-01-15 | 2025-10-30 | 2025-11-06 | 5
A30790 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-01 | 2026-03-12 | 2025-11-06 | 2026-01-01 | 40
A30800 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-02 | 2026-03-13 | 2026-01-01 | 2026-01-02 | 1
A30810 | Manufacturing / Ex Works (India/UAE) | 2026-05-22 | 2026-07-31 | 2026-01-02 | 2026-05-22 | 140
A30820 | Complete Manufacturing & ready for Final Inspection | 2026-06-03 | 2026-08-12 | 2026-05-22 | 2026-06-03 | 8
A30830 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-16 | 2026-08-25 | 2026-06-03 | 2026-06-16 | 9
A33870 | Start Production |  |  | 10-Aug-25 A |  | 0
A33880 | Delivery of Water Sump Pump (02) | 2026-07-28 | 2026-10-06 | 2026-06-16 | 2026-07-28 | 42
EOT Cranes |  | 2026-08-14 | 2026-10-21 | 15-Aug-25 A | 2026-08-14 | 224
EOT Crane for FG Compressor (1 = 60 Ton) |  | 2026-08-13 | 2026-10-14 | 15-Aug-25 A | 2026-08-13 | 223
A30950 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-01-28 | 2025-09-19 | 2025-11-27 | 50
A30960 | Purchase Order for Major Sub-ordered Materials | 2025-12-04 | 2026-02-04 | 2025-11-27 | 2025-12-04 | 5
A30970 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-29 | 2026-04-01 | 2025-12-04 | 2026-01-29 | 40
A30980 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-30 | 2026-04-02 | 2026-01-29 | 2026-01-30 | 1
A30990 | Manufacturing / Ex Works (India/UAE) | 2026-06-04 | 2026-08-05 | 2026-01-30 | 2026-06-04 | 125
A31000 | Complete Manufacturing & ready for Final Inspection | 2026-06-18 | 2026-08-19 | 2026-06-04 | 2026-06-18 | 10
A31010 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-09-02 | 2026-06-18 | 2026-07-02 | 10
A33910 | Start Production |  |  | 15-Aug-25 A |  | 0
A33920 | Delivery of Material in Warehouse (FG) Crane | 2026-08-13 | 2026-10-14 | 2026-07-02 | 2026-08-13 | 42
EOT Crane for OG Compressor (1 = 25 Ton) |  | 2026-08-14 | 2026-10-21 | 10-Sep-25 A | 2026-08-14 | 224
A31040 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-02-03 | 2025-09-19 | 2025-11-27 | 50
A31050 | Purchase Order for Major Sub-ordered Materials | 2025-12-04 | 2026-02-10 | 2025-11-27 | 2025-12-04 | 5
A31060 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-29 | 2026-04-07 | 2025-12-04 | 2026-01-29 | 40
A31070 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-30 | 2026-04-08 | 2026-01-29 | 2026-01-30 | 1
A31080 | Manufacturing / Ex Works (India/UAE) | 2026-06-05 | 2026-08-12 | 2026-01-30 | 2026-06-05 | 126
A31090 | Complete Manufacturing & ready for Final Inspection | 2026-06-19 | 2026-08-26 | 2026-06-05 | 2026-06-19 | 10
A31100 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-03 | 2026-09-09 | 2026-06-19 | 2026-07-03 | 10
A33930 | Start Production |  |  | 10-Sep-25 A |  | 0
A33940 | Delivery of (OG) Crane | 2026-08-14 | 2026-10-21 | 2026-07-03 | 2026-08-14 | 42
Heat Exchangers |  | 2026-06-19 | 2026-11-04 | 11-Jul-25 A | 2026-06-19 | 184
Heat Exchanger (Type S & T = 06 Nos) |  | 2026-06-19 | 2026-11-04 | 11-Jul-25 A | 2026-06-19 | 184
FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 |  | 2026-06-05 | 2026-07-18 | 11-Jul-25 A | 2026-06-05 | 175
A36300 | Start Production (13-HE-703) |  |  | 11-Jul-25 A |  | 0
A36310 | Key Vendor Drawings / Data Approved |  |  | 18-Jul-25 A | 28-Aug-25 A | 0
A36320 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2025-12-18 | 29-Aug-25 A | 2025-11-06 | 35
A36330 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-25 | 2026-02-05 | 2025-11-07 | 2025-12-25 | 35
A36340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-04 | 2026-02-16 | 2025-12-26 | 2026-01-04 | 10
A36350 | Manufacturing / Ex Works (India/UAE) | 2026-04-09 | 2026-05-22 | 2026-01-05 | 2026-04-09 | 95
A36360 | Complete Manufacturing & ready for Final Inspection | 2026-04-23 | 2026-06-04 | 2026-04-10 | 2026-04-23 | 10
A36370 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-08 | 2026-06-19 | 2026-04-24 | 2026-05-08 | 11
A36380 | Delivery of FG Comp. Interstage Cooler (BEM) - Tag# 13-HE-703 | 2026-06-05 | 2026-07-18 | 2026-05-09 | 2026-06-05 | 28
OG Comp. After Cooler (BEU) - Tag# 13-HE-709 |  | 2026-06-19 | 2026-08-22 | 11-Jul-25 A | 2026-06-19 | 184
A36430 | Start Production (13-HE-709) |  |  | 11-Jul-25 A |  | 0
A36440 | Key Vendor Drawings / Data Approved |  |  | 18-Jul-25 A | 28-Aug-25 A | 0
A36450 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-01-08 | 29-Aug-25 A | 2025-11-06 | 35
A36460 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-25 | 2026-02-26 | 2025-11-07 | 2025-12-25 | 35
A36470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-04 | 2026-03-09 | 2025-12-26 | 2026-01-04 | 10
A36480 | Manufacturing / Ex Works (India/UAE) | 2026-04-09 | 2026-06-12 | 2026-01-05 | 2026-04-09 | 95
A36490 | Complete Manufacturing & ready for Final Inspection | 2026-04-23 | 2026-06-25 | 2026-04-10 | 2026-04-23 | 10
A36500 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-08 | 2026-07-10 | 2026-04-24 | 2026-05-08 | 11
A36520 | Delivery of OG Comp. After Cooler (BEU) - Tag# 13-HE-709 | 2026-06-19 | 2026-08-22 | 2026-05-09 | 2026-06-19 | 42
FG Comp. After Cooler (BEM) - Tag# 13-HE-704 |  | 2026-06-05 | 2026-07-18 | 11-Jul-25 A | 2026-06-05 | 175
A36560 | Start Production (13-HE-704) |  |  | 11-Jul-25 A |  | 0
A36570 | Key Vendor Drawings / Data Approved |  |  | 18-Jul-25 A | 28-Aug-25 A | 0
A36580 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2025-12-18 | 29-Aug-25 A | 2025-11-06 | 35
A36590 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-25 | 2026-02-05 | 2025-11-07 | 2025-12-25 | 35
A36600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-04 | 2026-02-16 | 2025-12-26 | 2026-01-04 | 10
A36610 | Manufacturing / Ex Works (India/UAE) | 2026-04-09 | 2026-05-22 | 2026-01-05 | 2026-04-09 | 95
A36620 | Complete Manufacturing & ready for Final Inspection | 2026-04-23 | 2026-06-04 | 2026-04-10 | 2026-04-23 | 10
A36630 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-08 | 2026-06-19 | 2026-04-24 | 2026-05-08 | 11
A36660 | Delivery of FG Comp. After Cooler (BEM) - Tag# 13-HE-704 | 2026-06-05 | 2026-07-18 | 2026-05-09 | 2026-06-05 | 28
OG Comp. Interstage Cooler (BEU) (13-HE-708) |  | 2026-06-19 | 2026-08-22 | 11-Jul-25 A | 2026-06-19 | 184
A36690 | Start Production (13-HE-708) |  |  | 11-Jul-25 A |  | 0
A36700 | Key Vendor Drawings / Data Approved |  |  | 18-Jul-25 A | 28-Aug-25 A | 0
A36710 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-01-08 | 29-Aug-25 A | 2025-11-06 | 35
A36720 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-25 | 2026-02-26 | 2025-11-07 | 2025-12-25 | 35
A36730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-04 | 2026-03-09 | 2025-12-26 | 2026-01-04 | 10
A36740 | Manufacturing / Ex Works (India/UAE) | 2026-04-09 | 2026-06-12 | 2026-01-05 | 2026-04-09 | 95
A36750 | Complete Manufacturing & ready for Final Inspection | 2026-04-23 | 2026-06-25 | 2026-04-10 | 2026-04-23 | 10
A36760 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-08 | 2026-07-10 | 2026-04-24 | 2026-05-08 | 11
A36800 | Delivery of GG Comp. Interstage Cooler (BEU) (13-HE-708) | 2026-06-19 | 2026-08-22 | 2026-05-09 | 2026-06-19 | 42
C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) |  | 2026-05-28 | 2026-11-04 | 11-Jul-25 A | 2026-05-28 | 170
A36820 | Start Production (50-HE-1410) |  |  | 11-Jul-25 A |  | 0
A36830 | Key Vendor Drawings / Data Approved |  |  | 18-Jul-25 A | 28-Aug-25 A | 0
A36840 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-04-15 | 29-Aug-25 A | 2025-11-06 | 35
A36850 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-25 | 2026-06-03 | 2025-11-07 | 2025-12-25 | 35
A36860 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-04 | 2026-06-14 | 2025-12-26 | 2026-01-04 | 10
A36870 | Manufacturing / Ex Works (India/UAE) | 2026-03-25 | 2026-09-02 | 2026-01-05 | 2026-03-25 | 80
A36880 | Complete Manufacturing & ready for Final Inspection | 2026-04-08 | 2026-09-15 | 2026-03-26 | 2026-04-08 | 10
A36890 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-23 | 2026-09-30 | 2026-04-09 | 2026-04-23 | 11
A36940 | Delivery of C4 Guard Regen. Gas Cooler (BEU) (Tag#50-HE-1410) | 2026-05-28 | 2026-11-04 | 2026-05-05 | 2026-05-28 | 24
HVAC |  | 2026-08-27 | 2026-12-17 | 29-Aug-25 A | 2026-08-27 | 232
HVAC |  | 2026-08-27 | 2026-12-17 | 29-Aug-25 A | 2026-08-27 | 232
A30860 | Key Vendor Drawings / Data Approved | 2025-12-11 | 2026-02-24 | 03-Sep-25 A | 2025-12-11 | 60
A30870 | Purchase Order for Major Sub-ordered Materials | 2025-12-25 | 2026-03-10 | 2025-12-11 | 2025-12-25 | 10
A30880 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-26 | 2026-05-12 | 2025-12-25 | 2026-02-26 | 45
A30890 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-27 | 2026-05-13 | 2026-02-26 | 2026-02-27 | 1
A30900 | Manufacturing / Ex Works (India/UAE) | 2026-07-17 | 2026-09-30 | 2026-02-27 | 2026-07-17 | 140
A30910 | Complete Manufacturing & ready for Final Inspection | 2026-07-28 | 2026-10-09 | 2026-07-17 | 2026-07-28 | 7
A30920 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-10-20 | 2026-07-28 | 2026-08-06 | 7
A33890 | Start Production |  |  | 29-Aug-25 A |  | 0
A33900 | Delivery of Material HVAC (Main Equipments) | 2026-08-27 | 2026-12-17 | 2026-08-06 | 2026-08-27 | 21
A34770 | Delivery of HVAC Ducts, E&I Material , Clading, Piping, Insulation, Supports & Accessories | 2026-08-18 | 2026-11-01 | 2026-08-06 | 2026-08-18 | 12
Bulk Materials |  | 2026-09-24 | 2027-01-31 | 15-Mar-25 A | 2026-09-24 | 252
Drip Leg |  | 2026-06-16 | 2026-08-30 | 03-Sep-25 A | 2026-06-16 | 181
OG Comp. Dis. Drip leg (02 Nos) |  | 2026-06-16 | 2026-08-30 | 03-Sep-25 A | 2026-06-16 | 181
A30590 | Key Vendor Drawings / Data Approved | 2025-12-11 | 2026-02-24 | 2025-09-19 | 2025-12-11 | 60
A30600 | Purchase Order for Major Sub-ordered Materials | 2025-12-23 | 2026-03-06 | 2025-12-11 | 2025-12-23 | 8
A30610 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-27 | 2026-04-10 | 2025-12-23 | 2026-01-27 | 25
A30620 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-03 | 2026-04-20 | 2026-01-27 | 2026-02-03 | 7
A30630 | Manufacturing / Ex Works (India/UAE) | 2026-04-14 | 2026-06-29 | 2026-02-03 | 2026-04-14 | 70
A30640 | Complete Manufacturing & ready for Final Inspection | 2026-04-21 | 2026-07-03 | 2026-04-14 | 2026-04-21 | 5
A30650 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-05 | 2026-07-17 | 2026-04-21 | 2026-05-05 | 10
A33830 | Start Production |  |  | 03-Sep-25 A |  | 0
A33840 | Delivery of OG Compressor Discharge Drip Leg (02) | 2026-06-16 | 2026-08-30 | 2026-05-05 | 2026-06-16 | 42
Fire Fighting Equipment |  | 2026-07-27 | 2026-11-02 | 2025-09-19 | 2026-07-27 | 209
VESDA (Very Early Smoke Detection Apparatus) |  | 2026-07-10 | 2026-11-02 | 2025-09-19 | 2026-07-10 | 198
A32210 | Key Vendor Drawings / Data Approved | 2025-11-28 | 2026-03-20 | 2025-09-22 | 2025-11-28 | 50
A32220 | Purchase Order for Major Sub-ordered Materials | 2025-12-12 | 2026-04-03 | 2025-11-28 | 2025-12-12 | 10
A32230 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-06 | 2026-05-29 | 2025-12-12 | 2026-02-06 | 40
A32240 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-07 | 2026-06-01 | 2026-02-06 | 2026-02-07 | 1
A32250 | Manufacturing / Ex Works (India/UAE) | 2026-05-23 | 2026-09-14 | 2026-02-07 | 2026-05-23 | 105
A32260 | Complete Manufacturing & ready for Final Inspection | 2026-06-03 | 2026-09-24 | 2026-05-25 | 2026-06-03 | 8
A32270 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-12 | 2026-10-05 | 2026-06-03 | 2026-06-12 | 8
A34190 | Start Production |  |  | 2025-09-19 |  | 0
A34200 | Delivery and Manufacturing VESDA | 2026-07-10 | 2026-11-02 | 2026-06-13 | 2026-07-10 | 28
Fire Fighting Equipment |  | 2026-07-27 | 2026-10-07 | 2025-11-13 | 2026-07-27 | 170
A31310 | Key Vendor Drawings / Data Approved | 2026-02-05 | 2026-04-17 | 2025-11-14 | 2026-02-05 | 60
A31320 | Purchase Order for Major Sub-ordered Materials | 2026-02-19 | 2026-05-01 | 2026-02-05 | 2026-02-19 | 10
A31330 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-16 | 2026-06-26 | 2026-02-19 | 2026-04-16 | 40
A31340 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-17 | 2026-06-28 | 2026-04-16 | 2026-04-17 | 1
A31350 | Manufacturing / Ex Works (India/UAE) | 2026-06-16 | 2026-08-27 | 2026-04-17 | 2026-06-16 | 60
A31360 | Complete Manufacturing & ready for Final Inspection | 2026-06-25 | 2026-09-07 | 2026-06-16 | 2026-06-25 | 7
A31370 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-06 | 2026-09-16 | 2026-06-25 | 2026-07-06 | 7
A33990 | Start Production |  |  | 2025-11-13 |  | 0
A34000 | Delivery of Fire Fighting Equipments | 2026-07-27 | 2026-10-07 | 2026-07-06 | 2026-07-27 | 21
Tail Gas Filter/Silencer/Colesor |  | 2026-08-22 | 2026-11-04 | 2025-10-16 | 2026-08-22 | 209
Coalescer - (BF) |  | 2026-08-22 | 2026-11-04 | 2025-10-16 | 2026-08-22 | 209
A28250 | Key Vendor Drawings / Data Approved | 2025-12-25 | 2026-03-06 | 2025-10-16 | 2025-12-25 | 50
A28260 | Purchase Order for Major Sub-ordered Materials | 2026-01-15 | 2026-03-27 | 2025-12-25 | 2026-01-15 | 15
A28270 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-19 | 2026-05-29 | 2026-01-15 | 2026-03-19 | 45
A28280 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-26 | 2026-06-07 | 2026-03-19 | 2026-03-26 | 7
A28290 | Manufacturing / Ex Works (India/UAE) | 2026-07-04 | 2026-09-15 | 2026-03-26 | 2026-07-04 | 100
A28300 | Complete Manufacturing & ready for Final Inspection | 2026-07-14 | 2026-09-24 | 2026-07-06 | 2026-07-14 | 7
A28310 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-23 | 2026-10-05 | 2026-07-15 | 2026-07-23 | 7
A34680 | Start Production |  |  | 2025-10-16 |  | 0
A34690 | Delivery of Coalescer (Post TA) | 2026-08-22 | 2026-11-04 | 2026-07-24 | 2026-08-22 | 30
Steel Structure Greenfield (material +sandwitch Panel) |  | 2026-04-09 | 2026-11-22 | 21-Jun-25 A | 2026-04-09 | 138
Civil Bulk Material |  | 2026-03-18 | 2026-11-22 | 21-Jun-25 A | 2026-03-18 | 124
A28430 | Key Vendor Drawings / Data Approved | 2025-10-23 | 2026-06-29 | 2025-09-19 | 2025-10-23 | 25
A28440 | Purchase Order for Major Sub-ordered Materials | 2025-12-04 | 2026-08-10 | 2025-10-23 | 2025-12-04 | 30
A28450 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-25 | 2026-08-31 | 2025-12-04 | 2025-12-25 | 15
A28460 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-01 | 2026-09-08 | 2025-12-25 | 2026-01-01 | 7
A28470 | Manufacturing / Ex Works (India/UAE) | 2026-01-31 | 2026-10-08 | 2026-01-01 | 2026-01-31 | 30
A28480 | Complete Manufacturing & ready for Final Inspection | 2026-02-20 | 2026-10-28 | 2026-02-02 | 2026-02-20 | 15
A28490 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-03 | 2026-11-06 | 2026-02-23 | 2026-03-03 | 7
A28500 | Delivery of Civil Bulk Material | 2026-03-18 | 2026-11-22 | 2026-03-04 | 2026-03-18 | 15
A33330 | Start Production |  |  | 21-Jun-25 A |  | 0
Structural Steel |  | 2026-04-09 | 2026-05-10 | 2025-10-10 | 2026-04-09 | 122
A28520 | Key Vendor Drawings / Data Approved | 2025-11-07 | 2025-12-05 | 2025-10-10 | 2025-11-07 | 20
A28530 | Purchase Order for Major Sub-ordered Materials | 2025-11-14 | 2025-12-12 | 2025-11-07 | 2025-11-14 | 5
A28540 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-26 | 2026-01-23 | 2025-11-14 | 2025-12-26 | 30
A28550 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-02 | 2026-02-01 | 2025-12-26 | 2026-01-02 | 7
A28560 | Manufacturing / Ex Works (India/UAE) | 2026-03-03 | 2026-04-02 | 2026-01-02 | 2026-03-03 | 60
A28570 | Complete Manufacturing & ready for Final Inspection | 2026-03-10 | 2026-04-08 | 2026-03-03 | 2026-03-10 | 5
A28580 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-19 | 2026-04-17 | 2026-03-10 | 2026-03-19 | 7
A33340 | Delivery of Structural Steel GF | 2026-04-09 | 2026-05-10 | 2026-03-19 | 2026-04-09 | 21
A33350 | Start Production |  |  | 2025-10-10 |  | 0
Tubing Material [SS tubes, Connectors, unions, plugs etc.] |  | 2026-05-15 | 2026-10-29 | 2025-12-15 | 2026-05-15 | 105
Tubing Material [SS tubes, Connectors, unions, plugs etc] |  | 2026-05-15 | 2026-10-29 | 2025-12-15 | 2026-05-15 | 105
A30140 | Key Vendor Drawings / Data Approved | 2026-01-12 | 2026-06-26 | 2025-12-15 | 2026-01-12 | 20
A30150 | Purchase Order for Major Sub-ordered Materials | 2026-02-02 | 2026-07-17 | 2026-01-12 | 2026-02-02 | 15
A30160 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-23 | 2026-08-07 | 2026-02-02 | 2026-02-23 | 15
A30170 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-24 | 2026-08-10 | 2026-02-23 | 2026-02-24 | 1
A30180 | Manufacturing / Ex Works (India/UAE) | 2026-04-15 | 2026-09-29 | 2026-02-24 | 2026-04-15 | 50
A30190 | Complete Manufacturing & ready for Final Inspection | 2026-04-24 | 2026-10-08 | 2026-04-15 | 2026-04-24 | 7
A30200 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-05 | 2026-10-19 | 2026-04-24 | 2026-05-05 | 7
A33700 | Start Production |  |  | 2025-12-15 |  | 0
A33710 | Delivery at site - (Tubing Material) | 2026-05-15 | 2026-10-29 | 2026-05-05 | 2026-05-15 | 10
Steel Structure Brownfield |  | 2026-03-02 | 2026-09-20 | 15-Mar-25 A | 2026-03-02 | 103
Steel Structure - Post TA - BF |  | 2026-03-02 | 2026-09-20 | 2025-10-02 | 2026-03-02 | 103
A34560 | Start Production |  |  | 2025-10-02 |  | 0
A34570 | Key Vendor Drawings / Data Approved | 2025-10-30 | 2026-05-20 | 2025-10-03 | 2025-10-30 | 20
A34580 | Purchase Order for Major Sub-ordered Materials | 2025-11-19 | 2026-06-09 | 2025-10-30 | 2025-11-19 | 14
A34590 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-07-08 | 2025-11-19 | 2025-12-18 | 21
A34600 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-25 | 2026-07-16 | 2025-12-18 | 2025-12-25 | 7
A34610 | Manufacturing / Ex Works | 2026-02-03 | 2026-08-25 | 2025-12-25 | 2026-02-03 | 40
A34620 | Complete Manufacturing & ready for Final Inspection | 2026-02-12 | 2026-09-02 | 2026-02-03 | 2026-02-12 | 7
A34630 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-23 | 2026-09-11 | 2026-02-12 | 2026-02-23 | 7
A34650 | Delivery of (Steel Structure - PostTA) | 2026-03-02 | 2026-09-20 | 2026-02-23 | 2026-03-02 | 7
TA_Steel Structure ( Additional Steel Structure required for BFW) |  |  |  | 15-Mar-25 A | 09-May-25 A | 0
A27800 | Key Vendor Drawings / Data Approved |  |  | 15-Mar-25 A | 20-Mar-25 A | 0
A27810 | Purchase Order for Major Sub-ordered Materials |  |  | 17-Mar-25 A | 21-Mar-25 A | 0
A27820 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 22-Mar-25 A | 28-Mar-25 A | 0
A27830 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 29-Mar-25 A | 04-Apr-25 A | 0
A27840 | Manufacturing / Ex Works (India/UAE) |  |  | 05-Apr-25 A | 11-Apr-25 A | 0
A27850 | Complete Manufacturing & ready for Final Inspection |  |  | 12-Apr-25 A | 18-Apr-25 A | 0
A27860 | Materials Successfully Inspected, Tested / Ex Work |  |  | 19-Apr-25 A | 25-Apr-25 A | 0
A34450 | Delivery at Site by EPC ( Fabricated, Painted & Galvanized TA Steel Structure ) |  |  | 26-Apr-25 A | 09-May-25 A | 0
A34490 | Start Production |  |  | 15-Mar-25 A |  | 0
Telecom (ACS+LAN +CCTV+PAGA) |  | 2026-09-24 | 2026-12-10 | 2025-11-19 | 2026-09-24 | 208
Package 1&2 TA Deliveries - Telecom | [5 empty] | 0
Telecom (ACS + CCTV + PAGA) Integration |  | 2026-09-24 | 2026-12-10 | 2025-11-19 | 2026-09-24 | 208
A31400 | Key Vendor Drawings / Data Approved | 2026-01-14 | 2026-04-01 | 2025-11-19 | 2026-01-14 | 40
A31410 | Purchase Order for Major Sub-ordered Materials | 2026-01-28 | 2026-04-15 | 2026-01-14 | 2026-01-28 | 10
A31420 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-25 | 2026-06-10 | 2026-01-28 | 2026-03-25 | 40
A31430 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-26 | 2026-06-11 | 2026-03-25 | 2026-03-26 | 1
A31440 | Manufacturing / Ex Works (India/UAE) | 2026-07-16 | 2026-10-01 | 2026-03-26 | 2026-07-16 | 112
A31450 | Complete Manufacturing & ready for Final Inspection | 2026-07-30 | 2026-10-15 | 2026-07-16 | 2026-07-30 | 10
A31460 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-13 | 2026-10-29 | 2026-07-30 | 2026-08-13 | 10
A34010 | Start Production |  |  | 2025-11-19 |  | 0
A34020 | Delivery of Telecom (ACS + CCTV + PAGA) Integration | 2026-09-24 | 2026-12-10 | 2026-08-13 | 2026-09-24 | 42
Acess Control System |  | 2026-09-09 | 2026-10-26 | 2025-11-19 | 2026-09-09 | 197
A31490 | Key Vendor Drawings / Data Approved | 2026-01-28 | 2026-03-16 | 2025-11-19 | 2026-01-28 | 50
A31500 | Purchase Order for Major Sub-ordered Materials | 2026-02-11 | 2026-03-30 | 2026-01-28 | 2026-02-11 | 10
A31510 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-08 | 2026-05-25 | 2026-02-11 | 2026-04-08 | 40
A31520 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-09 | 2026-05-26 | 2026-04-08 | 2026-04-09 | 1
A31530 | Manufacturing / Ex Works (India/UAE) | 2026-07-30 | 2026-09-15 | 2026-04-09 | 2026-07-30 | 112
A31540 | Complete Manufacturing & ready for Final Inspection | 2026-08-10 | 2026-09-24 | 2026-07-30 | 2026-08-10 | 7
A31550 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-19 | 2026-10-05 | 2026-08-10 | 2026-08-19 | 7
A34030 | Start Production |  |  | 2025-11-19 |  | 0
A34040 | Delivery of ACS | 2026-09-09 | 2026-10-26 | 2026-08-19 | 2026-09-09 | 21
CCTV |  | 2026-08-27 | 2026-10-26 | 2025-11-19 | 2026-08-27 | 189
A32310 | Purchase Order for Major Sub-ordered Materials | 2026-02-11 | 2026-04-10 | 2026-01-28 | 2026-02-11 | 10
A32320 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-08 | 2026-06-05 | 2026-02-11 | 2026-04-08 | 40
A32330 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-09 | 2026-06-07 | 2026-04-08 | 2026-04-09 | 1
A32340 | Manufacturing / Ex Works (India/UAE) | 2026-07-18 | 2026-09-15 | 2026-04-09 | 2026-07-18 | 100
A32350 | Complete Manufacturing & ready for Final Inspection | 2026-07-28 | 2026-09-24 | 2026-07-20 | 2026-07-28 | 7
A32360 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-10-05 | 2026-07-29 | 2026-08-06 | 7
A34210 | Start Production |  |  | 2025-11-19 |  | 0
A34220 | Key Vendor Drawings / Data Approved | 2026-01-28 | 2026-03-27 | 2025-11-19 | 2026-01-28 | 50
A34250 | Delivery of CCTV | 2026-08-27 | 2026-10-26 | 2026-08-07 | 2026-08-27 | 21
PAGA + Telephone |  | 2026-08-27 | 2026-11-09 | 2025-11-19 | 2026-08-27 | 189
A31580 | Key Vendor Drawings / Data Approved | 2026-01-28 | 2026-04-10 | 2025-11-19 | 2026-01-28 | 50
A31590 | Purchase Order for Major Sub-ordered Materials | 2026-02-11 | 2026-04-24 | 2026-01-28 | 2026-02-11 | 10
A31600 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-08 | 2026-06-19 | 2026-02-11 | 2026-04-08 | 40
A31610 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-09 | 2026-06-21 | 2026-04-08 | 2026-04-09 | 1
A31620 | Manufacturing / Ex Works (India/UAE) | 2026-07-18 | 2026-09-29 | 2026-04-09 | 2026-07-18 | 100
A31630 | Complete Manufacturing & ready for Final Inspection | 2026-07-28 | 2026-10-08 | 2026-07-20 | 2026-07-28 | 7
A31640 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-10-19 | 2026-07-29 | 2026-08-06 | 7
A34050 | Start Production |  |  | 2025-11-19 |  | 0
A34060 | Delivery of PAGA + Telephone | 2026-08-27 | 2026-11-09 | 2026-08-07 | 2026-08-27 | 21
Lighting Fixtures |  | 2026-09-23 | 2027-01-31 | 2026-02-24 | 2026-09-23 | 142
Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 2026-09-23 | 2027-01-31 | 2026-02-24 | 2026-09-23 | 142
A32390 | Key Vendor Drawings / Data Approved | 2026-05-05 | 2026-09-11 | 2026-02-25 | 2026-05-05 | 50
A32400 | Purchase Order for Major Sub-ordered Materials | 2026-05-19 | 2026-09-25 | 2026-05-05 | 2026-05-19 | 10
A32410 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-06-30 | 2026-11-06 | 2026-05-19 | 2026-06-30 | 30
A32420 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-07-01 | 2026-11-09 | 2026-06-30 | 2026-07-01 | 1
A32430 | Manufacturing / Ex Works (India/UAE) | 2026-08-12 | 2026-12-21 | 2026-07-01 | 2026-08-12 | 42
A32440 | Complete Manufacturing & ready for Final Inspection | 2026-08-19 | 2026-12-25 | 2026-08-12 | 2026-08-19 | 5
A32450 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-26 | 2027-01-01 | 2026-08-19 | 2026-08-26 | 5
A34230 | Start Production |  |  | 2026-02-24 |  | 0
A34240 | Delivery of Material in Warehouse Lighting Fixtures | 2026-09-23 | 2027-01-31 | 2026-08-26 | 2026-09-23 | 28
Manual Valve |  | 2026-09-18 | 2026-10-26 | 2025-12-12 | 2026-09-18 | 190
Package 1&2 TA Deliveries - Manual Valves | [5 empty] | 0
Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) |  | 2026-09-18 | 2026-10-26 | 2025-12-12 | 2026-09-18 | 190
A30050 | Key Vendor Drawings / Data Approved | 2026-01-23 | 2026-02-27 | 2025-12-12 | 2026-01-23 | 30
A30060 | Purchase Order for Major Sub-ordered Materials | 2026-01-30 | 2026-03-06 | 2026-01-23 | 2026-01-30 | 5
A30070 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-13 | 2026-04-17 | 2026-01-30 | 2026-03-13 | 30
A30080 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-14 | 2026-04-20 | 2026-03-13 | 2026-03-14 | 1
A30090 | Manufacturing / Ex Works (India/UAE) | 2026-07-12 | 2026-08-18 | 2026-03-14 | 2026-07-12 | 120
A30100 | Complete Manufacturing & ready for Final Inspection | 2026-07-24 | 2026-08-31 | 2026-07-13 | 2026-07-24 | 9
A30110 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-07 | 2026-09-14 | 2026-07-24 | 2026-08-07 | 10
A33680 | Start Production |  |  | 2025-12-12 |  | 0
A33690 | Delivery at site warehouse for Manual Valves (Gate 9 Nos, Check 6 Nos, Globe Valves 64 Nos) | 2026-09-18 | 2026-10-26 | 2026-08-07 | 2026-09-18 | 42
Piping Bulk |  | 2026-06-23 | 2026-09-02 | 19-Sep-25 A | 2026-06-23 | 186
Package 1&2 TA Deliveries - Piping | [5 empty] | 0
Piping Lot for Post TA |  | 2026-03-27 | 2026-05-06 | 2025-10-29 | 2026-03-27 | 101
84.D50 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 2026-03-27 | 2026-05-06 | 2026-03-18 | 2026-03-27 | 10
A27990 | Purchase Order for Major Sub-ordered Materials | 2025-11-05 | 2025-12-12 | 2025-10-29 | 2025-11-05 | 5
A28000 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-11-26 | 2026-01-02 | 2025-11-05 | 2025-11-26 | 15
A28010 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-03 | 2026-01-12 | 2025-11-26 | 2025-12-03 | 7
A28020 | Manufacturing / Ex Works (India/UAE) | 2026-02-21 | 2026-04-02 | 2025-12-03 | 2026-02-21 | 80
A28030 | Complete Manufacturing & ready for Final Inspection | 2026-03-03 | 2026-04-10 | 2026-02-23 | 2026-03-03 | 7
A28040 | Materials Successfully Inspected, Tested / Ex Work | 2026-03-17 | 2026-04-24 | 2026-03-04 | 2026-03-17 | 10
A34500 | Start Production |  |  | 2025-10-29 |  | 0
Piping Supports (Swing Hangers) for Post TA |  | 2026-06-23 | 2026-08-09 | 2026-01-13 | 2026-06-23 | 107
A28070 | Key Vendor Drawings / Data Approved | 2026-02-10 | 2026-03-18 | 2026-01-13 | 2026-02-10 | 20
A28080 | Purchase Order for Major Sub-ordered Materials | 2026-02-17 | 2026-03-25 | 2026-02-10 | 2026-02-17 | 5
A28090 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-24 | 2026-04-29 | 2026-02-17 | 2026-03-24 | 25
A28100 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-31 | 2026-05-06 | 2026-03-24 | 2026-03-31 | 7
A28110 | Manufacturing / Ex Works | 2026-05-26 | 2026-07-01 | 2026-03-31 | 2026-05-26 | 56
A28120 | Complete Manufacturing & ready for Final Inspection | 2026-06-09 | 2026-07-15 | 2026-05-26 | 2026-06-09 | 10
A28130 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-16 | 2026-07-22 | 2026-06-09 | 2026-06-16 | 5
A34510 | Start Production |  |  | 2026-01-13 |  | 0
A34520 | Delivery of Material in Warehouse ( Piping Swing Hangers - PostTA) | 2026-06-23 | 2026-08-09 | 2026-06-16 | 2026-06-23 | 7
Piping 1st Lot for GF |  | 2026-01-12 | 2026-03-16 | 19-Sep-25 A | 2026-01-12 | 78
84.D40 | Delivery of Piping Material in Warehouse (1st Lot, GF) | 2026-01-12 | 2026-03-16 | 2025-12-30 | 2026-01-12 | 14
A28620 | Purchase Order for Major Sub-ordered Materials | 2025-09-25 | 2025-11-27 | 2025-09-19 | 2025-09-25 | 5
A28630 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-10-09 | 2025-12-11 | 2025-09-26 | 2025-10-09 | 10
A28640 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-10-16 | 2025-12-18 | 2025-10-10 | 2025-10-16 | 7
A28650 | Manufacturing / Ex Works (India/UAE) | 2025-12-15 | 2026-02-16 | 2025-10-17 | 2025-12-15 | 60
A28660 | Complete Manufacturing & ready for Final Inspection | 2025-12-22 | 2026-02-23 | 2025-12-16 | 2025-12-22 | 5
A28670 | Materials Successfully Inspected, Tested / Ex Work | 2025-12-29 | 2026-03-02 | 2025-12-23 | 2025-12-29 | 5
A33360 | Start Production |  |  | 19-Sep-25 A |  | 0
Piping 2nd Lot for GF (CS Material) |  | 2026-03-02 | 2026-03-26 | 2025-10-16 | 2026-03-02 | 93
85.D10 | Delivery of Piping Material in Warehouse (2nd Lot) | 2026-03-02 | 2026-03-26 | 2026-02-16 | 2026-03-02 | 14
A28710 | Purchase Order for Major Sub-ordered Materials | 2025-10-30 | 2025-11-21 | 2025-10-16 | 2025-10-30 | 10
A28720 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-11-20 | 2025-12-12 | 2025-10-30 | 2025-11-20 | 15
A28730 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-11-27 | 2025-12-21 | 2025-11-20 | 2025-11-27 | 7
A28740 | Manufacturing / Ex Works (India/UAE) | 2026-01-26 | 2026-02-19 | 2025-11-27 | 2026-01-26 | 60
A28750 | Complete Manufacturing & ready for Final Inspection | 2026-02-02 | 2026-02-26 | 2026-01-26 | 2026-02-02 | 5
A28760 | Materials Successfully Inspected, Tested / Ex Work | 2026-02-16 | 2026-03-12 | 2026-02-02 | 2026-02-16 | 10
A33370 | Start Production |  |  | 2025-10-16 |  | 0
Piping 3rd Lot GF (CS Material) |  | 2026-04-30 | 2026-07-14 | 2025-12-30 | 2026-04-30 | 83
A28800 | Purchase Order for Major Sub-ordered Materials | 2026-01-06 | 2026-03-20 | 2025-12-30 | 2026-01-06 | 5
A28810 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-27 | 2026-04-10 | 2026-01-06 | 2026-01-27 | 15
A28820 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-30 | 2026-04-13 | 2026-01-27 | 2026-01-30 | 3
A28830 | Manufacturing / Ex Works (India/UAE) | 2026-03-31 | 2026-06-12 | 2026-01-30 | 2026-03-31 | 60
A28840 | Complete Manufacturing & ready for Final Inspection | 2026-04-07 | 2026-06-19 | 2026-03-31 | 2026-04-07 | 5
A28850 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-16 | 2026-06-30 | 2026-04-07 | 2026-04-16 | 7
A28860 | Delivery of Piping Material in Warehouse (Final Lot) | 2026-04-30 | 2026-07-14 | 2026-04-16 | 2026-04-30 | 14
A33380 | Start Production |  |  | 2025-12-30 |  | 0
Piping Supports (Swing Hangers) for GF |  | 2026-04-28 | 2026-09-02 | 2026-02-20 | 2026-04-28 | 44
A28970 | Key Vendor Drawings / Data Approved | 2026-02-27 | 2026-07-03 | 2026-02-20 | 2026-02-27 | 5
A28980 | Purchase Order for Major Sub-ordered Materials | 2026-03-06 | 2026-07-10 | 2026-02-27 | 2026-03-06 | 5
A28990 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-13 | 2026-07-17 | 2026-03-06 | 2026-03-13 | 5
A29000 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-18 | 2026-07-24 | 2026-03-13 | 2026-03-18 | 5
A29010 | Manufacturing / Ex Works (India/UAE) | 2026-03-28 | 2026-08-03 | 2026-03-18 | 2026-03-28 | 10
A29020 | Complete Manufacturing & ready for Final Inspection | 2026-04-03 | 2026-08-10 | 2026-03-30 | 2026-04-03 | 5
A29030 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-13 | 2026-08-18 | 2026-04-06 | 2026-04-13 | 6
A29040 | Delivery of Pipng Supports | 2026-04-28 | 2026-09-02 | 2026-04-14 | 2026-04-28 | 15
A33400 | Start Production |  |  | 2026-02-20 |  | 0
HDPE Piping |  | 2026-07-17 | 2026-09-02 | 2026-01-07 | 2026-07-17 | 129
HDPE Piping GF (Fire Water Lines) |  | 2026-07-17 | 2026-09-02 | 2026-01-07 | 2026-07-17 | 129
A28880 | Key Vendor Drawings / Data Approved | 2026-02-04 | 2026-03-23 | 2026-01-07 | 2026-02-04 | 20
A28890 | Purchase Order for Major Sub-ordered Materials | 2026-02-11 | 2026-03-30 | 2026-02-04 | 2026-02-11 | 5
A28900 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-25 | 2026-05-11 | 2026-02-11 | 2026-03-25 | 30
A28910 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-01 | 2026-05-18 | 2026-03-25 | 2026-04-01 | 7
A28920 | Manufacturing / Ex Works | 2026-06-17 | 2026-08-03 | 2026-04-01 | 2026-06-17 | 77
A28930 | Complete Manufacturing & ready for Final Inspection | 2026-06-24 | 2026-08-10 | 2026-06-17 | 2026-06-24 | 5
A28940 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-03 | 2026-08-19 | 2026-06-24 | 2026-07-03 | 7
A28950 | Delivery of HDPE Piping GF (Fire Water Lines) | 2026-07-17 | 2026-09-02 | 2026-07-03 | 2026-07-17 | 14
A33390 | Start Production |  |  | 2026-01-07 |  | 0
Piping SP Items (strainer, filters) |  | 2026-09-03 | 2026-10-16 | 2025-11-18 | 2026-09-03 | 195
Specialized Items (Orifice Flanges) CS 300# 1" - 6" = 08 Nos |  | 2026-05-30 | 2026-10-16 | 2025-11-18 | 2026-05-30 | 128
A30230 | Key Vendor Drawings / Data Approved | 2025-12-16 | 2026-05-04 | 2025-11-18 | 2025-12-16 | 20
A30240 | Purchase Order for Major Sub-ordered Materials | 2025-12-23 | 2026-05-11 | 2025-12-16 | 2025-12-23 | 5
A30250 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-20 | 2026-06-08 | 2025-12-23 | 2026-01-20 | 20
A30260 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-21 | 2026-06-09 | 2026-01-20 | 2026-01-21 | 1
A30270 | Manufacturing / Ex Works (India/UAE) | 2026-04-21 | 2026-09-07 | 2026-01-21 | 2026-04-21 | 90
A30280 | Complete Manufacturing & ready for Final Inspection | 2026-04-28 | 2026-09-14 | 2026-04-21 | 2026-04-28 | 5
A30290 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-05 | 2026-09-21 | 2026-04-28 | 2026-05-05 | 5
A30300 | Delivery of Orifice Flanges | 2026-05-30 | 2026-10-16 | 2026-05-05 | 2026-05-30 | 25
A33720 | Start Production |  |  | 2025-11-18 |  | 0
Specialized Items (Strainer/Filter) CS & SS 150 # -300# 2" - 26" = 08 Nos |  | 2026-09-03 | 2026-10-16 | 2026-03-25 | 2026-09-03 | 110
A30320 | Key Vendor Drawings / Data Approved | 2026-04-22 | 2026-06-04 | 2026-03-25 | 2026-04-22 | 20
A30330 | Purchase Order for Major Sub-ordered Materials | 2026-04-29 | 2026-06-11 | 2026-04-22 | 2026-04-29 | 5
A30340 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-27 | 2026-07-09 | 2026-04-29 | 2026-05-27 | 20
A30350 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-28 | 2026-07-10 | 2026-05-27 | 2026-05-28 | 1
A30360 | Manufacturing / Ex Works (India/UAE) | 2026-07-23 | 2026-09-04 | 2026-05-28 | 2026-07-23 | 56
A30370 | Complete Manufacturing & ready for Final Inspection | 2026-07-30 | 2026-09-11 | 2026-07-23 | 2026-07-30 | 5
A30380 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-09-18 | 2026-07-30 | 2026-08-06 | 5
A30390 | Delivery of Strainer/Filters Flanges | 2026-09-03 | 2026-10-16 | 2026-08-06 | 2026-09-03 | 28
A33730 | Start Production |  |  | 2026-03-25 |  | 0
Pressure / Temperature / Level Instruments, Flowmeters |  | 2026-05-12 | 2026-10-07 | 2025-10-29 | 2026-05-12 | 132
PT, TT & DPT [PT 50 Nos, TT 33 Nos, DPT 20 Nos] |  | 2026-05-12 | 2026-10-07 | 2025-10-29 | 2026-05-12 | 132
A29510 | Key Vendor Drawings / Data Approved | 2025-11-26 | 2026-04-23 | 2025-10-29 | 2025-11-26 | 20
A29520 | Purchase Order for Major Sub-ordered Materials | 2025-12-24 | 2026-05-21 | 2025-11-26 | 2025-12-24 | 20
A29530 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-21 | 2026-06-18 | 2025-12-24 | 2026-01-21 | 20
A29540 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-22 | 2026-06-19 | 2026-01-21 | 2026-01-22 | 1
A29550 | Manufacturing / Ex Works (India/UAE) | 2026-03-23 | 2026-08-18 | 2026-01-22 | 2026-03-23 | 60
A29560 | Complete Manufacturing & ready for Final Inspection | 2026-04-13 | 2026-09-08 | 2026-03-23 | 2026-04-13 | 15
A29570 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-04 | 2026-09-29 | 2026-04-13 | 2026-05-04 | 15
A33510 | Start Production |  |  | 2025-10-29 |  | 0
A33520 | Delivery of Material in Warehouse for PT,TT & DPT | 2026-05-12 | 2026-10-07 | 2026-05-04 | 2026-05-12 | 8
Instrument Bulk Material |  | 2026-09-12 | 2026-11-04 | 24-May-25 A | 2026-09-12 | 243
Package 1&2 TA Deliveries - Instruments | [5 empty] | 0
Gauges (PG, TG, PDG) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 2026-07-16 | 2026-10-29 | 2025-11-25 | 2026-07-16 | 155
A32840 | Key Vendor Drawings / Data Approved | 2026-02-03 | 2026-05-18 | 2025-11-25 | 2026-02-03 | 50
A32850 | Purchase Order for Major Sub-ordered Materials | 2026-02-24 | 2026-06-08 | 2026-02-03 | 2026-02-24 | 15
A32860 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-07 | 2026-07-20 | 2026-02-24 | 2026-04-07 | 30
A32870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-14 | 2026-07-27 | 2026-04-07 | 2026-04-14 | 7
A32880 | Manufacturing / Ex Works (India/UAE) | 2026-06-13 | 2026-09-25 | 2026-04-14 | 2026-06-13 | 60
A32890 | Complete Manufacturing & ready for Final Inspection | 2026-06-23 | 2026-10-06 | 2026-06-15 | 2026-06-23 | 7
A32900 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-10-15 | 2026-06-24 | 2026-07-02 | 7
A34340 | Start Production |  |  | 2025-11-25 |  | 0
A34350 | Delivery of Magnetic Level Gauges, PG, TG, PDG | 2026-07-16 | 2026-10-29 | 2026-07-03 | 2026-07-16 | 14
Analyzers |  |  |  | 24-May-25 A | 12-Jul-25 A | 0
A57650 | Start Production |  |  | 24-May-25 A |  | 0
A57660 | Key Vendor Drawings / Data Approved |  |  | 25-May-25 A | 31-May-25 A | 0
A57670 | Purchase Order for Major Sub-ordered Materials |  |  | 01-Jun-25 A | 07-Jun-25 A | 0
A57680 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 07-Jun-25 A | 14-Jun-25 A | 0
A57690 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 15-Jun-25 A | 21-Jun-25 A | 0
A57700 | Manufacturing / Ex Works (India/UAE) |  |  | 22-Jun-25 A | 28-Jun-25 A | 0
A57710 | Complete Manufacturing & ready for Final Inspection |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
A57720 | Materials Successfully Inspected, Tested / Ex Work |  |  | 29-Jun-25 A | 05-Jul-25 A | 0
A57730 | Delivery of Material in Warehouse for Analyzer |  |  | 06-Jul-25 A | 12-Jul-25 A | 0
Flow Elements Venturi |  | 2026-09-12 | 2026-11-04 | 2025-11-25 | 2026-09-12 | 196
A57830 | Key Vendor Drawings / Data Approved | 2026-01-27 | 2026-03-19 | 2025-11-25 | 2026-01-27 | 45
A57840 | Manufacturing / Ex Works (India/UAE) | 2026-07-26 | 2026-09-15 | 2026-04-07 | 2026-07-26 | 110
A57850 | Purchase Order for Major Sub-ordered Materials | 2026-02-17 | 2026-04-09 | 2026-01-27 | 2026-02-17 | 15
A57860 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-31 | 2026-05-21 | 2026-02-17 | 2026-03-31 | 30
A57870 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-07 | 2026-05-28 | 2026-03-31 | 2026-04-07 | 7
A57880 | Complete Manufacturing & ready for Final Inspection | 2026-08-04 | 2026-09-24 | 2026-07-27 | 2026-08-04 | 7
A57890 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-13 | 2026-10-05 | 2026-08-05 | 2026-08-13 | 7
A57900 | Start Production |  |  | 2025-11-25 |  | 0
A57910 | Delivery of Material in Warehouse for Flow Elements Venturi | 2026-09-12 | 2026-11-04 | 2026-08-14 | 2026-09-12 | 30
Flow Elements Orifice |  | 2026-08-25 | 2026-11-04 | 2025-11-18 | 2026-08-25 | 187
A57740 | Start Production |  |  | 2025-11-18 |  | 0
A57750 | Key Vendor Drawings / Data Approved | 2025-12-30 | 2026-03-13 | 2025-11-18 | 2025-12-30 | 30
A57760 | Purchase Order for Major Sub-ordered Materials | 2026-01-20 | 2026-04-03 | 2025-12-30 | 2026-01-20 | 15
A57770 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-31 | 2026-06-12 | 2026-01-20 | 2026-03-31 | 50
A57780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-05 | 2026-06-17 | 2026-03-31 | 2026-04-05 | 5
A57790 | Manufacturing / Ex Works (India/UAE) | 2026-07-24 | 2026-10-05 | 2026-04-05 | 2026-07-24 | 110
A57800 | Complete Manufacturing & ready for Final Inspection | 2026-08-04 | 2026-10-14 | 2026-07-24 | 2026-08-04 | 7
A57810 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-13 | 2026-10-23 | 2026-08-04 | 2026-08-13 | 7
A57820 | Delivery of Material in Warehouse for Flow Elements Orifice | 2026-08-25 | 2026-11-04 | 2026-08-13 | 2026-08-25 | 12
Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty = 5982 Mtrs, JBs = 73 Nos) |  | 2026-06-11 | 2026-10-07 | 2025-11-13 | 2026-06-11 | 139
A29420 | Key Vendor Drawings / Data Approved | 2026-01-08 | 2026-05-06 | 2025-11-14 | 2026-01-08 | 40
A29430 | Purchase Order for Major Sub-ordered Materials | 2026-01-19 | 2026-05-15 | 2026-01-08 | 2026-01-19 | 7
A29440 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-02 | 2026-06-26 | 2026-01-19 | 2026-03-02 | 30
A29450 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-03 | 2026-06-28 | 2026-03-02 | 2026-03-03 | 1
A29460 | Manufacturing / Ex Works (India/UAE) | 2026-05-02 | 2026-08-27 | 2026-03-03 | 2026-05-02 | 60
A29470 | Complete Manufacturing & ready for Final Inspection | 2026-05-12 | 2026-09-07 | 2026-05-04 | 2026-05-12 | 7
A29480 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-21 | 2026-09-16 | 2026-05-13 | 2026-05-21 | 7
A33490 | Start Production |  |  | 2025-11-13 |  | 0
A33500 | Delivery of Material in Warehouse for Cable Tray and Instrument Junction Box | 2026-06-11 | 2026-10-07 | 2026-05-22 | 2026-06-11 | 21
Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 2026-04-30 | 2026-09-16 | 18-Aug-25 A | 2026-04-30 | 153
A32750 | Key Vendor Drawings / Data Approved | 2025-10-16 | 2026-03-02 | 2025-09-19 | 2025-10-16 | 20
A32760 | Purchase Order for Major Sub-ordered Materials | 2025-11-06 | 2026-03-23 | 2025-10-16 | 2025-11-06 | 15
A32770 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-18 | 2026-05-04 | 2025-11-06 | 2025-12-18 | 30
A32780 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-12-19 | 2026-05-05 | 2025-12-18 | 2025-12-19 | 1
A32790 | Manufacturing / Ex Works (India/UAE) | 2026-03-29 | 2026-08-13 | 2025-12-19 | 2026-03-29 | 100
A32800 | Complete Manufacturing & ready for Final Inspection | 2026-04-07 | 2026-08-24 | 2026-03-30 | 2026-04-07 | 7
A32810 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-16 | 2026-09-02 | 2026-04-08 | 2026-04-16 | 7
A34320 | Start Production |  |  | 18-Aug-25 A |  | 0
A34330 | Delivery of Fibre Optic Cable | 2026-04-30 | 2026-09-16 | 2026-04-17 | 2026-04-30 | 14
Magnetic Level Gauge ( 09 Nos) |  | 2026-06-15 | 2026-10-07 | 2025-10-21 | 2026-06-15 | 158
A29780 | Key Vendor Drawings / Data Approved | 2025-12-23 | 2026-04-16 | 2025-10-22 | 2025-12-23 | 45
A29790 | Purchase Order for Major Sub-ordered Materials | 2026-01-06 | 2026-04-30 | 2025-12-23 | 2026-01-06 | 10
A29800 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-17 | 2026-06-11 | 2026-01-06 | 2026-02-17 | 30
A29810 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-24 | 2026-06-18 | 2026-02-17 | 2026-02-24 | 7
A29820 | Manufacturing / Ex Works (India/UAE) | 2026-05-05 | 2026-08-27 | 2026-02-24 | 2026-05-05 | 70
A29830 | Complete Manufacturing & ready for Final Inspection | 2026-05-14 | 2026-09-07 | 2026-05-05 | 2026-05-14 | 7
A29840 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-25 | 2026-09-16 | 2026-05-14 | 2026-05-25 | 7
A33570 | Start Production |  |  | 2025-10-21 |  | 0
A33580 | Delivery of Material in Warehouse for Magnetic Level Gauge | 2026-06-15 | 2026-10-07 | 2026-05-25 | 2026-06-15 | 21
Others | [5 empty] | 0
Instrument Bulk Materia l(Single & Multicore = Approx. 78,130 Mtr, FO Cables JB & Cable Trays)) |  | 2025-12-26 | 2026-10-08 | 2025-09-19 | 2025-12-26 | 68
A27890 | Key Vendor Drawings / Data Approved | 2025-10-16 | 2026-07-29 | 2025-09-19 | 2025-10-16 | 20
A27900 | Purchase Order for Major Sub-ordered Materials | 2025-10-23 | 2026-08-05 | 2025-10-16 | 2025-10-23 | 5
A27910 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-10-30 | 2026-08-12 | 2025-10-23 | 2025-10-30 | 5
A27920 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2025-10-31 | 2026-08-13 | 2025-10-30 | 2025-10-31 | 1
A27930 | Manufacturing / Ex Works (India/UAE) | 2025-11-21 | 2026-09-03 | 2025-10-31 | 2025-11-21 | 21
A27940 | Complete Manufacturing & ready for Final Inspection | 2025-11-28 | 2026-09-10 | 2025-11-21 | 2025-11-28 | 5
A27950 | Materials Successfully Inspected, Tested / Ex Work | 2025-12-05 | 2026-09-17 | 2025-11-28 | 2025-12-05 | 5
A34460 | Delivery of Material in Warehouse Instrument Bulk (Post TA) | 2025-12-26 | 2026-10-08 | 2025-12-05 | 2025-12-26 | 21
A34470 | Start Production |  |  | 2025-09-19 |  | 0
Earthing & Power Cables |  | 2026-07-20 | 2026-10-18 | 2025-10-22 | 2026-07-20 | 181
Earthing and Power Cables |  | 2026-07-20 | 2026-10-18 | 2025-10-22 | 2026-07-20 | 181
A28340 | Key Vendor Drawings / Data Approved | 2025-11-19 | 2026-02-17 | 2025-10-22 | 2025-11-19 | 20
A28350 | Purchase Order for Major Sub-ordered Materials | 2025-12-31 | 2026-03-31 | 2025-11-19 | 2025-12-31 | 30
A28360 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-04 | 2026-06-02 | 2025-12-31 | 2026-03-04 | 45
A28370 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-11 | 2026-06-10 | 2026-03-04 | 2026-03-11 | 7
A28380 | Manufacturing / Ex Works (India/UAE) | 2026-06-09 | 2026-09-08 | 2026-03-11 | 2026-06-09 | 90
A28390 | Complete Manufacturing & ready for Final Inspection | 2026-06-18 | 2026-09-16 | 2026-06-09 | 2026-06-18 | 7
A28400 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-29 | 2026-09-25 | 2026-06-18 | 2026-06-29 | 7
A33310 | Start Production |  |  | 2025-10-22 |  | 0
A33320 | Delivery of Earthing and Power Cables | 2026-07-20 | 2026-10-18 | 2026-06-29 | 2026-07-20 | 21
Electrical Bulk |  | 2026-06-23 | 2026-10-26 | 2025-09-19 | 2026-06-23 | 186
Package 1&2 TA Deliveries - Electrical | [5 empty] | 0
Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc |  | 2026-05-11 | 2026-10-07 | 2026-01-28 | 2026-05-11 | 70
A29150 | Key Vendor Drawings / Data Approved | 2026-02-25 | 2026-07-24 | 2026-01-29 | 2026-02-25 | 20
A29160 | Purchase Order for Major Sub-ordered Materials | 2026-03-04 | 2026-07-31 | 2026-02-25 | 2026-03-04 | 5
A29170 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-11 | 2026-08-07 | 2026-03-04 | 2026-03-11 | 5
A29180 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-12 | 2026-08-09 | 2026-03-11 | 2026-03-12 | 1
A29190 | Manufacturing / Ex Works (India/UAE) | 2026-04-06 | 2026-09-02 | 2026-03-12 | 2026-04-06 | 25
A29200 | Complete Manufacturing & ready for Final Inspection | 2026-04-13 | 2026-09-09 | 2026-04-06 | 2026-04-13 | 5
A29210 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-20 | 2026-09-16 | 2026-04-13 | 2026-04-20 | 5
A33430 | Start Production |  |  | 2026-01-28 |  | 0
A33440 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 2026-05-11 | 2026-10-07 | 2026-04-20 | 2026-05-11 | 21
Power Cables ( 11kV & 33kV) |  | 2026-05-11 | 2026-10-07 | 2025-09-19 | 2026-05-11 | 159
A61450 | Power Cables | 2025-09-25 | 2026-06-26 | 2025-09-19 | 2025-09-25 | 5
A61460 | Key Vendor Drawings / Data Approved | 2026-02-25 | 2026-07-24 | 2026-01-29 | 2026-02-25 | 20
A61470 | Start Production |  |  | 2026-01-28 |  | 0
A61480 | Purchase Order for Major Sub-ordered Materials | 2026-03-04 | 2026-07-31 | 2026-02-25 | 2026-03-04 | 5
A61490 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-11 | 2026-08-07 | 2026-03-04 | 2026-03-11 | 5
A61500 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-12 | 2026-08-09 | 2026-03-11 | 2026-03-12 | 1
A61510 | Manufacturing / Ex Works (India/UAE) | 2026-04-06 | 2026-09-02 | 2026-03-12 | 2026-04-06 | 25
A61520 | Complete Manufacturing & ready for Final Inspection | 2026-04-13 | 2026-09-09 | 2026-04-06 | 2026-04-13 | 5
A61530 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-20 | 2026-09-16 | 2026-04-13 | 2026-04-20 | 5
A61540 | Delivery of Material in Warehouse for Cable Trays, JBs, Conduit Pipe, Cable Lugs, etc | 2026-05-11 | 2026-10-07 | 2026-04-20 | 2026-05-11 | 21
LCS & Snap Switches |  | 2026-05-14 | 2026-10-26 | 2026-01-29 | 2026-05-14 | 72
A29330 | Key Vendor Drawings / Data Approved | 2026-02-26 | 2026-08-10 | 2026-01-30 | 2026-02-26 | 20
A29340 | Purchase Order for Major Sub-ordered Materials | 2026-03-05 | 2026-08-17 | 2026-02-26 | 2026-03-05 | 5
A29350 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-19 | 2026-08-31 | 2026-03-05 | 2026-03-19 | 10
A29360 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-20 | 2026-09-01 | 2026-03-19 | 2026-03-20 | 1
A29370 | Manufacturing / Ex Works (India/UAE) | 2026-04-17 | 2026-09-29 | 2026-03-20 | 2026-04-17 | 28
A29380 | Complete Manufacturing & ready for Final Inspection | 2026-04-23 | 2026-10-05 | 2026-04-17 | 2026-04-23 | 4
A29390 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-30 | 2026-10-12 | 2026-04-24 | 2026-04-30 | 5
A33470 | Start Production |  |  | 2026-01-29 |  | 0
A33480 | Delivery of Material in Warehouse for LCS & snap Switches | 2026-05-14 | 2026-10-26 | 2026-05-01 | 2026-05-14 | 14
Electrical Bulk Material ( Earthing ,FO, Power Cables) |  | 2026-06-23 | 2026-10-05 | 2025-09-19 | 2026-06-23 | 186
A17930 | Start Production |  |  | 2025-09-19 |  | 0
A27440 | Key Vendor Drawings / Data Approved | 2026-01-01 | 2026-04-15 | 2025-09-19 | 2026-01-01 | 75
A27450 | Purchase Order for Major Sub-ordered Materials | 2026-01-15 | 2026-04-29 | 2026-01-01 | 2026-01-15 | 10
A27460 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-26 | 2026-06-10 | 2026-01-15 | 2026-02-26 | 30
A27470 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-27 | 2026-06-11 | 2026-02-26 | 2026-02-27 | 1
A27480 | Manufacturing / Ex Works (India/UAE) | 2026-05-13 | 2026-08-25 | 2026-02-27 | 2026-05-13 | 75
A27490 | Complete Manufacturing & ready for Final Inspection | 2026-05-22 | 2026-09-03 | 2026-05-13 | 2026-05-22 | 7
A27500 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-02 | 2026-09-14 | 2026-05-22 | 2026-06-02 | 7
A33300 | Delivery of Electrical Bulk Material (Earthing, FO, 11 KVA Cable) (Post TA) | 2026-06-23 | 2026-10-05 | 2026-06-02 | 2026-06-23 | 21
Main Automation Equipment |  | 2026-09-09 | 2026-12-10 | 26-Feb-25 A | 2026-09-09 | 240
On Off Valve / Control Valves |  | 2026-09-09 | 2026-10-29 | 2025-11-17 | 2026-09-09 | 198
ESD Valves |  | 2026-09-09 | 2026-10-29 | 2025-11-18 | 2026-09-09 | 197
A59810 | Key Vendor Drawings / Data Approved | 2026-02-10 | 2026-04-02 | 2025-11-19 | 2026-02-10 | 60
A59820 | Manufacturing / Ex Works (India/UAE) | 2026-08-08 | 2026-09-27 | 2026-01-05 | 2026-08-08 | 215
A59830 | Purchase Order for Major Sub-ordered Materials | 2025-11-27 | 2026-01-16 | 2025-11-19 | 2025-11-27 | 8
A59840 | Major Sub-ordered Materials Received by Vendor and Verified | 2025-12-29 | 2026-02-17 | 2025-11-27 | 2025-12-29 | 32
A59850 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-05 | 2026-02-24 | 2025-12-29 | 2026-01-05 | 7
A59860 | Complete Manufacturing & ready for Final Inspection | 2026-08-13 | 2026-10-03 | 2026-08-08 | 2026-08-13 | 6
A59870 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-19 | 2026-10-08 | 2026-08-13 | 2026-08-19 | 6
A59880 | Start Production |  |  | 2025-11-18 |  | 0
A59890 | Delivery of Control Valves | 2026-09-09 | 2026-10-29 | 2026-08-19 | 2026-09-09 | 21
Control Valves (1" - 24" Rating 150, 300 & 2500 = 32 Nos) + SDV |  | 2026-08-30 | 2026-10-29 | 2025-11-17 | 2026-08-30 | 191
A30410 | Key Vendor Drawings / Data Approved | 2026-01-26 | 2026-03-27 | 2025-11-18 | 2026-01-26 | 50
A30420 | Purchase Order for Major Sub-ordered Materials | 2026-02-09 | 2026-04-10 | 2026-01-26 | 2026-02-09 | 10
A30430 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-23 | 2026-05-22 | 2026-02-09 | 2026-03-23 | 30
A30440 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-30 | 2026-05-30 | 2026-03-23 | 2026-03-30 | 7
A30450 | Manufacturing / Ex Works (India/UAE) | 2026-07-28 | 2026-09-27 | 2026-03-30 | 2026-07-28 | 120
A30460 | Complete Manufacturing & ready for Final Inspection | 2026-08-03 | 2026-10-03 | 2026-07-28 | 2026-08-03 | 6
A30470 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-09 | 2026-10-08 | 2026-08-03 | 2026-08-09 | 6
A33740 | Start Production |  |  | 2025-11-17 |  | 0
A33750 | Delivery of Control Valves | 2026-08-30 | 2026-10-29 | 2026-08-09 | 2026-08-30 | 21
MOVs |  | 2026-07-23 | 2026-12-10 | 2025-09-19 | 2026-07-23 | 208
MOVs [Ball Type 24" 150# = 01 No] |  | 2026-07-23 | 2026-12-10 | 2025-09-19 | 2026-07-23 | 208
A32660 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-04-16 | 2025-09-19 | 2025-11-27 | 50
A32670 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-04-30 | 2025-11-27 | 2025-12-11 | 10
A32680 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-22 | 2026-06-11 | 2025-12-11 | 2026-01-22 | 30
A32690 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-23 | 2026-06-12 | 2026-01-22 | 2026-01-23 | 1
A32700 | Manufacturing / Ex Works (India/UAE) | 2026-06-12 | 2026-10-30 | 2026-01-23 | 2026-06-12 | 140
A32710 | Complete Manufacturing & ready for Final Inspection | 2026-06-23 | 2026-11-10 | 2026-06-12 | 2026-06-23 | 7
A32720 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-11-19 | 2026-06-23 | 2026-07-02 | 7
A34300 | Start Production |  |  | 2025-09-19 |  | 0
A34310 | Delivery of MOVs | 2026-07-23 | 2026-12-10 | 2026-07-02 | 2026-07-23 | 21
Machine Condition Monitoring System (MCMS) |  | 2026-05-11 | 2026-10-26 | 25-May-25 A | 2026-05-11 | 160
Machine Condition Monitoring System |  | 2026-05-11 | 2026-10-26 | 25-May-25 A | 2026-05-11 | 160
A31940 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-05-14 | 2025-09-19 | 2025-11-27 | 50
A31950 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-05-28 | 2025-11-27 | 2025-12-11 | 10
A31960 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-22 | 2026-07-09 | 2025-12-11 | 2026-01-22 | 30
A31970 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-25 | 2026-07-12 | 2026-01-22 | 2026-01-25 | 3
A31980 | Manufacturing / Ex Works (India/UAE) | 2026-04-10 | 2026-09-25 | 2026-01-25 | 2026-04-10 | 75
A31990 | Complete Manufacturing & ready for Final Inspection | 2026-04-17 | 2026-10-02 | 2026-04-10 | 2026-04-17 | 5
A32000 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-24 | 2026-10-09 | 2026-04-17 | 2026-04-24 | 5
A34130 | Start Production |  |  | 25-May-25 A |  | 0
A34140 | Delivery of MCMS | 2026-05-11 | 2026-10-26 | 2026-04-24 | 2026-05-11 | 17
IPCS Modification (ABB) |  | 2026-08-27 | 2026-10-14 | 21-Mar-25 A | 2026-08-27 | 232
TA_Integrated Protection and Control System BF - ABB/Hitachi |  |  |  | 21-Mar-25 A | 16-May-25 A | 0
A27710 | Key Vendor Drawings / Data Approved |  |  | 21-Mar-25 A | 28-Mar-25 A | 0
A27720 | Purchase Order for Major Sub-ordered Materials |  |  | 01-Apr-25 A | 04-Apr-25 A | 0
A27730 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 05-Apr-25 A | 11-Apr-25 A | 0
A27740 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 12-Apr-25 A | 18-Apr-25 A | 0
A27750 | Manufacturing / Ex Works (India/UAE) |  |  | 19-Apr-25 A | 25-Apr-25 A | 0
A27760 | Complete Manufacturing & ready for Final Inspection |  |  | 26-Apr-25 A | 02-May-25 A | 0
A27770 | Materials Successfully Inspected, Tested / Ex Work |  |  | 03-May-25 A | 09-May-25 A | 0
A27780 | Delivery of FOPP (02 Nos) |  |  | 10-May-25 A | 16-May-25 A | 0
A34480 | Start Production |  |  | 21-Mar-25 A |  | 0
Integrated Protection Control System |  | 2026-08-27 | 2026-10-14 | 25-Jul-25 A | 2026-08-27 | 232
A24030 | Start Production |  |  | 25-Jul-25 A |  | 0
A31220 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-01-13 | 10-Sep-25 A | 2025-11-27 | 50
A31230 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-01-27 | 2025-11-27 | 2025-12-11 | 10
A31240 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-05 | 2026-03-24 | 2025-12-11 | 2026-02-05 | 40
A31250 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-08 | 2026-03-27 | 2026-02-05 | 2026-02-08 | 3
A31260 | Manufacturing / Ex Works (India/UAE) | 2026-07-18 | 2026-09-03 | 2026-02-08 | 2026-07-18 | 160
A31270 | Complete Manufacturing & ready for Final Inspection | 2026-07-28 | 2026-09-14 | 2026-07-20 | 2026-07-28 | 7
A31280 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-06 | 2026-09-23 | 2026-07-29 | 2026-08-06 | 7
A33970 | Delivery of IPCS | 2026-08-27 | 2026-10-14 | 2026-08-07 | 2026-08-27 | 21
OTS |  | 2026-08-19 | 2026-10-14 | 13-Mar-25 A | 2026-08-19 | 227
TA_SCMS System - Siemens |  |  |  | 13-Mar-25 A | 11-May-25 A | 0
A27620 | Key Vendor Drawings / Data Approved |  |  | 13-Mar-25 A | 16-Mar-25 A | 0
A27630 | Purchase Order for Major Sub-ordered Materials |  |  | 24-Mar-25 A | 30-Mar-25 A | 0
A27640 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 31-Mar-25 A | 06-Apr-25 A | 0
A27650 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 07-Apr-25 A | 13-Apr-25 A | 0
A27660 | Manufacturing / Ex Works (India/UAE) |  |  | 14-Apr-25 A | 20-Apr-25 A | 0
A27670 | Complete Manufacturing & ready for Final Inspection |  |  | 21-Apr-25 A | 27-Apr-25 A | 0
A27680 | Materials Successfully Inspected, Tested / Ex Work |  |  | 28-Apr-25 A | 04-May-25 A | 0
A27690 | Delivery of SCMS |  |  | 05-May-25 A | 11-May-25 A | 0
A33290 | Start Production |  |  | 23-Mar-25 A |  | 0
SCMS System |  | 2026-08-19 | 2026-10-14 | 23-May-25 A | 2026-08-19 | 227
A60100 | Start Production |  |  | 23-May-25 A |  | 0
A60110 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-01-22 | 2025-09-19 | 2025-11-27 | 50
A60120 | Manufacturing / Ex Works (India/UAE) | 2026-07-09 | 2026-09-03 | 2026-01-30 | 2026-07-09 | 160
A60130 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-02-05 | 2025-11-27 | 2025-12-11 | 10
A60140 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-29 | 2026-03-26 | 2025-12-11 | 2026-01-29 | 35
A60150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-30 | 2026-03-27 | 2026-01-29 | 2026-01-30 | 1
A60160 | Complete Manufacturing & ready for Final Inspection | 2026-07-20 | 2026-09-14 | 2026-07-09 | 2026-07-20 | 7
A60170 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-29 | 2026-09-23 | 2026-07-20 | 2026-07-29 | 7
A60180 | Delivery of SCMS | 2026-08-19 | 2026-10-14 | 2026-07-29 | 2026-08-19 | 21
ICSS (Integrated Control and Safety System) including sys. Modifications |  | 2026-09-01 | 2026-10-22 | 20-Mar-25 A | 2026-09-01 | 235
TA_Integrated Control and Safety System BF - Honeywell |  |  |  | 20-Mar-25 A | 17-May-25 A | 0
A27530 | Key Vendor Drawings / Data Approved |  |  | 20-Mar-25 A | 29-Mar-25 A | 0
A27540 | Purchase Order for Major Sub-ordered Materials |  |  | 29-Mar-25 A | 05-Apr-25 A | 0
A27550 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 06-Apr-25 A | 12-Apr-25 A | 0
A27560 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 13-Apr-25 A | 19-Apr-25 A | 0
A27570 | Manufacturing / Ex Works (India/UAE) |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A27580 | Complete Manufacturing & ready for Final Inspection |  |  | 27-Apr-25 A | 03-May-25 A | 0
A27590 | Materials Successfully Inspected, Tested / Ex Work |  |  | 04-May-25 A | 10-May-25 A | 0
A27600 | Delivery of loose Material for ICSS Modification |  |  | 11-May-25 A | 17-May-25 A | 0
A33280 | Start Production |  |  | 22-Mar-25 A |  | 0
Integrated Control and Safety System GF |  | 2026-09-01 | 2026-10-22 | 20-Jun-25 A | 2026-09-01 | 235
A31130 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-01-16 | 2025-09-19 | 2025-11-27 | 50
A31140 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-01-30 | 2025-11-27 | 2025-12-11 | 10
A31150 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-22 | 2026-03-13 | 2025-12-11 | 2026-01-22 | 30
A31160 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-23 | 2026-03-15 | 2026-01-22 | 2026-01-23 | 1
A31170 | Manufacturing / Ex Works (India/UAE) | 2026-07-22 | 2026-09-11 | 2026-01-23 | 2026-07-22 | 180
A31180 | Complete Manufacturing & ready for Final Inspection | 2026-07-31 | 2026-09-22 | 2026-07-22 | 2026-07-31 | 7
A31190 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-11 | 2026-10-01 | 2026-07-31 | 2026-08-11 | 7
A33950 | Start Production |  |  | 20-Jun-25 A |  | 0
A33960 | Delivery of Material in Warehouse ICSS | 2026-09-01 | 2026-10-22 | 2026-08-11 | 2026-09-01 | 21
Instrument Cables |  | 2026-06-16 | 2026-10-07 | 2025-11-13 | 2026-06-16 | 141
Instrument Cable (Single & Multicore = Approx. 78,130 Mtr) |  | 2026-06-16 | 2026-10-07 | 2025-11-13 | 2026-06-16 | 141
A29690 | Key Vendor Drawings / Data Approved | 2025-12-25 | 2026-04-17 | 2025-11-14 | 2025-12-25 | 30
A29700 | Purchase Order for Major Sub-ordered Materials | 2026-01-08 | 2026-05-01 | 2025-12-25 | 2026-01-08 | 10
A29710 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-29 | 2026-05-22 | 2026-01-08 | 2026-01-29 | 15
A29720 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-05 | 2026-05-29 | 2026-01-29 | 2026-02-05 | 7
A29730 | Manufacturing / Ex Works (India/UAE) | 2026-05-06 | 2026-08-27 | 2026-02-05 | 2026-05-06 | 90
A29740 | Complete Manufacturing & ready for Final Inspection | 2026-05-15 | 2026-09-07 | 2026-05-06 | 2026-05-15 | 7
A29750 | Materials Successfully Inspected, Tested / Ex Work | 2026-05-26 | 2026-09-16 | 2026-05-15 | 2026-05-26 | 7
A33550 | Start Production |  |  | 2025-11-13 |  | 0
A33560 | Delivery of Material in Warehouse for Instrument Cable | 2026-06-16 | 2026-10-07 | 2026-05-26 | 2026-06-16 | 21
Local Fire Control Panel including F&G Detectors |  | 2026-08-01 | 2026-10-07 | 2025-11-12 | 2026-08-01 | 175
Fire Detection Alarm System and Local Fire Control Panel (Clean Agent Unit) |  | 2026-08-01 | 2026-10-07 | 2025-11-12 | 2026-08-01 | 175
A31760 | Key Vendor Drawings / Data Approved | 2025-12-24 | 2026-02-27 | 2025-11-13 | 2025-12-24 | 30
A31770 | Purchase Order for Major Sub-ordered Materials | 2026-01-07 | 2026-03-13 | 2025-12-24 | 2026-01-07 | 10
A31780 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-04 | 2026-05-08 | 2026-01-07 | 2026-03-04 | 40
A31790 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-05 | 2026-05-10 | 2026-03-04 | 2026-03-05 | 1
A31800 | Manufacturing / Ex Works | 2026-06-13 | 2026-08-18 | 2026-03-05 | 2026-06-13 | 100
A31810 | Complete Manufacturing & ready for Final Inspection | 2026-06-23 | 2026-08-27 | 2026-06-15 | 2026-06-23 | 7
A31820 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-09-07 | 2026-06-24 | 2026-07-02 | 7
A34090 | Start Production |  |  | 2025-11-12 |  | 0
A34100 | Delivery of FDAS, LFCP, Clean Agent Unit | 2026-08-01 | 2026-10-07 | 2026-07-03 | 2026-08-01 | 30
PSVs |  | 2026-07-29 | 2026-10-07 | 2025-11-06 | 2026-07-29 | 177
PSVs (1"x2" upto 8"x10" - CS Rating 150/150, 300/150 = 22 Nos) |  | 2026-07-29 | 2026-10-07 | 2025-11-06 | 2026-07-29 | 177
A29600 | Key Vendor Drawings / Data Approved | 2026-01-01 | 2026-03-12 | 2025-11-07 | 2026-01-01 | 40
A29610 | Purchase Order for Major Sub-ordered Materials | 2026-01-15 | 2026-03-26 | 2026-01-01 | 2026-01-15 | 10
A29620 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-19 | 2026-04-30 | 2026-01-15 | 2026-02-19 | 25
A29630 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-19 | 2026-04-30 | 2026-02-19 | 2026-02-19 | 0
A29640 | Manufacturing / Ex Works (India/UAE) | 2026-05-05 | 2026-07-14 | 2026-02-19 | 2026-05-05 | 75
A29650 | Complete Manufacturing & ready for Final Inspection | 2026-05-19 | 2026-07-28 | 2026-05-05 | 2026-05-19 | 10
A29660 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-02 | 2026-08-11 | 2026-05-19 | 2026-06-02 | 10
A33530 | Start Production |  |  | 2025-11-06 |  | 0
A33540 | Delivery of Material in Warehouse for PSVs | 2026-07-29 | 2026-10-07 | 2026-06-02 | 2026-07-29 | 57
Sampling System |  |  |  | 26-Feb-25 A | 12-May-25 A | 0
TA_SGM Replacement (Additional Item) |  |  |  | 26-Feb-25 A | 12-May-25 A | 0
A37420 | Start Production |  |  | 17-Mar-25 A |  | 0
A37430 | Key Vendor Drawings / Data Approved |  |  | 26-Feb-25 A | 24-Mar-25 A | 0
A37440 | Purchase Order for Major Sub-ordered Materials |  |  | 25-Mar-25 A | 31-Mar-25 A | 0
A37450 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 01-Apr-25 A | 07-Apr-25 A | 0
A37460 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 08-Apr-25 A | 14-Apr-25 A | 0
A37470 | Manufacturing / Ex Works (India/UAE) |  |  | 15-Apr-25 A | 21-Apr-25 A | 0
A37480 | Complete Manufacturing & ready for Final Inspection |  |  | 22-Apr-25 A | 28-Apr-25 A | 0
A37490 | Materials Successfully Inspected, Tested / Ex Work |  |  | 29-Apr-25 A | 05-May-25 A | 0
A37500 | Delivery of Additional Material to be Procured |  |  | 06-May-25 A | 12-May-25 A | 0
F&G Flame Detectors, MCP, Beacon, etc. |  | 2026-09-02 | 2026-10-31 | 2025-12-16 | 2026-09-02 | 176
F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 2026-09-02 | 2026-10-31 | 2025-12-16 | 2026-09-02 | 176
A32120 | Key Vendor Drawings / Data Approved | 2026-02-24 | 2026-04-23 | 2025-12-16 | 2026-02-24 | 50
A32130 | Purchase Order for Major Sub-ordered Materials | 2026-03-10 | 2026-05-07 | 2026-02-24 | 2026-03-10 | 10
A32140 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-05 | 2026-07-02 | 2026-03-10 | 2026-05-05 | 40
A32150 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-06 | 2026-07-04 | 2026-05-05 | 2026-05-06 | 1
A32160 | Manufacturing / Ex Works (India/UAE) | 2026-07-20 | 2026-09-17 | 2026-05-06 | 2026-07-20 | 75
A32170 | Complete Manufacturing & ready for Final Inspection | 2026-07-29 | 2026-09-25 | 2026-07-20 | 2026-07-29 | 7
A32180 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-05 | 2026-10-02 | 2026-07-29 | 2026-08-05 | 5
A34170 | Start Production |  |  | 2025-12-16 |  | 0
A34180 | Delivery of F&G Detectors | 2026-09-02 | 2026-10-31 | 2026-08-05 | 2026-09-02 | 28
Main Electrical Equipment |  | 2026-09-25 | 2027-01-03 | 25-Feb-25 A | 2026-09-25 | 253
DG Set (750 KVA) 01 Nos |  | 2026-08-06 | 2026-11-03 | 22-Aug-25 A | 2026-08-06 | 218
DG Set |  | 2026-08-06 | 2026-11-03 | 22-Aug-25 A | 2026-08-06 | 218
A33200 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-02-20 | 01-Sep-25 A | 2025-11-27 | 50
A33210 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-03-06 | 2025-11-27 | 2025-12-11 | 10
A33220 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-22 | 2026-04-17 | 2025-12-11 | 2026-01-22 | 30
A33230 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-24 | 2026-04-21 | 2026-01-22 | 2026-01-24 | 2
A33240 | Manufacturing / Ex Works (India/UAE) | 2026-06-28 | 2026-09-23 | 2026-01-24 | 2026-06-28 | 155
A33250 | Complete Manufacturing & ready for Final Inspection | 2026-07-07 | 2026-10-02 | 2026-06-29 | 2026-07-07 | 7
A33260 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-16 | 2026-10-13 | 2026-07-08 | 2026-07-16 | 7
A34420 | Start Production |  |  | 22-Aug-25 A |  | 0
A34430 | Delivery of Material in Warehouse DG Set | 2026-08-06 | 2026-11-03 | 2026-07-17 | 2026-08-06 | 21
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) 03 Nos. |  | 2026-09-25 | 2027-01-03 | 25-Feb-25 A | 2026-09-25 | 202
TA_UPS Modification - Chloride Technology |  |  |  | 25-Feb-25 A | 03-May-25 A | 0
A37280 | Start Production |  |  | 25-Feb-25 A |  | 0
A37290 | Key Vendor Drawings / Data Approved |  |  | 27-Feb-25 A | 04-Mar-25 A | 0
A37300 | Purchase Order for Major Sub-ordered Materials |  |  | 06-Mar-25 A | 22-Mar-25 A | 0
A37310 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 23-Mar-25 A | 29-Mar-25 A | 0
A37320 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 30-Mar-25 A | 05-Apr-25 A | 0
A37330 | Manufacturing / Ex Works (India/UAE) |  |  | 06-Apr-25 A | 12-Apr-25 A | 0
A37340 | Complete Manufacturing & ready for Final Inspection |  |  | 13-Apr-25 A | 19-Apr-25 A | 0
A37350 | Materials Successfully Inspected, Tested / Ex Work |  |  | 20-Apr-25 A | 26-Apr-25 A | 0
A37360 | Delivery of Material for UPS Modification |  |  | 27-Apr-25 A | 03-May-25 A | 0
UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 2026-09-25 | 2027-01-03 | 2025-11-28 | 2026-09-25 | 202
A31670 | Key Vendor Drawings / Data Approved | 2026-02-20 | 2026-05-29 | 2025-12-01 | 2026-02-20 | 60
A31680 | Purchase Order for Major Sub-ordered Materials | 2026-03-06 | 2026-06-12 | 2026-02-20 | 2026-03-06 | 10
A31690 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-04-17 | 2026-07-24 | 2026-03-06 | 2026-04-17 | 30
A31700 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-04-19 | 2026-07-27 | 2026-04-17 | 2026-04-19 | 2
A31710 | Manufacturing / Ex Works (India/UAE) | 2026-08-17 | 2026-11-24 | 2026-04-19 | 2026-08-17 | 120
A31720 | Complete Manufacturing & ready for Final Inspection | 2026-08-26 | 2026-12-02 | 2026-08-17 | 2026-08-26 | 7
A31730 | Materials Successfully Inspected, Tested / Ex Work | 2026-09-04 | 2026-12-11 | 2026-08-26 | 2026-09-04 | 7
A34070 | Start Production |  |  | 2025-11-28 |  | 0
A34080 | Delivery of Material in Warehouse UPS | 2026-09-25 | 2027-01-03 | 2026-09-04 | 2026-09-25 | 21
Power Transformer (05 Nos) |  | 2026-07-02 | 2026-10-12 | 10-Sep-25 A | 2026-07-02 | 193
Power Transformers (Qty 05) |  | 2026-07-02 | 2026-10-12 | 10-Sep-25 A | 2026-07-02 | 193
A31850 | Key Vendor Drawings / Data Approved | 2025-12-11 | 2026-03-20 | 2025-09-19 | 2025-12-11 | 60
A31860 | Purchase Order for Major Sub-ordered Materials | 2025-12-25 | 2026-04-03 | 2025-12-11 | 2025-12-25 | 10
A31870 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-05 | 2026-05-15 | 2025-12-25 | 2026-02-05 | 30
A31880 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-06 | 2026-05-17 | 2026-02-05 | 2026-02-06 | 1
A31890 | Manufacturing / Ex Works (India/UAE) | 2026-05-17 | 2026-08-25 | 2026-02-06 | 2026-05-17 | 100
A31900 | Complete Manufacturing & ready for Final Inspection | 2026-05-26 | 2026-09-03 | 2026-05-18 | 2026-05-26 | 7
A31910 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-04 | 2026-09-14 | 2026-05-27 | 2026-06-04 | 7
A34110 | Start Production |  |  | 10-Sep-25 A |  | 0
A34120 | Delivery of Material in Warehouse Power Transformers | 2026-07-02 | 2026-10-12 | 2026-06-05 | 2026-07-02 | 28
Electrical Heat Tracing |  | 2026-05-04 | 2026-10-26 | 2026-01-16 | 2026-05-04 | 73
Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 2026-05-04 | 2026-10-26 | 2026-01-16 | 2026-05-04 | 73
A29060 | Key Vendor Drawings / Data Approved | 2026-02-27 | 2026-08-24 | 2026-01-19 | 2026-02-27 | 30
A29070 | Purchase Order for Major Sub-ordered Materials | 2026-03-04 | 2026-08-27 | 2026-02-27 | 2026-03-04 | 3
A29080 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-11 | 2026-09-03 | 2026-03-04 | 2026-03-11 | 5
A29090 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-12 | 2026-09-04 | 2026-03-11 | 2026-03-12 | 1
A29100 | Manufacturing / Ex Works (India/UAE) | 2026-04-06 | 2026-09-28 | 2026-03-12 | 2026-04-06 | 25
A29110 | Complete Manufacturing & ready for Final Inspection | 2026-04-09 | 2026-10-01 | 2026-04-06 | 2026-04-09 | 3
A29120 | Materials Successfully Inspected, Tested / Ex Work | 2026-04-20 | 2026-10-12 | 2026-04-09 | 2026-04-20 | 7
A33410 | Start Production |  |  | 2026-01-16 |  | 0
A33420 | Delivery of Material in Warehouse for Electrical Heat Tracing | 2026-05-04 | 2026-10-26 | 2026-04-20 | 2026-05-04 | 14
CP |  | 2026-08-06 | 2026-10-26 | 2026-02-25 | 2026-08-06 | 109
Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 2026-08-06 | 2026-10-26 | 2026-02-25 | 2026-08-06 | 109
A29240 | Key Vendor Drawings / Data Approved | 2026-04-08 | 2026-06-26 | 2026-02-25 | 2026-04-08 | 30
A29250 | Purchase Order for Major Sub-ordered Materials | 2026-04-15 | 2026-07-03 | 2026-04-08 | 2026-04-15 | 5
A29260 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-05-13 | 2026-07-31 | 2026-04-15 | 2026-05-13 | 20
A29270 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-05-14 | 2026-08-01 | 2026-05-13 | 2026-05-14 | 1
A29280 | Manufacturing / Ex Works | 2026-06-28 | 2026-09-15 | 2026-05-14 | 2026-06-28 | 45
A29290 | Complete Manufacturing & ready for Final Inspection | 2026-07-09 | 2026-09-28 | 2026-06-29 | 2026-07-09 | 9
A29300 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-23 | 2026-10-12 | 2026-07-10 | 2026-07-23 | 10
A33450 | Start Production |  |  | 2026-02-25 |  | 0
A33460 | Delivery of Material in Warehouse for Cathodic Protection | 2026-08-06 | 2026-10-26 | 2026-07-24 | 2026-08-06 | 14
LV & MV Switchgears |  | 2026-07-23 | 2026-10-18 | 12-Sep-25 A | 2026-07-23 | 208
Switchgear (MV & LV) |  | 2026-07-23 | 2026-10-18 | 12-Sep-25 A | 2026-07-23 | 208
A32480 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-02-20 | 2025-09-19 | 2025-11-27 | 50
A32490 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-03-06 | 2025-11-27 | 2025-12-11 | 10
A32500 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-29 | 2026-04-24 | 2025-12-11 | 2026-01-29 | 35
A32510 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-30 | 2026-04-26 | 2026-01-29 | 2026-01-30 | 1
A32520 | Manufacturing / Ex Works (India/UAE) | 2026-06-14 | 2026-09-08 | 2026-01-30 | 2026-06-14 | 135
A32530 | Complete Manufacturing & ready for Final Inspection | 2026-06-23 | 2026-09-16 | 2026-06-15 | 2026-06-23 | 7
A32540 | Materials Successfully Inspected, Tested / Ex Work | 2026-07-02 | 2026-09-25 | 2026-06-24 | 2026-07-02 | 7
A34260 | Start Production |  |  | 12-Sep-25 A |  | 0
A34270 | Delivery of Switchgear (MV & LV) | 2026-07-23 | 2026-10-18 | 2026-07-03 | 2026-07-23 | 21
Switch Gear Modification (Siemens) |  |  |  | 17-Mar-25 A | 12-May-25 A | 0
TA_Switchgear (MV Switchgear Modifications) - Siemens |  |  |  | 17-Mar-25 A | 12-May-25 A | 0
A22410 | Delivery of Material For Switchgear Modification |  |  | 06-May-25 A | 12-May-25 A | 0
A22450 | Start Production |  |  | 17-Mar-25 A |  | 0
A22460 | Key Vendor Drawings / Data Approved |  |  | 18-Mar-25 A | 24-Mar-25 A | 0
A22470 | Manufacturing / Ex Works (India/UAE) |  |  | 15-Apr-25 A | 21-Apr-25 A | 0
A22740 | Purchase Order for Major Sub-ordered Materials |  |  | 25-Mar-25 A | 31-Mar-25 A | 0
A22760 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 01-Apr-25 A | 07-Apr-25 A | 0
A22770 | Complete Manufacturing & ready for Final Inspection |  |  | 22-Apr-25 A | 28-Apr-25 A | 0
A22780 | Materials Successfully Inspected, Tested / Ex Work |  |  | 29-Apr-25 A | 05-May-25 A | 0
A24280 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 08-Apr-25 A | 14-Apr-25 A | 0
MV & LV VFD's |  | 2026-02-18 | 2026-10-19 | 13-Aug-25 A | 2026-02-18 | 20
Variable Fequency Drives (VFDs) LV Qty = 03 |  | 2026-02-18 | 2026-10-19 | 13-Aug-25 A | 2026-02-18 | 20
A32570 | Key Vendor Drawings / Data Approved |  |  | 13-Aug-25 A | 14-Aug-25 A | 0
A32580 | Purchase Order for Major Sub-ordered Materials |  |  | 15-Aug-25 A | 16-Aug-25 A | 0
A32590 | Major Sub-ordered Materials Received by Vendor and Verified |  |  | 17-Aug-25 A | 18-Aug-25 A | 0
A32600 | Start Manufacturing / Pre-Inspection Meeting (PIM) |  |  | 19-Aug-25 A | 19-Aug-25 A | 0
A32610 | Manufacturing / Ex Works (India/UAE) |  |  | 20-Aug-25 A | 20-Aug-25 A | 0
A32620 | Complete Manufacturing & ready for Final Inspection |  |  | 20-Aug-25 A | 21-Aug-25 A | 0
A32630 | Materials Successfully Inspected, Tested / Ex Work |  |  | 22-Aug-25 A | 22-Aug-25 A | 0
A34280 | Start Production |  |  | 13-Aug-25 A |  | 0
A34290 | Delivery of VFDs | 2026-02-18 | 2026-10-19 | 2026-01-21 | 2026-02-18 | 28
HV Capacitor Bay |  | 2026-06-08 | 2026-11-16 | 2025-10-22 | 2026-06-08 | 152
HV Capacitor Bay |  | 2026-06-08 | 2026-11-16 | 2025-10-22 | 2026-06-08 | 152
A32030 | Key Vendor Drawings / Data Approved | 2025-12-31 | 2026-06-10 | 2025-10-22 | 2025-12-31 | 50
A32040 | Purchase Order for Major Sub-ordered Materials | 2026-01-14 | 2026-06-24 | 2025-12-31 | 2026-01-14 | 10
A32050 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-02-25 | 2026-08-05 | 2026-01-14 | 2026-02-25 | 30
A32060 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-02-26 | 2026-08-06 | 2026-02-25 | 2026-02-26 | 1
A32070 | Manufacturing / Ex Works (India/UAE) | 2026-05-12 | 2026-10-20 | 2026-02-26 | 2026-05-12 | 75
A32080 | Complete Manufacturing & ready for Final Inspection | 2026-05-21 | 2026-10-29 | 2026-05-12 | 2026-05-21 | 7
A32090 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-01 | 2026-11-09 | 2026-05-21 | 2026-06-01 | 7
A34150 | Start Production |  |  | 2025-10-22 |  | 0
A34160 | Delivery of Material in Warehouse HV Capacitor Bay | 2026-06-08 | 2026-11-16 | 2026-06-01 | 2026-06-08 | 7
Power Distribution Panel and LCS, Battery & Safety Switch, Resister Bank |  | 2026-07-09 | 2026-11-13 | 06-Jun-25 A | 2026-07-09 | 198
NGR Panel Qty 02 |  | 2026-07-09 | 2026-11-13 | 06-Jun-25 A | 2026-07-09 | 198
A33020 | Key Vendor Drawings / Data Approved | 2025-11-27 | 2026-04-03 | 2025-09-19 | 2025-11-27 | 50
A33030 | Purchase Order for Major Sub-ordered Materials | 2025-12-11 | 2026-04-17 | 2025-11-27 | 2025-12-11 | 10
A33040 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-01-22 | 2026-05-29 | 2025-12-11 | 2026-01-22 | 30
A33050 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-01-23 | 2026-05-31 | 2026-01-22 | 2026-01-23 | 1
A33060 | Manufacturing / Ex Works (India/UAE) | 2026-05-23 | 2026-09-28 | 2026-01-23 | 2026-05-23 | 120
A33070 | Complete Manufacturing & ready for Final Inspection | 2026-06-02 | 2026-10-07 | 2026-05-25 | 2026-06-02 | 7
A33080 | Materials Successfully Inspected, Tested / Ex Work | 2026-06-11 | 2026-10-16 | 2026-06-03 | 2026-06-11 | 7
A34380 | Start Production |  |  | 06-Jun-25 A |  | 0
A34390 | Delivery of NGR Panel | 2026-07-09 | 2026-11-13 | 2026-06-12 | 2026-07-09 | 28
Interposing Relay Panel (IRP) |  | 2026-09-10 | 2026-11-22 | 2025-11-28 | 2026-09-10 | 191
Interposing Relay Panel |  | 2026-09-10 | 2026-11-22 | 2025-11-28 | 2026-09-10 | 191
A33110 | Key Vendor Drawings / Data Approved | 2026-01-09 | 2026-03-25 | 2025-11-28 | 2026-01-09 | 30
A33120 | Purchase Order for Major Sub-ordered Materials | 2026-01-23 | 2026-04-08 | 2026-01-09 | 2026-01-23 | 10
A33130 | Major Sub-ordered Materials Received by Vendor and Verified | 2026-03-20 | 2026-06-03 | 2026-01-23 | 2026-03-20 | 40
A33140 | Start Manufacturing / Pre-Inspection Meeting (PIM) | 2026-03-23 | 2026-06-06 | 2026-03-20 | 2026-03-23 | 3
A33150 | Manufacturing / Ex Works (India/UAE) | 2026-08-05 | 2026-10-19 | 2026-03-23 | 2026-08-05 | 135
A33160 | Complete Manufacturing & ready for Final Inspection | 2026-08-14 | 2026-10-28 | 2026-08-05 | 2026-08-14 | 7
A33170 | Materials Successfully Inspected, Tested / Ex Work | 2026-08-25 | 2026-11-06 | 2026-08-14 | 2026-08-25 | 7
A34400 | Start Production |  |  | 2025-11-28 |  | 0
A34410 | Delivery of Interposing relay Panel | 2026-09-10 | 2026-11-22 | 2026-08-25 | 2026-09-10 | 16
Construction and Pre-Commissioning |  | 2027-03-24 | 2027-07-20 | 09-Jan-25 A | 2027-03-24 | 377
Construction/Pre-Commissioning |  | 2026-12-06 | 2027-01-03 | 10-Jun-25 A | 2026-12-06 | 299
Green Field Works |  | 2026-12-06 | 2027-01-03 | 10-Jun-25 A | 2026-12-06 | 299
General / Common |  | 2025-11-16 | 2026-08-22 | 10-Jun-25 A | 2025-11-16 | 50
A3250 | Complete Site Preparation and Grading works |  |  |  | 16-Jun-25 A | 0
CONS | TSF Construction / Commence on SITE | 2025-11-16 | 2026-08-22 | 01-Jul-25 A | 2025-11-16 | 50
CONS10 | Installation of Isolation Fence Plant Site |  |  | 10-Jun-25 A | 13-Aug-25 A | 0
Electrical & Instrumentation Works |  | 2026-12-06 | 2027-01-03 | 2026-03-30 | 2026-12-06 | 171
A18510 | Cable Laying - Trenches | 2026-06-13 | 2026-08-06 | 2026-03-30 | 2026-06-13 | 64
A3709 | E&I Bulk & Equipment Deliveries - Plant Site | 2026-09-18 | 2026-10-26 |  | 2026-09-18 | 0
A3719 | E&I Works (CCB & SIS) For cable trays and cable laying | 2026-10-25 | 2027-01-03 | 2026-07-29 | 2026-10-25 | 75
A3739 | Complete E&I Equipment / Panels Installation CCB &SIS | 2026-09-26 | 2027-01-03 |  | 2026-09-26 | 0
A3749 | Complete Cable termination and loop test - Overall | 2026-12-06 | 2027-01-03 |  | 2026-12-06 | 0
A3759 | Complete E&I Work at plant site | 2026-11-08 | 2026-12-20 |  | 2026-11-08 | 0
A3889 | Electrical Works Plant Site (Cable trays, cable laying, termination, DBs, Jbs etc) | 2026-11-02 | 2026-12-10 | 2026-08-19 | 2026-11-02 | 64
A3909 | Instrumentation Works Plant Site (Control/Manual Valves, Gauges, TT, PT, DPT, PSVs, Switches etc) | 2026-11-08 | 2026-12-20 | 2026-09-19 | 2026-11-08 | 44
Accommodation and Messing |  | 2025-09-23 | 2026-07-08 | 15-Apr-25 A | 2025-09-23 | 4
Mobilisation of Camp (Accommodation and Messing) |  | 2025-09-23 | 2026-07-08 | 15-Apr-25 A | 2025-09-23 | 4
A61550 | TA - Mobilisation of Camp (Accommodation and messing) |  |  | 15-Apr-25 A | 20-Apr-25 A | 0
A62210 | Main Scope - Mobilisation of Camp (Accommodation and messing) | 2025-09-23 | 2026-07-08 | 01-Aug-25 A | 2025-09-23 | 4
Fabrication, Storage, Workshops (Temporary Facilities) |  | 2027-03-24 | 2027-07-20 | 01-Apr-25 A | 2027-03-24 | 469
Mobilisation of Temporary Facilities |  | 2025-10-21 | 2026-08-05 | 01-Apr-25 A | 2025-10-21 | 24
A61560 | Mobilisation of Temporary Facilities - TA |  |  | 01-Apr-25 A | 31-May-25 A | 0
A62230 | Mobilisation of Temporary Facilities - Main Scope | 2025-10-21 | 2026-08-05 | 2025-09-24 | 2025-10-21 | 24
Maintenance of Temporary Facilities |  | 2026-04-07 | 2027-01-20 | 2025-10-22 | 2026-04-07 | 144
A61570 | Maintenance of Temporary Facilities - Q2 | 2025-12-16 | 2026-09-30 | 2025-11-19 | 2025-12-16 | 24
A62240 | Maintenance of Temporary Facilities - Q1 | 2025-11-18 | 2026-09-02 | 2025-10-22 | 2025-11-18 | 24
A62250 | Maintenance of Temporary Facilities - Q3 | 2026-01-13 | 2026-10-28 | 2025-12-17 | 2026-01-13 | 24
A62260 | Maintenance of Temporary Facilities - Q4 | 2026-02-10 | 2026-11-25 | 2026-01-14 | 2026-02-10 | 24
A62270 | Maintenance of Temporary Facilities - Q5 | 2026-03-10 | 2026-12-23 | 2026-02-11 | 2026-03-10 | 24
A62280 | Maintenance of Temporary Facilities - Q6 | 2026-04-07 | 2027-01-20 | 2026-03-11 | 2026-04-07 | 24
Demobilisation of Temporary Facilities |  | 2027-03-24 | 2027-07-20 | 25-Jun-25 A | 2027-03-24 | 24
A61580 | Demobiisation of Temporary Facilities - TA |  |  | 25-Jun-25 A | 11-Jul-25 A | 0
A62290 | Demobiisation of Temporary Facilities - Main Scope | 2027-03-24 | 2027-07-20 | 2027-02-24 | 2027-03-24 | 24
Civil Construction |  | 2026-12-20 | 2027-01-20 | 09-Jan-25 A | 2026-12-20 | 392
Site Preparation |  |  |  | 01-Apr-25 A | 15-Sep-25 A | 0
A61590 | Site Preparation - TA |  |  | 01-Apr-25 A | 15-Apr-25 A | 0
A62220 | Site Preparation - Main Scope |  |  | 22-Aug-25 A | 15-Sep-25 A | 0
Fencing |  |  |  | 17-Apr-25 A | 22-Aug-25 A | 0
A61600 | Fencing |  |  | 17-Apr-25 A | 22-Aug-25 A | 0
Excavation and trenching |  | 2026-07-15 | 2026-10-04 | 2025-11-18 | 2026-07-15 | 205
GF Sumps and Pits |  | 2026-04-18 | 2026-07-28 | 2025-11-23 | 2026-04-18 | 125
Accidentally Oily Water Sump 70-TD-1407 |  | 2026-04-02 | 2026-07-28 | 2025-12-06 | 2026-04-02 | 101
A26600 | Excavation | 2026-01-03 | 2026-04-14 | 2025-12-06 | 2026-01-03 | 24
A26610 | Surface leveling and compaction | 2026-01-05 | 2026-05-02 | 2026-01-03 | 2026-01-05 | 2
A26620 | Lean concrete | 2026-01-07 | 2026-05-04 | 2026-01-05 | 2026-01-07 | 2
A26630 | Water proofing and bitumen coating/sheet | 2026-01-19 | 2026-05-16 | 2026-01-14 | 2026-01-19 | 4
A26640 | Formworks | 2026-02-23 | 2026-06-20 | 2026-01-19 | 2026-02-23 | 30
A26650 | Rebar works | 2026-02-23 | 2026-06-20 | 2026-01-19 | 2026-02-23 | 30
A26660 | Concrete pouring | 2026-02-25 | 2026-06-22 | 2026-02-02 | 2026-02-25 | 20
A26670 | Concrete Curing | 2026-03-04 | 2026-06-29 | 2026-02-03 | 2026-03-04 | 25
A26680 | Formwork removal | 2026-03-01 | 2026-06-25 | 2026-02-05 | 2026-03-01 | 20
A26690 | Protective Coating | 2026-03-15 | 2026-07-09 | 2026-03-01 | 2026-03-15 | 12
A26700 | Back filling and compaction in layers | 2026-04-02 | 2026-07-28 | 2026-03-15 | 2026-04-02 | 16
Oil Contaminated Water Sump 70-TD-1408 |  | 2026-04-18 | 2026-07-28 | 2025-12-22 | 2026-04-18 | 100
A26710 | Excavation | 2026-01-19 | 2026-04-30 | 2025-12-22 | 2026-01-19 | 24
A26720 | Surface leveling and compaction | 2026-01-21 | 2026-05-03 | 2026-01-19 | 2026-01-21 | 2
A26730 | Lean concrete | 2026-01-24 | 2026-05-05 | 2026-01-21 | 2026-01-24 | 2
A26740 | Water proofing and bitumen coating/sheet | 2026-02-04 | 2026-05-17 | 2026-01-31 | 2026-02-04 | 4
A26750 | Formworks | 2026-03-11 | 2026-06-21 | 2026-02-04 | 2026-03-11 | 30
A26760 | Rebar works | 2026-03-11 | 2026-06-21 | 2026-02-04 | 2026-03-11 | 30
A26770 | Concrete pouring | 2026-03-14 | 2026-06-23 | 2026-02-18 | 2026-03-14 | 20
A26780 | Concrete Curing | 2026-03-21 | 2026-06-30 | 2026-02-19 | 2026-03-21 | 25
A26790 | Formwork removal | 2026-03-17 | 2026-06-27 | 2026-02-22 | 2026-03-17 | 20
A26800 | Protective Coating | 2026-03-31 | 2026-07-11 | 2026-03-17 | 2026-03-31 | 12
A26810 | Back filling and compaction in layers | 2026-04-18 | 2026-07-28 | 2026-03-31 | 2026-04-18 | 15
Sanitary Waste Water Sump 70-TD-1409 |  | 2026-03-05 | 2026-07-28 | 2025-12-27 | 2026-03-05 | 59
A26820 | Excavation | 2026-01-04 | 2026-05-28 | 2025-12-27 | 2026-01-04 | 7
A26830 | Surface leveling and compaction | 2026-01-06 | 2026-05-31 | 2026-01-04 | 2026-01-06 | 2
A26840 | Lean concrete | 2026-01-08 | 2026-06-02 | 2026-01-06 | 2026-01-08 | 2
A26850 | Water proofing and bitumen coating/sheet | 2026-01-20 | 2026-06-14 | 2026-01-15 | 2026-01-20 | 4
A26860 | Formworks | 2026-02-05 | 2026-06-30 | 2026-01-20 | 2026-02-05 | 14
A26870 | Rebar works | 2026-02-05 | 2026-06-30 | 2026-01-20 | 2026-02-05 | 14
A26880 | Concrete pouring | 2026-02-08 | 2026-07-02 | 2026-01-27 | 2026-02-08 | 10
A26890 | Concrete Curing | 2026-02-14 | 2026-07-08 | 2026-01-28 | 2026-02-14 | 14
A26900 | Formwork removal | 2026-02-11 | 2026-07-06 | 2026-01-31 | 2026-02-11 | 10
A26910 | Protective Coating | 2026-02-23 | 2026-07-18 | 2026-02-11 | 2026-02-23 | 10
A26920 | Back filling and compaction in layers | 2026-03-05 | 2026-07-28 | 2026-02-23 | 2026-03-05 | 9
PSA2 Slope Drum Pit |  | 2026-04-09 | 2026-07-28 | 2025-12-14 | 2026-04-09 | 100
A26930 | Excavation | 2026-01-11 | 2026-04-22 | 2025-12-14 | 2026-01-11 | 24
A26940 | Surface leveling and compaction | 2026-01-13 | 2026-05-03 | 2026-01-11 | 2026-01-13 | 2
A26950 | Lean concrete | 2026-01-15 | 2026-05-05 | 2026-01-13 | 2026-01-15 | 2
A26960 | Water proofing and bitumen coating/sheet | 2026-01-27 | 2026-05-17 | 2026-01-22 | 2026-01-27 | 4
A26970 | Formworks | 2026-03-03 | 2026-06-21 | 2026-01-27 | 2026-03-03 | 30
A26980 | Rebar works | 2026-03-03 | 2026-06-21 | 2026-01-27 | 2026-03-03 | 30
A26990 | Concrete pouring | 2026-03-05 | 2026-06-23 | 2026-02-10 | 2026-03-05 | 20
A27000 | Concrete Curing | 2026-03-12 | 2026-06-30 | 2026-02-11 | 2026-03-12 | 25
A27010 | Formwork removal | 2026-03-09 | 2026-06-27 | 2026-02-14 | 2026-03-09 | 20
A27020 | Protective Coating | 2026-03-23 | 2026-07-11 | 2026-03-09 | 2026-03-23 | 12
A27030 | Back filling and compaction in layers | 2026-04-09 | 2026-07-28 | 2026-03-23 | 2026-04-09 | 15
Cooling Water Valve Pit |  | 2026-03-21 | 2026-07-28 | 2025-11-23 | 2026-03-21 | 101
A27040 | Excavation | 2025-12-21 | 2026-04-29 | 2025-11-23 | 2025-12-21 | 24
A27050 | Surface leveling and compaction | 2025-12-23 | 2026-05-02 | 2025-12-21 | 2025-12-23 | 2
A27060 | Lean concrete | 2025-12-25 | 2026-05-04 | 2025-12-23 | 2025-12-25 | 2
A27070 | Water proofing and bitumen coating/sheet | 2026-01-06 | 2026-05-16 | 2026-01-01 | 2026-01-06 | 4
A27080 | Formworks | 2026-02-10 | 2026-06-20 | 2026-01-06 | 2026-02-10 | 30
A27090 | Rebar works | 2026-02-10 | 2026-06-20 | 2026-01-06 | 2026-02-10 | 30
A27100 | Concrete pouring | 2026-02-12 | 2026-06-22 | 2026-01-20 | 2026-02-12 | 20
A27110 | Concrete Curing | 2026-02-19 | 2026-06-29 | 2026-01-21 | 2026-02-19 | 25
A27120 | Formwork removal | 2026-02-16 | 2026-06-25 | 2026-01-24 | 2026-02-16 | 20
A27130 | Protective Coating | 2026-03-02 | 2026-07-09 | 2026-02-16 | 2026-03-02 | 12
A27140 | Back filling and compaction in layers | 2026-03-21 | 2026-07-28 | 2026-03-02 | 2026-03-21 | 16
GF UG Piping and Trenches |  | 2026-07-15 | 2026-09-08 | 2025-11-18 | 2026-07-15 | 205
Piping |  | 2026-03-07 | 2026-07-28 | 2025-11-18 | 2026-03-07 | 93
A18530 | Excavation and Valve Pits for Fire Water Line | 2026-01-26 | 2026-05-07 | 2025-11-18 | 2026-01-26 | 59
A3440 | Trenching for UG Piping | 2025-12-28 | 2026-05-20 | 2025-11-26 | 2025-12-28 | 27
A3450 | Complete UG Piping & Backfilling | 2026-03-07 | 2026-07-28 | 2025-12-28 | 2026-03-07 | 59
Cables |  | 2026-07-15 | 2026-09-08 | 2026-01-05 | 2026-07-15 | 164
A18460 | Direct Buried Trenches for Power and Instrumentation cables | 2026-02-03 | 2026-05-24 | 2026-01-05 | 2026-02-03 | 26
A18480 | Backfilling of E&I trenches | 2026-07-15 | 2026-09-08 | 2026-06-13 | 2026-07-15 | 28
A3460 | Concrete Trenches for Electrical and Instrumentation Cable | 2026-03-30 | 2026-05-24 | 2026-01-20 | 2026-03-30 | 59
BF Trenches |  | 2026-06-27 | 2026-10-04 | 2026-01-28 | 2026-06-27 | 128
A21770 | Direct buried trenches - BF | 2026-06-27 | 2026-10-04 | 2026-04-08 | 2026-06-27 | 68
A21800 | Duct Banks/Road Crossing | 2026-04-08 | 2026-07-18 | 2026-01-28 | 2026-04-08 | 60
Foundations |  | 2026-12-20 | 2027-01-20 | 03-Jul-25 A | 2026-12-20 | 392
GF SIS Building Structure Works |  | 2026-04-14 | 2026-06-18 | 2025-10-25 | 2026-04-14 | 148
Sub-Structure |  | 2026-02-19 | 2026-04-26 | 2025-10-25 | 2026-02-19 | 102
A1590 | Foundation Works (Excavation, PCC & RCC) | 2025-11-27 | 2026-02-01 | 2025-10-25 | 2025-11-27 | 30
A1600 | RCC Columns and Walls Upto FFL | 2026-01-01 | 2026-03-08 | 2025-11-08 | 2026-01-01 | 48
A1610 | Waterproofing & Backfilling | 2026-02-02 | 2026-04-08 | 2026-01-03 | 2026-02-02 | 27
A1620 | Plinth Beams | 2026-02-19 | 2026-04-26 | 2026-02-03 | 2026-02-19 | 15
Super-Structure |  | 2026-04-14 | 2026-06-18 | 2026-02-21 | 2026-04-14 | 46
A1500 | RCC Columns and Walls Upto First Slab | 2026-03-26 | 2026-05-31 | 2026-02-21 | 2026-03-26 | 30
A1510 | First Slab and Beams | 2026-04-14 | 2026-06-18 | 2026-03-11 | 2026-04-14 | 30
GF Sub-Station Sub-Structure |  | 2026-12-20 | 2027-01-20 | 25-Aug-25 A | 2026-12-20 | 392
A1030 | Plinth Beams (Casting Suti) | 2026-01-14 | 2026-08-16 | 2025-12-18 | 2026-01-14 | 24
A26360 | Foundation Works (Excavation, PCC & RCC) | 2025-10-12 | 2026-01-11 | 25-Aug-25 A | 2025-10-12 | 20
A26370 | RCC Base & Columns Upto FFL | 2025-11-04 | 2026-02-22 | 2025-10-13 | 2025-11-04 | 20
A26380 | Waterproofing & Backfilling (handingover to Precast) | 2025-11-12 | 2026-03-02 | 2025-10-21 | 2025-11-12 | 20
GF Sub-Station Super-Structure |  | 2026-12-20 | 2027-01-20 | 2025-11-13 | 2026-12-20 | 345
Ground Floor - Cellar Area |  | 2026-01-04 | 2026-04-23 | 2025-11-13 | 2026-01-04 | 45
A26390 | RCC Columns and Walls Upto First Slab | 2025-12-17 | 2026-04-06 | 2025-11-13 | 2025-12-17 | 30
A26400 | First Slab and Beams | 2026-01-04 | 2026-04-23 | 2025-12-01 | 2026-01-04 | 30
First Floor |  | 2026-12-20 | 2027-01-20 | 2025-12-20 | 2026-12-20 | 314
A26410 | RCC Columns Upto 2nd Slab | 2026-01-19 | 2026-07-19 | 2025-12-20 | 2026-01-19 | 27
A26420 | 2nd Slab and Beams | 2026-02-16 | 2026-08-16 | 2026-01-04 | 2026-02-16 | 38
C1059 | Punch List Close Out (Construction / Mechanical) | 2026-12-20 | 2027-01-20 | 2026-12-06 | 2026-12-20 | 12
GF Transformers Structure Works |  | 2026-05-19 | 2026-08-27 | 2025-11-29 | 2026-05-19 | 148
Sub-Structure |  | 2026-02-17 | 2026-07-23 | 2025-11-29 | 2026-02-17 | 70
A1150 | RCC Walls Upto FFL | 2026-02-03 | 2026-07-09 | 2025-12-31 | 2026-02-03 | 30
A26460 | Foundation Works (Excavation, PCC & RCC) | 2026-01-20 | 2026-06-25 | 2025-11-29 | 2026-01-20 | 46
A26470 | Waterproofing & Backfilling | 2026-02-17 | 2026-07-23 | 2026-01-14 | 2026-02-17 | 30
Super-Structure |  | 2026-05-19 | 2026-08-27 | 2026-04-15 | 2026-05-19 | 30
A1190 | RCC Walls above Ground | 2026-05-19 | 2026-08-27 | 2026-04-15 | 2026-05-19 | 30
Roads and Pavement Construction |  | 2026-11-26 | 2027-01-20 | 2026-06-03 | 2026-11-26 | 151
A6860 | Subgarde and Sub-Base for Road | 2026-08-02 | 2026-09-26 | 2026-06-03 | 2026-08-02 | 51
A6870 | Base Course and Asphalt working | 2026-11-26 | 2027-01-20 | 2026-09-28 | 2026-11-26 | 51
A6880 | Concrete Flooring on Plant Side | 2026-09-28 | 2026-11-22 | 2026-08-02 | 2026-09-28 | 49
BF Foundation |  | 2026-03-01 | 2026-11-04 | 2025-10-13 | 2026-03-01 | 120
BFW3000 | General Civil Work - Equipment Foundations & Pipe Support (TBC) | 2026-03-01 | 2026-11-04 | 2025-10-13 | 2026-03-01 | 120 | 0.3294%
GF Foundations |  | 2026-05-05 | 2026-08-22 | 03-Jul-25 A | 2026-05-05 | 195
FG/OG Compressor and Shleter Foundation including shelter concrete trench |  | 2025-12-31 | 2026-03-15 | 19-Sep-25 A | 2025-12-31 | 89
A15660 | Excavation | 2025-10-09 | 2025-12-22 | 19-Sep-25 A | 2025-10-09 | 18 | 0.1647%
A15670 | Surface leveling and compaction | 2025-10-16 | 2025-12-29 | 2025-09-27 | 2025-10-16 | 18
A15740 | Lean concrete | 2025-10-23 | 2026-01-05 | 2025-10-04 | 2025-10-23 | 18
A15750 | Water proofing and bitumen coating/sheet | 2025-10-30 | 2026-01-12 | 2025-10-11 | 2025-10-30 | 18
A15790 | Formworks | 2025-11-27 | 2026-02-09 | 2025-10-18 | 2025-11-27 | 36
A15840 | Rebar works | 2025-11-27 | 2026-02-09 | 2025-10-18 | 2025-11-27 | 36
A15850 | Concrete pouring | 2025-12-04 | 2026-02-16 | 2025-10-25 | 2025-12-04 | 36
A15860 | Concrete Curing | 2025-12-11 | 2026-02-23 | 2025-10-25 | 2025-12-11 | 42
A15870 | Formwork removal | 2025-12-11 | 2026-02-23 | 2025-11-01 | 2025-12-11 | 36
A15880 | Protective Coating | 2025-12-25 | 2026-03-09 | 2025-11-08 | 2025-12-25 | 42
A15890 | Back filling and compaction in layers | 2025-12-31 | 2026-03-15 | 2025-11-15 | 2025-12-31 | 41
Pipe Rack (Primary SR81 & Secondary SR80) Foundation |  | 2026-03-05 | 2026-04-29 | 2025-11-11 | 2026-03-05 | 98
A26240 | Excavation - Pipe Rack (SR81 & SR80) | 2025-12-09 | 2026-02-02 | 2025-11-11 | 2025-12-09 | 24
A26250 | Surface leveling and compaction | 2025-12-16 | 2026-02-09 | 2025-11-18 | 2025-12-16 | 24
A26260 | Lean concrete | 2025-12-23 | 2026-02-16 | 2025-11-25 | 2025-12-23 | 24
A26270 | Water proofing and bitumen coating/sheet | 2025-12-30 | 2026-02-23 | 2025-12-02 | 2025-12-30 | 24
A26280 | Formworks | 2026-02-03 | 2026-03-30 | 2025-12-09 | 2026-02-03 | 48
A26290 | Rebar works | 2026-02-03 | 2026-03-30 | 2025-12-09 | 2026-02-03 | 48
A26300 | Concrete Pouring | 2026-02-10 | 2026-04-06 | 2025-12-16 | 2026-02-10 | 48
A26310 | Concrete Curing | 2026-02-18 | 2026-04-14 | 2025-12-17 | 2026-02-18 | 54
A26320 | Formwork removal | 2026-02-14 | 2026-04-09 | 2025-12-20 | 2026-02-14 | 48
A26330 | Protective Coating | 2026-02-28 | 2026-04-23 | 2025-12-27 | 2026-02-28 | 54
A26340 | Back filling and compaction in layers | 2026-03-05 | 2026-04-29 | 2026-01-03 | 2026-03-05 | 53
OG Compressor Discharge Drip Leg (13-SP-7004) |  | 2026-04-25 | 2026-08-16 | 2026-02-17 | 2026-04-25 | 57
A24810 | Excavation | 2026-02-22 | 2026-06-10 | 2026-02-17 | 2026-02-22 | 4
A24820 | Surface leveling and compaction | 2026-02-26 | 2026-06-20 | 2026-02-22 | 2026-02-26 | 4
A24830 | Lean concrete | 2026-03-03 | 2026-06-24 | 2026-02-26 | 2026-03-03 | 4
A24840 | Water proofing and bitumen coating/sheet | 2026-03-12 | 2026-07-04 | 2026-03-03 | 2026-03-12 | 8
A24850 | Formworks | 2026-03-30 | 2026-07-21 | 2026-03-12 | 2026-03-30 | 15
A24860 | Rebar works | 2026-03-30 | 2026-07-21 | 2026-03-12 | 2026-03-30 | 15
A24870 | Concrete pouring | 2026-04-04 | 2026-07-26 | 2026-03-30 | 2026-04-04 | 4
A24880 | Concrete Curing | 2026-04-13 | 2026-08-04 | 2026-03-30 | 2026-04-13 | 12
A24890 | Formwork removal | 2026-04-06 | 2026-07-28 | 2026-04-01 | 2026-04-06 | 4
A24900 | Protective Coating | 2026-04-15 | 2026-08-06 | 2026-04-06 | 2026-04-15 | 8
A24910 | Back filling and compaction in layers | 2026-04-25 | 2026-08-16 | 2026-04-15 | 2026-04-25 | 8
PSA2 Package by Linde ( 10 Vessels) |  | 2025-12-18 | 2026-04-15 | 03-Jul-25 A | 2025-12-18 | 73
A24920 | Excavation |  |  | 03-Jul-25 A | 10-Jul-25 A | 0
A24930 | Surface leveling and compaction |  |  | 11-Jul-25 A | 15-Jul-25 A | 0
A24940 | Lean concrete |  |  | 16-Jul-25 A | 18-Sep-25 A | 0
A24950 | Water proofing and bitumen coating/sheet | 2025-10-01 | 2026-01-27 | 2025-09-25 | 2025-10-01 | 6
A24960 | Formworks | 2025-11-05 | 2026-03-03 | 2025-10-09 | 2025-11-05 | 24
A24970 | Rebar works | 2025-10-29 | 2026-02-24 | 2025-10-02 | 2025-10-29 | 24
A24980 | Concrete pouring | 2025-11-08 | 2026-03-05 | 2025-11-06 | 2025-11-08 | 2
A24990 | Concrete Curing | 2025-11-15 | 2026-03-12 | 2025-11-09 | 2025-11-15 | 6
A25000 | Formwork removal | 2025-11-22 | 2026-03-19 | 2025-11-11 | 2025-11-22 | 10
A25010 | Protective Coating | 2025-12-01 | 2026-03-29 | 2025-11-18 | 2025-12-01 | 12
A25020 | Back filling and compaction in layers | 2025-12-18 | 2026-04-15 | 2025-11-25 | 2025-12-18 | 21
OG Comp After Cooler ( 13-HE-709) |  | 2026-04-04 | 2026-08-08 | 2026-02-17 | 2026-04-04 | 39
A25030 | Excavation | 2026-02-21 | 2026-06-27 | 2026-02-17 | 2026-02-21 | 3
A25040 | Surface leveling and compaction | 2026-02-23 | 2026-06-29 | 2026-02-21 | 2026-02-23 | 2
A25050 | Lean concrete | 2026-02-25 | 2026-07-01 | 2026-02-23 | 2026-02-25 | 2
A25060 | Water proofing and bitumen coating/sheet | 2026-03-07 | 2026-07-11 | 2026-03-04 | 2026-03-07 | 2
A25070 | Formworks | 2026-03-21 | 2026-07-25 | 2026-03-07 | 2026-03-21 | 12
A25080 | Rebar works | 2026-03-21 | 2026-07-26 | 2026-03-07 | 2026-03-21 | 12
A25090 | Concrete pouring | 2026-03-29 | 2026-08-02 | 2026-03-15 | 2026-03-29 | 12
A25100 | Concrete Curing | 2026-04-01 | 2026-08-05 | 2026-03-16 | 2026-04-01 | 14
A25110 | Formwork removal | 2026-04-01 | 2026-08-05 | 2026-03-18 | 2026-04-01 | 12
A25120 | Protective Coating | 2026-03-28 | 2026-08-01 | 2026-03-23 | 2026-03-28 | 4
A25130 | Back filling and compaction in layers | 2026-04-04 | 2026-08-08 | 2026-03-28 | 2026-04-04 | 6
FG Comp 2nd Stage Discharge Drum(13-VV-707) |  | 2026-03-16 | 2026-07-23 | 2026-01-03 | 2026-03-16 | 62
A25140 | Excavation | 2026-01-06 | 2026-05-16 | 2026-01-03 | 2026-01-06 | 3
A25150 | Surface leveling and compaction | 2026-01-08 | 2026-05-18 | 2026-01-06 | 2026-01-08 | 2
A25160 | Lean concrete | 2026-01-10 | 2026-05-19 | 2026-01-08 | 2026-01-10 | 1
A25170 | Water proofing and bitumen coating/sheet | 2026-01-21 | 2026-05-31 | 2026-01-17 | 2026-01-21 | 4
A25180 | Formworks | 2026-02-08 | 2026-06-17 | 2026-01-21 | 2026-02-08 | 15
A25190 | Rebar works | 2026-02-08 | 2026-06-17 | 2026-01-21 | 2026-02-08 | 15
A25200 | Concrete pouring | 2026-02-19 | 2026-06-30 | 2026-02-04 | 2026-02-19 | 13
A25210 | Concrete Curing | 2026-02-26 | 2026-07-06 | 2026-02-05 | 2026-02-26 | 18
A25220 | Formwork removal | 2026-02-23 | 2026-07-04 | 2026-02-08 | 2026-02-23 | 14
A25230 | Protective Coating | 2026-03-02 | 2026-07-11 | 2026-02-24 | 2026-03-02 | 6
A25240 | Back filling and compaction in layers | 2026-03-16 | 2026-07-23 | 2026-03-03 | 2026-03-16 | 11
FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-02-19 | 2026-08-01 | 2025-12-20 | 2026-02-19 | 53
A25360 | Excavation | 2025-12-23 | 2026-05-02 | 2025-12-20 | 2025-12-23 | 3
A25370 | Surface leveling and compaction | 2025-12-25 | 2026-06-06 | 2025-12-23 | 2025-12-25 | 2
A25380 | Lean concrete | 2025-12-28 | 2026-06-08 | 2025-12-25 | 2025-12-28 | 2
A25390 | Water proofing and bitumen coating/sheet | 2026-01-08 | 2026-06-20 | 2026-01-04 | 2026-01-08 | 4
A25400 | Formworks | 2026-01-26 | 2026-07-07 | 2026-01-08 | 2026-01-26 | 15
A25410 | Rebar works | 2026-01-26 | 2026-07-07 | 2026-01-08 | 2026-01-26 | 15
A25420 | Concrete pouring | 2026-02-01 | 2026-07-13 | 2026-01-22 | 2026-02-01 | 8
A25430 | Concrete Curing | 2026-02-04 | 2026-07-16 | 2026-01-24 | 2026-02-04 | 10
A25440 | Formwork removal | 2026-02-04 | 2026-07-16 | 2026-01-26 | 2026-02-04 | 8
A25450 | Protective Coating | 2026-02-11 | 2026-07-23 | 2026-02-04 | 2026-02-11 | 6
A25460 | Back filling and compaction in layers | 2026-02-19 | 2026-08-01 | 2026-02-11 | 2026-02-19 | 7
FG Comp 2nd Stage Suction Drum(13-VV-706) |  | 2026-03-10 | 2026-07-19 | 2025-12-27 | 2026-03-10 | 63
A25470 | Excavation | 2025-12-30 | 2026-05-09 | 2025-12-27 | 2025-12-30 | 3
A25480 | Surface leveling and compaction | 2026-01-01 | 2026-05-12 | 2025-12-30 | 2026-01-01 | 2
A25490 | Lean concrete | 2026-01-04 | 2026-05-14 | 2026-01-01 | 2026-01-04 | 2
A25500 | Water proofing and bitumen coating/sheet | 2026-01-15 | 2026-05-26 | 2026-01-11 | 2026-01-15 | 4
A25510 | Formworks | 2026-02-12 | 2026-06-23 | 2026-01-15 | 2026-02-12 | 24
A25520 | Rebar works | 2026-02-12 | 2026-06-23 | 2026-01-15 | 2026-02-12 | 24
A25530 | Concrete pouring | 2026-02-14 | 2026-06-24 | 2026-01-29 | 2026-02-14 | 13
A25540 | Concrete Curing | 2026-02-21 | 2026-07-01 | 2026-01-31 | 2026-02-21 | 18
A25550 | Formwork removal | 2026-02-18 | 2026-06-29 | 2026-02-02 | 2026-02-18 | 14
A25560 | Protective Coating | 2026-02-25 | 2026-07-06 | 2026-02-18 | 2026-02-25 | 6
A25570 | Back filling and compaction in layers | 2026-03-10 | 2026-07-19 | 2026-02-25 | 2026-03-10 | 11
PSA2 Slope Drum ( 70-VV-1415) |  | 2025-12-08 | 2026-08-22 | 03-Jul-25 A | 2025-12-08 | 69
A25580 | Excavation | 2025-09-23 | 2026-06-07 | 03-Jul-25 A | 2025-09-23 | 4
A25590 | Surface leveling and compaction | 2025-09-28 | 2026-06-11 | 2025-09-24 | 2025-09-28 | 4
A25600 | Lean concrete | 2025-10-02 | 2026-06-16 | 2025-09-29 | 2025-10-02 | 4
A25610 | Water proofing and bitumen coating/sheet | 2025-10-12 | 2026-06-25 | 2025-10-04 | 2025-10-12 | 8
A25620 | Formworks | 2025-11-09 | 2026-07-23 | 2025-10-13 | 2025-11-09 | 24
A25630 | Rebar works | 2025-11-09 | 2026-07-23 | 2025-10-13 | 2025-11-09 | 24
A25640 | Concrete pouring | 2025-11-13 | 2026-07-28 | 2025-11-10 | 2025-11-13 | 4
A25650 | Concrete Curing | 2025-11-23 | 2026-08-06 | 2025-11-10 | 2025-11-23 | 12
A25660 | Formwork removal | 2025-11-16 | 2026-07-30 | 2025-11-12 | 2025-11-16 | 4
A25670 | Protective Coating | 2025-11-25 | 2026-08-09 | 2025-11-17 | 2025-11-25 | 8
A25680 | Back filling and compaction in layers | 2025-12-08 | 2026-08-22 | 2025-11-26 | 2025-12-08 | 11
FG Comp After Cooler ( 13-HE-704) |  | 2026-02-15 | 2026-07-11 | 2025-12-30 | 2026-02-15 | 40
A25690 | Excavation | 2026-01-03 | 2026-05-12 | 2025-12-30 | 2026-01-03 | 3
A25700 | Surface leveling and compaction | 2026-01-05 | 2026-05-31 | 2026-01-03 | 2026-01-05 | 2
A25710 | Lean concrete | 2026-01-07 | 2026-06-02 | 2026-01-05 | 2026-01-07 | 2
A25720 | Water proofing and bitumen coating/sheet | 2026-01-17 | 2026-06-11 | 2026-01-14 | 2026-01-17 | 2
A25730 | Formworks | 2026-02-03 | 2026-06-29 | 2026-01-17 | 2026-02-03 | 15
A25740 | Rebar works | 2026-02-03 | 2026-06-29 | 2026-01-17 | 2026-02-03 | 15
A25750 | Concrete pouring | 2026-02-07 | 2026-07-02 | 2026-01-24 | 2026-02-07 | 12
A25760 | Concrete Curing | 2026-02-14 | 2026-07-09 | 2026-01-25 | 2026-02-14 | 17
A25770 | Formwork removal | 2026-02-10 | 2026-07-06 | 2026-01-27 | 2026-02-10 | 12
A25780 | Protective Coating | 2026-02-09 | 2026-07-05 | 2026-01-31 | 2026-02-09 | 8
A25790 | Back filling and compaction in layers | 2026-02-15 | 2026-07-11 | 2026-02-09 | 2026-02-15 | 5
FG Comp Interstage Cooler ( 13-HE-703) |  | 2026-02-09 | 2026-07-25 | 2025-12-23 | 2026-02-09 | 41
A26490 | Excavation | 2025-12-27 | 2026-05-05 | 2025-12-23 | 2025-12-27 | 3
A26500 | Surface leveling and compaction | 2025-12-29 | 2026-06-13 | 2025-12-27 | 2025-12-29 | 2
A26510 | Lean concrete | 2025-12-31 | 2026-06-15 | 2025-12-29 | 2025-12-31 | 2
A26520 | Water proofing and bitumen coating/sheet | 2026-01-10 | 2026-06-24 | 2026-01-07 | 2026-01-10 | 2
A26530 | Formworks | 2026-01-27 | 2026-07-12 | 2026-01-10 | 2026-01-27 | 15
A26540 | Rebar works | 2026-01-27 | 2026-07-12 | 2026-01-10 | 2026-01-27 | 15
A26550 | Concrete pouring | 2026-01-31 | 2026-07-15 | 2026-01-17 | 2026-01-31 | 12
A26560 | Concrete Curing | 2026-02-07 | 2026-07-22 | 2026-01-18 | 2026-02-07 | 17
A26570 | Formwork removal | 2026-02-03 | 2026-07-20 | 2026-01-20 | 2026-02-03 | 12
A26580 | Protective Coating | 2026-02-03 | 2026-07-19 | 2026-01-25 | 2026-02-03 | 8
A26590 | Back filling and compaction in layers | 2026-02-09 | 2026-07-25 | 2026-02-03 | 2026-02-09 | 5
OG Comp 2nd Stage Suction Drum(13-VV-713) |  | 2026-05-05 | 2026-08-22 | 2026-02-25 | 2026-05-05 | 59
A25800 | Excavation | 2026-03-01 | 2026-06-17 | 2026-02-25 | 2026-03-01 | 3
A25810 | Surface leveling and compaction | 2026-03-03 | 2026-06-20 | 2026-03-01 | 2026-03-03 | 2
A25820 | Lean concrete | 2026-03-05 | 2026-06-22 | 2026-03-03 | 2026-03-05 | 2
A25830 | Water proofing and bitumen coating/sheet | 2026-03-17 | 2026-07-04 | 2026-03-12 | 2026-03-17 | 4
A25840 | Formworks | 2026-04-14 | 2026-08-01 | 2026-03-17 | 2026-04-14 | 24
A25850 | Rebar works | 2026-04-14 | 2026-08-01 | 2026-03-17 | 2026-04-14 | 24
A25860 | Concrete pouring | 2026-04-15 | 2026-08-02 | 2026-03-31 | 2026-04-15 | 13
A25870 | Concrete Curing | 2026-04-22 | 2026-08-09 | 2026-04-01 | 2026-04-22 | 18
A25880 | Formwork removal | 2026-04-20 | 2026-08-06 | 2026-04-04 | 2026-04-20 | 14
A25890 | Protective Coating | 2026-04-27 | 2026-08-13 | 2026-04-20 | 2026-04-27 | 6
A25900 | Back filling and compaction in layers | 2026-05-05 | 2026-08-22 | 2026-04-27 | 2026-05-05 | 7
OG Buffer Drum (13-VV-712) |  | 2026-03-02 | 2026-08-22 | 2025-12-16 | 2026-03-02 | 65
A26020 | Excavation | 2025-12-20 | 2026-04-07 | 2025-12-16 | 2025-12-20 | 3
A26030 | Surface leveling and compaction | 2025-12-22 | 2026-04-09 | 2025-12-20 | 2025-12-22 | 2
A26040 | Lean concrete | 2025-12-24 | 2026-04-12 | 2025-12-22 | 2025-12-24 | 2
A26050 | Water proofing and bitumen coating/sheet | 2025-12-29 | 2026-04-16 | 2025-12-24 | 2025-12-29 | 4
A26060 | Formworks | 2026-01-22 | 2026-05-11 | 2025-12-29 | 2026-01-22 | 21
A26070 | Rebar works | 2026-01-22 | 2026-05-11 | 2025-12-29 | 2026-01-22 | 21
A26080 | Concrete pouring | 2026-02-07 | 2026-05-26 | 2026-01-22 | 2026-02-07 | 13
A26090 | Concrete Curing | 2026-02-12 | 2026-06-01 | 2026-01-22 | 2026-02-12 | 18
A26100 | Formwork removal | 2026-02-10 | 2026-05-30 | 2026-01-25 | 2026-02-10 | 14
A26110 | Protective Coating | 2026-02-17 | 2026-06-06 | 2026-02-10 | 2026-02-17 | 6
A26120 | Back filling and compaction in layers | 2026-03-02 | 2026-08-22 | 2026-02-17 | 2026-03-02 | 11
OG Compressor Interstage Cooler (13-HE-708) |  | 2026-04-08 | 2026-08-09 | 2026-02-22 | 2026-04-08 | 39
A26130 | Excavation | 2026-02-25 | 2026-06-14 | 2026-02-22 | 2026-02-25 | 3
A26140 | Surface leveling and compaction | 2026-02-28 | 2026-06-30 | 2026-02-25 | 2026-02-28 | 2
A26150 | Lean concrete | 2026-03-02 | 2026-07-02 | 2026-02-28 | 2026-03-02 | 2
A26160 | Water proofing and bitumen coating/sheet | 2026-03-11 | 2026-07-12 | 2026-03-09 | 2026-03-11 | 2
A26170 | Formworks | 2026-03-29 | 2026-07-29 | 2026-03-11 | 2026-03-29 | 15
A26180 | Rebar works | 2026-03-29 | 2026-07-29 | 2026-03-11 | 2026-03-29 | 15
A26190 | Concrete pouring | 2026-04-01 | 2026-08-02 | 2026-03-18 | 2026-04-01 | 12
A26200 | Concrete Curing | 2026-04-08 | 2026-08-09 | 2026-03-19 | 2026-04-08 | 17
A26210 | Formwork removal | 2026-04-05 | 2026-08-06 | 2026-03-22 | 2026-04-05 | 12
A26220 | Protective Coating | 2026-04-02 | 2026-08-03 | 2026-03-26 | 2026-04-02 | 6
A26230 | Back filling and compaction in layers | 2026-04-07 | 2026-08-08 | 2026-04-02 | 2026-04-07 | 4
Structural Steel and Shades |  | 2026-10-19 | 2027-01-06 | 09-Mar-25 A | 2026-10-19 | 168
TA Prefabrication of Steel Structure for BFW |  |  |  | 09-Mar-25 A | 18-May-25 A | 0
A61610 | TA prefabrication of steel structure for BFW |  |  | 09-Mar-25 A | 18-May-25 A | 0
TA Erection of Steel Structure for BFW |  |  |  | 19-Apr-25 A | 24-May-25 A | 0
A23330 | Erection of Steel Structure of BFW Preheater - Pre TA ( By external Subcontractor) |  |  | 19-Apr-25 A | 24-May-25 A | 0
BF Structure Steel |  | 2026-05-21 | 2026-11-04 | 2026-04-06 | 2026-05-21 | 39
BFW4020 | Structure Installation (Platform on the existing Piperack + strengthen) | 2026-05-21 | 2026-11-04 | 2026-04-06 | 2026-05-21 | 39
GF Steel Works |  | 2026-10-19 | 2027-01-06 | 2026-05-10 | 2026-10-19 | 139
A17810 | Compressors Area- Steel Structure Erection | 2026-09-10 | 2026-09-10 | 2026-05-10 | 2026-09-10 | 106
A17820 | Pipe Rack SR81 - Structure Installation | 2026-09-10 | 2026-09-10 | 2026-06-27 | 2026-09-10 | 65
A18420 | Secondary Pipe Rack (SR80) Structure installation | 2026-09-10 | 2026-12-01 | 2026-08-13 | 2026-09-10 | 24
A23500 | Piping Platforms | 2026-09-10 | 2026-09-10 | 2026-08-11 | 2026-09-10 | 26
A23510 | Transformer Shed - Sub Station Building | 2026-10-19 | 2027-01-06 | 2026-09-24 | 2026-10-19 | 22
External Finishes |  | 2026-10-26 | 2027-01-20 | 2026-08-04 | 2026-10-26 | 72
A61620 | External Finishing | 2026-10-26 | 2027-01-20 | 2026-08-04 | 2026-10-26 | 72
Internal Finishes |  | 2026-10-21 | 2027-01-20 | 2025-11-13 | 2026-10-21 | 294
GF SIS Building Architectural Works |  | 2026-08-03 | 2026-10-07 | 2025-11-13 | 2026-08-03 | 226
A1540 | Block Works and E&I Conduiting Works | 2026-05-25 | 2026-07-29 | 2026-04-15 | 2026-05-25 | 35
A1550 | Plaster Works | 2026-07-11 | 2026-09-14 | 2026-05-06 | 2026-07-11 | 57
A1560 | Painting Works | 2026-08-03 | 2026-10-07 | 2026-06-16 | 2026-08-03 | 42
A1570 | Roof Treatments | 2026-06-01 | 2026-10-07 | 2026-04-29 | 2026-06-01 | 29
A1580 | PCC Flooring Works | 2025-12-13 | 2026-08-12 | 2025-11-13 | 2025-12-13 | 26
A1660 | Floor Finshes (Tiling, Skirting & Dado etc.) | 2026-02-07 | 2026-10-07 | 2025-12-14 | 2026-02-07 | 48
GF Transformers Architectural Works |  | 2026-10-21 | 2027-01-20 | 2026-05-10 | 2026-10-21 | 142
A1240 | Painting External Works | 2026-06-29 | 2026-10-07 | 2026-05-10 | 2026-06-29 | 44
A1250 | Foundation for E&I Support Structure | 2026-06-25 | 2026-10-07 | 2026-05-20 | 2026-06-25 | 32
A1260 | Installation of Fence and Doors | 2026-06-29 | 2026-10-07 | 2026-06-04 | 2026-06-29 | 22
A1270 | Steel Structure / Corrugated Sheet Installation | 2026-10-21 | 2027-01-20 | 2026-09-24 | 2026-10-21 | 24
GF Sub-Station Architectural Works |  | 2026-05-03 | 2027-01-20 | 2026-01-05 | 2026-05-03 | 102
Ground Floor - Cellar Area |  | 2026-03-28 | 2027-01-20 | 2026-01-05 | 2026-03-28 | 71
A1630 | E&I Support Structure | 2026-01-31 | 2026-11-25 | 2026-01-05 | 2026-01-31 | 23
A1640 | Flooring works | 2026-03-07 | 2026-12-30 | 2026-02-01 | 2026-03-07 | 30
A1650 | Installation of Fence and Doors | 2026-03-28 | 2027-01-20 | 2026-03-08 | 2026-03-28 | 18
First Floor |  | 2026-05-03 | 2026-10-07 | 2026-01-19 | 2026-05-03 | 90
A1090 | Plaster Works | 2026-03-30 | 2026-09-03 | 2026-02-03 | 2026-03-30 | 48
A1180 | PCC Flooring Works | 2026-03-25 | 2026-09-08 | 2026-02-23 | 2026-03-25 | 27
A1200 | Floor Finshes (Tiling, Skirting & Dado etc.) | 2026-04-23 | 2026-10-07 | 2026-03-26 | 2026-04-23 | 25
A26430 | Block Works and E&I Conduiting Works | 2026-03-15 | 2026-08-19 | 2026-01-19 | 2026-03-15 | 48
A26440 | Roof Treatments | 2026-04-09 | 2026-10-07 | 2026-03-02 | 2026-04-09 | 34
A26450 | Painting Works (Release for Electrical Equipments) | 2026-05-03 | 2026-10-07 | 2026-03-15 | 2026-05-03 | 43
Others |  |  |  | 09-Jan-25 A | 20-Jun-25 A | 0
Topographic |  |  |  | 09-Jan-25 A | 23-May-25 A | 0
Topographic/UG Survey |  |  |  | 09-Jan-25 A | 22-May-25 A | 0
A28960 | TBE for Topo,UG & Getechnical Survey_IFD/IFC |  |  | 11-Feb-25 A | 01-Mar-25 A | 0
A56190 | TBE for Topo,UG & Getechnical Survey_IFR |  |  | 09-Jan-25 A | 15-Jan-25 A | 0
A56200 | TBE for Topo,UG & Getechnical Survey_RCC |  |  | 16-Jan-25 A | 10-Feb-25 A | 0
E1060 | Geotech / Survery of Site |  |  | 09-May-25 A | 15-May-25 A | 0
E1070 | Topo/ UG Scanning Survey |  |  | 18-Apr-25 A | 30-Apr-25 A | 0
E1080 | TBE & PO issuance of Geotech / UG Scanning |  |  | 02-Mar-25 A | 20-Mar-25 A | 0
E1090 | Mobilization of Geotech / UG Scanning |  |  | 01-May-25 A | 08-May-25 A | 0
E1100 | Reports of Getech Investigation / UG Scanning |  |  | 16-May-25 A | 22-May-25 A | 0
E1110 | CICPA Passes for Geotech Sub Contractor |  |  | 21-Mar-25 A | 17-Apr-25 A | 0
Geotech/ Topographic/UG Survey |  |  |  | 11-Feb-25 A | 23-May-25 A | 0
E1000 | RFQ of Geotech / UG Scanning |  |  | 11-Feb-25 A | 01-Mar-25 A | 0
E1010 | TBE & PO issuance of Geotech / UG Scanning |  |  | 02-Mar-25 A | 20-Mar-25 A | 0
E1020 | Mobilization of Geotech / UG Scanning |  |  | 01-May-25 A | 08-May-25 A | 0
E1030 | Geotech / Survery of Site |  |  | 10-May-25 A | 16-May-25 A | 0
E1040 | Reports of Getech Investigation / UG Scanning |  |  | 17-May-25 A | 23-May-25 A | 0
E1050 | CICPA Passes for Geotech Sub Contractor |  |  | 21-Mar-25 A | 17-Apr-25 A | 0
Piling (No required) |  |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
Piling Works |  |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A15550 | Piling Work (Compressors, Sheds & Equipment) |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A15570 | Piling Works - Pipe Racks and OG Buffer Drum |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A15610 | Piling work PSA2 Unit (10 Vessels) |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A15650 | Test Piles (including curing time) |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A15690 | Data for Test pile |  |  |  | 20-Jun-25 A | 0
A15720 | PO for Piling Contractor |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A15730 | Mobilization of piling contractor |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
A23610 | Mobilization for Production Piles |  |  | 20-Jun-25 A | 20-Jun-25 A | 0
Mechanical Construction |  | 2027-01-26 | 2027-07-20 | 05-Mar-25 A | 2027-01-26 | 274
Equipment erection and installation |  | 2026-12-01 | 2027-01-20 | 19-Apr-25 A | 2026-12-01 | 236
HVAC Works |  | 2026-11-07 | 2027-01-20 | 2026-08-18 | 2026-11-07 | 69
A18570 | Fabrication and installation of ductwork inside the building | 2026-09-17 | 2026-12-01 | 2026-08-18 | 2026-09-17 | 26
A18580 | Fabrication and installation of ductwork outside the building | 2026-09-22 | 2026-12-16 | 2026-08-23 | 2026-09-22 | 26
A18590 | Insulation of ductwork outside the building | 2026-10-11 | 2027-01-04 | 2026-09-06 | 2026-10-11 | 30
A18760 | Installation of electrical works inside the building (excluding installation of HVAC power control panel) | 2026-09-24 | 2026-12-17 | 2026-08-25 | 2026-09-24 | 26
A18770 | Installation of piping inside and outside the building | 2026-09-17 | 2026-12-01 | 2026-08-18 | 2026-09-17 | 26
A18780 | Pressure testing of pipes | 2026-10-01 | 2026-12-15 | 2026-09-17 | 2026-10-01 | 12
A18790 | Flushing, cleaning, air blowing of Piping | 2026-10-08 | 2026-12-22 | 2026-09-24 | 2026-10-08 | 12
A18820 | Assembly of Air Handling Unit (AHU) | 2026-10-14 | 2026-12-28 | 2026-10-08 | 2026-10-14 | 5
A18830 | Installation and alignment of air handling units (AHU) | 2026-10-21 | 2027-01-04 | 2026-10-14 | 2026-10-21 | 6
A18840 | Installation of Exhaust Fan | 2026-10-21 | 2027-01-11 | 2026-10-14 | 2026-10-21 | 6
A18850 | Complete Duct Connection to AHU & Fan | 2026-10-27 | 2027-01-16 | 2026-10-15 | 2026-10-27 | 10
A18860 | Installation and alignment of refrigerant cycle and chiller | 2026-10-21 | 2027-01-04 | 2026-10-14 | 2026-10-21 | 6
A18870 | Installation of buffer tank | 2026-10-21 | 2027-01-04 | 2026-10-14 | 2026-10-21 | 6
A18890 | Insulation of refrigerant pipework outside the building | 2026-10-14 | 2027-01-04 | 2026-09-27 | 2026-10-14 | 15
A18910 | Installation of electrical / power system and HVAC control system | 2026-10-12 | 2027-01-04 | 2026-09-24 | 2026-10-12 | 15
A18920 | HVAC Testing and Commissioning works | 2026-11-07 | 2027-01-20 | 2026-10-21 | 2026-12-16 | 14
GF Sanitary Water Sump Pump (01 No) (70-PC-1409) |  | 2026-10-01 | 2026-11-29 | 2026-08-16 | 2026-10-01 | 40
A22600 | Installation of Sanitary Water Sump Pump (70-PC-1409) | 2026-08-30 | 2026-10-28 | 2026-08-16 | 2026-08-30 | 12
A22830 | Alignment of Sanitary Water Sump Pump (70-PC-1409) | 2026-09-20 | 2026-11-18 | 2026-08-30 | 2026-09-20 | 18
A22840 | Grouting of Sanitary Water Sump Pump (70-PC-1409) | 2026-10-01 | 2026-11-29 | 2026-09-20 | 2026-10-01 | 10
GF Feed Gas Compressor and Auxilary Equipment Errection |  | 2026-12-01 | 2026-12-01 | 2026-03-15 | 2026-12-01 | 224
FG Comp 1st Stage Suction Drum(13-VV-705) |  | 2026-08-18 | 2026-10-10 | 2026-06-23 | 2026-08-18 | 48
A22480 | Delivery inspection, Unpacked and Installation of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-01 | 2026-08-23 | 2026-06-23 | 2026-07-01 | 7
A23020 | Alignment of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-09 | 2026-08-31 | 2026-07-01 | 2026-07-09 | 7
A23030 | Grouting of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-07-15 | 2026-09-06 | 2026-07-09 | 2026-07-15 | 5
A23080 | Internals (Demister) of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-08-02 | 2026-09-23 | 2026-07-15 | 2026-08-02 | 15
A23230 | Insulation of FG Comp 1st Stage Suction Drum(13-VV-705) | 2026-08-18 | 2026-10-10 | 2026-08-02 | 2026-08-18 | 14
FG Compressor Interstage Cooler (13-HE-703) |  | 2026-08-10 | 2026-09-22 | 2026-06-13 | 2026-08-10 | 51
A23600 | Intallation of FG Compressor Interstage Cooler (13-HE-703) | 2026-06-23 | 2026-08-05 | 2026-06-13 | 2026-06-23 | 10
A23910 | Alignment of FG Compressor Interstage Cooler (13-HE-703) | 2026-07-05 | 2026-08-17 | 2026-06-24 | 2026-07-05 | 10
A23920 | Grouting of FG Compressor Interstage Cooler (13-HE-703) | 2026-07-16 | 2026-08-29 | 2026-07-06 | 2026-07-16 | 10
A23980 | Insulation of FG Compressor Interstage Cooler (13-HE-703) | 2026-08-10 | 2026-09-22 | 2026-07-18 | 2026-08-10 | 21
FG Comp After Cooler ( 13-HE-704) |  | 2026-08-10 | 2026-09-22 | 2026-06-13 | 2026-08-10 | 51
A22540 | Installation of FG Comp After Cooler ( 13-HE-704) | 2026-06-23 | 2026-08-05 | 2026-06-13 | 2026-06-23 | 10
A23240 | Alignment of FG Comp After Cooler ( 13-HE-704) | 2026-07-05 | 2026-08-17 | 2026-06-24 | 2026-07-05 | 10
A23250 | Grouting of FG Comp After Cooler ( 13-HE-704) | 2026-07-16 | 2026-08-29 | 2026-07-06 | 2026-07-16 | 10
A23370 | Insulation of FG Comp After Cooler ( 13-HE-704) | 2026-08-10 | 2026-09-22 | 2026-07-18 | 2026-08-10 | 21
FG Comp 2nd Stage Discharge Drum(13-VV-707) |  | 2026-08-04 | 2026-09-22 | 2026-06-20 | 2026-08-04 | 40
A22530 | Installation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-06-24 | 2026-08-12 | 2026-06-20 | 2026-06-24 | 5
A23380 | Alignment of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-06-30 | 2026-08-18 | 2026-06-25 | 2026-06-30 | 5
A23390 | Grouting of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-06 | 2026-08-24 | 2026-07-01 | 2026-07-06 | 5
A23400 | Internals (Demister Pad) of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-07-18 | 2026-09-05 | 2026-07-07 | 2026-07-18 | 10
A23410 | Insulation of FG Comp 2nd Stage Discharge Drum (13-VV-707) | 2026-08-04 | 2026-09-22 | 2026-07-19 | 2026-08-04 | 15
FG Comp 2nd Stage Suction Drum(13-VV-706) |  | 2026-07-23 | 2026-09-22 | 2026-06-02 | 2026-07-23 | 44
A22490 | Delivery inspection, Unpacked and Installation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-06-14 | 2026-08-13 | 2026-06-02 | 2026-06-14 | 10
A23420 | Alignment of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-06-20 | 2026-08-19 | 2026-06-14 | 2026-06-20 | 5
A23430 | Grouting of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-06-25 | 2026-08-25 | 2026-06-20 | 2026-06-25 | 5
A23440 | Internals (Demister Pad) of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-07 | 2026-09-06 | 2026-06-25 | 2026-07-07 | 10
A23450 | Insulation of FG Comp 2nd Stage Suction Drum (13-VV-706) | 2026-07-23 | 2026-09-22 | 2026-07-07 | 2026-07-23 | 14
Feed Gas (FG) Compressor Installation |  | 2026-12-01 | 2026-12-01 | 2026-03-15 | 2026-12-01 | 224
C1000 | FG Foundation Plan - Foundation Check & Dimensional Examination - FG Compressor | 2026-04-01 | 2026-04-01 | 2026-03-15 | 2026-04-01 | 15
C1001 | Installation of FG Compressor (Setting of Pad, Preparation, Position and Leveling) | 2026-05-10 | 2026-05-10 | 2026-04-26 | 2026-05-10 | 12
C1002 | Setting of FG Compressor Base Plate (Temporary settng, Elevation, Level, Tolerance, Position) | 2026-04-26 | 2026-04-26 | 2026-04-01 | 2026-04-26 | 21
C1003 | Grouting - FG Compressor | 2026-06-20 | 2026-08-11 | 2026-06-08 | 2026-06-20 | 10
C1004 | Pre-alignment of FG Compressor | 2026-06-08 | 2026-07-30 | 2026-05-21 | 2026-06-08 | 15
C1005 | Coupling Alignment - FG Compressor | 2026-07-13 | 2026-09-10 | 2026-06-20 | 2026-07-13 | 20
C1006 | Installation of Auxiliary Equipment - FG Compressor | 2026-08-27 | 2026-10-10 |  | 2026-08-27 | 0
C1007 | Installation of Piping - FG Compressor | 2026-11-02 | 2026-11-02 | 2026-09-10 | 2026-11-02 | 45
C1008 | E&I Installation - FG Compressor | 2026-11-19 | 2026-11-19 | 2026-10-04 | 2026-11-19 | 40
C1009 | Punch List Close Out FG Compressor | 2026-12-01 | 2026-12-01 | 2026-11-19 | 2026-12-01 | 10
C1031 | Installation of FG Compressor Main Driver Motor | 2026-05-21 | 2026-07-13 | 2026-05-10 | 2026-05-21 | 10
GF Off Gas Compressor and Auxilary Equipment Errection |  | 2026-11-23 | 2026-12-01 | 2026-02-07 | 2026-11-23 | 249
Off Gas (OG) Compressor Installation |  | 2026-11-23 | 2026-12-01 | 2026-02-07 | 2026-11-23 | 249
C1069 | OG Foundation Plan - Foundation Check & Dimensional Examination | 2026-02-23 | 2026-06-22 | 2026-02-07 | 2026-02-23 | 15
C1079 | Installation of OG Compressor (Setting of Pad, Preparation, Position and Leveling) | 2026-04-02 | 2026-07-30 | 2026-03-21 | 2026-04-02 | 12
C1089 | Setting of OG Compressor Base Plate (Temporary setting, Elevation, Level, Tolerance, Position) | 2026-03-19 | 2026-07-16 | 2026-02-24 | 2026-03-19 | 21
C1099 | Grouting - OG Compressor | 2026-05-21 | 2026-09-07 | 2026-05-10 | 2026-05-21 | 10
C1109 | Pre-alignment of OG Compressor | 2026-04-29 | 2026-08-26 | 2026-04-13 | 2026-04-29 | 15
C1119 | Coupling and Alignment - OG Compressor | 2026-06-14 | 2026-09-30 | 2026-05-21 | 2026-06-14 | 20
C1129 | Installation of Auxiliary Equipment - OG Compressor | 2026-08-09 | 2026-10-06 |  | 2026-08-09 | 0
C1139 | Installation of Piping - OG Compressor | 2026-11-01 | 2026-11-10 | 2026-09-21 | 2026-11-01 | 35
C1149 | E&I Installation - OG Compressor | 2026-11-08 | 2026-11-16 | 2026-09-28 | 2026-11-08 | 35
C1159 | Punch List Close Out (Mechanical) - OG Compressor | 2026-11-23 | 2026-12-01 | 2026-11-08 | 2026-11-23 | 13
C1169 | Installation of OG Compressor Main Driver Motor | 2026-04-12 | 2026-08-09 | 2026-04-04 | 2026-04-12 | 8
OG Buffer Drum (13-VV-712) |  | 2026-09-03 | 2026-11-29 | 2026-06-16 | 2026-09-03 | 68
A22500 | Installation of OG Buffer Drum (13-VV-712) | 2026-07-14 | 2026-10-08 | 2026-07-07 | 2026-07-14 | 6
A22790 | Alignment of OG Buffer Drum (13-VV-712) | 2026-07-21 | 2026-10-22 | 2026-07-14 | 2026-07-21 | 6
A22800 | Grouting of OG Buffer Drum (13-VV-712) | 2026-07-28 | 2026-10-29 | 2026-07-21 | 2026-07-28 | 6
A22810 | Internals (Demister) of OG Buffer Drum (13-VV-712) | 2026-08-18 | 2026-11-12 | 2026-08-04 | 2026-08-18 | 12
A22820 | Insulation of OG Buffer Drum (13-VV-712) | 2026-09-03 | 2026-11-29 | 2026-08-18 | 2026-09-03 | 14
A25270 | Ground Preparatory Works for Crane | 2026-06-30 | 2026-10-01 | 2026-06-16 | 2026-06-30 | 12
A25280 | Scafolding Works | 2026-08-04 | 2026-10-29 | 2026-07-14 | 2026-08-04 | 18
OG Compressor Interstage Cooler (13-HE-708) |  | 2026-08-03 | 2026-10-06 | 2026-06-20 | 2026-08-03 | 39
A22570 | Intallation of OG Compressor Interstage Cooler (13-HE-708) | 2026-06-23 | 2026-08-26 | 2026-06-20 | 2026-06-23 | 4
A23460 | Alignment of OG Compressor Interstage Cooler (13-HE-708) | 2026-06-29 | 2026-09-01 | 2026-06-24 | 2026-06-29 | 5
A23470 | Grouting of OG Compressor Interstage Cooler (13-HE-708) | 2026-07-11 | 2026-09-13 | 2026-06-30 | 2026-07-11 | 10
A23480 | Insulation of OG Compressor Interstage Cooler (13-HE-708) | 2026-08-03 | 2026-10-06 | 2026-07-12 | 2026-08-03 | 20
OG Comp After Cooler ( 13-HE-709) |  | 2026-08-03 | 2026-10-06 | 2026-06-20 | 2026-08-03 | 39
A22550 | Installation of OG Comp After Cooler ( 13-HE-709) | 2026-06-24 | 2026-08-27 | 2026-06-20 | 2026-06-24 | 5
A23490 | Alignment of OG Comp After Cooler ( 13-HE-709) | 2026-06-29 | 2026-09-01 | 2026-06-25 | 2026-06-29 | 4
A23930 | Grouting of OG Comp After Cooler ( 13-HE-709) | 2026-07-11 | 2026-09-13 | 2026-06-30 | 2026-07-11 | 10
A23990 | Insulation of OG Comp After Cooler ( 13-HE-709) | 2026-08-03 | 2026-10-06 | 2026-07-12 | 2026-08-03 | 20
OG Compressor Discharge Drip Leg (13-SP-7004) |  | 2026-07-23 | 2026-10-06 | 2026-06-16 | 2026-07-23 | 32
A3490 | Installation of OG Compressor Discharge Drip Leg | 2026-06-21 | 2026-09-03 | 2026-06-16 | 2026-06-21 | 4
A3500 | Alignment of OG Compressor Discharge Drip Leg | 2026-06-25 | 2026-09-08 | 2026-06-21 | 2026-06-25 | 4
A3510 | Grouting of OG Compressor Discharge Drip Leg | 2026-06-30 | 2026-09-13 | 2026-06-25 | 2026-06-30 | 4
A3520 | Internals of OG Compressor Discharge Drip Leg | 2026-07-12 | 2026-09-24 | 2026-06-30 | 2026-07-12 | 10
A3530 | Insulation of OG Compressor Discharge Drip Leg | 2026-07-23 | 2026-10-06 | 2026-07-12 | 2026-07-23 | 10
OG Comp 2nd Stage Suction Drum(13-VV-713) |  | 2026-08-09 | 2026-10-06 | 2026-06-23 | 2026-08-09 | 40
A22510 | Installation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-06-29 | 2026-08-26 | 2026-06-23 | 2026-06-29 | 5
A24000 | Alignment of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-05 | 2026-09-01 | 2026-06-29 | 2026-07-05 | 5
A24010 | Grouting of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-11 | 2026-09-07 | 2026-07-05 | 2026-07-11 | 5
A25250 | Internals (Demster Pad) of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-07-22 | 2026-09-19 | 2026-07-11 | 2026-07-22 | 10
A25260 | Insulation of OG Comp 2nd Stage Suction Drum (13-VV-713) | 2026-08-09 | 2026-10-06 | 2026-07-22 | 2026-08-09 | 15
TA Boiler Feed Water Installation |  |  |  | 19-Apr-25 A | 24-May-25 A | 0
A3787 | Installation of BFW Preheater |  |  | 19-Apr-25 A | 24-May-25 A | 0
BF Mechanical Equipments |  | 2026-10-07 | 2026-12-21 | 2026-05-30 | 2026-10-07 | 113
A22560 | Installation of C4 Guard Regeneration Cooler (50-HE-1410) | 2026-07-14 | 2026-12-21 | 2026-05-30 | 2026-07-14 | 40
A9650 | Installation of Dripleg (1 No) | 2026-08-05 | 2026-12-21 | 2026-06-20 | 2026-08-05 | 40
A9660 | Installation of Coalescer (1 No) | 2026-10-07 | 2026-12-21 | 2026-08-23 | 2026-10-07 | 40
GF PSA2 Package by Linde ( 10 Vessels) |  | 2026-10-20 | 2026-11-29 | 2025-12-20 | 2026-10-20 | 262
A22610 | Installation of PSA2 Package by Linde ( 10 Vessels) | 2026-02-26 | 2026-06-24 | 2025-12-20 | 2026-02-26 | 60
A22850 | Alignment of PSA2 Package by Linde ( 10 Vessels) | 2026-04-20 | 2026-08-16 | 2026-02-28 | 2026-04-20 | 45
A22860 | Grouting of PSA2 Package by Linde ( 10 Vessels) | 2026-06-11 | 2026-10-07 | 2026-04-21 | 2026-06-11 | 45
A22870 | Internals of PSA2 Package by Linde ( 10 Vessels) | 2026-10-20 | 2026-11-29 | 2026-08-30 | 2026-10-20 | 45
GF Water Sump Pump (02 Nos) (70-PC-1407) |  | 2026-09-20 | 2026-11-29 | 2026-08-04 | 2026-09-20 | 40
A22590 | Installation of Water Sump Pump (70-PC-1407) | 2026-08-18 | 2026-10-27 | 2026-08-04 | 2026-08-18 | 12
A22880 | Alignment of Water Sump Pump (70-PC-1407) | 2026-09-08 | 2026-11-17 | 2026-08-18 | 2026-09-08 | 18
A22890 | Grouting of Water Sump Pump (70-PC-1407) | 2026-09-20 | 2026-11-29 | 2026-09-08 | 2026-09-20 | 10
GF PSA2 Slope Drum ( 70-VV-1415) |  | 2026-07-21 | 2026-11-29 | 2026-06-09 | 2026-07-21 | 36
A22520 | Installation of PSA2 Slope Drum ( 70-VV-1415) | 2026-06-15 | 2026-10-24 | 2026-06-09 | 2026-06-15 | 5
A22930 | Alignment of PSA2 Slope Drum ( 70-VV-1415) | 2026-06-21 | 2026-10-29 | 2026-06-15 | 2026-06-21 | 5
A22960 | Grouting of PSA2 Slope Drum ( 70-VV-1415) | 2026-06-27 | 2026-11-04 | 2026-06-21 | 2026-06-27 | 5
A22990 | Internals of PSA2 Slope Drum ( 70-VV-1415) | 2026-07-08 | 2026-11-16 | 2026-06-27 | 2026-07-08 | 10
A23010 | Insulation of PSA2 Slope Drum ( 70-VV-1415) | 2026-07-21 | 2026-11-29 | 2026-07-08 | 2026-07-21 | 11
GF EOT Crane for FG Compressor |  | 2026-10-12 | 2026-11-19 | 2026-09-10 | 2026-10-12 | 27
C1319 | LT rail line installation | 2026-09-22 | 2026-10-26 | 2026-09-10 | 2026-09-22 | 10
C1329 | Assembly of main girders at ground level | 2026-09-22 | 2026-10-31 | 2026-09-10 | 2026-09-22 | 10
C1339 | Installation of electrical equipment | 2026-09-15 | 2026-10-31 | 2026-09-10 | 2026-09-15 | 4
C1349 | Installation of end carriage & main girder | 2026-09-27 | 2026-11-04 | 2026-09-22 | 2026-09-27 | 4
C1359 | Crab erection | 2026-09-30 | 2026-11-08 | 2026-09-27 | 2026-09-30 | 3
C1369 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 2026-10-12 | 2026-11-19 | 2026-09-30 | 2026-10-12 | 10
GF EOT Crane for OG Compressor |  | 2026-10-13 | 2026-11-16 | 2026-09-17 | 2026-10-13 | 22
C1259 | LT rail line installation | 2026-09-29 | 2026-11-02 | 2026-09-17 | 2026-09-29 | 10
C1269 | Assembly of main girders at ground level | 2026-09-29 | 2026-11-02 | 2026-09-17 | 2026-09-29 | 10
C1279 | Installation of end carriage & main girder | 2026-10-04 | 2026-11-07 | 2026-09-29 | 2026-10-04 | 4
C1289 | Crab erection | 2026-10-06 | 2026-11-09 | 2026-10-04 | 2026-10-06 | 2
C1299 | Installation of the platform, hand railing, cabin, ladder, DSL cage and DSL guard | 2026-10-13 | 2026-11-16 | 2026-10-04 | 2026-10-13 | 8
C1309 | Installation of electrical equipment | 2026-09-22 | 2026-11-02 | 2026-09-17 | 2026-09-22 | 4
Piping Fabrication |  |  |  | 05-Mar-25 A | 18-Apr-25 A | 0
TA Piping Work |  |  |  | 05-Mar-25 A | 18-Apr-25 A | 0
A17730 | Installation of Scaffolding |  |  | 05-Mar-25 A | 08-Apr-25 A | 0
BFW4000 | Prefabrication of Tie-ins Spools |  |  | 28-Mar-25 A | 04-Apr-25 A | 0
BFW4010 | Prefabrication of Piping Spools for the BFW |  |  | 11-Apr-25 A | 18-Apr-25 A | 0
BFW4050 | Sand blastinfg and painting |  |  | 01-Apr-25 A | 15-Apr-25 A | 0
Piping and Valves Installation |  | 2027-01-26 | 2027-03-11 | 29-Mar-25 A | 2027-01-26 | 240
BF Piping Works |  | 2026-10-27 | 2026-12-02 | 2026-02-07 | 2026-10-27 | 226
A18520 | Scaffolding for Piping errection on Piperack | 2026-03-17 | 2026-05-06 | 2026-02-07 | 2026-03-17 | 34
A9670 | Piping Erection / Installation in Brown Field | 2026-08-18 | 2026-09-23 | 2026-03-31 | 2026-08-18 | 120
BFW4030 | Piping Hydrotesting - BF | 2026-09-22 | 2026-10-28 | 2026-08-06 | 2026-09-22 | 40
BFW4040 | Piping connections with tie-ins | 2026-10-27 | 2026-12-02 | 2026-09-09 | 2026-10-27 | 41
TA Tie-In Execution - A/G Tie-Ins |  |  |  | 29-Mar-25 A | 24-May-25 A | 0
Package 1 |  |  |  | 11-Apr-25 A | 24-May-25 A | 0
Tailgas from Tie In point EU3 to EU3 H2 Tag # IP-B-B3-H3-L-2010 |  |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38390 | Start of Work |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38400 | Removal of insulation & Wallthickness measurement |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38410 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38420 | Install pipe supports (if any) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A38430 | Prepare and hydrotest up to XX BarG (if required) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A38440 | Hydrotest witness inspection (if required) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A9680 | Obtain Work Permit |  |  | 11-Apr-25 A | 24-May-25 A | 0
A9710 | Cut old piping (existing line 45024), haul to ground level |  |  | 11-Apr-25 A | 24-May-25 A | 0
A9720 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 11-Apr-25 A | 24-May-25 A | 0
A9730 | Full welding of joints & installation of Tie-In spool 45076 |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A9740 | Inspection NDT / RT of selected joints |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A9780 | Reinstall back piping components (TW/TE, TG, PT, PG if any) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A9790 | Touch-up painting works |  |  | 25-Apr-25 A | 15-May-25 A | 0
A9800 | Deblinding, remove temporary support / scaffolds |  |  | 25-Apr-25 A | 15-May-25 A | 0
A9810 | Reinstall insulation (if any) |  |  | 25-Apr-25 A | 15-May-25 A | 0
A9820 | Torquing / flange management & hand-over to Ops |  |  | 25-Apr-25 A | 15-May-25 A | 0
A9830 | End of Work |  |  | 16-May-25 A | 17-May-25 A | 0
Tailgas Tag # IP-B-B3-M3-L-3010 |  |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38280 | Start of Work |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38290 | Obtain Work Permit |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38300 | Removal of insulation & Wallthickness measurement |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38310 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38320 | Cut old piping (existing line 45024), haul to ground level |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38330 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 11-Apr-25 A | 24-May-25 A | 0
A38340 | Full welding of joints & installation of Tie-In spool 45024 |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A38350 | Inspection NDT / RT of selected joints |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A38360 | Install pipe supports (if any) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A38370 | Torquing / flange management & hand-over to Ops |  |  | 25-Apr-25 A | 15-May-25 A | 0
A38380 | End of Work |  |  | 16-May-25 A | 17-May-25 A | 0
A9590 | Prepare and hydrotest up to XX BarG (if required) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A9600 | Hydrotest witness inspection (if required) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A9610 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 25-Apr-25 A | 26-Apr-25 A | 0
A9620 | Touch-up painting works |  |  | 25-Apr-25 A | 15-May-25 A | 0
A9630 | Deblinding, remove temporary support / scaffolds |  |  | 25-Apr-25 A | 15-May-25 A | 0
A9640 | Reinstall insulation (if any) |  |  | 25-Apr-25 A | 15-May-25 A | 0
Tailgas Tag # IP-B-M3-B3-L-3020 |  |  |  | 11-Apr-25 A | 17-May-25 A | 0
A38270 | Touch-up painting works |  |  | 16-May-25 A | 17-May-25 A | 0
A9330 | Start of Work |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9340 | Obtain Work Permit |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9350 | Removal of insulation & Wallthickness measurement |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9360 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9370 | Cut old piping (existing line 45024), haul to ground level |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9380 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9390 | Full welding of joints & installation of Tie-In spool 45024 |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9400 | Inspection NDT / RT of selected joints |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9410 | Install pipe supports (if any) |  |  | 11-Apr-25 A | 11-Apr-25 A | 0
A9420 | Prepare and hydrotest up to XX BarG (if required) |  |  | 16-May-25 A | 17-May-25 A | 0
A9430 | Hydrotest witness inspection (if required) |  |  | 16-May-25 A | 17-May-25 A | 0
A9440 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 16-May-25 A | 17-May-25 A | 0
A9460 | Deblinding, remove temporary support / scaffolds |  |  | 16-May-25 A | 17-May-25 A | 0
A9470 | Reinstall insulation (if any) |  |  | 16-May-25 A | 17-May-25 A | 0
A9480 | Torquing / flange management & hand-over to Ops |  |  | 16-May-25 A | 17-May-25 A | 0
A9490 | End of Work |  |  | 16-May-25 A | 17-May-25 A | 0
Tailgas Tag # IP-B-B3-M3-L-3030 |  |  |  | 11-Apr-25 A | 17-May-25 A | 0
A38230 | Cut old piping (existing line 45024), haul to ground level |  |  | 11-Apr-25 A | 17-May-25 A | 0
A38240 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 11-Apr-25 A | 17-May-25 A | 0
A38250 | Full welding of joints & installation of Tie-In spool 45075 |  |  | 11-Apr-25 A | 17-May-25 A | 0
A38260 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9160 | Start of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9170 | Obtain Work Permit |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9180 | Removal of insulation & Wall thickness measurement |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9190 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9230 | Inspection NDT / RT of selected joints |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9240 | Install pipe supports (if any) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9250 | Prepare and hydrotest up to XX BarG |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9260 | Hydrotest witness inspection |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9280 | Touch-up painting works |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9290 | Deblinding, remove temporary support / scaffolds |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9300 | Reinstall insulation (if any) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9310 | Torquing / flange management & hand-over to Ops |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9320 | End of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
Tailgas Tag # IP-B-B3-M3-L-3050 |  |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8990 | Start of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9000 | Obtain Work Permit |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9010 | Removal of existing valve |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9020 | Installation of new valve |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9030 | Gas measurement |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9120 | Deblinding, remove temporary support / scaffolds |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9130 | Reinstall insulation (if any) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9140 | Torquing / flange management & hand-over to Ops |  |  | 11-Apr-25 A | 17-May-25 A | 0
A9150 | End of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
Regeneration gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3090 |  |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8820 | Start of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8830 | Obtain Work Permit |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8840 | Wallthickness measurement |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8850 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8860 | Cut old piping (existing line 140025), haul to ground level |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8870 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8880 | Full welding of joints & installation of Tie-In spool 140068 |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8890 | Inspection NDT / RT of selected joints |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8900 | Install pipe supports (if any) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8910 | Prepare and hydrotest up to XX BarG |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8920 | Hydrotest witness inspection |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8930 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8940 | Touch-up painting works |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8950 | Deblinding, remove temporary support / scaffolds |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8960 | Reinstall insulation (if any) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8970 | Torquing / flange management & hand-over to Ops |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8980 | End of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
Tailgas from 13-KX-402 Tag # IP-B-B3-M3-L-3100 |  |  |  | 11-Apr-25 A | 17-May-25 A | 0
A38220 | Reinstall insulation (if any) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8650 | Start of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8660 | Obtain Work Permit |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8670 | Removal of insulation & Wallthickness measurement |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8680 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8690 | Cut old piping (existing line 45024), haul to ground level |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8700 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8710 | Full welding of joints & installation of Tie-In spool 45024 |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8720 | Inspection NDT / RT of selected joints |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8730 | Install pipe supports (if any) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8740 | Prepare and hydrotest up to XX BarG (if required) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8750 | Hydrotest witness inspection (if required) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8760 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8770 | Touch-up painting works |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8780 | Deblinding, remove temporary support / scaffolds |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8800 | Torquing / flange management & hand-over to Ops |  |  | 11-Apr-25 A | 17-May-25 A | 0
A8810 | End of Work |  |  | 11-Apr-25 A | 17-May-25 A | 0
Cooling Water from EU3 Tie In Point to 50-HE-1410 Tag # IP-B-B3-M3-L-3120 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38210 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8480 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8500 | Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8510 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8520 | Cut old piping (existing line 140036) , haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8530 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8540 | Full welding of joints & installation of Tie-In spool 140033 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8550 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8560 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8570 | Prepare and hydrotest up to XX BarG (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8580 | Hydrotest witness inspection (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8590 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8600 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8610 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8620 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8630 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8640 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
Regeneration Gas C4 Hydrogenation from 13-VA-804A/B Tag # IP-B-B3-M3-L-3170 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38150 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38160 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38170 | Removal of insulation & Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38180 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38190 | Full welding of joints & installation of Tie-In spool 81142 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38200 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8350 | Cut old piping (existing line 41022), haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8360 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8380 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8390 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8400 | Prepare and hydrotest up to XX BarG (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8410 | Hydrotest witness inspection (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8420 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8440 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8450 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8460 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8470 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
Tailgas line bleed Tag # IP-B-B3-M3-L-3180 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38110 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38120 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38130 | Removal of insulation & Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38140 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8170 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8180 | Cut old piping (existing line 45024), haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8190 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8200 | Full welding of joints & installation of Tie-In spool 45024 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8210 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8220 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8230 | Prepare and hydrotest up to XX BarG (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8240 | Hydrotest witness inspection (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8260 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8270 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8280 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8290 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8300 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
Treated VHP BFW Preheater 52-HE-1402 bypass valve Tag # IP-B-B3-M3-L-3190 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A38100 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7970 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7980 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7990 | Removal of insulation & Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8000 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8010 | Cut old piping (existing line 140025), haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8020 | Grinding, bevelling & fit-up of valve with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8030 | Welding of gate valve & installation of Tie-In spool 140025 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8040 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8050 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8060 | Prepare and hydrotest up to XX BarG (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8070 | Hydrotest witness inspection (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8080 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8090 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8100 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8110 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A8120 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
Treated VHP BFW from EU3 to 52-HE-1402 Tag # IP-B-B3-M3-L-3210 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7800 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7810 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7820 | Removal of insulation & Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7830 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7840 | Cut old piping (existing line 140025), haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7850 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7860 | Full welding of joints & installation of Tie-In spool 140219 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7870 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7880 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7890 | Prepare and hydrotest up to XX BarG |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7900 | Hydrotest witness inspection |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7910 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7920 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7930 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7940 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7950 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7960 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
LP- Steam from EU3 Tie In Point to 52-HE-1402 Tag # IP-B-B3-M3-L-3230 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7630 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7640 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7650 | Removal of insulation & Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7660 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7670 | Cut old piping (existing line 140472), haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7680 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7690 | Welding of weldolet and installation of Tie-In spool 140489 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7700 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7710 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7720 | Prepare and hydrotest up to XX BarG Iif required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7730 | Hydrotest witness inspection Iif required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7740 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7750 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7760 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7770 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7780 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7790 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
Package 2 |  |  |  | 29-Mar-25 A | 20-May-25 A | 0
Regeneration Gas from 50-HE-1402 Tag # IP-B-B3-M3-L-3260 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7460 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7470 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7480 | Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7490 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7500 | Cut old piping (existing line 140025), haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7510 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7520 | Full welding of joints & installation of Tie-In spool 140025 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7530 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7540 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7550 | Prepare and hydrotest up to XX BarG (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7560 | Hydrotest witness inspection (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7570 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7580 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7590 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7600 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7610 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7620 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
Nitrogen from EU3 to 64PSV14001 Tag # IP-B-B3-M3-L-3380 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7290 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7300 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7310 | Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7320 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7330 | Cut old piping (existing line 140148) , haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7340 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7350 | Full welding of joints & installation of Tie-In spool 140038 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7360 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7370 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7380 | Prepare and hydrotest up to XX BarG |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7390 | Hydrotest witness inspection |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7400 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7410 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7420 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7430 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7440 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7450 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
Regeneration Gas C4 Hydrogenation Tag # IP-B-B3-M3-L-3390 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7120 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7130 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7140 | Removal of insulation & Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7150 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7160 | Cut old piping (existing line 81142), haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7170 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7180 | Full welding of joints & installation of Tie-In spool 81184 |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7190 | Inspection NDT / RT of selected joints & Additional Testing of Tie-in Valve |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7200 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7210 | Prepare and hydrotest up to XX BarG (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7220 | Hydrotest witness inspection (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7230 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7240 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7250 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7260 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7270 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7280 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
50AT-14101A sample tap Tag # IP-B-B3-M3-L-3430 |  |  |  | 15-Apr-25 A | 20-May-25 A | 0
A6950 | Start of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
A6960 | Obtain Work Permit |  |  | 15-Apr-25 A | 20-May-25 A | 0
A6970 | Removal of insulation & Wallthickness measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A6980 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 15-Apr-25 A | 20-May-25 A | 0
A6990 | Cut old piping & support, haul to ground level |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7000 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7010 | Full welding of joints including weldolet & installation of Tie-In spool |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7020 | Inspection NDT / RT of selected joints |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7030 | Install pipe supports (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7040 | Prepare and hydrotest up to XX BarG (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7050 | Hydrotest witness inspection (if required) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7060 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7070 | Touch-up painting works |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7080 | Deblinding, remove temporary support / scaffolds |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7090 | Reinstall insulation (if any) |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7100 | Torquing / flange management & hand-over to Ops |  |  | 15-Apr-25 A | 20-May-25 A | 0
A7110 | End of Work |  |  | 15-Apr-25 A | 20-May-25 A | 0
Regeneration Gas C4 Hydrogenation vent point Tag # P-B-B3-M3-L-3500 |  |  |  | 29-Mar-25 A | 17-May-25 A | 0
A38070 | Install pipe supports (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A38080 | Prepare and hydrotest up to XX BarG (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A38090 | Hydrotest witness inspection (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6780 | Start of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6790 | Obtain Work Permit |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6800 | Removal of Insulation & Wallthickness measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6810 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6820 | Cut old piping (existing line 81142), haul to ground level |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6830 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6840 | Welding of 8x1" weldolet and flange with valve and instrument |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6850 | Inspection NDT / RT of selected joints |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6890 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6900 | Touch-up painting works |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6910 | Deblinding, remove temporary support / scaffolds |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6920 | Reinstall insulation (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6930 | Torquing / flange management & hand-over to Ops |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6940 | End of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
Sample point in Regeneration gas cooler outlet Tag # IP-B-B3-M3-L-3510 |  |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6610 | Start of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6620 | Obtain Work Permit |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6630 | Wallthickness measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6640 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6650 | Cut old piping (existing line 140024), haul to ground level |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6660 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6670 | Welding of 20x1" weldolet and flange with valve and instrument 50S-14161L |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6680 | Inspection NDT / RT of selected joints |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6690 | Install pipe supports (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6700 | Prepare and hydrotest up to XX BarG (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6710 | Hydrotest witness inspection (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6720 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6730 | Touch-up painting works |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6740 | Deblinding, remove temporary support / scaffolds |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6750 | Reinstall insulation (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6760 | Torquing / flange management & hand-over to Ops |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6770 | End of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
Reinforced Branch connection for WG flare (Installation of 5 Tie Ins) Tag # IP-B-B3-M3-L-3520 |  |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6440 | Start of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6450 | Obtain Work Permit |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6460 | Wallthickness measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6470 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6480 | Cut old piping (existing line 140301), haul to ground level |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6490 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6500 | Full welding of joints (tie in Tee piece, than the tie in spools) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6510 | Inspection NDT / RT of selected joints |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6520 | Install pipe supports (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6530 | Prepare and hydrotest up to XX BarG (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6540 | Hydrotest witness inspection (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6550 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6560 | Touch-up painting works |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6570 | Deblinding, remove temporary support / scaffolds |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6580 | Reinstall insulation (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6590 | Torquing / flange management & hand-over to Ops |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6600 | End of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
Reinforced Branch connection pipe specification break for WG flare Tag # P-B-B3-M3-L-3530 |  |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6270 | Start of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6280 | Obtain Work Permit |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6290 | Wallthickness measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6300 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6310 | Cut old piping (existing line 140301), haul to ground level |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6320 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6330 | Full welding of joints |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6340 | Inspection NDT / RT of selected joints |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6350 | Install pipe supports (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6360 | Prepare and hydrotest up to XX BarG (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6370 | Hydrotest witness inspection (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6380 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6390 | Touch-up painting works |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6400 | Deblinding, remove temporary support / scaffolds |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6410 | Reinstall insulation (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6420 | Torquing / flange management & hand-over to Ops |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6430 | End of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
PSA2 Off Gas from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2022 |  |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6100 | Start of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6110 | Obtain Work Permit |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6120 | Removal of insulation & Wallthickness measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6130 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6140 | Cut old piping (existing line 45024) , haul to ground level |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6150 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6160 | Full welding of joints, Tee & installation of Tie-In spool 72069 |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6170 | Inspection NDT / RT of selected joints |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6180 | Install pipe supports (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6190 | Prepare and hydrotest up to XX BarG (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6200 | Hydrotest witness inspection (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6210 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6220 | Touch-up painting works |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6230 | Deblinding, remove temporary support / scaffolds |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6240 | Reinstall insulation (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6250 | Torquing / flange management & hand-over to Ops |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6260 | End of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
Process Water from EU3 H2 to EU3 Tie In Point Tag # IP-B-H3-B3-L-2042 |  |  |  | 29-Mar-25 A | 17-May-25 A | 0
A5930 | Start of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
A5940 | Obtain Work Permit |  |  | 29-Mar-25 A | 17-May-25 A | 0
A5950 | Wallthickness measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A5960 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 29-Mar-25 A | 17-May-25 A | 0
A5970 | Cut old piping (existing line 20002), haul to ground level |  |  | 29-Mar-25 A | 17-May-25 A | 0
A5980 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 29-Mar-25 A | 17-May-25 A | 0
A5990 | Welding of Tie-in spool weldolet |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6000 | Inspection NDT / RT of selected joints |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6010 | Install pipe supports (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6020 | Prepare and hydrotest up to XX BarG (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6030 | Hydrotest witness inspection (if required) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6050 | Touch-up painting works |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6060 | Deblinding, remove temporary support / scaffolds |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6070 | Reinstall insulation (if any) |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6080 | Torquing / flange management & hand-over to Ops |  |  | 29-Mar-25 A | 17-May-25 A | 0
A6090 | End of Work |  |  | 29-Mar-25 A | 17-May-25 A | 0
Warm Liquid Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2052 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5760 | Start of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5770 | Obtain Work Permit |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5780 | Wallthickness measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5790 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5800 | Cut old piping (existing line 140301), haul to ground level |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5810 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5820 | Full welding of joints & installation of Tie-In spool 140382 |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5830 | Inspection NDT / RT of selected joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5840 | Install pipe supports (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5850 | Prepare and hydrotest up to XX BarG |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5860 | Hydrotest witness inspection |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5870 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5880 | Touch-up painting works |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5890 | Deblinding, remove temporary support / scaffolds |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5900 | Reinstall insulation (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5910 | Torquing / flange management & hand-over to Ops |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5920 | End of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
Warm Gas Flare from EU3 to EU3 Tie In point Tag # IP-B-H3-B3-L-2062 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5590 | Start of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5600 | Obtain Work Permit |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5610 | Wallthickness measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5620 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5630 | Cut old piping (existing line 140301), haul to ground level |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5640 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5650 | Full welding of joints & installation of Tie-In spool 140381 |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5660 | Inspection NDT / RT of selected joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5670 | Install pipe supports (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5680 | Prepare and hydrotest up to XX BarG |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5690 | Hydrotest witness inspection |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5700 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5710 | Touch-up painting works |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5720 | Deblinding, remove temporary support / scaffolds |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5730 | Reinstall insulation (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5740 | Torquing / flange management & hand-over to Ops |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5750 | End of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
LP Condensate from EU3 H2 to EU3 Tie In point Tag # IP-B-H3-B3-L-2072 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5420 | Start of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5430 | Obtain Work Permit |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5440 | Removal of insulation & Wallthickness measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5450 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5460 | Cut old piping (existing line 140101), haul to ground level |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5470 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5480 | Full welding of joints including weldolet & installation of Tie-In spool 140434 |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5490 | Inspection NDT / RT of selected joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5500 | Install pipe supports (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5510 | Prepare and hydrotest up to XX BarG (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5520 | Hydrotest witness inspection (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5530 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5540 | Touch-up painting works |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5550 | Deblinding, remove temporary support / scaffolds |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5560 | Reinstall insulation (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5570 | Torquing / flange management & hand-over to Ops |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5580 | End of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
Package 3 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
Cooling Water Return from EU3 H2 to U&O3 Tie In point Tag # IP-B-H3-U3-L-1101 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5250 | Start of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5260 | Obtain Work Permit |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5270 | Wall thickness measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5280 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5290 | Cut old piping (existing line '00018), haul to ground level |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5300 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5310 | Full welding of joints including weldolet & installation of Tie-In spool 00215 |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5320 | Inspection NDT / RT of selected joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5330 | Install pipe supports (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5340 | Prepare and hydrotest up to XX BarG (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5350 | Hydrotest witness inspection (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5360 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5370 | Touch-up painting works |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5380 | Deblinding, remove temporary support / scaffolds |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5390 | Reinstall insulation (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5400 | Torquing / flange management & hand-over to Ops |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5410 | End of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
PSA2 Off Gas Recycle to CGC Tag # IP-B-M3-B3-L-3040 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
A38010 | Install pipe supports (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A38020 | Prepare and hydrotest up to XX BarG (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A38030 | Hydrotest witness inspection (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A38040 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A38050 | Touch-up painting works |  |  | 02-Apr-25 A | 17-May-25 A | 0
A38060 | Deblinding, remove temporary support / scaffolds |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5080 | Start of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5090 | Obtain Work Permit |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5100 | Removal of insulation & Wall thickness measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5110 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5120 | Cut old piping & support, haul to ground level |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5130 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5140 | Full welding of weldolet & installation of Tie-In spool 72068 |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5150 | Inspection NDT / RT of selected joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5220 | Reinstall insulation (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5230 | Torquing / flange management & hand-over to Ops |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5240 | End of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
Regeneration Gas from 50-HE-1410 to 50-VV-1401 Tag # IP-B-M3-B3-L-3070 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4910 | Start of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4920 | Obtain Work Permit |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4930 | Removal of insulation & Wall thickness measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4940 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4950 | Cut old piping (existing line 45024), haul to ground level |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4960 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4970 | Full welding of joints & installation of Tie-In spool 140489 |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4980 | Inspection NDT / RT of selected joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4990 | Install pipe supports (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5000 | Prepare and hydrotest up to XX BarG (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5010 | Hydrotest witness inspection (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5020 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5030 | Touch-up painting works |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5040 | Deblinding, remove temporary support / scaffolds |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5050 | Reinstall insulation (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5060 | Torquing / flange management & hand-over to Ops |  |  | 02-Apr-25 A | 17-May-25 A | 0
A5070 | End of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
Regeneration Gas to 50-VV-1401 Tag # IP-B-M3-B3-L-3110 |  |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4740 | Start of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4750 | Obtain Work Permit |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4760 | Wall thickness measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4770 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4780 | Cut old piping (existing line 140025) , haul to ground level |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4790 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4800 | Full welding of joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4810 | Inspection NDT / RT of selected joints |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4820 | Install pipe supports (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4830 | Prepare and hydrotest up to XX BarG (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4840 | Hydrotest witness inspection (if required) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4850 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4860 | Touch-up painting works |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4870 | Deblinding, remove temporary support / scaffolds |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4880 | Reinstall insulation (if any) |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4890 | Torquing / flange management & hand-over to Ops |  |  | 02-Apr-25 A | 17-May-25 A | 0
A4900 | End of Work |  |  | 02-Apr-25 A | 17-May-25 A | 0
Cooling Water from 50-HE-1410 to EU3 Tie-In Point Tag # IP-B-M3-B3-L-3130 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4570 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4580 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4590 | Wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4600 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4610 | Cut old piping (existing line 140034) & support, haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4620 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4630 | Full welding of joints & installation of Tie-In spool 140065 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4640 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4650 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4660 | Prepare and hydrotest up to XX BarG (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4670 | Hydrotest witness inspection (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4680 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4690 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4700 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4710 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4720 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4730 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
Warm Gas Flare from 50-HE-1410 to EU3 Tie In Point Tag # IP-B-M3-B3-L-3140 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4400 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4410 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4420 | Wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4430 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4440 | Cut old piping (existing line 140301), haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4450 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4460 | Full welding of joints & installation of Tie-In spool 140379 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4470 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4480 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4490 | Prepare and hydrotest up to XX BarG (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4500 | Hydrotest witness inspection (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4510 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4520 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4530 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4540 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4550 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4560 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
Treated VHP BFW from 52-HE-1402 to EU3 Tag # IP-B-M3-B3-L-3220 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4230 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4240 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4250 | Removal of insulation and wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4260 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4270 | Cut old piping (existing line 140025) & support, haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4280 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4290 | Full welding of joints (Tee-piece) & installation of Tie-In spool 140218 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4300 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4310 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4320 | Prepare and hydrotest up to XX BarG (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4330 | Hydrotest witness inspection (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4340 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4350 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4360 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4370 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4380 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4390 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
LP- Condensate from 52-HE-1402 to 54-VV-1402 Tag # IP-B-M3-B3-L-3240 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4060 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4070 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4080 | Removal of insulation |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4090 | Removal of blind flange 54-VV-1402, N02 & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4100 | Check of cleanliness of vessel and new pipe |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4110 | Connection of tie in spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4190 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4200 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4210 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4220 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
Tailgas to 50-VV-1401 Tag # IP-B-M3-B3-L-3250 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A38000 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3890 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3900 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3910 | Removal of insulation and wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3920 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3930 | Cut old piping (existing line 45024), haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3940 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3950 | Full welding of joints & installation of Tie-In spool 45024 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3960 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3970 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3980 | Prepare and hydrotest up to XX BarG (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3990 | Hydrotest witness inspection (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4000 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4010 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4020 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4030 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A4040 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
Regeneration Gas C4 Hydrogenation to 50-HE-1402 Tag # IP-B-M3-B3-L-3280 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3720 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3730 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3740 | Removal of insulation and wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3750 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3760 | Cut old piping (existing line 41022), haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3770 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3780 | Full welding of joints & installation of Tie-In spool 81142 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3790 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3800 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3810 | Prepare and hydrotest up to XX BarG (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3820 | Hydrotest witness inspection (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3830 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3840 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3850 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3860 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3870 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3880 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
Regeneration Gas C4 Hydrogenation Condensate Tag # IP-B-M3-B3-L-3290 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3550 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3570 | Wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3600 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3610 | Full welding of joints & installation of Tie-In spool 140066 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3620 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3630 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3640 | Prepare and hydrotest up to XX BarG (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3650 | Hydrotest witness inspection (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3660 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3670 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3680 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3690 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3700 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3710 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37970 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37980 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37990 | Cut old piping (existing line 140028) , haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
Warm Gas Flare from 13-KX-402/50-HE-1402 to EU3 Tie In Point Tag # P-B-M3-B3-L-3300 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3390 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3540 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37820 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37830 | Wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37840 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37850 | Cut old piping (existing line 140301) , haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37860 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37870 | Full welding of joints & installation of Tie-In spool 140301 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37880 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37890 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37900 | Prepare and hydrotest up to XX BarG |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37910 | Hydrotest witness inspection |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37920 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37930 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37940 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37950 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37960 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
Cold Gas from 13-PSV-4508 to EU3 Tie In Tag # P-B-M3-B3-L-3410 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3210 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3220 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3230 | Wall thickness measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3240 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3260 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3270 | Purge with 24" balloons & welding of Tie-In spool 144564 |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3280 | Inspection NDT / RT of selected joints |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3290 | Install pipe supports (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3300 | Prepare and hydrotest up to XX BarG (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3310 | Hydrotest witness inspection (if required) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3320 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3330 | Touch-up painting works |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3340 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3360 | Torquing / flange management & hand-over to Ops |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3370 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37800 | Cut old piping (existing line 140321) & support, haul to ground level |  |  | 10-Apr-25 A | 17-May-25 A | 0
A37810 | Reinstall insulation (if any) |  |  | 10-Apr-25 A | 17-May-25 A | 0
Package 4 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
50AT-14101A sample tap vent return to process Tag # IP-B-M3-B3-L-3420 |  |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3040 | Start of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3050 | Obtain Work Permit |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3060 | Gas measurement |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3070 | Making tubing connection |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3170 | Deblinding, remove temporary support / scaffolds |  |  | 10-Apr-25 A | 17-May-25 A | 0
A3200 | End of Work |  |  | 10-Apr-25 A | 17-May-25 A | 0
Instrument Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1020 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2870 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2880 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A3030 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
Plant Air from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1030 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2700 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2710 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2860 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
Nitrogen from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1040 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2530 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2540 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2690 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
LP Steam from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1050 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2360 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2370 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2380 | Wall thickness measurement |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2390 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2400 | Cut old piping (existing line 00271) & support, haul to ground level |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2410 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2420 | Full welding of joints & Installation of Tie-In spool '0005 |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2430 | Inspection NDT / RT of selected joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2440 | Install pipe supports (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2450 | Prepare and hydrotest up to XX BarG |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2460 | Hydrotest witness inspection |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2470 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2480 | Touch-up painting works |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2490 | Deblinding, remove temporary support / scaffolds |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2500 | Reinstall insulation (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2510 | Torquing / flange management & hand-over to Ops |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2520 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
Service water from U&O3 Tie In point to to EU3 H2 Tag # IP-B-U3-H3-L-1060 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2190 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2200 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2210 | Removal of insulation and wall thickness measurement |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2220 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2230 | Cut old piping (existing line '00061) & support, haul to ground level |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2240 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2250 | Full welding of joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2260 | Inspection NDT / RT of selected joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2270 | Install pipe supports (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2280 | Prepare and hydrotest up to XX BarG |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2290 | Hydrotest witness inspection |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2300 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2310 | Touch-up painting works |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2320 | Deblinding, remove temporary support / scaffolds |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2330 | Reinstall insulation (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2340 | Torquing / flange management & hand-over to Ops |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2350 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
Potable water from U&O3 Tie In point to EU3 H2 Tag # IP-B-U3-H3-L-1070 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2020 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2030 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2040 | Wall thickness measurement |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2050 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2060 | Cut old piping & support, haul to ground level |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2070 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2080 | Full welding of joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2090 | Inspection NDT / RT of selected joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2100 | Install pipe supports (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2110 | Prepare and hydrotest up to XX BarG |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2120 | Hydrotest witness inspection |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2130 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2140 | Touch-up painting works |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2150 | Deblinding, remove temporary support / scaffolds |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2160 | Reinstall insulation (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2170 | Torquing / flange management & hand-over to Ops |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2180 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
Cooling Water Supply from U&O3 Tie In Point to EU3 H2 Tag # P-B-U3-H3-L-1090 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1340 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1350 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1360 | Removal of insulation (if any) & measurement of wall thickness |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1370 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1380 | Cut old piping (existing line '00234) & support, haul to ground level |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1390 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1400 | Welding of weldolet |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1410 | Inspection NDT / RT of selected joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1420 | Install pipe supports (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1430 | Prepare and hydrotest up to XX BarG (if required) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1440 | Hydrotest witness inspection (if required) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1450 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1460 | Touch-up painting works (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1470 | Deblinding, remove temporary support / scaffolds |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1480 | Reinstall insulation (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1490 | Torquing / flange management & hand-over to Ops |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37650 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
Oily water from EU3 H2 to U&O3 Tie In point Tag # IP-B-U3-H3-L-1121 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1210 | Cut old piping (existing line '00018), haul to ground level |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1220 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1230 | Full welding of joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1280 | Reinstall back piping components (TW/TE, TG, PT, PG if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1290 | Touch-up painting works |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1300 | Deblinding, remove temporary support / scaffolds |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1310 | Reinstall insulation (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1320 | Torquing / flange management & hand-over to Ops |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1330 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37570 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37580 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37590 | Removal of insulation & measurement of wall thickness |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37600 | Drilling one hole (cold drilling, air-driven) & Gas measurement |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37610 | Inspection NDT / RT of selected joints |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37620 | Install pipe supports (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37630 | Prepare and hydrotest up to XX BarG (if required) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A37640 | Hydrotest witness inspection (if required) |  |  | 08-Apr-25 A | 17-May-25 A | 0
TA Tie-In Execution - U/G Tie-Ins |  |  |  | 03-Apr-25 A | 17-May-25 A | 0
Package 4 |  |  |  | 03-Apr-25 A | 17-May-25 A | 0
Fire Water from U&O3 Tie point to EU3 H2 (South west) Tag # IP-B-U3-H3-L-1080 |  |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1850 | Start of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1860 | Obtain Work Permit |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1870 | Install temporary support / scaffolds as site |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1880 | Install isolation balloon |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1980 | Deblinding, remove temporary support / scaffolds |  |  | 08-Apr-25 A | 17-May-25 A | 0
A1990 | Reinstall insulation (if any) |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2000 | Torquing / flange management & hand-over to Ops |  |  | 08-Apr-25 A | 17-May-25 A | 0
A2010 | End of Work |  |  | 08-Apr-25 A | 17-May-25 A | 0
Fire Water from U&O3 Tie point to EU3 H2 (south east) Tag # IP-B-U3-H3-L-1082 |  |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1680 | Start of Work |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1690 | Obtain Work Permit |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1700 | Removal of insulation & wall thickness measurement |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1710 | Drilling one hole (cold drilling, airdriven) & Gas measurement |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1720 | Cut old piping & support, haul to ground level |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1730 | Grinding, bevelling of old piping & fit-up with new spool |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1740 | Full welding of joints |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1750 | Inspection NDT / RT of selected joints |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1760 | Install pipe supports (if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1770 | Prepare and hydrotest up to XX BarG |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1780 | Hydrotest witness inspection |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1790 | Reinstall back piping components (TW/TE, TG, PT, PG if a ny) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1800 | Touch-up painting works |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1810 | Deblinding, remove temporary support / scaffolds |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1820 | Reinstall insulation (if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1830 | Torquing / flange management & hand-over to Ops |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1840 | End of Work |  |  | 03-Apr-25 A | 17-May-25 A | 0
Fire Water from U&O3 Tie point to EU3 H2 (North east) Tag # IP-B-U3-H3-L-1086 |  |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1520 | Obtain Work Permit |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1530 | Install temporary support / scaffolds as site |  |  | 03-Apr-25 A | 17-May-25 A | 0
A1670 | End of Work |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37660 | Start of Work |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37670 | Pull-out piping components (Valves, TW/TE, TG, PT, PG if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37680 | Cut old piping (20" HDPE Line), haul to ground level |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37690 | Grinding, bevelling of old piping & fit-up with new spool (new HDPE TEE) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37700 | Installation, alignment and welding of HDPE Tee to existing header 18011 & install. of tie-in spools 18481 & welding |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37710 | Inspection (all required HDPE welding examinations) of selected joints |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37720 | Install pipe supports (if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37730 | Prepare and hydrotest up to XX BarG (if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37740 | Hydrotest witness inspection (if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37750 | Reinstall back piping components (TW/TE, TG, PT, PG if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37760 | Touch-up painting works |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37770 | Deblinding, remove temporary support / scaffolds |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37780 | Reinstall insulation (if any) |  |  | 03-Apr-25 A | 17-May-25 A | 0
A37790 | Torquing / flange management & hand-over to Ops |  |  | 03-Apr-25 A | 17-May-25 A | 0
GF Piping Works |  | 2027-01-26 | 2027-03-11 | 2026-03-02 | 2027-01-26 | 283
AG |  | 2027-01-26 | 2027-03-11 | 2026-03-02 | 2027-01-26 | 283
A3380 | Piping Eection at Site | 2026-10-21 | 2026-11-15 | 2026-06-03 | 2026-10-21 | 120
A3400 | Painting Piping - Fabrication Shop | 2026-08-24 | 2026-09-17 | 2026-04-29 | 2026-08-24 | 100
A3410 | Piping Insulation | 2027-01-26 | 2027-03-11 | 2026-10-18 | 2027-01-26 | 86
A3420 | Final Touch up and painting of joints | 2026-11-24 | 2027-01-07 | 2026-10-10 | 2026-11-24 | 38
A3430 | Hydro testing and reinstatment | 2026-11-25 | 2027-01-09 | 2026-09-28 | 2026-11-25 | 50
A60800 | Piping - Pre-Fabrication Shop | 2026-07-20 | 2026-08-13 | 2026-03-02 | 2026-07-20 | 120
UG |  | 2026-12-03 | 2027-01-20 | 2026-06-21 | 2026-12-03 | 142
A23540 | Piping Erection of Fire water piping (HDPE) UG including hydrotesting | 2026-12-03 | 2027-01-20 | 2026-07-18 | 2026-12-03 | 120
A3470 | U/G Piping Erection & Hydrotesting Cooling Water Lines (CS) | 2026-10-15 | 2026-12-09 | 2026-06-21 | 2026-10-15 | 100
A3480 | U/G Piping Erection Oily Water (CS) | 2026-08-09 | 2027-01-20 | 2026-07-15 | 2026-08-09 | 21
Testing | [5 empty] | 0
BF Piping Testing | [5 empty] | 0
Insulation |  | 2026-12-12 | 2027-01-20 | 2026-10-21 | 2026-12-12 | 45
A3580 | Complete Insulation, Fire-Proofing and Painting works | 2026-12-12 | 2027-01-20 | 2026-10-21 | 2026-12-12 | 45
Painting |  | 2027-01-13 | 2027-07-15 | 2026-09-23 | 2027-01-13 | 96
A61630 | Painting | 2027-01-13 | 2027-07-15 | 2026-09-23 | 2027-01-13 | 96
Others |  | 2027-01-18 | 2027-07-20 | 2027-01-13 | 2027-01-18 | 4
A61640 | Painting punch clearing | 2027-01-18 | 2027-07-20 | 2027-01-13 | 2027-01-18 | 4
Electrical Construction |  | 2026-12-27 | 2027-01-20 | 01-Mar-25 A | 2026-12-27 | 161
Equipment Installation |  | 2026-12-27 | 2027-01-20 | 03-Apr-25 A | 2026-12-27 | 161
System and Panels Installation |  | 2026-09-10 | 2027-01-20 | 2026-07-18 | 2026-09-10 | 48
A61650 | System and Panels Installations | 2026-09-10 | 2027-01-20 | 2026-07-18 | 2026-09-10 | 48
GF Interposing Relay Panel |  | 2026-11-09 | 2027-01-20 | 2026-09-10 | 2026-11-09 | 51
A24070 | Installation of Interposting Relay Panel | 2026-09-24 | 2026-12-06 | 2026-09-10 | 2026-09-24 | 12
A24580 | Cable terminations and loop testing - IRP | 2026-10-19 | 2026-12-30 | 2026-09-24 | 2026-10-19 | 21
A24790 | IRP - Pre Comm | 2026-11-09 | 2027-01-20 | 2026-10-19 | 2026-11-09 | 18
GF DG Set |  | 2026-10-24 | 2027-01-20 | 2026-08-08 | 2026-10-24 | 67
A24590 | Cable terminations and loop testing - DG Set | 2026-10-03 | 2026-12-30 | 2026-09-08 | 2026-10-03 | 22
A24800 | DG Set - Pre Comm | 2026-10-24 | 2027-01-20 | 2026-10-04 | 2026-10-24 | 18
A3829 | Installation of DG Set | 2026-09-07 | 2026-12-05 | 2026-08-08 | 2026-09-07 | 27
GF Electrical Heat Tracing (53 Meter for piping + 340 Meter for instrumentation) |  | 2026-07-15 | 2027-01-20 | 2026-05-04 | 2026-07-15 | 62
A24090 | Electrical Heat Tracing works | 2026-05-27 | 2026-12-02 | 2026-05-04 | 2026-05-27 | 20
A24410 | Cable terminations and loop testing - Electric Heat Tracing | 2026-06-24 | 2026-12-30 | 2026-05-27 | 2026-06-24 | 24
A24660 | Electric Heat Tracing - Pre Comm | 2026-07-15 | 2027-01-20 | 2026-06-24 | 2026-07-15 | 18
GF Power Transformers (Qty 05) |  | 2026-11-11 | 2027-01-20 | 2026-08-04 | 2026-11-11 | 86
A24120 | Installation of Power Transformers | 2026-09-23 | 2026-12-02 | 2026-08-04 | 2026-09-23 | 44
A24470 | Cable terminations and loop testing - Power Transformers | 2026-10-21 | 2026-12-30 | 2026-09-24 | 2026-10-21 | 24
A24680 | Power Transformers - Pre Comm | 2026-11-11 | 2027-01-20 | 2026-10-22 | 2026-11-11 | 18
GF HV Capacitor Bay |  | 2026-10-07 | 2027-01-20 | 2026-08-04 | 2026-10-07 | 56
A24080 | Installation of Capacitor Bay | 2026-08-24 | 2026-12-07 | 2026-08-04 | 2026-08-24 | 18
A24490 | Cable terminations and HV Capacitor Bay | 2026-09-17 | 2026-12-31 | 2026-08-25 | 2026-09-17 | 21
A24700 | HV Capacitor Bay - Pre Comm | 2026-10-07 | 2027-01-20 | 2026-09-19 | 2026-10-07 | 17
GF Switchgear (LV, MV) |  | 2026-11-05 | 2027-01-20 | 2026-08-04 | 2026-11-05 | 81
A24530 | Cable terminations and loop testing - Switchgear (LV, MV) | 2026-10-12 | 2026-12-27 | 2026-09-08 | 2026-10-12 | 30
A24740 | Switchgear (LV, MV) - Pre Comm | 2026-11-05 | 2027-01-20 | 2026-10-13 | 2026-11-05 | 21
A3839 | Installation of Switchgear | 2026-09-07 | 2026-11-22 | 2026-08-04 | 2026-09-07 | 30
GF Variable Fequency Drives (VFDs) LV Qty = 03 |  | 2026-11-04 | 2027-01-20 | 2026-08-04 | 2026-11-04 | 80
A24140 | Installation of VFD | 2026-08-31 | 2026-11-16 | 2026-08-04 | 2026-08-31 | 24
A24540 | Cable terminations and loop testing - VFD | 2026-10-07 | 2026-12-23 | 2026-09-01 | 2026-10-07 | 32
A24750 | VFDs - Pre Comm | 2026-11-04 | 2027-01-20 | 2026-10-08 | 2026-11-04 | 24
GF NGR Panel Qty 02 |  | 2026-09-30 | 2027-01-20 | 2026-08-04 | 2026-09-30 | 50
A24570 | Cable terminations and loop testing NGR Panel | 2026-09-10 | 2026-12-31 | 2026-08-18 | 2026-09-10 | 21
A24780 | NGR Panel - Pre Comm | 2026-09-30 | 2027-01-20 | 2026-09-12 | 2026-09-30 | 17
A3869 | Installation of NGR Panel | 2026-08-17 | 2026-12-07 | 2026-08-04 | 2026-08-17 | 12
GF Cathodic Protection (CP) Total CS Piping Length - 499 Meters |  | 2026-12-27 | 2027-01-20 | 2026-10-01 | 2026-12-27 | 74
A24100 | Cathodic Protection for complete CS Piping | 2026-11-08 | 2026-12-02 | 2026-10-01 | 2026-11-08 | 32
A24420 | Cable terminations and loop testing - Cathodic Protection | 2026-12-06 | 2026-12-30 | 2026-11-08 | 2026-12-06 | 24
A24670 | Cathodic Protection - Pre Comm | 2026-12-27 | 2027-01-20 | 2026-12-06 | 2026-12-27 | 18
GF UPS (AC - 60 KVA, 20 KVA, DC-UPS 6.5 KVA) Qty 1+1+1 = 03 Nos |  | 2026-10-14 | 2027-01-20 | 2026-08-04 | 2026-10-14 | 62
A24060 | Installation of UPS | 2026-08-31 | 2026-12-07 | 2026-08-04 | 2026-08-31 | 24
A24450 | Cable terminations and loop testing - UPS | 2026-09-23 | 2026-12-30 | 2026-09-01 | 2026-09-23 | 20
A24640 | UPS - Pre Comm | 2026-10-14 | 2027-01-20 | 2026-09-24 | 2026-10-14 | 18
TA IPCS Modification by ABB |  |  |  | 03-Apr-25 A | 10-May-25 A | 0
A34830 | Installation of FOPP (02 )in existing CCB |  |  | 03-Apr-25 A | 10-May-25 A | 0
TA Switchgear Modification by SIEMENS |  |  |  | 03-Apr-25 A | 10-May-25 A | 0
A17970 | Bus-bar differential testing Bus-A - feeder H01 (TA) |  |  | 03-Apr-25 A | 10-May-25 A | 0
A17980 | Bus-bar differential testing Bus-B - feeder H16 (TA) |  |  | 03-Apr-25 A | 10-May-25 A | 0
A34440 | Switchgear Modifications - Siemens |  |  | 03-Apr-25 A | 10-May-25 A | 0
A34800 | Installation of Surge Arersstor |  |  | 03-Apr-25 A | 10-May-25 A | 0
A34810 | Installation of Dummy Plugs |  |  | 03-Apr-25 A | 10-May-25 A | 0
A34820 | Installation of Castle key interlock and key exchange box |  |  | 03-Apr-25 A | 10-May-25 A | 0
TA SCMS Modification by SIEMENS |  |  |  | 14-Apr-25 A | 14-May-25 A | 0
A17990 | SCMS FOPP Modifications - Siemens (By Client) |  |  | 14-Apr-25 A | 25-Apr-25 A | 0
A34780 | Mapping of SCMS in IPCS |  |  | 26-Apr-25 A | 30-Apr-25 A | 0
A34840 | Annuciator Panel Modification |  |  | 01-May-25 A | 09-May-25 A | 0
A34850 | HMI Graphics Update |  |  | 10-May-25 A | 14-May-25 A | 0
TA UPS Modification |  |  |  | 15-Apr-25 A | 13-May-25 A | 0
A17960 | Modification in DC power supply arrangmeent- UPS |  |  | 15-Apr-25 A | 13-May-25 A | 0
Cabling Work |  | 2026-10-12 | 2027-01-20 | 2026-06-27 | 2026-10-12 | 92
BF Electrical Works |  | 2026-10-12 | 2027-01-20 | 2026-06-27 | 2026-10-12 | 92
A17740 | Power Cables Laying | 2026-08-08 | 2026-11-16 | 2026-06-27 | 2026-08-08 | 36
A18740 | Termination of Power cables and Loop Testing | 2026-09-07 | 2026-12-16 | 2026-08-08 | 2026-09-07 | 26
A18750 | FO Cable laying for IPCSS and SCMS | 2026-08-08 | 2026-11-25 | 2026-06-27 | 2026-08-08 | 36
A21980 | FO Cable termination for IPCSS and SCMS | 2026-09-19 | 2026-12-28 | 2026-08-19 | 2026-09-19 | 26
BFW4080 | Other Electrical Works | 2026-10-12 | 2027-01-20 | 2026-09-19 | 2026-10-12 | 20
Earthing System Installation |  | 2026-10-22 | 2027-01-20 | 2026-07-30 | 2026-10-22 | 72
A61660 | Earthing System Installation | 2026-10-08 | 2027-01-06 | 2026-07-30 | 2026-10-08 | 60
A61670 | Earthing System Testing | 2026-10-22 | 2027-01-20 | 2026-10-08 | 2026-10-22 | 12
Lightning System Installation |  | 2026-09-13 | 2027-01-20 | 2026-08-26 | 2026-09-13 | 15
GF Lighting Fixtures (Almost 50% Exd = 354 Nos) |  | 2026-09-13 | 2027-01-20 | 2026-08-26 | 2026-09-13 | 15
A3590 | Complete Street lighting | 2026-09-13 | 2027-01-20 | 2026-08-26 | 2026-09-13 | 15
Testing | [5 empty] | 0
Others |  |  |  | 01-Mar-25 A | 15-Mar-25 A | 0
TA Site Survey AC & DC UPS(Chloride Terchnology) |  |  |  | 01-Mar-25 A | 15-Mar-25 A | 0
A35010 | Site Survey for UPS Modification |  |  | 01-Mar-25 A | 07-Mar-25 A | 0
A37540 | Site Survey Report for UPS Modification |  |  | 08-Mar-25 A | 15-Mar-25 A | 0
TA Site Survey MCMS System (Bently Nevada) |  |  |  | 01-Mar-25 A | 15-Mar-25 A | 0
A35020 | Site Survey for MCMS Modification |  |  | 01-Mar-25 A | 07-Mar-25 A | 0
A37550 | Site Survey Report for MCMS Modification |  |  | 08-Mar-25 A | 15-Mar-25 A | 0
For Switchgear & SCMS(Siemens) |  |  |  | 01-Mar-25 A | 15-Mar-25 A | 0
A34980 | Site Survey for SG & SCMS Modification |  |  | 01-Mar-25 A | 07-Mar-25 A | 0
A35140 | Health Check / Site Survey Report |  |  | 08-Mar-25 A | 15-Mar-25 A | 0
Instrumentation/Telecom Construction |  | 2026-12-05 | 2027-01-20 | 11-Feb-25 A | 2026-12-05 | 232
MCMS/DCS/ESD/F&G Modification / Installation (as applicable) |  | 2026-11-23 | 2027-01-20 | 01-May-25 A | 2026-11-23 | 105
GF Fire Fighting Equipment |  | 2026-10-25 | 2027-01-20 | 2026-08-04 | 2026-10-25 | 71
A24400 | Cable terminations and loop testing - Fire Fighting Equipment | 2026-10-04 | 2026-12-30 | 2026-09-15 | 2026-10-04 | 17
A24610 | Fire Fighting Equip - Pre Comm | 2026-10-25 | 2027-01-20 | 2026-10-05 | 2026-10-25 | 18
A3849 | Installation of Fire Fighting Equipment | 2026-09-14 | 2026-12-10 | 2026-08-04 | 2026-09-14 | 36
BF DCS/ESD Modification by Honeywell |  | 2026-08-06 | 2026-11-30 | 2026-06-27 | 2026-08-06 | 35
A17750 | DCS modification for integration between brownfield and greenfield | 2026-08-06 | 2026-11-30 | 2026-06-27 | 2026-08-06 | 35
GF Fire Detection Alarm System, Local Fire Control Panel & Clean Agent Unit |  | 2026-11-16 | 2027-01-20 | 2026-08-04 | 2026-11-16 | 90
A24110 | Installation of Fire Detection Alarm System, LFCP and Clean Agent Unit | 2026-09-14 | 2026-11-18 | 2026-08-04 | 2026-09-14 | 36
A24460 | Cable terminations and loop testing - FDAS, LFCP and Clean Agent Unit | 2026-10-19 | 2026-12-23 | 2026-09-15 | 2026-10-19 | 30
A24650 | FDAS, LFCP & CAU - Pre Comm | 2026-11-16 | 2027-01-20 | 2026-10-20 | 2026-11-16 | 24
TA EU3 ICSS(DCS/ESD/GDS) Modifications by HONEYWELL |  |  |  | 01-May-25 A | 15-May-25 A | 0
A21970 | Cross wiring between existing marshalling racks ( Instrument Tie-in No 6,7) |  |  | 01-May-25 A | 15-May-25 A | 0
A34910 | Installation of New Non-IS ESD Cabinet (83-JM3021-D) (Intrument Tie-In-8) |  |  | 01-May-25 A | 15-May-25 A | 0
A34920 | Non-UPS Power &earthing for New Non-IS ESD Cabinet (Intrument Tie-In- 9) |  |  | 01-May-25 A | 15-May-25 A | 0
A34930 | (OEM) Vendor (Honeywell) loose supplied (Intrument Tie-In- 9.1) |  |  | 01-May-25 A | 15-May-25 A | 0
A34940 | COLD Section ESD shutdown console switches (Intrument Tie-In- 11) |  |  | 01-May-25 A | 15-May-25 A | 0
A34950 | OEM) Vendor loose supplied material installation Including Honeywell, Safetec (Instrument Tie-12) |  |  | 01-May-25 A | 15-May-25 A | 0
A34960 | Change in the Existing DCS configuration for BF added/ Modified Field Tag (Instrument TieIn-14) |  |  | 01-May-25 A | 15-May-25 A | 0
A34970 | Change in the Existing ESD configuration for BF added/ Modified Field Tag(Instrument TieIn-14.1) |  |  | 01-May-25 A | 15-May-25 A | 0
Branch Cable Laying (67 B/F - I/O +addl HW signal Exchange) | [5 empty] | 0
GF F&G Flame Detectors, MCP, Beacon (Nos 324) |  | 2026-11-23 | 2027-01-20 | 2026-09-02 | 2026-11-23 | 70
A24130 | Installation of F&G Detectors, MCP,Beacon | 2026-10-06 | 2026-12-03 | 2026-09-02 | 2026-10-06 | 29
A24500 | Cable terminations and loop testing - F&G Detectors, MCP, Beacon | 2026-11-02 | 2026-12-30 | 2026-10-06 | 2026-11-02 | 23
A24710 | F&G, MCP, Beacon - Pre Comm | 2026-11-23 | 2027-01-20 | 2026-11-02 | 2026-11-23 | 18
TA Fire Alarm System Modification by SAFCO+HONEYWELL |  |  |  | 15-May-25 A | 25-May-25 A | 0
A34740 | Existing Deluge Console switches shall be relocated including retesting of existing loops on new dual tier Console |  |  | 15-May-25 A | 25-May-25 A | 0
TA Modification in MCMS System by BENTLY NAVEDA |  |  |  | 01-May-25 A | 15-May-25 A | 0
A34710 | Existing MCMS system 1 will be upgraded with new EVO series servers for EU3 existing network |  |  | 01-May-25 A | 15-May-25 A | 0
Field Instrument Installation |  | 2026-12-05 | 2027-01-20 | 01-May-25 A | 2026-12-05 | 92
GF Machine Condition Monitoring System |  | 2026-10-28 | 2027-01-20 | 2026-08-04 | 2026-10-28 | 74
A24480 | Cable terminations and loop testing - MCMS | 2026-10-08 | 2026-12-31 | 2026-09-15 | 2026-10-08 | 21
A24690 | MCMS - Pre Comm | 2026-10-28 | 2027-01-20 | 2026-10-10 | 2026-10-28 | 17
A3789 | Installation of MCMS | 2026-09-14 | 2026-12-07 | 2026-08-04 | 2026-09-14 | 36
TA Replacement of Existing Air Distribution Pot |  |  |  | 01-May-25 A | 15-May-25 A | 0
A34860 | Replacoment of existing ADP (E3-SP-0146) from 6-ways to 10-ways (Intrument Tie-In- 1.1) |  |  | 01-May-25 A | 15-May-25 A | 0
A34870 | Replacoment of existing ADP (E3-SP-0322) from 6-ways to 10-ways (Intrument Tie-In- 1) |  |  | 01-May-25 A | 15-May-25 A | 0
A34880 | Replacoment of existing ADP (E3-SP-0149) from 6-ways to 10-ways (Intrument Tie-In- 2) |  |  | 01-May-25 A | 15-May-25 A | 0
GF Acess Control System |  | 2026-12-05 | 2027-01-20 | 2026-09-09 | 2026-12-05 | 74
A24430 | Cable terminations and loop testing - ACS | 2026-11-14 | 2026-12-30 | 2026-10-07 | 2026-11-14 | 32
A24620 | ACS - Pre Comm | 2026-12-05 | 2027-01-20 | 2026-11-14 | 2026-12-05 | 18
A3859 | Installation of Access Control System | 2026-10-07 | 2026-11-23 | 2026-09-09 | 2026-10-07 | 24
GF VESDA (Very Early Smoke Detection Apparatus) |  | 2026-10-21 | 2027-01-20 | 2026-08-04 | 2026-10-21 | 68
A24510 | Cable terminations and loop testing VESDA | 2026-09-30 | 2026-12-30 | 2026-09-05 | 2026-09-30 | 23
A24720 | VESDA - Pre Comm | 2026-10-21 | 2027-01-20 | 2026-10-01 | 2026-10-21 | 18
A3799 | Installation of VESDA | 2026-09-03 | 2026-12-03 | 2026-08-04 | 2026-09-03 | 27
GF MOVs [Ball Type 24" 150# = 01 No] |  | 2026-08-26 | 2027-01-20 | 2026-07-23 | 2026-08-26 | 29
A24160 | Installatrion of MOV | 2026-07-29 | 2026-12-20 | 2026-07-23 | 2026-07-29 | 5
A24550 | Cable terminations and lop termination - MOVs | 2026-08-12 | 2027-01-03 | 2026-07-29 | 2026-08-12 | 12
A24760 | MOVS - Pre Comm | 2026-08-26 | 2027-01-20 | 2026-08-12 | 2026-08-26 | 12
TA Compresoor CGC Turbine by MHI |  |  |  | 01-Sep-25 A | 10-Sep-25 A | 0
A21840 | Turbine Governor Software modification by MHI (Intrument Tie-In- 15) |  |  | 01-Sep-25 A | 10-Sep-25 A | 0
TA SGM Replacement (EMERSON) |  |  |  | 01-May-25 A | 15-May-25 A | 0
A34720 | Existing Gas density Meter to replaced by SGM (EMERSON) (Intrument Tie-In- 3) |  |  | 01-May-25 A | 15-May-25 A | 0
A34890 | SGM meter connection to nearest Power Distruribution Board (Intrument Tie-In- 3.1) |  |  | 01-May-25 A | 15-May-25 A | 0
A34900 | New Tubing for Votex cooling of sgm Cabinet SGM (EMERSON) ((Intrument Tie-In- 2) |  |  | 01-May-25 A | 15-May-25 A | 0
GF Integrated Control and Safety System GF |  | 2026-11-30 | 2027-01-20 | 2026-09-01 | 2026-11-30 | 77
A3729 | Installation of ICSS System | 2026-10-12 | 2026-12-02 | 2026-09-01 | 2026-10-12 | 35
A3879 | Cable terminations and loop testing ICSS - GF | 2026-11-05 | 2026-12-27 | 2026-10-12 | 2026-11-05 | 21
A3899 | ICSS - Pre Comm | 2026-11-30 | 2027-01-20 | 2026-11-05 | 2026-11-30 | 21
GF Gauges (PG, TG, PDG, Analzer, FE) PG - 10bar & 40bar = 19 Nos, DP = 05 Nos, TG = 09 Nos |  | 2026-11-28 | 2027-01-20 | 2026-09-13 | 2026-11-28 | 66
A24150 | Installation of Field Instruments | 2026-10-10 | 2026-12-02 | 2026-09-13 | 2026-10-10 | 24
A24560 | Cable terminations and loop testing - Gauges (PG, TG, PDG) | 2026-11-07 | 2026-12-30 | 2026-10-11 | 2026-11-07 | 24
A24770 | Guages (PG, TG, PDG) - Pre Comm (Calibration/Testing) | 2026-11-28 | 2027-01-20 | 2026-11-08 | 2026-11-28 | 18
TA Field Instrument Modification |  |  |  | 01-May-25 A | 15-May-25 A | 0
A21850 | Dp Flow Transmitters to be re-calibrated ( approx qty- 20 nos.) in existing EU3 plant area |  |  | 01-May-25 A | 15-May-25 A | 0
A21860 | Replacement of 13-PV-4515 and stroke calibration, loop Testing (Intrument Tie-In- 4) |  |  | 01-May-25 A | 15-May-25 A | 0
A34700 | Flow Element to be re-calibrated ( approx qty- 19 nos.) in existing EU3 plant area |  |  | 01-May-25 A | 15-May-25 A | 0
GF Integrated Protection Control System |  | 2026-12-03 | 2027-01-20 | 2026-08-29 | 2026-12-03 | 84
A24390 | Cable terminations and loop testing - IPCS | 2026-11-05 | 2026-12-23 | 2026-10-03 | 2026-11-05 | 30
A24600 | IPCS - Pre Comm | 2026-12-03 | 2027-01-20 | 2026-11-07 | 2026-12-03 | 24
A3769 | Installation of IPCS | 2026-10-01 | 2026-11-18 | 2026-08-29 | 2026-10-01 | 30
TA Instrumentation Work |  |  |  | 01-May-25 A | 15-May-25 A | 0
A18330 | Instrument Air Tubing from existing Spare ADP connections to new valves in Brown Field area- @ 7 nos. |  |  | 01-May-25 A | 15-May-25 A | 0
A23560 | Heath Check for ICSS Report |  |  | 01-May-25 A | 15-May-25 A | 0
Cabling work |  | 2026-11-18 | 2027-01-20 | 2025-12-27 | 2026-11-18 | 281
GF Cable Tray and Instrument Junction Box (Perforated Cable tray Heavy duty= 5982 Mtrs, JBs= 73 Nos) |  | 2026-11-18 | 2027-01-20 | 2026-07-29 | 2026-11-18 | 96
A61680 | GF Cable Tray and Junction Box | 2026-11-18 | 2027-01-20 | 2026-07-29 | 2026-11-18 | 96
GF Fibre Optic Cable (Armoured, Telecom/IT/MAS) |  | 2026-08-20 | 2027-01-06 | 2026-05-02 | 2026-08-20 | 96
v' | GF Fiber Optic cable | 2026-08-20 | 2027-01-06 | 2026-05-02 | 2026-08-20 | 96
BF Instrumentation Works |  | 2026-08-23 | 2027-01-20 | 2025-12-27 | 2026-08-23 | 205
A18730 | Laying UTP/CAT5 cable from B3-CCB Network cabinet (82-JS- 4844) located Ethernet swtich to B3-CCB located SOE PC | 2026-07-19 | 2026-11-05 | 2026-06-27 | 2026-07-19 | 19
A21790 | Cable tray in EU3 SIS and H2 Extraction Plant SIS | 2026-07-09 | 2026-11-25 | 2026-06-27 | 2026-07-09 | 11
FO Cable Laying |  | 2026-07-27 | 2026-12-09 | 2026-06-27 | 2026-07-27 | 26
A17760 | Laying FO cables inside existing trenches/pipe/conduit between EU3 SIS &new H2 Plant SIS | 2026-07-25 | 2026-12-09 | 2026-06-27 | 2026-07-25 | 24
A21780 | Laying FO cables inside existing trenches/pipe/conduit between B3 CCB to new H2 Plant SIS | 2026-07-27 | 2026-11-03 | 2026-07-06 | 2026-07-27 | 18
A21880 | Laying PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB for TRICONEX PLC | 2026-07-25 | 2026-11-01 | 2026-07-11 | 2026-07-25 | 12
Hardwired Cable Laying |  | 2026-08-06 | 2027-01-20 | 2026-05-19 | 2026-08-06 | 68
A17770 | Trench & cable laying | 2026-08-06 | 2027-01-20 | 2026-06-27 | 2026-08-06 | 35
A18320 | Hardwired multicore/pair cable laying between EU3 SIS to H2 Extraction Plant SIS | 2026-06-16 | 2026-10-26 | 2026-05-19 | 2026-06-16 | 24
Termination |  | 2026-08-23 | 2026-11-30 | 2025-12-27 | 2026-08-23 | 205
A17780 | FO Patch cord laying | 2026-01-22 | 2026-11-05 | 2025-12-27 | 2026-01-22 | 24
A21810 | Termination & Testing of various FO cables laid between EU3 SIS to new H2 Plant SIS | 2026-08-12 | 2026-11-30 | 2026-07-19 | 2026-08-12 | 21
A21820 | Termination & Testing of FO cables laid between B3-CCB to new H2 Plant SIS | 2026-08-12 | 2026-11-30 | 2026-07-19 | 2026-08-12 | 21
A21830 | Termination of Hardwiring multicore/pair cable inside existing/new marshalling cabinets | 2026-07-07 | 2026-11-15 | 2026-06-16 | 2026-07-07 | 18
A21890 | Termination at Green Field H2 SIS of' PU ASC PLC (TRICONEX) FO cable between new SIS at H2 Green Field area and B3-CCB | 2026-08-23 | 2026-11-30 | 2026-07-25 | 2026-08-23 | 25
Telecommunication System Installation |  | 2026-11-22 | 2027-01-20 | 01-May-25 A | 2026-11-22 | 60
GF PAGA + Telephone |  | 2026-11-08 | 2027-01-20 | 2026-08-29 | 2026-11-08 | 62
A24440 | Cable terminations and loop testing - PAGA + Telephone | 2026-10-18 | 2026-12-30 | 2026-09-26 | 2026-10-18 | 20
A24630 | PAGA + Telephone - Pre Comm | 2026-11-08 | 2027-01-20 | 2026-10-19 | 2026-11-08 | 18
A3809 | Installation of PAGA+Telephone | 2026-09-24 | 2026-12-07 | 2026-08-29 | 2026-09-24 | 24
GF CCTV |  | 2026-11-22 | 2027-01-20 | 2026-08-29 | 2026-11-22 | 74
A24520 | Cable terminations and loop testing - CCTV | 2026-11-01 | 2026-12-30 | 2026-10-06 | 2026-11-01 | 23
A24730 | CCTV - Pre Comm | 2026-11-22 | 2027-01-20 | 2026-11-02 | 2026-11-22 | 18
A3819 | Installation of CCTV | 2026-10-05 | 2026-12-03 | 2026-08-29 | 2026-10-05 | 33
TA Telecom Related |  |  |  | 01-May-25 A | 15-May-25 A | 0
A18010 | Installation of 08 Nos of Cards in existing system |  |  | 01-May-25 A | 15-May-25 A | 0
A37380 | Installation of SFP in existing distribution switch (Hemal / Rommel). |  |  | 01-May-25 A | 15-May-25 A | 0
Testing |  | 2026-09-05 | 2027-01-20 | 2026-07-25 | 2026-09-05 | 36
A61700 | Fiber Optical Testing | 2026-09-05 | 2027-01-20 | 2026-07-25 | 2026-09-05 | 36
Others |  |  |  | 11-Feb-25 A | 26-Apr-25 A | 0
TA Site Survey For IPCS (ABB) |  |  |  | 20-Feb-25 A | 18-Mar-25 A | 0
A34990 | Site Survey for IPCS Modification |  |  | 20-Feb-25 A | 25-Feb-25 A | 0
A35150 | Health Check / Site Survey Report |  |  | 26-Feb-25 A | 18-Mar-25 A | 0
TA Site Survey For ICSS (Honeywell) |  |  |  | 20-Feb-25 A | 18-Mar-25 A | 0
A35000 | Site Survey for ICSS Modification |  |  | 20-Feb-25 A | 25-Feb-25 A | 0
A37510 | Health Check / Site Survey Report |  |  | 26-Feb-25 A | 18-Mar-25 A | 0
TA Site Survey For LAN System (CISCO) |  |  |  | 19-Apr-25 A | 26-Apr-25 A | 0
A37370 | Site Survey for LAN System Modification |  |  | 19-Apr-25 A | 22-Apr-25 A | 0
A37520 | Health Check / Site Survey Report |  |  | 23-Apr-25 A | 26-Apr-25 A | 0
TA Site Survey For CGC Turbine Software Upgarde |  |  |  | 11-Feb-25 A | 21-Feb-25 A | 0
A37390 | Site Survey for CGC Turbine Software Upgrade |  |  | 11-Feb-25 A | 14-Feb-25 A | 0
A37530 | Site Survey Report for CGC Turbine Software Upgrade |  |  | 17-Feb-25 A | 21-Feb-25 A | 0
TA Site Survey Fire Alarm System (SAFCO) |  |  |  | 19-Apr-25 A | 26-Apr-25 A | 0
A35030 | Site Survey for Fire Alaram System Modification |  |  | 19-Apr-25 A | 22-Apr-25 A | 0
A37560 | Site Survey Report for Fire Alaram System Modification |  |  | 23-Apr-25 A | 26-Apr-25 A | 0
Pre-commissioning |  | 2027-01-20 | 2027-01-20 | 2026-08-23 | 2027-01-20 | 130
GF Pre Commissioning FG/OG Compressor |  | 2027-01-20 | 2027-01-20 | 2026-12-01 | 2027-01-20 | 43
C1010 | Flushing/Airblowing and inspection of piping | 2026-12-19 | 2026-12-19 | 2026-12-01 | 2026-12-19 | 15
C1011 | Lube Oil Flushing | 2026-12-13 | 2026-12-13 | 2026-12-01 | 2026-12-13 | 10
C1013 | Final compressor/driver alignment | 2027-01-03 | 2027-01-03 | 2026-12-13 | 2027-01-03 | 18
C1014 | Pre-commissioning punchlist clearing | 2027-01-20 | 2027-01-20 | 2027-01-03 | 2027-01-20 | 15
GF Pre-Comm |  | 2026-12-30 | 2027-01-20 | 2026-10-15 | 2026-12-30 | 65
A17800 | Overall Plant & CCB/SIS Building Pre-Commissioning | 2026-12-30 | 2027-01-20 |  | 2026-12-30 | 0
A23590 | Plant Equipments Pre Commissionning | 2026-12-30 | 2027-01-20 | 2026-11-19 | 2026-12-30 | 35
A23900 | CCB/SIS systems overall Pre-commissioning | 2026-12-05 | 2027-01-20 |  | 2026-12-05 | 0
A3560 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 2026-11-26 | 2027-01-20 | 2026-10-15 | 2026-11-26 | 36
BF Pre Commissioning |  | 2026-12-27 | 2027-01-20 | 2026-08-23 | 2026-12-27 | 109
BFW4070 | Pre Commissioning works - Instrumentation & Control | 2026-09-26 | 2027-01-03 | 2026-08-23 | 2026-09-26 | 29
BFW4090 | Piping Cleaning, Flushing & Blowing (Pre Comm) | 2026-12-27 | 2027-01-20 | 2026-11-08 | 2026-12-27 | 42
BFW4100 | Equipment pre commissioning | 2026-11-07 | 2027-01-20 | 2026-10-08 | 2026-11-07 | 26
Commissioning, RFSU, Start-Up |  | 2027-05-30 | 2027-07-20 | 2026-06-27 | 2027-05-30 | 289
Commissioning and Start-up |  | 2027-05-30 | 2027-07-20 | 2026-06-27 | 2027-05-30 | 289
A26480 | Telecom (PAGA / PABX / LAN / CCTV) | 2027-03-09 | 2027-03-28 | 2027-02-25 | 2027-03-09 | 10
A27150 | Emergency Diesel Storage & Power Generation System | 2027-02-18 | 2027-03-09 | 2027-02-07 | 2027-02-18 | 10
A27160 | Potable & Service Water System | 2027-02-06 | 2027-02-24 | 2027-01-28 | 2027-02-06 | 7
A27170 | Sanitary Waste Water System | 2027-02-10 | 2027-03-01 | 2027-02-04 | 2027-02-10 | 5
A27180 | Industrial Buildings (MCC / Control Room including HVAC System / Building Fire Alarm System / Clean Agent etc) | 2027-02-03 | 2027-02-22 | 2027-01-20 | 2027-02-03 | 12
A27190 | Plant Lighting System | 2027-02-28 | 2027-03-18 | 2027-02-16 | 2027-02-28 | 10
A27200 | Power Supply System (Existing 33 KVA) | 2027-02-21 | 2027-03-11 | 2027-02-09 | 2027-02-21 | 10
A27240 | MCC | 2027-02-25 | 2027-03-16 | 2027-02-11 | 2027-02-25 | 12
A27250 | UPS System | 2027-02-25 | 2027-03-16 | 2027-02-14 | 2027-02-25 | 10
A27260 | DCS / ESD / Compressor Control Systems / Machine Monitoring Systems (MMS) | 2027-03-11 | 2027-03-30 | 2027-02-18 | 2027-03-11 | 18
A27270 | Anti-Surge Protection System/ PSA2 PLC Control System / Plant F&G System / Deluge Fire Suppression System / Analyzers | 2027-03-07 | 2027-03-25 | 2027-02-21 | 2027-03-07 | 12
A27280 | CP System / Heat Tracing System | 2027-03-07 | 2027-03-25 | 2027-02-23 | 2027-03-07 | 10
A27290 | Instrument & Plant Air System | 2027-02-06 | 2027-02-24 | 2027-01-25 | 2027-02-06 | 10
A27300 | Inert Gas / Nitrogen System | 2027-02-09 | 2027-02-28 | 2027-01-26 | 2027-02-09 | 12
A27310 | Fire Water & Fire Suppression System | 2027-02-03 | 2027-02-22 | 2027-01-23 | 2027-02-03 | 10
A27320 | LP Steam System | 2027-02-11 | 2027-03-02 | 2027-01-31 | 2027-02-11 | 10
A27330 | Oily Water System | 2027-03-08 | 2027-03-27 | 2027-03-02 | 2027-03-08 | 5
A27340 | Slop / Drainage System | 2027-03-06 | 2027-03-24 | 2027-02-28 | 2027-03-06 | 5
A27350 | Warm & Cold Flare Blowdown System | 2027-03-21 | 2027-04-08 | 2027-03-07 | 2027-03-21 | 12
A27360 | LP Condensate Collection System | 2027-02-14 | 2027-03-04 | 2027-02-02 | 2027-02-14 | 10
A27370 | Cooling Water Distribution System | 2027-03-13 | 2027-03-31 | 2027-03-04 | 2027-03-13 | 7
A27380 | C4 Guard Bed Adsorber Regeneration Gas Cooler & Drip Leg to Existing Fuel Gas System | 2027-03-23 | 2027-04-11 | 2027-03-09 | 2027-03-23 | 12
A27390 | Feed Gas from Existing Fuel Gas, C1/C2 Separation Tail Gas Expander Booster Interface Battery Limits | 2027-03-25 | 2027-04-13 | 2027-03-11 | 2027-03-25 | 12
A27400 | PSA2 Feed Gas Compressor | 2027-03-29 | 2027-04-17 | 2027-03-15 | 2027-03-29 | 12
A27410 | PSA2 H2 Extraction Unit, Closed Sampling & Onwards to Interface Battery Limits | 2027-04-01 | 2027-04-20 | 2027-03-18 | 2027-04-01 | 12
A27420 | PSA2 Off Gas Compression (including all drums & coolers), Drip Leg & Onwards to Interface Battery Limits | 2027-04-04 | 2027-04-21 | 2027-03-22 | 2027-04-04 | 10
Commissioning & Handover |  | 2027-02-17 | 2027-07-20 | 2026-06-27 | 2027-02-17 | 203
A9915 | As BuiltUpdation of UG Composite Layouts in B3/U3 areas, Substation Layouts (B3/ U3) under revamp / modification scope | 2026-10-17 | 2027-07-20 | 2026-06-27 | 2026-10-17 | 96
C1039 | PSSR | 2027-02-17 | 2027-03-22 | 2027-01-20 | 2027-02-17 | 24
FG & OG Compressor - Commissioing |  | 2027-03-10 | 2027-04-06 | 2027-01-20 | 2027-03-10 | 42
C1015 | Compressor UCP Pre-Check / Power | 2027-02-10 | 2027-03-09 | 2027-01-20 | 2027-02-10 | 18
C1016 | Hot Loop Testing | 2027-02-16 | 2027-03-15 | 2027-01-26 | 2027-02-16 | 18
C1017 | Energization and Motor Solo Run | 2027-02-21 | 2027-03-20 | 2027-01-31 | 2027-02-21 | 18
C1018 | Interlock and Emergency Shutdown Tests - Part of Dry Commissioning (C&E Check) | 2027-03-01 | 2027-03-28 | 2027-02-08 | 2027-03-01 | 18
C1019 | Control system sequence checks - Part of Dry Commissioning | 2027-03-10 | 2027-04-06 | 2027-02-17 | 2027-03-10 | 18
C1020 | Compressor Oil Lubrication System Check | 2027-02-23 | 2027-03-22 | 2027-02-17 | 2027-02-23 | 5
C1021 | PSSR | 2027-03-02 | 2027-03-29 | 2027-02-23 | 2027-03-02 | 6
RFSU & Handover |  | 2027-05-30 | 2027-07-20 | 2027-03-02 | 2027-05-30 | 75
PC1010 | Ready for Start-Up | 2027-04-04 | 2027-04-21 |  | 2027-04-04 | 0
PC1030 | Issue "AS BUILT STATUS" Maintenance & Safety Manual | 2027-05-30 | 2027-07-20 | 2027-04-04 | 2027-05-30 | 48
PC1050 | Project Close Out ( Handover of Care, Custody & Control of Plant ) | 2027-04-14 | 2027-07-20 |  | 2027-04-14 | 0
FG & OG Compressor - RFSU |  | 2027-03-25 | 2027-04-21 | 2027-03-02 | 2027-03-25 | 20
C1022 | Surge Testing | 2027-03-23 | 2027-04-19 | 2027-03-02 | 2027-03-23 | 18
C1023 | For motor drives, motor current readings shall be obtained. | 2027-03-23 | 2027-04-19 | 2027-03-02 | 2027-03-23 | 18
C1024 | Vibration signatures shall be obtained for all bearings | 2027-03-23 | 2027-04-19 | 2027-03-02 | 2027-03-23 | 18
C1025 | Equipment performance data - Mapping | 2027-03-25 | 2027-04-21 | 2027-03-04 | 2027-03-25 | 18
Commissioning |  | 2027-03-17 | 2027-06-08 | 2027-01-20 | 2027-03-17 | 48
A61710 | Commissioning | 2027-03-17 | 2027-06-08 | 2027-01-20 | 2027-03-17 | 48
Start-up |  | 2027-03-31 | 2027-07-07 | 2027-03-17 | 2027-03-31 | 12
A61720 | Start-Up | 2027-03-31 | 2027-07-07 | 2027-03-17 | 2027-03-31 | 12
Initial Operations |  | 2027-04-07 | 2027-07-14 | 2027-03-31 | 2027-04-07 | 6
A61730 | Intial Operations | 2027-04-07 | 2027-07-14 | 2027-03-31 | 2027-04-07 | 6
Performance Test Run |  | 2027-04-14 | 2027-07-20 | 2027-04-07 | 2027-04-14 | 6
A61740 | Performance test Run | 2027-04-14 | 2027-07-20 | 2027-04-07 | 2027-04-14 | 6
Training |  | 2027-04-28 | 2027-07-20 | 2027-03-17 | 2027-04-28 | 36
A61750 | Training | 2027-04-28 | 2027-07-20 | 2027-03-17 | 2027-04-28 | 36
Optional Item’s Prices |  |  |  | 10-Sep-25 A | 10-Sep-25 A | 0
Furnace Modification – Optional Scope |  |  |  | 10-Sep-25 A | 10-Sep-25 A | 0
A61080 | COMPANY Activation for Optional Scope |  |  |  | 10-Sep-25 A | 0
Cost of Package 2 Novation | [5 empty] | 0
Reimbursable Items (Provisional Sums) |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Provisional Sum for Two Year Operating Spares |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61760 | Provisional Sum for Two Year Operating Spares | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Provisional Sum for Additional Assistance to Company IPMT’s |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61770 | Provisional Sum for Additional Assistance to Company IPMT’s | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Provisional Sum for Additional Start Up Assistance to COMPANY |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61780 | Provisional Sum for Additional Start Up Assistance to COMPANY | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Training of COMPANY personnel |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61790 | Training of COMPANY personnel | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61800 | Initial Fills and / or One (1) full Spare Charge (refer to Addendum to Scope | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Feed-gas Compressor Final design configuration (3 Casing design) |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61810 | Feed-gas Compressor Final design configuration (3 Casing design) | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Accommodation for IPMT (Site) |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61820 | Accommodation for IPMT (Site) | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
Unforeseen development during Execution for additional services over and above |  | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48
A61830 | Unforeseen development during Execution for additional services over and above | 2027-03-09 | 2027-07-20 | 2027-01-20 | 2027-03-09 | 48